## Slide 1: 5MS & GS Readiness Working Group #23 (incl. Systems Working Group)
Thursday, 13 May 2021
This meeting is recorded for the purpose of minute taking.
Please disconnect from your workplace VPN for the WebEx call

## Slide 2: AEMO Competition Law Meeting Protocol
Under no circumstances must Participants share Competitively Sensitive Information. Competitively Sensitive Information means confidential information relating to a Participant which if disclosed to a competitor could affect its current or future commercial strategies, such as pricing information, customer terms and conditions, supply terms and conditions, sales, marketing or procurement strategies, product development, margins, costs, capacity or production planning.
AEMO is committed to complying with all applicable laws, including the Competition and Consumer Act 2010 (CCA). In any dealings with AEMO regarding proposed reforms or other initiatives, all participants agree to adhere to the CCA at all times and to comply with this Protocol. Participants must arrange for their representatives to be briefed on competition law risks and obligations.
Participants in AEMO discussions must:
Ensure that discussions are limited to the matters contemplated by the agenda for the discussion
Make independent and unilateral decisions about their commercial positions and approach in relation to the matters under discussion with AEMO
Immediately and clearly raise an objection with AEMO or the Chair of the meeting if a matter is discussed that the participant is concerned may give rise to competition law risks or a breach of this Protocol
Participants in AEMO meetings must not discuss or agree on the following topics:
Which customers they will supply or market to
The price or other terms at which Participants will supply
Bids or tenders, including the nature of a bid that a Participant intends to make or whether the Participant will participate in the bid
Which suppliers Participants will acquire from (or the price or other terms on which they acquire goods or services)
Refusing to supply a person or company access to any products, services or inputs they require

## Slide 3: Agenda
NO | Indicative Time | AGENDA ITEM | Responsible
1 | 10:30 - 10:40 | Welcome and Introduction | Greg Minney
2 | 11:00 - 11:20 | May Rollout plan overview (inc CATS transaction update) | Blaine Miner / Paul Lyttle
3 | 11:20 - 11:40 | MTP Update | Blaine Miner
4 | 11:40 - 12:00 | Next Steps and General Business | Greg Minney

## Slide 4: Welcome
Greg Minney

## Slide 5: May Rollout Plan Overview
Blaine Miner / Paul Lyttle

## Slide 6: Rollout Plan Responses
Organisation | MC/MP Tranche 1 | MDP Tranche 1 | MDP Tranche 2 | MP RTC T2 | MDP Net to Reg T1 and T2 | LNSP NCONUML and Cross Boundary | Explicit Consent Provided
AusNet Services |  |  | Yes | Yes | Yes | Yes | No
Ausgrid | Yes |  |  |  |  | Yes | Yes
Citipower/ Powercor | Yes |  | Yes | Yes | Yes | Yes | Yes
ElectraNet | Yes |  |  |  |  |  | Yes
Endeavour Energy |  |  |  |  | Yes | Yes | Yes
Energex |  |  | Yes | Yes | Yes | Yes | Yes
Ergon |  |  | Yes | Yes | Yes | Yes | Yes
EvoEnergy | Yes |  |  |  | Yes | Yes | No
Intellihub | Yes | Yes | Yes | Yes | Yes |  | No
Organisation | MC/MP Tranche 1 | MDP Tranche 1 | MDP Tranche 2 | MP RTC T2 | MDP Net to Reg T1 and T2 | LNSP NCONUML and Cross Boundary | Explicit Consent Provided
Mondo | Yes | Yes | Yes |  |  |  | No
Origin | Yes |  |  |  |  |  | No
PlusES | Yes | Yes | Yes | Yes | Yes |  | Yes
Powerlink | Yes |  |  |  |  |  | Yes
SAPN |  |  |  |  |  | Yes | Yes
TasNetworks |  |  |  |  | Yes | Yes | Yes
Transgrid | Yes |  |  |  |  |  | Yes
United Energy | Yes |  | Yes | Yes | Yes | Yes | Yes
Vector |  |  | Yes | Yes | Yes |  | No
Received rollout plan updates from 18 organisations
Over 40% of tranche 1 meters reported as installed/reconfigured

## Slide 7: Tranche 1 – Consolidated Plan results
Consolidated Meter Replacement and Reconfigurations
Consolidated RTC code changes
Peak month is August with 14,645 CRs to be raised
Numbers of Meters to start delivering Data in 5 minute intervals
A total of 19,370 meters to be providing 5 minute reads by end of September
Consolidated Cross Boundary and Non-Contestable Unmetered Load creation and metering.
Peak month is July with 126,008 CRs to be raised

## Slide 8: Pre 5MS Consolidated Plan Simmary
Consolidated Tranche 1 & 2 Change requests
Estimated Peak in July with 136,543 CRs to be raised
Numbers include:
  Meter Replacement & Reconfigurations
  RTC updates
  Cross Boundary registration and metering
  Non-Contestable registration and metering
Consolidated Tranche 1 & 2 Meter data delivery in 5 minutes.
A total of 38,964 meters estimated to be providing 5 minute reads by end of September

## Slide 9: Tranche 2 – Consolidated Plan results
Consolidated RTC Code changes
Peak month is April 2022 with 315,000 CRs to be raised
Consolidated Net to Register conversions
Peak month is December 2021 with 378,500 CRs expected to be initiated

## Slide 10: Post 5MS Consolidated Plan Summary
Consolidated Tranche 1 & 2 Change requests
Estimated Peak in April with 632,500 CRs to be raised
Numbers include:
  RTC updates
  Net to Register Conversion
Consolidated Tranche 1 & 2 meter data delivery in 5 minutes.
A total of 2,803,964 meters estimated to be providing 5 minute reads by December 2022

## Slide 11: MTP Update
Blaine Miner

## Slide 12: New Values in Existing MSATS Fields
Examples of effected fields:
  NMI Classification Code e.g. NCONUML, NREG, etc.
  Datastream Type Code – introduction of the ‘non-settlement’ code of ‘N’
  Read Type Code – 4 character codes e.g. RWDA
Schema considerations
  Do you need to go onto the new schema?
    No, both current and superseded schemas support existing fields i.e. new values don’t require a schema change
    ‘New’ schema required for new fields e.g. TNI2 code and new RM reports
Participant system considerations:
  Processing
  Validations
  Application

## Slide 13: MTP Update
Description | Date | Activity ID
AEMO Metering Business approve MDP NCONUML profiles/algorithms | By 1 May 2021 | A89
MDPs to provide AEMO estimated number of NMIs and associated energy volumes for each Unmetered Device category within calculation methodology | By 1 May 2021 | A89a
Activities Now Deemed Completed or Late
Description | Date | Activity ID
AEMO to provide TNI2 values to LNSPs to support the updating of applicable TNI fields i.e. TNI fields associated to NMIs downstream of a cross boundary NMI (new activity) | By 31 August 2021 | A97a
LNSPs to update the TNI field, for NMIs downstream of a cross boundary NMI, with the AEMO provided TNI2 value (new activity) | By 31 August 2021 | A97b
Provide AEMO estimated number of NMIs and associated energy volumes for each Unmetered Device category within calculation methodology (change in wording) | By 1 May 2021 | A89a
Proposed Updates

## Slide 14: Upcoming Transition End Date Activities
Description | Transition End Date | Activity IDMDPs
Participants to ensure capability to receive and process new NMI classification codes | By 30 May 2021 | A102, A104, A106, A108, A110, A112, A114
Participants to establish agreements to allow the delivery of 5min metering data pre 1 Oct 2021 between NSP, Retailer, MDP and AEMO, as applicable | By 31 May 2021 | A32, A37, A42, A47, A53, A59, A65, A71, A84, A88
SAPN - Convert 'SASCALE NMI’ Make existing 'Bulk' NMI extinct in MSATS Create individual controlled load Datastreams in MSATS Create individual controlled load Registers in MSATS | By 30 June 2021 | A101a, A101b, A101c
MDPs - Create/activate tier 1 basic meter datastreams as required | By 30 June 2021 | A117, A118
MDPs - Delivery of tier 1 basic meter metering data (Actuals, Subs and Forward Estimates) to AEMO | By 30 June 2021 | A93
MPs - Install or reconfigure meters as required | By 31 July 2021 | A4, A9, A14, A20
MPs - Update Meter Read Type code with RWDA | By 31 July 2021 | A4a, A9a, A14a, A20a
MPs - Apply for data storage exemptions as required | By 31 July 2021 | A5, A10, A15, A21

## Slide 15: Upcoming Transition Start Date Activities
Description | Transition Start Date | Activity ID
MPs able to update the Meter Read Type code (RTC) with four-character values, resulting from BAU activities | From 1 May 2021 | A4a, A9a, A14a, A20a
MDPs able to create/convert export and import Active (kWh) and Reactive (kVarh) energy datastreams, where applicable, in the CNDS table | From 31 May 2021 | A36, A40, A45, A51, A57, A63, A69, A75
Participants able to create cross-boundary NMIs, datastreams and registers | From 31 May 2021 | A95, A96, A97
Participants able to create NCONUML NMIs, datastreams and registers | From 31 May 2021 | A99, A100, A101
MDPs able to send 15 and 30min metering data via MDFF to AEMO | From 31 May 2021 | A94
LNSPs able to apply new NMI classification codes | From 31 May 2021 | A103, A105, A107, A109, A111, A113, A115
MDPs able to provide 5min metering data to AEMO (MDFF) (Export and import (active (kWh) and reactive (kVarh)) energy metering data as applicable) | From 21 June 2021 | A35, A41, A46, A50, A56, A62, A68, A74, A86, A92

## Slide 16: Next steps and General Business
Greg Minney

## Slide 17: Next steps and General Business
Next TFG scheduled for Thursday 10 June

## Slide 18: Thank you for your attendance and participation!