## Victoria Summary
VIC
Disclaimer
This document is subject to an important disclaimer that limits or excludes AEMO's liability.
Please read the full disclaimer at
http://www.aemo.com.au/Electricity/National-Electricity-Market-NEM/Planning-and-forecasting/Generation-information
Data presented is current as at 31 October 2018
Victoria Summary
Changes since last update
Lal Lal Wind Energy Facility - Yendon end: Lal Lal Wind Energy Facility - Yendon end (144.4MW) is now reported as committed since Northleaf /InfraRed/Macquarie Capital advise that it has commenced construction.
Gannawarra Solar Farm: Gannawarra Solar Farm Pty Ltd advises that Gannawarra Solar Farm (50 MW) is operational.
Numurkah Solar Farm : Neoen advises that Numurkah Solar Farm (100MW) is now a committed project.
Moorabool Wind Farm: Goldwind advises that Moorabool Wind Farm (320MW) is now a committed project.
Kiamal Solar Farm - Stage 1: Kiamal Solar Farm - Stage 1 (200MW) is now reported as committed since Total Eren advises that it has commenced construction.
Bulgana Green Power Hub - Wind Farm: Bulgana Green Power Hub - Wind Farm (194MW) is now reported as committed since Neoen advises that it has commenced construction.
Generation withdrawals
Withdrawn
AEMO has not been advised of any recent withdrawals for this region.
Announced withdrawals (i.e. Mothballed, Seasonal Shut down etc.)
AEMO has not been advised of any announced withdrawals for this region.
Committed projects
Coal, CCGT, OCGT, Gas other, Water, Biomass, Geo-thermal, Other : None to report.
Solar: Bannerton Solar Park (88 MW), Karadoc Solar Farm (90 MW), Kiamal Solar Farm - Stage 1 (200 MW), Numurkah Solar Farm (100 MW), Wemen Solar Farm (87.75 MW), Yatpool Solar Farm (81 MW)
Wind: Bulgana Green Power Hub - Wind Farm (194 MW), Crowlands Wind Farm (79.95 MW), Lal Lal Wind Energy Facility - Elaine end (83.6 MW), Lal Lal Wind Energy Facility - Yendon end (144.4 MW), Moorabool Wind Farm (320 MW), Mt Gellibrand (132 MW), Murra Warra Wind Farm - stage 1 (225.7 MW), Stockyard Hill (532 MW).
Storage: Ballarat Energy Storage System (30 MW / 30 MWh ), Bulgana Green Power Hub - BESS (20 MW / 34 MWh ), Gannawarra Energy Storage System (25 MW / 50 MWh )
Proposed projects
Please refer to information presented in the worksheet titled 'New Developments'.
Plant limitations
AEMO has not been advised of any plant limitations for this region.
Victoria existing and potential new developments by generation type (MW)
| Status | Coal | CCGT | OCGT | Gas other | Solar* | Wind | Water | Biomass | Battery Storage | Other | Total
| Existing | 4660 | 21 | 1916.8 | 522.612 | 71.3115 | 1612.9 | 2286.237 | 57.604 | 0 | 0 | 11148.4645
| Announced Withdrawal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Existing less Announced Withdrawal | 4660 | 21 | 1916.8 | 522.612 | 71.3115 | 1612.9 | 2286.237 | 57.604 | 0 | 0 | 11148.4645
| Upgrade | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80
| Committed | 0 | 0 | 0 | 0 | 646.75 | 1711.65 | 0 | 0 | 75 | 0 | 2433.4
| Proposed | 0 | 0 | 765 | 0 | 2114.5 | 6001 | 34 | 0 | 92 | 0 | 9006.5
| Withdrawn | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note: Existing includes Announced Withdrawal
* Solar excludes rooftop PV installations

## Change Log
Victoria Change Log
Lists all key updates to new development projects and existing generation information between publication dates since the 2012 ESOO.
Publication Date: | 2012-12-20
Morwell Power Station: Energy Brix Australia Corporation Pty Ltd advises that the Morwell plant has revised its available capacity from 104 MW to 75 MW (-29 MW) in summer and winter, due to generation units with DUID MOR1 in operation and generation unit with DUID MOR2 operational when generation unit with DUID MOR1 is under maintenance. Generation unit with DUID MOR3 will be available on a 30 day recall.
Qenos Cogeneration Facility: AGL Energy advises that Qenos Cogeneration Facility is a committed project. The 21 MW combined-cycle gas turbine (CCGT) construction completion achieved in October 2012 and full commissioning at the end of March 2013.
Publication Date: | 2013-06-30
Macarthur Wind Farm: AGL Energy advises that the 420 MW Macarthur wind farm project was completed in January 2013.
Mortons Lane Wind Farm: Mortons Lane Windfarm Pty Ltd advises that the 19.5 MW Mortons Lane wind farm project was completed in December 2012.
Qenos Cogeneration Facility: AGL Energy advises that 21 MW Qenos Cogeneration Facility project was completed in March 2013.
Mt Mercer Wind Farm: Mt Mercer Wind Farm Pty Ltd advises that Mt Mercer wind farm is a committed project. The 131.2 MW wind farm expected commissioning is January 2015.
Mildura Power Station: Solar Systems advises that Mildura Power Station demonstration facility is a committed project. The 1.5 MW solar plant is under construction and expected completion is July 2013.
Hallam Road Power Station: LMS Energy advises that the upgrades to Unit 7 was completed in June 2012 and Unit 8 in November 2012 increasing the capacity by 2.2 MW.
Publication Date: | 2013-08-13
Mildura Power Station: Solar Systems advises that Mildura Power Station Stage 2 of the project is to be 100 MW of capacity.
Publication Date: | 2013-11-15
Mildura Power Station: Solar Systems advises that Mildura Power Station demonstration facility (1.5 MW) project was completed in July 2013.
Portland Stage 4 Cape Nelson North and Cape Sir William Grant: Pacific Hydro Australia advises that Portland Stage 4 Cape Nelson North and Cape Sir William Grant (47.15 MW) construction at the site is to commence in September 2013, with full commissioning planned for September 2015.
Publication Date: | 2014-05-30
Loy Yang A: AGL Energy advises Loy Yang A Power Station has revised its available capacity to 2100 MW (-90 MW) in summer due to operational experience in ambient conditions.
Macarthur: AGL Energy advises Macarthur Power Station has revised its available capacity to 315 MW (-105 MW) in summer to reflect the actual behaviour of the wind generation assets during high temperature days.
Morwell/Energy Brix: Energy Brix Australia Corporation Pty Ltd advises Morwell/Energy Brix Power Station has revised its available capacity to 65 MW (-10 MW) in summer due to the Morwell mine fire destroying conveyors, thus restricting coal supply.
Mt Mercer Wind Farm: Mt Mercer Wind Farm Pty Ltd advises that Mt Mercer wind farm is a committed project. The 131.2 MW wind farm expected commissioning is July 2014.
Bald Hill Wind Farm (Phase 1): Mitsui and Co. Australia Ltd advises that Bald Hill wind farm is a committed project. The 106.6 MW wind farm expected commissioning is May 2015.
Portland Stage 4 Cape Nelson North and Cape Sir William Grant: Pacific Hydro Portland Wind Farm Pty Ltd advises that Portland Stage 4 Cape Nelson North and Cape Sir William Grant wind farm is a committed project. The 47.15 MW wind farm expected commissioning is May 2015.
Publication Date: | 2014-08-07
Mt Mercer Wind Farm: Mt Mercer Wind Farm Pty Ltd advises that Mt Mercer wind farm has been in full production since July 2014. The commissioning date has been revised to February 2015.
Anglesea Power Station: Alcoa of Australia Limited advises that Anglesea Power Station is changed its registration classification from Non-Scheduled to a Scheduled generator.
Publication Date: | 2014-12-10
Bald Hills Wind Farm (Phase 1): Mitsui and Co. Australia Ltd advises that Bald Hills wind farm (106.6 MW) is a committed project. The wind farm is under construction with expected commissioning in May 2015.
Mt Mercer Wind Farm: Mt Mercer Wind Farm Pty Ltd advises that Mt Mercer wind farm (131.2 MW) project is completed and in full commercial operation since mid 2014.
Morwell/Energy Brix: Energy Brix Australia Corporation Pty Ltd advises Morwell/Energy Brix Power Station has been withdrawn from service since August 2014.
Publication Date: | 2015-05-15
Portland Stage 4 Cape Nelson North and Cape Sir William Grant: Pacific Hydro Portland Wind Farm Pty Ltd advises that Portland Stage 4 (47.15 MW) project is completed and in full commercial operation since end of Feb 2015.
Ararat Wind Farm: Ararat Wind Farm Pty Ltd advises that Ararat wind farm (240 MW) is to start construction in July 2015 with full commercial operation expected in May 2016.
Coonooer Bridge Wind Farm: Windlab Systems Pty Ltd advises that Coonooer Bridge wind farm (19.8 MW) is to start construction in April 2015 with full commercial operation expected in March 2016.
Anglesea Power Station: Alcoa of Australia Limited advises Anglesea Power Station will retire from service from 31 August 2015 and to be decommissioned.
Publication Date: | 2015-08-13
Yallourn W Power Station: EnergyAustralia Holdings Pty Ltd advises Yallourn W Power Station has revised its available capacity to 1516 MW (+12 MW) in summer due to turbine upgrades.
Loy Yang A: AGL Energy advises Loy Yang A Power Station has revised its available capacity to 2070 MW (-30 MW) in summer due to change in performance re-evaluation. Also, revised its available capacity to 2210 MW (-60 MW) in winter due to the difficulty of producing maximum daily capacity for extended periods.
Loy Yang B: AGL Energy advises Loy Yang B Power Station has revised its available capacity to 980 MW (+15 MW) in summer due to increase in condenser vacuum limit. Also, revised its available capacity to 1070 MW (+20 MW) in winter due to increase in condenser vacuum limit.
Ararat Wind Farm: Ararat Wind Farm Pty Ltd advises that Ararat wind farm (240 MW) is to start construction in July 2015 with full commercial operation expected in May 2017.
Morwell/Energy Brix: Energy Brix Australia Corporation Pty Ltd advises Morwell/Energy Brix Power Station has temporarily closed its operations from August 2014.
Publication Date: | 2015-10-23
Coonooer Bridge Wind Farm: Windlab Systems Pty Ltd advises that Coonooer Bridge wind farm (19.8 MW) is now a committed project. Full commercial operation is expected in March 2016.
Publication Date: | 2016-03-03
Ararat Wind Farm: Ararat Wind Farm Pty Ltd advises that Ararat wind farm (240 MW) is to be in full commercial operation expected in May 2017.
Coonooer Bridge Wind Farm: Windlab Systems Pty Ltd advises that Coonooer Bridge wind farm (19.8 MW) is now a committed project. Full commercial operation is expected in March 2016.
Publication Date: | 2016-04-15
Ararat Wind Farm: Ararat Wind Farm Pty Ltd advises that Ararat wind farm (240 MW) is to be in full commercial operation expected in May 2017.
Coonooer Bridge Wind Farm: Windlab Systems Pty Ltd advises that Coonooer Bridge wind farm (19.8 MW) is now a committed project. Full commercial operation is expected in March 2016.
Publication Date: | 2016-08-11
Mt Gellibrand Wind Farm: Acciona Energy advises that Mt Gellibrand Stage 1 (66 MW) is a committed project.
New Development: Mallee Solar Park, Kiata Wind Farm.
Publication Date: | 2016-11-18
Hazelwood: Hazelwood Power advises that Hazelwood Power Station will cease generation at the end of March 2017.
Publication Date: | 2017-02-27
Kiata Wind Farm: Kiata Wind Farm Pty Ltd advises that Kiata Wind Farm (31.05 MW) is now a committed project with full commercial use expected December 2017.
Publication Date: | 2017-06-05
Ararat: Ararat Wind Farm Pty Ltd advises that Ararat (240MW) is now completed and is undergoing commissioning tests with full commercial operation having commenced in May 2017.
Gannawarra Solar Farm: Gannawarra Solar Farm Pty Ltd advises that Gannawarra Solar Farm (50 MW) is now a committed project, with full commercial use expected April 2018.
Hazelwood: Hazelwood Power advises that Hazelwood Power Station (1600 MW) has closed operations at the end of March 2017 and is undergoing decommissioning.
Longford: Longford Gas Plant advises that Longford has increased its total nameplate capacity from 32 MW to 45 MW in December 2016.
Yaloak South: Energy Pacific Vic Pty Ltd advises that Yaloak South (28.7 MW) is now a committed project.
Publication Date: | 2017-12-22
Bannerton Solar Park: Foresight Solar Australia Pty Ltd advises that Bannerton Solar Park (88 MW) is now a committed project.
Gannawarra Solar Farm: Gannawarra Solar Farm Pty Ltd advises that Gannawarra Solar Farm has increased from 50 MW to 55 MW.
Crowlands Wind Farm: Energy Pacific Vic Pty Ltd advises that Crowlands Wind Farm (80 MW) is now a committed project
Kiata Wind Farm: Kiata Wind Farm Pty Ltd advises that Kiata Wind Farm (31.05 MW) is now a committed project
Mt Gellibrand Wind Farm: Acciona Energy advises that Mt Gellibrand (132 MW) is a committed project.
Loy Yang B (upgrade) : Loy Yang B upgrade (78 MW) is now reported as committed since Alinta advises that it has commenced construction
Swan Hill Solar Farm : Swan Hill Solar Farm (15 MW) is now reported as committed since Solar PowerStation Victoria Pty Ltd advises that it has commenced construction
Yatpool Solar Farm: Yatpool Solar Farm (81 MW) is now reported as committed since Overland Sun Farming Pty Ltd advises that it has commenced construction
Publication Date: | 2018-03-16
Salt Creek Wind Farm : Tilt Renewables advises that Salt Creek Wind Farm (54 MW) is now a committed project.
Publication Date: | 2018-07-31
Ballarat Energy Storage System: Ballarat Energy Storage System (30 MW) is now reported as committed since AusNet Services advises that it has commenced construction
Bulgana Green Power Hub - Wind Farm: Bulgana Green Power Hub - Wind Farm (204 MW) is now reported as committed since Neoen advises that it has commenced construction.
Bulgana Green Power Hub - BESS: Bulgana Green Power Hub - Battery Energy Storage System (BESS) (21 MW) is now reported as committed since Neoen advises that it has commenced construction.
Gannawarra Energy Storage System: Gannawarra Energy Storage System (25 MW) is now reported as committed since GESS Co advises that it has commenced construction
Karadoc Solar Farm: Karadoc Solar Farm (90 MW) is now reported as committed since Overland Sun Farming Pty Ltd advises that it has commenced construction
Lal Lal Wind Energy Facility - Elaine end: Lal Lal Wind Energy Facility - Elaine end (79 MW) is now reported as committed since Westwind Energy Pty Ltd advises that it has commenced construction
Loy Yang B: Alinta Energy is reviewing the Loy Yang B upgrade project, and will provide an update before the 2018-19 Summer season.
Moorabool Wind Farm: Moorabool Wind Farm (320 MW) is now reported as committed since Goldwind advises that it has commenced construction
Murra Warra Wind Farm - stage 1 : RES Australia advises that Murra Warra Wind Farm - stage 1 (226 MW) is now a committed project.
Stockyard Hill : Goldwind advises that Stockyard Hill (532 MW) is now a committed project.
Wemen Solar Farm: Wemen Asset Co Pty Ltd advises that Wemen Solar Farm (87.75 MW) is now a committed project.
Publication Date: | 2018-10-31
Lal Lal Wind Energy Facility - Yendon end: Lal Lal Wind Energy Facility - Yendon end (144.4MW) is now reported as committed since Northleaf /InfraRed/Macquarie Capital advise that it has commenced construction.
Gannawarra Solar Farm: Gannawarra Solar Farm Pty Ltd advises that Gannawarra Solar Farm (50 MW) is operational.
Numurkah Solar Farm : Neoen advises that Numurkah Solar Farm (100MW) is now a committed project.
Moorabool Wind Farm: Goldwind advises that Moorabool Wind Farm (320MW) is now a committed project.
Kiamal Solar Farm - Stage 1: Kiamal Solar Farm - Stage 1 (200MW) is now reported as committed since Total Eren advises that it has commenced construction.
Bulgana Green Power Hub - Wind Farm: Bulgana Green Power Hub - Wind Farm (194MW) is now reported as committed since Neoen advises that it has commenced construction.
Note: Updated “Background Information” with changes to categories of proposed generation in the NEM.

## Existing S & SS Generation
Existing & committed scheduled and semi-scheduled generation
Power Station | Owner | Unit Number and Nameplate Capacity (MW) | Nameplate Capacity (MW) | Technology Type | Fuel Type | Dispatch Type | Service Status | Region | summary_status | summary_bucket
Ararat Wind Farm | Ararat Wind Farm Pty Ltd | 75 x 3.2 | 240 | Wind - Onshore | Wind | SS | In Service | VIC | Existing less Announced Withdrawal | Wind
Bairnsdale | Alinta DEBO | 2 x 47 | 94 | OCGT | Natural Gas Pipeline | S | In Service | VIC | Existing less Announced Withdrawal | OCGT
Bald Hills Wind Farm | Infrastructure Capital Group | 52 x 2.05 | 106.6 | Wind - Onshore | Wind | SS | In Service | VIC | Existing less Announced Withdrawal | Wind
Bogong / Mackay | AGL | 2 x 70 6 x 27 | 300 | Hydro - Gravity | Water | S | In Service | VIC | Existing less Announced Withdrawal | Water
Dartmouth | AGL | 1 x 185 | 185 | Hydro - Gravity | Water | S | In Service | VIC | Existing less Announced Withdrawal | Water
Eildon | AGL | 2 x 60 2 x 7.5 | 135 | Hydro - Gravity | Water | S | In Service | VIC | Existing less Announced Withdrawal | Water
Gannawarra Solar Farm | Gannawarra Solar Farm Pty Ltd | 22 x 2.5 | 50 | PV panels | Solar | SS | In Service | VIC | Existing less Announced Withdrawal | Solar
Hume VIC | GSP Energy Pty Ltd | 1 x 29 | 29 | Hydro - Gravity | Water | S | In Service | VIC | Existing less Announced Withdrawal | Water
Jeeralang A | Ecogen Energy Py Ltd | 4 x 53 | 212 | OCGT | Natural Gas Pipeline | S | In Service | VIC | Existing less Announced Withdrawal | OCGT
Jeeralang B | Ecogen Energy Pty Ltd | 3 x 76 | 228 | OCGT | Natural Gas Pipeline | S | In Service | VIC | Existing less Announced Withdrawal | OCGT
Kiata Wind Farm | Kiata Wind Farm Pty Ltd | 9 x 3.45 | 31.05 | Wind - Onshore | Wind | SS | In Service | VIC | Existing less Announced Withdrawal | Wind
Laverton North | Snowy Hydro Ltd | 2 x 156 | 312 | OCGT | Natural Gas Pipeline | S | In Service | VIC | Existing less Announced Withdrawal | OCGT
Loy Yang A | AGL Energy | 3 x 560 1 x 530 | 2210 | Steam Sub Critical | Brown Coal | S | In Service | VIC | Existing less Announced Withdrawal | Coal
Loy Yang B | Gippsland Power Pty Ltd ABN 30 077 851 079 / LYB Ventures Australia Pty Ltd ABN 57 055 984 499 / Traralgon Power Pty Ltd ABN 64 056 292 623 / Latrobe Power Pty Ltd ABN 42 055 983 563 / LYB Australia Limited ABN 87 055 563 785 | 2 x 500 | 1000 | Steam Sub Critical | Brown Coal | S | In Service | VIC | Existing less Announced Withdrawal | Coal
Macarthur Wind Farm | Macarthur Wind Farm Pty Ltd and Meridian Wind Macarthur Pty Ltd | 140 x 3 | 420 | Wind - Onshore | Wind | SS | In Service | VIC | Existing less Announced Withdrawal | Wind
Mortlake | Origin Energy Power Limited | 2 x 283 | 566 | OCGT | Natural Gas Pipeline | S | In Service | VIC | Existing less Announced Withdrawal | OCGT
Mt Mercer Wind Farm | Mt Mercer Windfarm Pty Ltd | 64 x 2.05 | 131.2 | Wind - Onshore | Wind | SS | In Service | VIC | Existing less Announced Withdrawal | Wind
Murray 1 | Snowy Hydro Ltd | 10 x 95 | 950 | Hydro - Gravity | Water | S | In Service | VIC | Existing less Announced Withdrawal | Water
Murray 2 | Snowy Hydro Ltd | 4 x 138 | 552 | Hydro - Gravity | Water | S | In Service | VIC | Existing less Announced Withdrawal | Water
Newport | Ecogen Energy Pty Ltd | 1 x 510 | 510 | Steam Sub Critical | Natural Gas Pipeline | S | In Service | VIC | Existing less Announced Withdrawal | Gas other
Oaklands Hill Wind Farm | Oaklands Hill Wind farm pty ltd | 32 x 2.1 | 67.2 | Wind - Onshore | Wind | SS | In Service | VIC | Existing less Announced Withdrawal | Wind
Salt Creek Wind Farm | Salt Creek Wind Farm Pty Ltd | 15 x 3.6 | 54 | Wind - Onshore | Wind | SS | In Service | VIC | Existing less Announced Withdrawal | Wind
Somerton | AGL Energy | 4 x 40 | 160 | OCGT | Natural Gas Pipeline | S | In Service | VIC | Existing less Announced Withdrawal | OCGT
Valley Power | Snowy Hydro Ltd | 6 x 50 | 300 | OCGT | Natural Gas Pipeline | S | In Service | VIC | Existing less Announced Withdrawal | OCGT
West Kiewa | AGL | 4 x 15 | 60 | Hydro - Gravity | Water | S | In Service | VIC | Existing less Announced Withdrawal | Water
Yallourn W | EnergyAustralia Holdings Pty Ltd | 2 x 350 2 x 375 | 1450 | Steam Sub Critical | Brown Coal | S | In Service | VIC | Existing less Announced Withdrawal | Coal
Total |  |  | 10353.05
* In Commissioning includes facilities that have both obtained NEM registration, and have demonstrated the ability to export at least 50% of Nameplate capacity under commissioning conditions, but are not yet operating unrestricted at the time of publication. These projects are included under the "Existing Less Announced Withdrawal" category in the Summary Table.

## Summer Scheduled Capacities
Summer aggregate available scheduled and semi-scheduled generation
PowerStation | 201819 | 201920 | 202021 | 202122 | 202223 | 202324 | 202425 | 202526 | 202627 | 202728 | DispatchType | FuelType | Region | Season
Ararat Wind Farm | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | SS | Wind | VIC | summer
Bairnsdale | 78 | 78 | 78 | 78 | 78 | 78 | 78 | 78 | 78 | 78 | S | Fossil | VIC | summer
Bald Hills Wind Farm | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | SS | Wind | VIC | summer
Ballarat Energy Storage System | 28.8 | 28.8 | 28.8 | 28.8 | 28.8 | 28.8 | 28.8 | 28.8 | 28.8 | 28.8 | S | N/A | VIC | summer
Bannerton Solar Park | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | SS | Solar | VIC | summer
Bogong / Mackay | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | S | Hydro | VIC | summer
Bulgana Green Power Hub - BESS | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | SS | N/A | VIC | summer
Bulgana Green Power Hub - Wind Farm | 0 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | SS | Wind | VIC | summer
Crowlands Wind Farm | 0 | 79.95 | 79.95 | 79.95 | 79.95 | 79.95 | 79.95 | 79.95 | 79.95 | 79.95 | SS | Wind | VIC | summer
Dartmouth | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | S | Hydro | VIC | summer
Eildon | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | S | Hydro | VIC | summer
Gannawarra Energy Storage System | 25.33 | 25.33 | 25.33 | 25.33 | 25.33 | 25.33 | 25.33 | 25.33 | 25.33 | 25.33 | S | N/A | VIC | summer
Gannawarra Solar Farm | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | SS | Solar | VIC | summer
Hume VIC | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | S | Hydro | VIC | summer
Jeeralang A | 189 | 189 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | S | Fossil | VIC | summer
Jeeralang B | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | S | Fossil | VIC | summer
Karadoc Solar Farm | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | SS | Solar | VIC | summer
Kiamal Solar Farm - Stage 1 | 0 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | SS | Solar | VIC | summer
Kiata Wind Farm | 31.05 | 31.05 | 31.05 | 31.05 | 31.05 | 31.05 | 31.05 | 31.05 | 31.05 | 31.05 | SS | Wind | VIC | summer
Lal Lal Wind Energy Facility - Elaine end | 0 | 83.6 | 83.6 | 83.6 | 83.6 | 83.6 | 83.6 | 83.6 | 83.6 | 83.6 | SS | Wind | VIC | summer
Lal Lal Wind Energy Facility - Yendon end | 0 | 144.4 | 144.4 | 144.4 | 144.4 | 144.4 | 144.4 | 144.4 | 144.4 | 144.4 | SS | Wind | VIC | summer
Laverton North | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | S | Fossil | VIC | summer
Loy Yang A | 2144 | 2144 | 2144 | 2144 | 2144 | 2144 | 2144 | 2144 | 2144 | 2136 | S | Fossil | VIC | summer
Loy Yang B | 980 | 980 | 980 | 980 | 980 | 980 | 980 | 980 | 980 | 980 | S | Fossil | VIC | summer
Macarthur Wind Farm | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | SS | Wind | VIC | summer
Moorabool Wind Farm | 0 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | SS | Wind | VIC | summer
Mortlake | 518 | 518 | 518 | 518 | 518 | 518 | 518 | 518 | 518 | 518 | S | Fossil | VIC | summer
Mt Gellibrand | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | SS | Wind | VIC | summer
Mt Mercer Wind Farm | 131.2 | 131.2 | 131.2 | 131.2 | 131.2 | 131.2 | 131.2 | 131.2 | 131.2 | 131.2 | SS | Wind | VIC | summer
Murra Warra Wind Farm - stage 1 | 0 | 226 | 226 | 226 | 226 | 226 | 226 | 226 | 226 | 226 | SS | Wind | VIC | summer
Murray 1 | 950 | 855 | 855 | 950 | 855 | 855 | 855 | 950 | 950 | 950 | S | Hydro | VIC | summer
Murray 2 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | S | Hydro | VIC | summer
Newport | 475 | 475 | 475 | 475 | 475 | 475 | 475 | 475 | 475 | 475 | S | Fossil | VIC | summer
Numurkah Solar Farm | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | SS | Solar | VIC | summer
Oaklands Hill Wind Farm | 41.6 | 41.6 | 41.6 | 41.6 | 41.6 | 41.6 | 41.6 | 41.6 | 41.6 | 41.6 | SS | Wind | VIC | summer
Salt Creek Wind Farm | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | SS | Wind | VIC | summer
Somerton | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | S | Fossil | VIC | summer
Stockyard Hill | 0 | 400 | 532 | 532 | 532 | 532 | 532 | 532 | 532 | 532 | SS | Wind | VIC | summer
Valley Power | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | S | Fossil | VIC | summer
Wemen Solar Farm | 87.75 | 87.75 | 87.75 | 87.75 | 87.75 | 87.75 | 87.75 | 87.75 | 87.75 | 87.75 | SS | Solar | VIC | summer
West Kiewa | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | S | Hydro | VIC | summer
Yallourn W | 1420 | 1420 | 1420 | 1420 | 1420 | 1420 | 1420 | 1420 | 1420 | 1420 | S | Fossil | VIC | summer
Yatpool Solar Farm | 0 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | SS | Solar | VIC | summer
Total | 10383.33 | 12137.28 | 12272.28 | 12367.28 | 12272.28 | 12272.28 | 12272.28 | 12367.28 | 12367.28 | 12359.28
The table above lists the latest Summer capacities for Victorian generation. Summer conditions relate to statistically predicted contribution under 10% POE maximum demand conditions.
Due to the intermittent nature of wind, wind generation capacities are de-rated to account for the output most likely to be available during times of maximum demand. AEMO refers to this as the "firm contribution" from wind generators during peak periods. These figures are 8.1% of the installed capacity during summer, and 7.3% during winter, based on AEMO's analysis of historical wind output over summer 2012-13 to 2016-17, and winter 2013 to 2017.
Due to the intermittent nature of sunlight, solar generation capacities are de-rated to account for the output most likely to be available during times of maximum demand. However, AEMO has not yet calculated contribution factors for solar, due to there being insufficient historical data to analyse for semi-scheduled solar generation in Victoria. Thus the Firm Solar Capacity values in the table below are shown as NA, and do not contribute to the total capacity in that table.
The two tables below have been included to better represent the supply availability in Victoria, by taking into account the firm contribution by semi-scheduled generation. The Summer aggregate scheduled and firm semi-scheduled generation table presents scheduled generation and aggregated firm semi-scheduled generation. The Summer aggregate available semi-scheduled generation table lists the total available capacity for semi-scheduled generation for the Summer period. The total refers to the maximum amount that can be generated from the semi-scheduled generation at the Summer reference temperatures.
Summer aggregate scheduled and firm semi-scheduled generation
PowerStation | 201819 | 201920 | 202021 | 202122 | 202223 | 202324 | 202425 | 202526 | 202627 | 202728 | DispatchType | FuelType | Region | Season
Bairnsdale | 78 | 78 | 78 | 78 | 78 | 78 | 78 | 78 | 78 | 78 | S | Fossil | VIC | summer
Ballarat Energy Storage System | 28.8 | 28.8 | 28.8 | 28.8 | 28.8 | 28.8 | 28.8 | 28.8 | 28.8 | 28.8 | S | N/A | VIC | summer
Bogong / Mackay | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | S | Hydro | VIC | summer
Dartmouth | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | S | Hydro | VIC | summer
Eildon | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | S | Hydro | VIC | summer
Gannawarra Energy Storage System | 25.33 | 25.33 | 25.33 | 25.33 | 25.33 | 25.33 | 25.33 | 25.33 | 25.33 | 25.33 | S | N/A | VIC | summer
Hume VIC | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | S | Hydro | VIC | summer
Jeeralang A | 189 | 189 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | S | Fossil | VIC | summer
Jeeralang B | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | S | Fossil | VIC | summer
Laverton North | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | S | Fossil | VIC | summer
Loy Yang A | 2144 | 2144 | 2144 | 2144 | 2144 | 2144 | 2144 | 2144 | 2144 | 2136 | S | Fossil | VIC | summer
Loy Yang B | 980 | 980 | 980 | 980 | 980 | 980 | 980 | 980 | 980 | 980 | S | Fossil | VIC | summer
Mortlake | 518 | 518 | 518 | 518 | 518 | 518 | 518 | 518 | 518 | 518 | S | Fossil | VIC | summer
Murray 1 | 950 | 855 | 855 | 950 | 855 | 855 | 855 | 950 | 950 | 950 | S | Hydro | VIC | summer
Murray 2 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | S | Hydro | VIC | summer
Newport | 475 | 475 | 475 | 475 | 475 | 475 | 475 | 475 | 475 | 475 | S | Fossil | VIC | summer
Somerton | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | S | Fossil | VIC | summer
Valley Power | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | S | Fossil | VIC | summer
West Kiewa | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | S | Hydro | VIC | summer
Yallourn W | 1420 | 1420 | 1420 | 1420 | 1420 | 1420 | 1420 | 1420 | 1420 | 1420 | S | Fossil | VIC | summer
Firm Wind Capacity | 90.0275 | 207.3114 | 218.0034 | 218.0034 | 218.0034 | 218.0034 | 218.0034 | 218.0034 | 218.0034 | 218.0034 | SS
Firm Solar Capacity | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | SS
Total | 9046.1575 | 9068.4414 | 9082.1334 | 9177.1334 | 9082.1334 | 9082.1334 | 9082.1334 | 9177.1334 | 9177.1334 | 9169.1334
Summer aggregate available semi-scheduled generation
PowerStation | 201819 | 201920 | 202021 | 202122 | 202223 | 202324 | 202425 | 202526 | 202627 | 202728 | DispatchType | FuelType | Region | Season
Ararat Wind Farm | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | SS | Wind | VIC | summer
Bald Hills Wind Farm | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | SS | Wind | VIC | summer
Bannerton Solar Park | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | SS | Solar | VIC | summer
Bulgana Green Power Hub - BESS | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | SS | N/A | VIC | summer
Bulgana Green Power Hub - Wind Farm | 0 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | SS | Wind | VIC | summer
Crowlands Wind Farm | 0 | 79.95 | 79.95 | 79.95 | 79.95 | 79.95 | 79.95 | 79.95 | 79.95 | 79.95 | SS | Wind | VIC | summer
Gannawarra Solar Farm | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | SS | Solar | VIC | summer
Karadoc Solar Farm | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | SS | Solar | VIC | summer
Kiamal Solar Farm - Stage 1 | 0 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | SS | Solar | VIC | summer
Kiata Wind Farm | 31.05 | 31.05 | 31.05 | 31.05 | 31.05 | 31.05 | 31.05 | 31.05 | 31.05 | 31.05 | SS | Wind | VIC | summer
Lal Lal Wind Energy Facility - Elaine end | 0 | 83.6 | 83.6 | 83.6 | 83.6 | 83.6 | 83.6 | 83.6 | 83.6 | 83.6 | SS | Wind | VIC | summer
Lal Lal Wind Energy Facility - Yendon end | 0 | 144.4 | 144.4 | 144.4 | 144.4 | 144.4 | 144.4 | 144.4 | 144.4 | 144.4 | SS | Wind | VIC | summer
Macarthur Wind Farm | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | SS | Wind | VIC | summer
Moorabool Wind Farm | 0 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | SS | Wind | VIC | summer
Mt Gellibrand | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | SS | Wind | VIC | summer
Mt Mercer Wind Farm | 131.2 | 131.2 | 131.2 | 131.2 | 131.2 | 131.2 | 131.2 | 131.2 | 131.2 | 131.2 | SS | Wind | VIC | summer
Murra Warra Wind Farm - stage 1 | 0 | 226 | 226 | 226 | 226 | 226 | 226 | 226 | 226 | 226 | SS | Wind | VIC | summer
Numurkah Solar Farm | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | SS | Solar | VIC | summer
Oaklands Hill Wind Farm | 41.6 | 41.6 | 41.6 | 41.6 | 41.6 | 41.6 | 41.6 | 41.6 | 41.6 | 41.6 | SS | Wind | VIC | summer
Salt Creek Wind Farm | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | SS | Wind | VIC | summer
Stockyard Hill | 0 | 400 | 532 | 532 | 532 | 532 | 532 | 532 | 532 | 532 | SS | Wind | VIC | summer
Wemen Solar Farm | 87.75 | 87.75 | 87.75 | 87.75 | 87.75 | 87.75 | 87.75 | 87.75 | 87.75 | 87.75 | SS | Solar | VIC | summer
Yatpool Solar Farm | 0 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | SS | Solar | VIC | summer
Total (Wind) | 1111.45 | 2559.4 | 2691.4 | 2691.4 | 2691.4 | 2691.4 | 2691.4 | 2691.4 | 2691.4 | 2691.4
Total (Solar) | 315.75 | 696.75 | 696.75 | 696.75 | 696.75 | 696.75 | 696.75 | 696.75 | 696.75 | 696.75
Total (Storage) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Winter Scheduled Capacities
Winter aggregate available scheduled and semi-scheduled generation
PowerStation | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | DispatchType | FuelType | Region | Season
Ararat Wind Farm | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | SS | Wind | VIC | winter
Bairnsdale | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | S | Fossil | VIC | winter
Bald Hills Wind Farm | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | SS | Wind | VIC | winter
Ballarat Energy Storage System | 29.9 | 29.9 | 29.9 | 29.9 | 29.9 | 29.9 | 29.9 | 29.9 | 29.9 | 29.9 | S | N/A | VIC | winter
Bannerton Solar Park | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | SS | Solar | VIC | winter
Bogong / Mackay | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | S | Hydro | VIC | winter
Bulgana Green Power Hub - BESS | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | SS | N/A | VIC | winter
Bulgana Green Power Hub - Wind Farm | 0 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | SS | Wind | VIC | winter
Crowlands Wind Farm | 79.95 | 79.95 | 79.95 | 79.95 | 79.95 | 79.95 | 79.95 | 79.95 | 79.95 | 79.95 | SS | Wind | VIC | winter
Dartmouth | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | S | Hydro | VIC | winter
Eildon | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | S | Hydro | VIC | winter
Gannawarra Energy Storage System | 25.33 | 25.33 | 25.33 | 25.33 | 25.33 | 25.33 | 25.33 | 25.33 | 25.33 | 25.33 | S | N/A | VIC | winter
Gannawarra Solar Farm | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | SS | Solar | VIC | winter
Hume VIC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S | Hydro | VIC | winter
Jeeralang A | 224 | 224 | 224 | 224 | 224 | 224 | 224 | 224 | 224 | 224 | S | Fossil | VIC | winter
Jeeralang B | 255 | 255 | 255 | 255 | 255 | 255 | 255 | 255 | 255 | 255 | S | Fossil | VIC | winter
Karadoc Solar Farm | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | SS | Solar | VIC | winter
Kiamal Solar Farm - Stage 1 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | SS | Solar | VIC | winter
Kiata Wind Farm | 31.05 | 31.05 | 31.05 | 31.05 | 31.05 | 31.05 | 31.05 | 31.05 | 31.05 | 31.05 | SS | Wind | VIC | winter
Lal Lal Wind Energy Facility - Elaine end | 83.6 | 83.6 | 83.6 | 83.6 | 83.6 | 83.6 | 83.6 | 83.6 | 83.6 | 83.6 | SS | Wind | VIC | winter
Lal Lal Wind Energy Facility - Yendon end | 144.4 | 144.4 | 144.4 | 144.4 | 144.4 | 144.4 | 144.4 | 144.4 | 144.4 | 144.4 | SS | Wind | VIC | winter
Laverton North | 340 | 340 | 340 | 340 | 340 | 340 | 340 | 340 | 340 | 340 | S | Fossil | VIC | winter
Loy Yang A | 2210 | 2210 | 2210 | 2210 | 2210 | 2210 | 2210 | 2210 | 2210 | 2210 | S | Fossil | VIC | winter
Loy Yang B | 1110 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | S | Fossil | VIC | winter
Macarthur Wind Farm | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | SS | Wind | VIC | winter
Moorabool Wind Farm | 320 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | SS | Wind | VIC | winter
Mortlake | 584 | 584 | 584 | 584 | 584 | 584 | 584 | 584 | 584 | 584 | S | Fossil | VIC | winter
Mt Gellibrand | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | SS | Wind | VIC | winter
Mt Mercer Wind Farm | 131.2 | 131.2 | 131.2 | 131.2 | 131.2 | 131.2 | 131.2 | 131.2 | 131.2 | 131.2 | SS | Wind | VIC | winter
Murra Warra Wind Farm - stage 1 | 226 | 226 | 226 | 226 | 226 | 226 | 226 | 226 | 226 | 226 | SS | Wind | VIC | winter
Murray 1 | 855 | 950 | 950 | 950 | 950 | 855 | 950 | 950 | 950 | 950 | S | Hydro | VIC | winter
Murray 2 | 560 | 420 | 420 | 420 | 420 | 560 | 560 | 560 | 560 | 560 | S | Hydro | VIC | winter
Newport | 510 | 510 | 510 | 510 | 510 | 510 | 510 | 510 | 510 | 510 | S | Fossil | VIC | winter
Numurkah Solar Farm | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | SS | Solar | VIC | winter
Oaklands Hill Wind Farm | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | SS | Wind | VIC | winter
Salt Creek Wind Farm | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | SS | Wind | VIC | winter
Somerton | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | S | Fossil | VIC | winter
Stockyard Hill | 0 | 532 | 532 | 532 | 532 | 532 | 532 | 532 | 532 | 532 | SS | Wind | VIC | winter
Valley Power | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | S | Fossil | VIC | winter
Wemen Solar Farm | 87.75 | 87.75 | 87.75 | 87.75 | 87.75 | 87.75 | 87.75 | 87.75 | 87.75 | 87.75 | SS | Solar | VIC | winter
West Kiewa | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | S | Hydro | VIC | winter
Yallourn W | 1528 | 1528 | 1528 | 1528 | 1528 | 1528 | 1528 | 1528 | 1528 | 1528 | S | Fossil | VIC | winter
Yatpool Solar Farm | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | SS | Solar | VIC | winter
Total | 12172.78 | 12913.78 | 12913.78 | 12913.78 | 12913.78 | 12958.78 | 13053.78 | 13053.78 | 13053.78 | 13053.78
The table above lists the latest Winter capacities for Victorian generation. Winter conditions relate to statistically predicted contribution under 10% POE maximum demand conditions.
Due to the intermittent nature of wind, wind generation capacities are de-rated to account for the output most likely to be available during times of maximum demand. AEMO refers to this as the "firm contribution" from wind generators during peak periods. These figures are 8.1% of the installed capacity during summer, and 7.3% during winter, based on AEMO's analysis of historical wind output over summer 2012-13 to 2016-17, and winter 2013 to 2017.
Due to the intermittent nature of sunlight, solar generation capacities are de-rated to account for the output most likely to be available during times of maximum demand. However, AEMO has not yet calculated contribution factors for solar, due to there being insufficient historical data to analyse for semi-scheduled solar generation in Victoria. Thus the Firm Solar Capacity values in the table below are shown as NA, and do not contribute to the total capacity in that table.
The two tables below have been included to better represent the supply availability in Victoria, by taking into account the firm contribution by semi-scheduled generation. The Winter aggregate scheduled and firm semi-scheduled generation table presents scheduled generation and aggregated firm semi-scheduled generation. The Winter aggregate available semi-scheduled generation table lists the total available capacity for semi-scheduled generation for the Winter period. The total refers to the maximum amount that can be generated from the semi-scheduled generation at the Winter reference temperatures.
Winter aggregate scheduled and firm semi-scheduled generation
PowerStation | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | DispatchType | FuelType | Region | Season
Bairnsdale | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | S | Fossil | VIC | winter
Ballarat Energy Storage System | 29.9 | 29.9 | 29.9 | 29.9 | 29.9 | 29.9 | 29.9 | 29.9 | 29.9 | 29.9 | S | N/A | VIC | winter
Bogong / Mackay | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | S | Hydro | VIC | winter
Dartmouth | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | S | Hydro | VIC | winter
Eildon | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | S | Hydro | VIC | winter
Gannawarra Energy Storage System | 25.33 | 25.33 | 25.33 | 25.33 | 25.33 | 25.33 | 25.33 | 25.33 | 25.33 | 25.33 | S | N/A | VIC | winter
Hume VIC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S | Hydro | VIC | winter
Jeeralang A | 224 | 224 | 224 | 224 | 224 | 224 | 224 | 224 | 224 | 224 | S | Fossil | VIC | winter
Jeeralang B | 255 | 255 | 255 | 255 | 255 | 255 | 255 | 255 | 255 | 255 | S | Fossil | VIC | winter
Laverton North | 340 | 340 | 340 | 340 | 340 | 340 | 340 | 340 | 340 | 340 | S | Fossil | VIC | winter
Loy Yang A | 2210 | 2210 | 2210 | 2210 | 2210 | 2210 | 2210 | 2210 | 2210 | 2210 | S | Fossil | VIC | winter
Loy Yang B | 1110 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | S | Fossil | VIC | winter
Mortlake | 584 | 584 | 584 | 584 | 584 | 584 | 584 | 584 | 584 | 584 | S | Fossil | VIC | winter
Murray 1 | 855 | 950 | 950 | 950 | 950 | 855 | 950 | 950 | 950 | 950 | S | Hydro | VIC | winter
Murray 2 | 560 | 420 | 420 | 420 | 420 | 560 | 560 | 560 | 560 | 560 | S | Hydro | VIC | winter
Newport | 510 | 510 | 510 | 510 | 510 | 510 | 510 | 510 | 510 | 510 | S | Fossil | VIC | winter
Somerton | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | S | Fossil | VIC | winter
Valley Power | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | S | Fossil | VIC | winter
West Kiewa | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | S | Hydro | VIC | winter
Yallourn W | 1528 | 1528 | 1528 | 1528 | 1528 | 1528 | 1528 | 1528 | 1528 | 1528 | S | Fossil | VIC | winter
Firm Wind Capacity | 148.3214 | 201.3194 | 201.3194 | 201.3194 | 201.3194 | 201.3194 | 201.3194 | 201.3194 | 201.3194 | 201.3194 | SS
Firm Solar Capacity | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | SS
Total | 9592.5514 | 9640.5494 | 9640.5494 | 9640.5494 | 9640.5494 | 9685.5494 | 9780.5494 | 9780.5494 | 9780.5494 | 9780.5494
Winter aggregate available semi-scheduled generation
PowerStation | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | DispatchType | FuelType | Region | Season
Ararat Wind Farm | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | SS | Wind | VIC | winter
Bald Hills Wind Farm | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | SS | Wind | VIC | winter
Bannerton Solar Park | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | SS | Solar | VIC | winter
Bulgana Green Power Hub - BESS | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | SS | N/A | VIC | winter
Bulgana Green Power Hub - Wind Farm | 0 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | SS | Wind | VIC | winter
Crowlands Wind Farm | 79.95 | 79.95 | 79.95 | 79.95 | 79.95 | 79.95 | 79.95 | 79.95 | 79.95 | 79.95 | SS | Wind | VIC | winter
Gannawarra Solar Farm | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | SS | Solar | VIC | winter
Karadoc Solar Farm | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | SS | Solar | VIC | winter
Kiamal Solar Farm - Stage 1 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | SS | Solar | VIC | winter
Kiata Wind Farm | 31.05 | 31.05 | 31.05 | 31.05 | 31.05 | 31.05 | 31.05 | 31.05 | 31.05 | 31.05 | SS | Wind | VIC | winter
Lal Lal Wind Energy Facility - Elaine end | 83.6 | 83.6 | 83.6 | 83.6 | 83.6 | 83.6 | 83.6 | 83.6 | 83.6 | 83.6 | SS | Wind | VIC | winter
Lal Lal Wind Energy Facility - Yendon end | 144.4 | 144.4 | 144.4 | 144.4 | 144.4 | 144.4 | 144.4 | 144.4 | 144.4 | 144.4 | SS | Wind | VIC | winter
Macarthur Wind Farm | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | SS | Wind | VIC | winter
Moorabool Wind Farm | 320 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | SS | Wind | VIC | winter
Mt Gellibrand | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | SS | Wind | VIC | winter
Mt Mercer Wind Farm | 131.2 | 131.2 | 131.2 | 131.2 | 131.2 | 131.2 | 131.2 | 131.2 | 131.2 | 131.2 | SS | Wind | VIC | winter
Murra Warra Wind Farm - stage 1 | 226 | 226 | 226 | 226 | 226 | 226 | 226 | 226 | 226 | 226 | SS | Wind | VIC | winter
Numurkah Solar Farm | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | SS | Solar | VIC | winter
Oaklands Hill Wind Farm | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | SS | Wind | VIC | winter
Salt Creek Wind Farm | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | SS | Wind | VIC | winter
Stockyard Hill | 0 | 532 | 532 | 532 | 532 | 532 | 532 | 532 | 532 | 532 | SS | Wind | VIC | winter
Wemen Solar Farm | 87.75 | 87.75 | 87.75 | 87.75 | 87.75 | 87.75 | 87.75 | 87.75 | 87.75 | 87.75 | SS | Solar | VIC | winter
Yatpool Solar Farm | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | SS | Solar | VIC | winter
Total (Wind) | 2031.8 | 2757.8 | 2757.8 | 2757.8 | 2757.8 | 2757.8 | 2757.8 | 2757.8 | 2757.8 | 2757.8
Total (Solar) | 696.75 | 696.75 | 696.75 | 696.75 | 696.75 | 696.75 | 696.75 | 696.75 | 696.75 | 696.75
Total (Solar) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Existing NS Generation
Existing non-scheduled generation
Power Station | Owner | Nameplate Capacity (MW) | Technology Type | Fuel Type | Service Status | Region | summary_bucket | summary_status
200 Victoria St | Cogent Energy Pty Ltd | 0.386 | Compression Reciprocating Engine | Natural Gas Pipeline | In service | VIC | Gas other | Existing less Announced Withdrawal
321 Exhibition Street Trigen | Cogent Energy | 1.2 | Spark Ignition Reciprocating Engine | Natural Gas Pipeline | In service | VIC | Gas other | Existing less Announced Withdrawal
990 Latrobe St | Cogent Energy Pty Ltd | 0.386 | Compression Reciprocating Engine | Natural Gas Pipeline | In service | VIC | Gas other | Existing less Announced Withdrawal
Aeroten Leongatha Solar | TBA | 0.1996 | PV Panels | Solar | In service | VIC | Solar | Existing less Announced Withdrawal
Ballarat | LMS ENERGY Pty Ltd | 0.789 | Spark Ignition Reciprocating Engine | Landfill Methane / Landfill Gas | In service | VIC | Biomass | Existing less Announced Withdrawal
Ballarat Base Hospital | Ballarat Base Hospital | 3.06 | Spark Ignition Reciprocating Engine | Natural Gas Pipeline | In service | VIC | Gas other | Existing less Announced Withdrawal
Banimboola | AGL | 12.2 | Hydro - Gravity | Water | In service | VIC | Water | Existing less Announced Withdrawal
Bayswood Timber Hallam VIC | Bayswood Timber | 0.1502 | PV Panels | Solar | In service | VIC | Solar | Existing less Announced Withdrawal
Beaconhills College Berwick | TBA | 0.2002 | PV Panels | Solar | In service | VIC | Solar | Existing less Announced Withdrawal
Bendigo | LMS ENERGY Pty Ltd | 0.5 | Spark Ignition Reciprocating Engine | Landfill Methane / Landfill Gas | In service | VIC | Biomass | Existing less Announced Withdrawal
Berwick | EDL LFG Vic Pty Ltd | 4.57 | Spark Ignition Reciprocating Engine | Landfill Methane / Landfill Gas | In service | VIC | Biomass | Existing less Announced Withdrawal
Boronia Mini Hydro | TBA | 0.11 | Hydro - Gravity | Water | In service | VIC | Water | Existing less Announced Withdrawal
Bridgewater | Ceramet | 1.3 | PV Panels | Solar | In service | VIC | Solar | Existing less Announced Withdrawal
Broadmeadows | EDL LFG Vic Pty Ltd | 6.18 | Spark Ignition Reciprocating Engine | Landfill Methane / Landfill Gas | In service | VIC | Biomass | Existing less Announced Withdrawal
Brooklyn | EDL LFG Vic Pty Ltd | 2.83 | Spark Ignition Reciprocating Engine | Landfill Methane / Landfill Gas | In service | VIC | Biomass | Existing less Announced Withdrawal
Bunurong 260 kW Solar PV Bangholme | TBA | 0.26 | PV Panels | Solar | In service | VIC | Solar | Existing less Announced Withdrawal
Cardinia Creek Mini-Hydro | TBA | 0.09 | Hydro - Gravity | Water | In service | VIC | Water | Existing less Announced Withdrawal
CARINA WEST H2E | TBA | 3.1 | Steam Sub Critical | Bagasse | In service | VIC | Biomass | Existing less Announced Withdrawal
Cedar Meats Solar Geelong | Cedar Meats | 0.1998 | PV Panels | Solar | In service | VIC | Solar | Existing less Announced Withdrawal
Challicum Hills | Pacific Hydro Challicum Hills Pty Ltd | 52.5 | Wind - Onshore | Wind | In service | VIC | Wind | Existing less Announced Withdrawal
Chepstowe Wind Farm | Chepstowe Wind Farm Pty Ltd | 6.15 | Wind - Onshore | Wind | In service | VIC | Wind | Existing less Announced Withdrawal
Clayton | EDL LFG Vic Pty Ltd | 12 | Spark Ignition Reciprocating Engine | Landfill Methane / Landfill Gas | In service | VIC | Biomass | Existing less Announced Withdrawal
Clover | AGL | 29 | Hydro - Gravity | Water | In service | VIC | Water | Existing less Announced Withdrawal
Codrington | Energy Pacific Vic Pty Ltd | 18.2 | Wind - Onshore | Wind | In service | VIC | Wind | Existing less Announced Withdrawal
Coonooer Bridge Wind Farm | Coonooer Bridge Wind Farm Pty Ltd | 19.8 | Wind - Onshore | Wind | In service | VIC | Wind | Existing less Announced Withdrawal
Corio | EDL LFG Vic Pty Ltd | 1 | Spark Ignition Reciprocating Engine | Landfill Methane / Landfill Gas | In service | VIC | Biomass | Existing less Announced Withdrawal
Crown Melbourne | Crown Resorts | 5.58 | Spark Ignition Reciprocating Engine | Natural Gas Pipeline | In service | VIC | Gas other | Existing less Announced Withdrawal
Dandenong PEP | Cogent Energy Pty Ltd | 2 | Compression Reciprocating Engine | Natural Gas Pipeline | In service | VIC | Gas other | Existing less Announced Withdrawal
Eildon Small Hydro | Pacific Hydro Investments Pty Ltd | 4.5 | Hydro - Gravity | Water | In service | VIC | Water | Existing less Announced Withdrawal
Flavorite Marketing | TBA | 0.1494 | PV Panels | Solar | In service | VIC | Solar | Existing less Announced Withdrawal
Glenmaggie Hydro | Pacific Hydro Investments Pty Ltd | 3.8 | Hydro - Gravity | Water | In service | VIC | Water | Existing less Announced Withdrawal
Hallam Road | LMS Energy Pty Ltd | 8.984 | Spark Ignition Reciprocating Engine | Landfill Methane / Landfill Gas | In service | VIC | Biomass | Existing less Announced Withdrawal
HYMIVC06 Belgrave-Hallam Rd Micro Hydro | South East Water | 0.25 | Hydro - Gravity | Water | In service | VIC | Water | Existing less Announced Withdrawal
Jessica Way Truganina Solar | TBA | 0.365 | PV Panels | Solar | In service | VIC | Solar | Existing less Announced Withdrawal
JL King & Co 150kW- Solar- | TBA | 0.15 | PV Panels | Solar | In service | VIC | Solar | Existing less Announced Withdrawal
Leonards Hill | Hepburn Community Wind Park Co-operative Limited | 4.1 | Wind - Onshore | Wind | In service | VIC | Wind | Existing less Announced Withdrawal
Longford | Longford Gas Plant | 44.8 | OCGT | Natural Gas Pipeline | In service | VIC | OCGT | Existing less Announced Withdrawal
Maroona Wind Farm | Myamba Developments Pty Ltd | 7.2 | Wind - Onshore | Wind | In service | VIC | Wind | Existing less Announced Withdrawal
Midland Highway Orrvale | TBA | 0.509 | PV Panels | Solar | In service | VIC | Solar | Existing less Announced Withdrawal
Mornington Waste Disposal Facility | LMS Energy Pty Ltd | 0.77 | Spark Ignition Reciprocating Engine | Landfill Methane / Landfill Gas | In service | VIC | Biomass | Existing less Announced Withdrawal
Mortons Lane Wind Farm | Mortons Lane Windfarm Pty Ltd | 19.5 | Wind - Onshore | Wind | In service | VIC | Wind | Existing less Announced Withdrawal
Mount Waverley Mini Hydro | TBA | 0.355 | Hydro - Gravity | Water | In service | VIC | Water | Existing less Announced Withdrawal
Newhaven College | TBA | 0.2432 | PV Panels | Solar | In service | VIC | Solar | Existing less Announced Withdrawal
Portland Wind Farm | Pacific Hydro Portland Wind Farm Pty Ltd | 151.7 | Wind - Onshore | Wind | In service | VIC | Wind | Existing less Announced Withdrawal
Qenos Cogeneration Facility | AGL | 21 | CCGT | Natural Gas Pipeline | In service | VIC | CCGT | Existing less Announced Withdrawal
REWASTE WOLLERT | TBA | 1.06 | Reciprocating engines (gas/diesel) | Landfill Methane / Landfill Gas | In service | VIC | Biomass | Existing less Announced Withdrawal
Rubicon Mountain Streams | AGL | 13.5 | Hydro - Gravity | Water | In service | VIC | Water | Existing less Announced Withdrawal
SALE HOSPITAL - SOLAR | TBA | 0.2636 | PV Panels | Solar | In service | VIC | Solar | Existing less Announced Withdrawal
SCS Shepparton | TBA | 0.3 | PV Panels | Solar | In service | VIC | Solar | Existing less Announced Withdrawal
Shamic Sheetmetal | TBA | 0.3052 | PV Panels | Solar | In service | VIC | Solar | Existing less Announced Withdrawal
Shepparton | LMS ENERGY Pty Ltd | 0.78 | Spark Ignition Reciprocating Engine | Non-biomass recycled municipal and industrial materials | In service | VIC | Biomass | Existing less Announced Withdrawal
Shepparton Wastewater Treatment Facility | Diamond Energy Pty Ltd | 1.1 | Spark Ignition Reciprocating Engine | Sewerage / Waste Water | In service | VIC | Biomass | Existing less Announced Withdrawal
Springvale | EDL LFG Vic Pty Ltd | 4.2 | Spark Ignition Reciprocating Engine | Landfill Methane / Landfill Gas | In service | VIC | Biomass | Existing less Announced Withdrawal
Swan Hill Solar Farm 1 Unit 1 | Solar Powerstations Victoria Pty Ltd | 7.2 | PV-Tracking Flat panel | Solar | In service | VIC | Solar | Existing less Announced Withdrawal
Swan Hill Solar Farm 2 Unit 1 | Solar Powerstations Victoria Pty Ltd | 7.2 | PV-Tracking Flat panel | Solar | In service | VIC | Solar | Existing less Announced Withdrawal
Tatura Biomass Generator | Diamond Energy Pty Ltd | 1.1 | Spark Ignition Reciprocating Engine | Sewerage / Waste Water | In service | VIC | Biomass | Existing less Announced Withdrawal
Todae Solar – La Trobe University Bendigo | TBA | 0.3498 | PV Panels | Solar | In service | VIC | Solar | Existing less Announced Withdrawal
Todae Solar – La Trobe University Wodonga | TBA | 0.223 | PV Panels | Solar | In service | VIC | Solar | Existing less Announced Withdrawal
Todae Solar - Nillumbik | TBA | 0.1245 | PV Panels | Solar | In service | VIC | Solar | Existing less Announced Withdrawal
Todae Solar SV - Eltham | TBA | 0.1842 | PV Panels | Solar | In service | VIC | Solar | Existing less Announced Withdrawal
Toora | Ratch Australia | 21 | Wind - Onshore | Wind | In service | VIC | Wind | Existing less Announced Withdrawal
University of Melbourne Archives Brunswick | TBA | 0.0916 | PV Panels | Solar | In service | VIC | Solar | Existing less Announced Withdrawal
University of Melbourne McCoy Carlton | TBA | 0.0733 | PV Panels | Solar | In service | VIC | Solar | Existing less Announced Withdrawal
University of Melbourne Performing Arts Centre Southbank | TBA | 0.1365 | PV Panels | Solar | In service | VIC | Solar | Existing less Announced Withdrawal
University of Melbourne Peter Hall Parkville | TBA | 0.0478 | PV Panels | Solar | In service | VIC | Solar | Existing less Announced Withdrawal
University of Melbourne Sports Centre Parkville | TBA | 0.1608 | PV Panels | Solar | In service | VIC | Solar | Existing less Announced Withdrawal
University of Melbourne The Spot Carlton | TBA | 0.0588 | PV Panels | Solar | In service | VIC | Solar | Existing less Announced Withdrawal
Vawdrey Manufacturing | TBA | 0.7526 | PV Panels | Solar | In service | VIC | Solar | Existing less Announced Withdrawal
Wantirna Mini Hydro | TBA | 0.132 | Hydro - Gravity | Water | In service | VIC | Water | Existing less Announced Withdrawal
Waubra | Pyrenees Wind Energy Developments | 192 | Wind - Onshore | Wind | In service | VIC | Wind | Existing less Announced Withdrawal
William Hovel | Pacific Hydro Investments Pty Ltd | 1.8 | Hydro - Gravity | Water | In service | VIC | Water | Existing less Announced Withdrawal
Wollert | LMS Energy Pty Ltd | 6.738 | Spark Ignition Reciprocating Engine | Landfill Methane / Landfill Gas | In service | VIC | Biomass | Existing less Announced Withdrawal
Wonthaggi Wind Farm | Vision Super Pty Ltd | 12 | Wind - Onshore | Wind | In service | VIC | Wind | Existing less Announced Withdrawal
Wyndham Renewable Energy Facility | LMS Energy Pty Ltd | 1.903 | Spark Ignition Reciprocating Engine | Landfill Methane / Landfill Gas | In service | VIC | Biomass | Existing less Announced Withdrawal
Yaloak South Wind Farm | Pacific Hydro Yaloak South Pty Ltd | 28.7 | Wind - Onshore | Wind | In service | VIC | Wind | Existing less Announced Withdrawal
Yambuk | Energy Pacific Vic Pty Ltd | 30 | Wind - Onshore | Wind | In service | VIC | Wind | Existing less Announced Withdrawal
Yarrawonga | AGL | 9.5 | Hydro - Gravity | Water | In service | VIC | Water | Existing less Announced Withdrawal
Zilzie Winery Solar System | TBA | 0.1134 | PV Panels | Solar | In service | VIC | Solar | Existing less Announced Withdrawal
Total |  | 795.4145

## New Developments
Projects under development
Project | Owner | Unit ID | Technology Type | Fuel Type | Unit Status | Nameplate Capacity (MW) | Dispatch Type | Full Commercial Use Date | Source | summary_status | nameplatecapacity_mw_max | capacity_empty | region | summary_bucket
Alberton Wind Farm | Synergy Wind Pty Ltd | 1 - 34 | Wind - Onshore | Wind | Publicly Announced | 122.4 | SS |  | http://www.synergy-wind.com/ | Proposed | 122.4 | No | VIC | Wind
Ballarat Energy Storage System | AusNet Services | 1 | Battery Storage | N/A | Com* | 30 MW / 30 MWh | S | Summer 2018-19 | https://www.spotless.com/clients/ballarat-battery-energy-storage-system/ | Committed | 30 | No | VIC | Battery Storage
Bannerton Solar Park | Foresight Solar Australia Pty Ltd | 1 | PV panels | Solar | Committed | 88 | SS | Sep 2018 | http://www.bannertonsolarfarm.com.au/ www.foresightgroup.eu | Committed | 88 | No | VIC | Solar
Ben More | Ratch Australia | 23 - 37 | Wind - Onshore | Wind | Publicly Announced | 70 - 110 | SS |  |  | Proposed | 110 | No | VIC | Wind
Berrimal | ACCIONA Energy | 1-24 | Wind - Onshore | Wind | Publicly Announced | 24 - 66 | SS |  |  | Proposed | 66 | No | VIC | Wind
Berrimal Wind Farm | Acciona Energy Australia Global | 1-16 | Wind - Onshore | Wind | Publicly Announced | 72 | SS |  | http://www.acciona.com.au/projects/energy/wind-power/berrimal-wind-farm/ | Proposed | 72 | No | VIC | Wind
Berrybank Wind Farm | Berrybank Development Pty Ltd | Units 1-79 | Wind - Onshore | Wind | Publicly Announced | 331.8 | SS | Sep 2020 |  | Proposed | 331.8 | No | VIC | Wind
Bulgana Green Power Hub - BESS | Bulgana Wind Farm Pty Ltd | 1 | Battery Storage | N/A | Com* | 20 MW / 34 MWh | SS | Aug 2019 | https://bulganawindfarm.com.au/ | Committed | 20 | No | VIC | Battery Storage
Bulgana Green Power Hub - Wind Farm | Bulgana Wind Farm Pty Ltd | 1-56 | Wind - Onshore | Wind | Com* | 194 | SS | May 2019 | https://bulganawindfarm.com.au/ | Committed | 194 | No | VIC | Wind
Cherry Tree Wind Farm | Infigen Energy | Units 1-16 | Wind - Onshore | Wind | Publicly Announced | 55 | SS |  | https://www.infigenenergy.com/about-us/news/cherry-tree-wind-farm-development-approval/ | Proposed | 55 | No | VIC | Wind
Crowlands Wind Farm | Pacific Hydro Crowlands Pty Ltd | Units 1-39 | Wind - Onshore | Wind | Committed | 79.95 | SS | Winter 2019 | www.pacifichydro.com.au | Committed | 79.95 | No | VIC | Wind
Dundonnell | Tilt Renewables | 1-80 | Wind - Onshore | Wind | Publicly Announced | 336 | SS | Jan 2020 |  | Proposed | 336 | No | VIC | Wind
Ferguson Wind Farm | Future Energy Pty Ltd | 1 | Wind - Onshore | Wind | Publicly Announced | 9 | NS |  |  | Proposed | 9 | No | VIC | Wind
Gannawarra Energy Storage System | GESS Co | 1 | Battery Storage | N/A | Com* | 25 MW / 50 MWh | S | Summer 2018-19 | http://edifyenergy.com/projects/gannawarra-energy-storage-system/ | Committed | 25 | No | VIC | Battery Storage
Girgarre Solar Farm | Leeson Group | TBA | TBA | Solar | Publicly Announced | 118 | SS |  | https://www.leesongroup.com.au/single-post/2018/05/24/Girgarre-Solar-Farm---Shepparton-News | Proposed | 118 | No | VIC | Solar
Glenrowan Solar Farm | ESCO Pacific | 140 | PV panels | Solar | Publicly Announced | 140 | SS |  |  | Proposed | 140 | No | VIC | Solar
Glenrowan Sun Farm | Overland Sun Farming Pty Ltd | Solar Panels | PV-Tracking Flat panel | Solar | Publicly Announced | 110 | SS |  | http://www.overlandsunfarming.com.au/sun-farms.html | Proposed | 110 | No | VIC | Solar
Golden Plains Wind Farm | Westwind Energy Pty Ltd | 1-228 | Wind - Onshore | Wind | Publicly Announced | 800 - 1100 | SS | Oct 2024 | http://w-wind.com.au/golden-plains-wind-farm | Proposed | 1100 | No | VIC | Wind
GV Community Energy | GV Community Energy | 1 | PV panels | Solar | Publicly Announced | 12 | NS |  |  | Proposed | 12 | No | VIC | Solar
Hawkesdale Wind Farm | Ryan Corner Development Pty Ltd | Units 1-26 | Wind - Onshore | Wind | Publicly Announced | 109.2 | SS |  |  | Proposed | 109.2 | No | VIC | Wind
Horsham Solar Farm | ESCO Pacific | TBA | PV panels | Solar | Publicly Announced | 130 | SS |  | http://horshamsolarfarm.com.au/ | Proposed | 130 | No | VIC | Solar
Inverleigh Solar Farm | TBA | 22 | PV panels | Solar | Publicly Announced | 22 | SS |  | http://www.inverleighwindfarm.net/ | Proposed | 22 | No | VIC | Solar
Inverleigh Storage | TBA | 1 | Battery Storage | N/A | Publicly Announced | 12 | SS |  | http://www.inverleighwindfarm.net/ | Proposed | 12 | No | VIC | Battery Storage
Inverleigh Wind Farm | Woolsthorpe Wind Farm Pty Ltd | 16 | Wind - Onshore | Wind | Publicly Announced | 76.8 | SS |  | http://www.inverleighwindfarm.net/ | Proposed | 76.8 | No | VIC | Wind
Iraak Solar Farm | BayWa r.e. Solar Project Pty Ltd | 1 | PV panels | Solar | Publicly Announced | 90 | SS |  |  | Proposed | 90 | No | VIC | Solar
Karadoc Solar Farm | Overland Sun Farming Pty Ltd | Solar Panels | PV-Tracking Flat panel | Solar | Com* | 90 | SS | Summer 2018-19 |  | Committed | 90 | No | VIC | Solar
Kerang Solar Farm | Acciona Energy Australia Global | 1 | PV panels | Solar | Publicly Announced | 37.1 | SS |  | http://www.acciona.com.au/projects/energy/solar-photovoltaic/kerang-solar/ | Proposed | 37.1 | No | VIC | Solar
Kiamal Solar Farm - Stage 1 | Total Eren S.A. | Units 1 - 150 | PV-Tracking Flat panel | Solar | Com* | 200 | SS | Winter 2019 |  | Committed | 200 | No | VIC | Solar
Kiamal Solar Farm - Stage 2 | Total Eren S.A. | Units 1 - TBD | PV-Tracking Flat panel | Solar | Publicly Announced | 150 | SS |  |  | Proposed | 150 | No | VIC | Solar
Lal Lal Wind Energy Facility - Elaine end | Westwind Energy Pty Ltd | 39-60 | Wind - Onshore | Wind | Com* | 83.6 | SS | Jul 2019 |  | Committed | 83.6 | No | VIC | Wind
Lal Lal Wind Energy Facility - Yendon end | Northleaf /InfraRed/Macquarie Capital | 1-38 | Wind - Onshore | Wind | Com* | 144.4 | SS | Mar 2019 | http://www.lallalwindfarms.com.au/ | Committed | 144.4 | No | VIC | Wind
Loy Yang B Upgrade | Alinta | TBA | Steam Sub Critical | Brown Coal | Upgrade | 80 | S | Summer 2020/21 |  | Upgrade | 80 | No | VIC | Coal
Mallee Solar Park | EnergyAustralia | 1 | PV panels | Solar | Publicly Announced | 250 | SS |  |  | Proposed | 250 | No | VIC | Solar
Mildura Power Station | Ceramet | PV Solar | PV-Tracking Flat panel | Solar | Publicly Announced | 9.6 | SS |  |  | Proposed | 9.6 | No | VIC | Solar
Moira Solar Farm | X-Elio Australia Pty Ltd | 1 | PV panels | Solar | Publicly Announced | 40 | SS |  |  | Proposed | 40 | No | VIC | Solar
Moorabool Wind Farm | Goldwind | Units 1-104 | Wind - Onshore | Wind | Committed | 320 | SS | Sep 2019 | http://mooraboolwindfarm.com/ | Committed | 320 | No | VIC | Wind
Mortlake Expansion | Origin Energy | Mortlake 21 Mortlake 22 Mortlake 23 | TBA | TBA | Publicly Announced | 165 | S |  |  | Proposed | 165 | No | VIC | OCGT
Mortlake South | ACCIONA Energy | 1-35 | Wind - Onshore | Wind | Publicly Announced | 157.5 | SS |  | http://www.acciona.com.au/projects/energy/wind-power/mortlake-south-wind-farm/ | Proposed | 157.5 | No | VIC | Wind
Mount Fyans | Woolnorth Wind Farm Holding | 1-88 | Wind - Onshore | Wind | Publicly Announced | 300 | SS |  | www.woolnorthwind.com.au | Proposed | 300 | No | VIC | Wind
Mt Gellibrand | ACCIONA Energy | 1-22 23-44 | Wind - Onshore | Wind | Committed | 132 | SS | Winter 2018 |  | Committed | 132 | No | VIC | Wind
Murra Warra Solar Farm | RES Australia Pty Ltd | 1 | PV panels | Solar | Publicly Announced | 200 | SS |  |  | Proposed | 200 | No | VIC | Solar
Murra Warra Wind Farm - stage 1 | Murra Warra Project Co Pty Ltd | 1-61 | Wind - Onshore | Wind | Committed | 225.7 | SS | Winter 2019 | http://www.murrawarra-windfarm.com/ | Committed | 225.7 | No | VIC | Wind
Murra Warra Wind Farm - stage 2 | Murra Warra Project Co Pty Ltd | 1-55 | Wind - Onshore | Wind | Publicly Announced | 203.5 | SS |  | http://www.murrawarra-windfarm.com/ | Proposed | 203.5 | No | VIC | Wind
Naring Solar Farm | Lightsource | TBA | PV panels | Solar | Publicly Announced | 60 | SS |  | http://www.moira.vic.gov.au/files/7fadec2c-74c3-4c22-97da-a88000c60b87/Planning_Report_-_Naring_Solar_Farm_-_Final.pdf | Proposed | 60 | No | VIC | Solar
Naroghid | Alinta Energy Retail Sales Pty Ltd | Unit 1 | Wind - Onshore | Wind | Publicly Announced | 50 | SS | Feb 2020 | http://naroghidwindfarm.net/ | Proposed | 50 | No | VIC | Wind
Nhill Wind Farm | BayWa r.e. | 2 | Wind - Onshore | Wind | Emerging | 7.2 | NS | Mar 2019 | http://www.baywa-re.com.au/en/projects/nhill/ | Proposed | 7.2 | No | VIC | Wind
Nowingi Solar Storage - Solar | Lyon Solar | Solar Panels | PV-Tracking Flat panel | Solar | Publicly Announced | 250 | SS |  |  | Proposed | 250 | No | VIC | Solar
Nowingi Solar Storage - Storage | Lyon Solar | TBA | Battery Storage | Storage | Publicly Announced | 80 MW / 320 MWh | S |  | http://www.lyoninfrastructure.com.au/projects/nowingi-solar-storage/ | Proposed | 80 | No | VIC | Battery Storage
Numurkah Solar Farm | Neoen | Solar Panels | PV panels | Solar | Committed | 100 | SS | May 2019 | https://numurkahsolarfarm.com.au/ | Committed | 100 | No | VIC | Solar
Ouyen Solar Farm | BayWa r.e. Solar Project Pty Ltd | 1 | PV panels | Solar | Publicly Announced | 10 | NS |  |  | Proposed | 10 | No | VIC | Solar
Penshurst | RES Australia Pty Ltd | 1-134 | Wind - Onshore | Wind | Publicly Announced | 198 | SS |  |  | Proposed | 198 | No | VIC | Wind
Port Phillip Heads Tidal Energy Project | Tenax Energy | 1 | Tidal | Water | Publicly Announced | 34 | NS |  |  | Proposed | 34 | No | VIC | Water
Prairie | Pacific Hydro Developments Australia | Units 1-40 | PV-Tracking Flat panel | Solar | Publicly Announced | 100 - 250 | SS | Jun 2020 |  | Proposed | 250 | No | VIC | Solar
Rifle Butts Wind Farm | NewEn | TBA | TBA | Wind | Publicly Announced | 40 | SS |  | http://www.newen.com.au/project/rifle-butts-wind-farm/ | Proposed | 40 | No | VIC | Wind
Ryan Corner Wind Farm | Ryan Corner Development Pty Ltd | Units 1-56 | Wind - Onshore | Wind | Publicly Announced | 235.2 | SS |  |  | Proposed | 235.2 | No | VIC | Wind
Shepparton Solar Farm | Neoen | Solar Panels | PV panels | Solar | Publicly Announced | 100 | SS |  |  | Proposed | 100 | No | VIC | Solar
Spring Hill Wind Farm | BayWa r.e. | 2 | Wind - Onshore | Wind | Emerging | 4 | NS | Mar 2019 | https://altenergy.com.au/listing/spring-hill-wind-farm/ | Proposed | 4 | No | VIC | Wind
Star of The South | Offshore Energy | 1 | Wind - Offshore | Wind | Publicly Announced | 2000 | SS |  |  | Proposed | 2000 | No | VIC | Wind
Stockyard Hill | Goldwind | 1-149 | Wind - Onshore | Wind | Committed | 532 | SS | Dec 2019 |  | Committed | 532 | No | VIC | Wind
Tarrone GT | AGL Energy Limited | 1-2 | OCGT | Natural Gas Pipeline | Publicly Announced | 500 - 600 | S |  |  | Proposed | 600 | No | VIC | OCGT
Timboon West Wind Farm | BayWa r.e. | 2 | Wind - Onshore | Wind | Emerging | 7.2 | NS | Sep 2018 | http://www.baywa-re.com.au/en/projects/timboon-west/ | Proposed | 7.2 | No | VIC | Wind
Wangaratta Solar Farm | Countrywide Energy Pty Ltd | SMA Inverter | PV-Tracking Flat panel | Solar | Publicly Announced | 22 | NS |  |  | Proposed | 22 | No | VIC | Solar
Warracknabeal Wind Farm | Westwind Energy Pty Ltd | 15 | Wind - Onshore | Wind | Publicly Announced | 50 | SS |  |  | Proposed | 50 | No | VIC | Wind
Wemen Solar Farm | Wemen Asset Co Pty Ltd as Trustee to Wemen Solar Unit Trust | Wemen Solar Farm 1 - 39 | PV panels | Solar | Committed | 87.75 | SS | Oct 2018 | https://wirsol.com.au/portfolio/wemen-solar-farm/ | Committed | 87.75 | No | VIC | Solar
Willatook | Wind Prospect WA Pty Ltd | 50-100 | Wind - Onshore | Wind | Publicly Announced | 285 | SS |  |  | Proposed | 285 | No | VIC | Wind
Winton Solar Farm | FRV | TBA | PV-Tracking Flat panel | Solar | Publicly Announced | 15 | SS |  | http://wintonsolarfarm.com/ | Proposed | 15 | No | VIC | Solar
Winton Solar Farm | Winton Asset Trust Fotowatio Renewable Ventures | 1 | PV panels | Solar | Publicly Announced | 98.8 | SS | Jan 2020 | https://www.energy.vic.gov.au/__data/assets/pdf_file/0029/391178/Winton-Solar-Farm-Fact-Sheet.pdf | Proposed | 98.8 | No | VIC | Solar
Woolsthorpe Wind Farm | Woolsthorpe Wind Farm Pty Ltd | 20 | Wind - Onshore | Wind | Publicly Announced | 68 | SS | Mar 2019 |  | Proposed | 68 | No | VIC | Wind
Yatpool Solar Farm | BayWa r.e | Solar Panels | PV-Tracking Flat panel | Solar | Com* | 81 | SS | Winter 2019 | http://www.baywa-re.com.au/en/projects/yatpool/ | Committed | 81 | No | VIC | Solar
Yawong Wind Farm | BayWa r.e. | 2 | Wind - Onshore | Wind | Emerging | 7.2 | NS | Oct 2018 | http://www.baywa-re.com.au/en/projects/yawong/ | Proposed | 7.2 | No | VIC | Wind
Com* - Identifies projects that are under construction, but AEMO has not been informed that the project meets all commitment criteria.

## Background Information
Generation capacity in the NEM
Any person who owns, controls, or operates a generating system connected to a transmission or distribution network must register with AEMO as a generator unless it has the benefit of an exemption from that requirement. A generating system’s registered capacity is the aggregate megawatt (MW) capacity of all its component generation units, as registered with AEMO.
The registered capacity should be the same as a generating system’s nameplate capacity. Nameplate capacity represents the maximum continuous output or consumption in MW, as specified by the manufacturer, or as subsequently modified. Nameplate capacity can change for a number of reasons, such as upgrade projects, age or a review of performance.
Under the National Electricity Rules (NER), generating units are classified as scheduled (S), semi-scheduled (SS), or non-scheduled (NS).
For further information about generation classification guide, please refer to the AEMO Generation Exemption and Classification Guide on the AEMO website: http://aemo.com.au/-/media/Files/Electricity/NEM/Participant_Information/New-Participants/Generator-Exemption-and-Classification-Guide.pdf
For the purposes of reliability assessments, and consistent with market systems, AEMO measures scheduled and semi-scheduled generation capacity on an as-generated basis, noting that for semi-scheduled systems the generating unit terminals are taken to be at the connection point. Non-scheduled generation is measured as sent-out (at the connection point) because it can include co-generation plants (that usually produce both heat and electricity), where the bulk of the capacity is consumed locally.
Temperature effects on generation
The actual level of generation available at any particular time will depend on the condition of the generating plant. This includes factors such as age, outages, and wear. Another important factor with respect to output is the reduction in thermal efficiency as the temperature increases.
Because temperature can affect plant generation capacities in different ways, basing generation capacities on region-specific reference temperatures facilitates more effective assessment of available generation capacity under weather conditions frequently associated with high demand.
To produce the supply-demand outlook, AEMO — in consultation with the Jurisdictional Planning Bodies (JPBs) — undertakes the following:
· Uses historical data to estimate typical weather conditions, and to determine reference temperatures frequently associated with times of 10% probability of exceedance (POE) maximum demand in the major load centres for each region.
· Asks generators to provide generating unit capacities for summer and winter using these common reference temperatures. The table below lists the common reference temperatures AEMO applies for each region. In general, annual maximum demands occur during summer; the exception is Tasmania, where maximum demand occurs during winter. Summer maximum demand in Tasmania occurs during colder temperatures, resulting in a relatively low summer reference temperature.
Generation capacity reference temperatures
Region | Summer (°C) | Winter (°C)
Queensland | 37 | 15
New South Wales | 42 | 9
Victoria | 41 | 8
South Australia | 43 | 11
Tasmania | 7.7 | 1.2
Maximum capacity
Some thermal (generation that burns fuel) and non-thermal (renewable generation) generating systems can provide additional, short-term capacity that exceeds the registered capacity. This is known as maximum capacity.
Proposed generation in the NEM
In addition to capacity forecasts, generation plant owners advise AEMO about the status of generation projects currently under development in each region.
Generation projects can be at different stages of development, which are assessed using AEMO’s five (5) commitment criteria, covering site acquisition, contracts for major components, planning and other approvals, financing, and date (see table below for a description of the criteria).
Projects are categorised as follows:
· Committed projects, representing generation and storage for which formal commitment has been made for construction or installation. These are further identified as:
- Committed proposals, representing projects that have satisfied all five (5) of AEMO's commitment criteria.
- Committed* proposals, representing projects that don't satisfy all five (5) of AEMO's commitment criteria, but construction or installation has commenced.
· Proposed projects, which are further identified as:
- Advanced proposals, representing projects that are highly likely to proceed, satisfying Site and Finance criteria plus either Planning and approvals or Major components criteria, and have notified AEMO of a scheduled commercial operation date. Typically included in sensitivity analysis for MLF.
- Maturing proposals, representing projects that have progressed with site, planning applications, and finance arrangements, but not to the point that they can be classified as advanced. Maturing projects may be explicitly included in scenario analysis to assess future reliability or market impacts and are tested for economic efficiency in capacity outlook modelling.
- Emerging proposals, representing projects where sites have been identified, planning applications lodged and the development is considered financially and technically viable. However, planning approvals/construction is uncertain, and development maybe subject to changes in policy or commercial environment. These projects may be explicitly included in scenario analysis to assess future market impacts, and are tested for economic efficiency in capacity outlook modelling. However, a higher weighted average cost of capital will be assumed to reflect greater development uncertainty compared to maturing projects.
- Publicly Announced proposals, representing projects that have been announced publicly, but may not yet meet all or any of the commitment criteria. Costs and capabilities of these projects are developed using recently-completed projects and projections of cost components such as raw material supply and labour.
Generation project commitment criteria
Category | Criteria
Site | The project proponent has purchased/settled/acquired (or commenced legal proceedings to purchase/settle/acquire) land for the construction of the project.
Major components | Contracts for the supply and construction of major plant or equipment components (such as generating units, turbines, boilers, transmission towers, conductors, and terminal station equipment) have been finalised and executed, including any provisions for cancellation payments.
Planning and Approvals | The proponent has obtained all required planning consents, construction approvals, connection contracts (including approval of proposed negotiated Generator Performance Standards from AEMO under clause 5.3.4A of the National Electricity Rules), and licences, including completion and acceptance of any necessary environmental impact statements.
Finance | The financing arrangements for the proposal, including any debt plans, must have been concluded and contracts executed.
Date | Construction of the proposal must either have commenced or a firm commencement date must have been set. Commercial use date for full operation must have been set.