## Slide 1: 5MS & GS Program Timelines (v1.0)
TUe 17 aUGUST 2021

## Slide 2: Information
This document contains the set of key dates which are used across the program.
The Level 1 and Level 2 Milestones are managed by the Program Consultative Forum (PCF) on a monthly basis. After that meeting this document will be published on AEMO’s website.
This version is up to date as of: 17-Aug-2021.
Please mail the 5MS mailbox if there are any questions about the dates or information which you require that is not present.

## Slide 3: 5MS & GS Program Timeline
Current as at 17-08-2021

## Slide 4: 5MS Program Timeline (complete 2019) Level 1 and External Level 2 Milestones

## Slide 5: 5MS Program Timeline Level 1 and External Level 2 Milestones

## Slide 6: 5MS Program Timeline Readiness and Go-Live
Current as at 17-08-2021

## Slide 7: Level 1 Milestones
ID | Milestone | Target Date | Expected Date | Owner | Status
L1-1 | 5MS Drafting Amendments submitted to AEMC | 20-Mar-2019 | 15-Mar-2019 | AEMO | Complete
L1-11 | All AEMO workstream development commenced | 23-May-2019 | 23-May-2019 | AEMO | Complete
L1-2 | IEC Approves B2B Procedures | 01-Jul-2019 | 01-Jul-2019 | AEMO | Complete
L1-15 | 5MS Drafting Amendments determined by AEMC | 31-Aug-2019 | 08-Aug-2019 | AEMO | Complete
L1-12 | 5MS Staging Environment live | 01-Dec-2019 | 01-Dec-2019 | AEMO | Complete
L1-3 | AEMO publishes NEM Procedures | 01-Dec-2019 | 01-Dec-2019 | AEMO | Complete
L1-7 | Market Readiness Strategy published by AEMO | 20-Jan-2020 | 29-Oct-2019 | AEMO | Complete
L1-13 | AEMO internal development complete | 31-Aug-2020 | 31-Aug-2020 | AEMO | Complete
L1-16 | 5MS Cost Recovery approach finalised | 31-Mar-2021 | 31-Mar-2021 | AEMO | Complete
L1-19 | AEMO Metering Solution – Go-Live | 21-Jun-2021 | 21-Jun-2021 | AEMO | Complete
L1-17 | 5MS Market Trial Commences | 19-July-2021 | 19-July-2021 | AEMO | Complete
L1-21 | 5-min Bidding Phased Go-Live begins | 01-Apr-2021 | 01-Apr-2021 | AEMO | Complete
L1-22 | Settlement Platform Go-Live | 17-May-2021 | 17-May-2021 | AEMO | Complete
L1-9 | 5MS Market Trial Successfully completed | 10-Sep-2021 | 10-Sep-2021 | AEMO | 
L1-10 | Metering accreditation complete | 31-Aug-2021 | 31-Aug-2021 | AEMO / MSPs | 
L1-4 | 5MS & UFE Market go Live | 01-Oct-2021 | 01-Oct-2021 | AEMO / Participants | 
L1-18 | GS Market Trial Commences | 01-Feb-2022 | 01-Feb-2022 | AEMO | 
L1-20 | GS Market Trial concludes | 15-Mar-2022 | 15-Mar-2022 | AEMO | 
L1-5 | GS Market go live | 01-May-2022 | 01-May-2022 | AEMO / Participants | 
L1-6 | Mandatory 5MS meter data delivery | 01-Dec-2022 | 01-Dec-2022 | AEMO | 
Domain | Initiative | 2020 |  |  |  |  |  |  |  |  |  |  |  | 2021 |  |  |  |  |  |  |  |  |  |  |  | 2022 |  |  |  |  |  |  |  |  |  |  | 
 |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  | 
Program |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec
L1-13
L1-9
L1-10
L1-4
L1-16
L1-17
L1-18
L1-19
L1-21
L1-22
L1-20
Current as at 17-08-2021
L1-5
L1-6
Milestone complete
Milestone on track
Milestone not achieved
Milestone at risk
Milestone re-planned

## Slide 8: Level 2 Milestones – Metering
Domain | Initiative | 2019 |  |  |  |  |  |  |  |  |  |  |  | 2020 |  |  |  |  |  |  |  |  |  |  |  | 2021 |  |  |  |  |  |  |  |  |  |  | 
 |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  | 
Metering |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec
Milestone complete
Milestone on track
Milestone not achieved
Milestone at risk
L2-M1
L2-M2
L2-M4
L2-M5
L2-M7
L2-M6
L2-M3
Key Milestones (Program) |  |  |  |  | 
ID | Milestone | Target Date | Expected Date | Owner | Status
L2-M1 | AEMO internal metering solution – solution design complete (internal) | 31-May-2019 | 17-Jun-2019 | AEMO | Complete
L2-M2 | Final technical specifications for Package 1 published by AEMO | 30-Jun-2019 | 30-Apr-2019 | AEMO | Complete
L2-M3 | Final technical specifications for Package 2 published by AEMO | 30-Sep-2019 | 30-Sep-2019 | AEMO | Complete
L2-M4 | Final technical specifications for Package 3 published by AEMO | 30-Sep-2019 | 30-Sep-2019 | AEMO | Complete
L2-M5 | Software Release 1 for Packages 1 & 2 in 5MS Staging Environment | 01-Dec-2019 | 01-Dec-2019 | AEMO | Complete
L2-M6 | Software Release 2 for Package 3 in 5MS Staging Environment | 15-Jun-2020 | 15-Jun-2020 | AEMO | Complete
L2-M7 | AEMO internal metering solution – build complete (internal) | 31-Aug-2020 | 31-Aug-2020 | AEMO | Complete
L2-M8 | Software Release 3 for Package 3 in 5MS Staging Environment | 31-Aug-2020 | 31-Aug-2020 | AEMO | Complete
L2-M8

## Slide 9: Level 2 Milestones - Dispatch
Domain | Initiative | 2019 |  |  |  |  |  |  |  |  |  |  |  | 2020 |  |  |  |  |  |  |  |  |  |  |  | 2021 |  |  |  |  |  |  |  |  |  |  | 
 |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  | 
Dispatch |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec
Key Milestones (Program) |  |  |  |  | 
ID | Milestone | Target Date | Expected Date | Owner | Status
L2-D1 | Final technical specifications for Package 1 published by AEMO | 2-Apr-2019 | 2-Apr-2019 | AEMO | Complete
L2-D2 | Final technical specifications for Package 2 published by AEMO | 31-Jul-2019 | 31-Jul-2019 | AEMO | Complete
L2D12 | Final technical specifications for Package 4 published by AEMO | 31-Jul-2019 | 31-Jul-2019 | AEMO | Complete
L2-D3 | Software drop for Packages 1,2 & 3 in 5MS Staging Environment | 29-Nov-2019 | 29-Nov-2019 | AEMO | Complete
L2-D13 | Final technical specifications for Package 5 published by AEMO | 31-Jan-2020 | 16-Mar-2020 | AEMO | Complete
L2-D5 | Software drop for Package 4 in 5MS Staging Environment | 15-May-2020 | 15-May-2020 | AEMO | Complete
L2-D4 | Development completed (internal) | 31-May-2020 | 31-May-2020 | AEMO | Complete
Milestone complete
Milestone on track
Milestone not achieved
Milestone at risk
L2-D1
L2-D2
L2-D3
L2-D5
L2-D4
L2-D12
L2-D13

## Slide 10: Level 2 Milestones – Settlements
Domain | Initiative | 2019 |  |  |  |  |  |  |  |  |  |  |  | 2020 |  |  |  |  |  |  |  |  |  |  |  | 2021 |  |  |  |  |  |  |  |  |  |  | 
 |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  | 
Settlements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec
Key Milestones (Program) |  |  |  |  | 
ID | Milestone | Target Date | Expected Date | Owner | Status
L2-S1 | Final technical specifications for Package 1 published by AEMO | 15-Oct-2019 | 15-Oct-2019 | AEMO | Complete
L2-S2 | Software drop for Package 1 | 01-Nov-2019 | 01-Nov-2019 | AEMO | Complete
L2-S3 | Final technical specifications for Package 2 published by AEMO | 15-Dec-2019 | 16-Dec-2019 | AEMO | Complete
L2-S4 | Final technical specifications for Package 3 published by AEMO | 31-Jan-2020 | 31-Jan-2020 | AEMO | Complete
L2-S6 | Software drop for Package 2 in 5MS Staging Environment | 16-Mar-2020 | 16-Mar-2020 | AEMO | Complete
L2-S7 | Software drop for Package 3 in 5MS Staging Environment | 15-May-2020 | 15-May-2020 | AEMO | Complete
L2-S5 | Development completed (internal) | 31-May-2020 | 31-May-2020 | AEMO | Complete
Milestone complete
Milestone on track
Milestone not achieved
Milestone at risk
L2-S1
L2-S2
L2-S3
L2-S4
L2-S5
L2-S6
L2-S7

## Slide 11: Procedures workstream status

## Slide 12: Systems Workstream – Metering
5 MINUTE SETTLEMENT SYSTEMS TRACKING | TIMING |  |  |  |  |  |  |  |  | 
 | Internal HLIA | Focus/Group | SWG Engagement | External HLIA | Draft Tech Spec | Final Tech Spec | User Guides | 5MS Staging | Preprod | Production
METERING |  |  |  |  |  |  |  |  |  | 
PACKAGE 1 - Metering Data & Metrology |  |  |  |  |  |  |  |  |  | 
MDFF • MDFF Specification NEM12 NEM13 v20 | Aug-18 | Oct-18 | Oct-18 | Nov-18 | Jan-19 | Apr-19 | - | 1-Dec-19 | 19-Apr-21 | 21-Jun-21
PACKAGE 2 - MSATS & SLPs |  |  |  |  |  |  |  |  |  | 
Transition • MSATS Technical Specification | Aug-18 | Sep-18 | Aug-18 | Nov-18 | 31-May-19 | 30-Sep-19 | - | - | - | -
Meter Data - MDFF and MDMF • MDM File Format and Load Process (User Guide) • MSATS Technical Specification | Aug-18 | Oct-18 | Sep-18 | Nov-18 | 31-May-19 | 30-Sep-19 | - | 1-Dec-19 | 19-Apr-21 | 21-Jun-21
PACKAGE 3 - Miscellaneous |  |  |  |  |  |  |  |  |  | 
B2M via API • MSATS Technical Specification | Oct-18 | - | Apr-19 | 9-May-19 | 31-May-19 | 30-Sep-19 | 01-Jun-20 (Draft) | 15-Jun-20 | 19-Apr-21 | 21-Jun-21
 |  |  |  |  |  |  | 14-Sep-20 (Final) |  |  | 
MSATS Browser (LVI) changes • MSATS Technical Specification | Aug-18 | - | May-19 | 9-May-19 | 28-Jun-19 | 30-Sep-19 | 10-Oct-20 | 15-Jun-20 | 19-Apr-21 | 21-Jun-21
MSATS Report changes • MSATS Procedures MDM Procedure • MDM File Format and Load Process (User Guide) • MSATS Technical Specification General Process & Document Clean-up | Oct-18 | - | Apr-19 | Apr-19 | 28-Jun-19 | 30-Sep-19 | - | 31-Aug-20 | 19-Apr-21 | 21-Jun-21

## Slide 13: Systems Workstream – Dispatch & Operations
Current as at 17-08-2021
5 MINUTE SETTLEMENT SYSTEMS TRACKING | TIMING |  |  |  |  |  |  |  |  | 
 | Internal HLIA | Focus/Group | SWG Engagement | External HLIA | Draft Tech Spec | Final Tech Spec | User Guides | 5MS Staging | Preprod | Production
DISPATCH and OPERATIONS |  |  |  |  |  |  |  |  |  | 
PACKAGE 1 - Bidding FTP and API |  |  |  |  |  |  |  |  |  | 
Transition | Aug-18 | Oct-18 | Aug-18 | Nov-18 | Dec-18 | 2-Apr-19 | 31-Oct-19 | 29-Nov-19 | 30-Nov-20 | 01-Apr-21
Bidding Data Model | Aug-18 | - | Sep-18 | Mar-19 | Dec-18 | 2-Apr-19 | 31-Oct-19 | 29-Nov-19 | 30-Nov-20 | 01-Apr-21
Bidding Format | Aug-18 | - | Sep-18 | Nov-18 | Dec-18 | 2-Apr-19 | 31-Oct-19 | 29-Nov-19 | 30-Nov-20 | 01-Apr-21
PACKAGE 2 - Bidding Web UI |  |  |  |  |  |  |  |  |  | 
Bidding Web UI and APIs | Aug-18 | Nov-18 | Dec-18 | Jan-19 | Mar-19 | 31-Jul-19 | 16-Dec-19 | 29-Nov-19 | 30-Nov-20 | 01-Apr-21
PACKAGE 3 - Dispatch, Pre-dispatch and PASA |  |  |  |  |  |  |  |  |  | 
Dispatch | Aug-18 | - | Oct-18 | Nov-18 | Oct-18 | 2-Apr-19 | - | 29-Nov-19 | 30-Nov-20 | 01-Apr-21
Predispatch P30/7DAY | Aug-18 | - | Oct-18 | Nov-18 | Oct-18 | 2-Apr-19 | - | 29-Nov-19 | 30-Nov-20 | 01-Apr-21
Pre-dispatch P5 - Fast Start Inflexibility Profile | Nov-18 | Jan-20 | Nov-18 | Jan-20 | May-20 | 10-Nov-20 | - | - | 01-Apr-21 | 30-Jun-21
5MPD - Price Sensitivities | - | Jan-20 | Nov-18 | Jan-20 | May-20 | 10-Nov-20 | - | - | 16-Jun-21 | 07-Jul-21
ST and PD PASA | Aug-18 | - | Oct-18 | Nov-18 | Oct-18 | 2-Apr-19 | 31-Oct-19 | 29-Nov-19 | 30-Nov-20 | 01-Apr-21
PACKAGE 4 - Pricing and Miscellaneous |  |  |  |  |  |  |  |  |  | 
Trading Price / Price Revision | Aug-18 | - | Feb-19 | Nov-18 | Mar-19 | 31-Jul-19 | - | 15-May-20 | 30-Jul-21 | 01-Oct-21
Administered Pricing and CPT | Aug-18 | - | Feb-19 | Dec-18 | Mar-19 | 31-Jul-19 | - | 15-May-20 | 30-Jul-21 | 01-Oct-21
Suspension Pricing | Sep-18 | - | Feb-19 | Dec-18 | Mar-19 | 31-Jul-19 | - | 15-May-20 | 30-Jul-21 | 01-Oct-21
Negative Residue Management | Sep-18 | - | Feb-19 | Dec-18 | Jun-19 | 31-Jul-19 | - | 15-May-20 | - | -
RERT | Oct-18 | - | - | - | - | - | - | - | - | -
PACKAGE 5 - Full Data Model |  |  |  |  |  |  |  |  |  | 
Full Data Model | Sep-18 | Ongoing | Ongoing | Apr-19 | Ongoing | 31-Jan-20 | 16-Mar-20 | 29-Nov-19 | 30-Nov-20 | 01-Apr-21

## Slide 14: Systems Workstream – Settlements
5 MINUTE SETTLEMENT SYSTEMS TRACKING | TIMING |  |  |  |  |  |  |  |  | 
 | Internal HLIA | Focus/Group | SWG Engagement | External HLIA | Draft Tech Spec | Final Tech Spec | User Guides | 5MS Staging | Preprod | Production
SETTLEMENTS |  |  |  |  |  |  |  |  |  | 
PACKAGE 1 - Reallocations |  |  |  |  |  |  |  |  |  | 
Reallocations | Dec-18 | Nov-18 | Dec-18 | Mar-19 | 31-Jul-19 | 15-Oct-19 | 1-Nov-19 | 1-Nov-19 | 1-Mar-20 | 1-Apr-20
PACKAGE 2 - Settlements and Billing |  |  |  |  |  |  |  |  |  | 
Settlements | Oct-18 | Nov-18 | Dec-18 | Mar-19 | 30-Aug-19 | 15-Dec-19 | - | 16-Mar-20 | 22-Mar-21 | 17-May-21
Billing | Oct-18 | Nov-18 | Dec-18 | Mar-19 | 30-Aug-19 | 15-Dec-19 | - | 16-Mar-20 | 22-Mar-21 | 17-May-21
PACKAGE 3 - Prudentials and Estimation |  |  |  |  |  |  |  |  |  | 
Prudentials | Sep-18 | Nov-18 | Dec-18 | Mar-19 | 31-Oct-19 | 31-Jan-20 | 15-May-20 | 15-May-20 | 22-Mar-21 | 17-May-21
Estimation | Oct-18 | Nov-18 | Dec-18 | Mar-19 | 31-Oct-19 | 31-Jan-20 | - | 15–May-20 | 22-Mar-21 | 17-May-21
Full Data Model | Refer DISPATCH |  |  |  |  |  |  |  |  | 

## Slide 15: Level 2 Milestones – Readiness
Domain | Initiative | 2019 |  |  |  |  |  |  |  |  |  |  |  | 2020 |  |  |  |  |  |  |  |  |  |  |  | 2021 |  |  |  |  |  |  |  |  |  |  | 
 |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  | 
Readiness |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec
Key Milestones (Program) |  |  |  |  | 
ID | Milestone | Target Date | Expected Date | Owner | Status
L2-RE01 | Industry Working Group Established | 15-Jul-2019 | 15-Jul-2019 | AEMO | Complete
L2-RE02 | Market Readiness Strategy Industry Draft | 30-Aug-2019 | 30-Aug-2019 | AEMO | Complete
L2-RE03 | Market Readiness Strategy Finalised | 29-Nov-2019 | 30-Oct-2019 | AEMO | Complete
L2-RE04 | Industry Test Strategy Industry Draft Released | 30-Sep-2019 | 30-Sep-2019 | AEMO | Complete
L2-RE05 | Industry Test Strategy Finalised | 29-Nov-2019 | 29-Nov-2019 | AEMO | Complete
L2-RE06 | Transition and Go Live Strategy Industry Draft Released | 30-Sep-2019 | 30-Sep-2019 | AEMO | Complete
L2-RE07 | Transition and Go Live Strategy Finalised | 29-Nov-2019 | 29-Nov-2019 | AEMO | Complete
L2-RE08 | Market Trial Strategy Industry Draft | 30-Sep-2019 | 30-Sep-2019 | AEMO | Complete
L2-RE09 | Market Trial Strategy Finalised | 29-Nov-2020 | 29-Nov-2019 | AEMO | Complete
L2-RE10 | Metering Service Provider Accreditation Update Plan Industry Draft | 29-Nov-2019 | 29-Nov-2019 | AEMO | Complete
L2-RE12 | Industry Readiness Reporting Plan Industry Draft | 31-Oct-2019 | 31-Oct-2019 | AEMO | Complete
L2-RE13 | Industry Readiness Reporting Plan Finalised | 13-Dec-2019 | 13-Dec-2019 | AEMO | Complete
L2-RE15 | Industry Transition Plan – Metering final complete | 07-Feb-2020 | 07-Feb-2020 | AEMO | Complete
L2-RE14 | 5MS / GS Industry Readiness Reporting Implemented | 28-Feb-2020 | 02-Mar-2020 | AEMO | Complete
L2-S8 | Industry Test start for Reallocations | 01-Mar-2020 | 28-Feb-2020 | AEMO | Complete
L2-RE13
L2-RE01
L2-RE02
L2-RE03
L2-RE04
L2-RE09
L2-RE06
L2-RE08
L2-RE05
L2-RE07
L2-RE10
L2-RE12
L2-RE14
L2-RE15
L2-S8
L2-RE11
L2-RE32
L2-S12
L2-RE22
L2-RE18
L2-D7
L2-D8
L2-S10
L2-S11
L2-RE23
L2-RE24
L2-RE20
L2-D10
L2-D11
L2-RE25
L2-RE21
L1-RE31
L2-RE28
Current as at 17-08-2021
L2-M11
L2-M12
L2-M24
L2-M10
L2-RE29
L2-RE30
Milestone complete
Milestone on track
Milestone not achieved
Milestone at risk
Milestone re-planned
L2-RE33
L2-RE35
L2-RE19
L2-RE34

## Slide 16: Level 2 Milestones – Readiness
Key Milestones (Program) |  |  |  |  | 
ID | Milestone | Target Date | Expected Date | Owner | Status
L2-RE32 | Industry Test for Reallocations Concludes | 31-Mar-2020 | 31-Mar-2020 | AEMO | Complete
L2-RE11 | Metering Service Provider Accreditation Plan Finalised | 13-Mar-2020 | 18-Feb-2020 | AEMO | Complete
L2-S12 | Reallocations Go-Live | 01-Apr-2020 | 01-Apr-2020 | AEMO | Complete
L2-RE22 | Industry Transition Plan – Dispatch​ final complete | 28-Aug-2020 | 28-Aug-2020 | AEMO | Complete
L2-M11 | Industry Test preparation completed by participants for MDM and B2M Go-Live | 19-Apr-2021 | 19-Apr-2021 | Participants | Complete
L2-M12 | Industry Test preparation completed by AEMO for MDM and B2M Go-Live | 19-Apr-2021 | 19-Apr-2021 | AEMO | Complete
L2-RE29 | Retail MDM (incl. B2M) Industry Test Commences | 19-Apr-2021 | 19-Apr-2021 | AEMO | Complete
L2-RE30 | Retail MDM (incl. B2M) Industry Test Concludes | 14-Jun-2021 | 14-Jun-2021 | AEMO | Complete
L2-RE18 | Industry Go-Live Plan Retail MDM finalised (Interim) | 11-Dec-2020 | 11-Dec-2020 | AEMO | Complete
L2-RE35 | Industry Go-Live Plan Retail MDM final | 16-Apr-2021 | 11-May-2021 | AEMO | Complete
L2-M24 | Retail MDM (incl. B2M) Go-Live | 21-Jun-2021 | 21-Jun-2021 | AEMO | 
L2-M10 | 5 minute files in MDFF accepted by AEMO | 22-Jun-2021 | 22-Jun-2021 | AEMO | 
L2-D7 | Dispatch Industry Test preparation completed by participants | 29-Nov-2020 | 29-Nov-2020 | Participants | Complete
L2-D8 | Dispatch Industry Test preparation completed by AEMO | 29-Nov-2020 | 29-Nov-2020 | AEMO | Complete
Domain | Initiative | 2019 |  |  |  |  |  |  |  |  |  |  |  | 2020 |  |  |  |  |  |  |  |  |  |  |  | 2021 |  |  |  |  |  |  |  |  |  |  | 
 |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  | 
Readiness |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec
L2-RE11
L2-RE32
L2-S12
L2-RE22
L2-M11
L2-M12
L2-RE18
L2-M24
L2-M10
L2-D7
L2-D8
L2-RE29
L2-RE30
Milestone complete
Milestone on track
Milestone not achieved
Milestone at risk
Milestone re-planned
L2-S8
L2-RE35

## Slide 17: Level 2 Milestones – Readiness
Key Milestones (Program) |  |  |  |  | 
ID | Milestone | Target Date | Expected Date | Owner | Status
L2-RE28 | Dispatch Industry Test concludes | 15-Mar-2021 | 15-Mar-2021 | AEMO | Complete
L2-S10 | Settlements Industry Test preparation completed by participants | 22-Mar-2021 | 22-Mar-2021 | Participants | Complete
L2-RE34 | Industry Go-Live Plan – Dispatch & Bidding finalised | 19-Mar-2021 | 09-Mar-2021 | AEMO | Complete
L2-S11 | Settlements Industry Test preparation completed by AEMO | 22-Mar-2021 | 22-Mar-2021 | AEMO | Complete
L2-RE33 | Settlements Industry Test concludes | 13-May-2021 | 13-May-2021 | AEMO | Complete
L2-RE19 | Industry Go-Live Plan Settlements finalised | 16-Apr-2021 | 20-Apr-2021 | AEMO | Complete
L2-RE23 | 5MS Capability Market Trial preparation completed by participants | 12-Jul-2021 | 19-Jul-2021 | Participants | Complete
L2-RE24 | 5MS Capability Market Trial preparation completed by AEMO | 12-Jul-2021 | 19-Jul-2021 | AEMO | Complete
L2-RE31 | 5MS Capability Market Trial commences | 19-Jul-2021 | 19-Jul-2021 | AEMO | Complete
L2-RE20 | Industry Go-Live Plan – 5MS Capability final complete | 01-Aug-2021 | 27-Aug-2021 | AEMO | 
L2-D10 | 5MS Capability Market Trial concludes | 10-Sep-2021 | 10-Sep-2021 | AEMO | 
L2-D11 | 30-min Bidding no longer accepted by AEMO | 01-Oct-2021 | 01-Oct-2021 | AEMO | 
L2-RE25 | MDMT format no longer accepted by AEMO for interval meters | 01-Oct-2021 | 01-Oct-2021 | AEMO | 
L2-RE26 | GS Market Trial preparation completed by participants | 01-Feb-2022 | 01-Feb-2022 | Participants | 
L2-RE27 | GS Market Trial preparation completed by AEMO | 01-Feb-2022 | 01-Feb-2022 | AEMO | 
L2-RE21 | Industry Go-Live Plan – GS Capability final complete | 21-Dec-2021 | 21-Dec-2021 | AEMO | 
Domain | Initiative | 2019 |  |  |  |  |  |  |  |  |  |  |  | 2020 |  |  |  |  |  |  |  |  |  |  |  | 2021 |  |  |  |  |  |  |  |  |  |  | 
 |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  | 
Readiness |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec
L2-S10
L2-S11
L2-RE33
L2-RE23
L2-RE24
L2-RE20
L2-D10
L2-D11
L2-RE25
L2-RE21
L2-RE31
L2-RE328
Current as at 17-08-2021
L2-RE19
Milestone complete
Milestone on track
Milestone not achieved
Milestone at risk
Milestone re-planned
L2-RE34

## Slide 18: Staged Transition – System Implementations
Current as at 17-08-2021
Notes: Context and Background
Power of Choice program was implemented with a “big bang” approach
For 5MS and GS, Industry has consistently flagged a preference for a phased implementation that avoids a big bang implementation
The mandated dates for market start assume a level of preparatory activity e.g. 5MS metering transition
Individual workstreams (systems, procedures) have proposed transitional approaches within key areas
Transition Strategy consolidates those individual approaches in-line with the objectives to enable a program level approach to be formalised
  Present this as a strawperson
Our challenge:
  Develop transition plan, considering industry positions, into an integrated whole that best meets the transition strategy principles

## Slide 19: Contingency Planning