## Version Control
AEMO 5MS Functional Deployment Matrix - Version 1.0 Version Control
Version | Date | Comments
1.0 | 2020-07-13 | AEMO distribution of 'AEMO 5MS Functional Deployment Matrix' to RWG, SWG and ITWG
1.1 | 2020-08-06 | Added R30 into the staging 30 min tab
1.2 | 2020-09-10 | Updated Preprod dates for Settlement and addtion of "Transition" tab
1.3 | 2020-11-10 | Updated Martix ID R35 and R24
1.4 | 2021-02-03 | Updated release dates for retail and Settlements delay
1.5 | 2021-06-23 | Updated to reflect new Market Trial timing as a result of Retail Go-Live on 21 June
1.6 | 2021-11-05 | Updated to reflect Global Settlement delivery updates
1.7 | 2021-12-17 | Updated to relfect MCPI delivery for May 2022

## Introduction
AEMO 5MS Functional Deployment Matrix, Version 1.0 Introduction
Ref. # | Details
1 | The 'AEMO 5MS Functional Deployment Matrix' provides NEM Industry Participants with a detailed view of the AEMO 5MS programme delivery of 5MS and GS AEMO functions with consideration to: - AEMO environments i.e. 5MS Staging and PreProduction - AEMO Workstreams i.e. Retail, Dispach and Settlements - NEM Settlement calculations i.e. 30 minute, 5 minute and Global Settlements
2 | This matrix maybe referenced by NEM Industry Particpants to determine when AEMO specific 5MS and GS functional testing can be initiated.
3 | The AEMO 5MS Programme functions have been logically grouped by AEMO Environment and NEM Settlement calculation: - 'Staging_30 min' - All functionality to be delivered into the 5MS Staging environment for functions related to 30-Minute NEM Settlements - 'Staging_5min': All functionality to be delivered into the 5MS Staging environment for functions related to 5-Minute NEM Settlements (5MS) - 'Staging_GS' : All functionality to be delivered into the 5MS Staging environment for functions related to Global Settlements (GS) - 'PreProduction': All functionality to be delivered into the AEMO PreProduction environment for functions related to 30-Minute NEM Settlements, 5-Minute NEM Settlements and Global Settlements
4 | This document is intended to be a living document updated in collaboration with NEM Industry Participants. Related questions and clarifications will be registered within this document and distributed for NEM Industry Participant reference.

## Preprod-GS
AEMO 5MS / GS Functional Deployment Matrix, Version 1.7
Environment: AEMO PreProduction Environment Settlement: Global Settlement Date of MSATS data refresh: TBD AEMO Work Streams: Retail, Dispatch, Settlements
AEMO Functional Matrix ID | AEMO WorkStream | AEMO GS and MCPI Programme: Function | Industry Test |  | Market Trials - 5MS |  | Market Trials - GS / MCPI
|  |  | Function included in Industry Testing? | Functional Testing Considerations (Industry Test) | Function included in Market Trials - 5MS? | Functional Testing Considerations (Market Trials - 5MS) | Capability available for industry test or Market Trial (GS/MCPI) | Functional Testing Considerations (Market Trials - GS / MCPI)
D1 | Dispatch | 5MS Bidding Service (API, FTP, JSON Format) |  |  | 2021-07-30 | None. | N/A | N/A
D2 | Dispatch | Bid submission using API |  |  | 2021-07-30 | None. | N/A | N/A
D3 | Dispatch | Bid submission using FTP |  |  | 2021-07-30 | None. | N/A | Not in Scope for GS Mkt Trial
D4 | Dispatch | Bid submission using Bid Web Portal |  |  | 2021-07-30 | None. | N/A | Not in Scope for GS Mkt Trial
D5 | Dispatch | Acknowledgement of submitted Bid |  |  | 2021-07-30 | None. | N/A | Not in Scope for GS Mkt Trial
D6 | Dispatch | Request Bid Reports through data-interchange/data model |  |  | 2021-07-30 | None. | N/A | Not in Scope for GS Mkt Trial
D7 | Dispatch | Dispatch, 5min Pre-Dispatch, Pre-Dispatch, and DS PASA using 5min Bids |  |  | 2021-07-30 | None. | N/A | Not in Scope for GS Mkt Trial
D19 | Dispatch | Full Data Model (5.0) |  |  | 2021-07-30 | None. | N/A | Not in Scope for GS Mkt Trial
D20 | Dispatch | NEM Reports |  |  | 2021-07-30 | None. | N/A | Not in Scope for GS Mkt Trial
D23 | Dispatch | Rolling Sum Price Report |  |  | 2021-07-30 | None. | N/A | Not in Scope for GS Mkt Trial
R1 | Retail | MDFF NEM12 at any data interval via FTP |  |  | 2021-07-19 | None. | N/A | No Change from current production
R2 | Retail | B2M MTRD MDFF NEM12 at any data interval via MSATS Browser 'B2B Browser > Upload File' pg |  |  | 2021-07-19 | None. | N/A | No Change from current production
R3 | Retail | MDFF NEM13 via FTP |  |  | 2021-07-19 | None. | N/A | No Change from current production
R4 | Retail | B2M MTRD MDFF NEM13 via MSATS Browser 'B2B Browser > Upload File' pg |  |  | 2021-07-19 | None. | N/A | No Change from current production
R5 | Retail | MDMT MDMF Interval and Basic meter data files |  |  | 2021-07-19 | None. | N/A | MDMT no valid for Interval Meters from 1/10/21
R6 | Retail | API Push Functionality for B2M MTRD and MDMT, CATS, NMID |  |  | 2021-07-19 | None. | N/A | No Change from current production
R7 | Retail | MSATS Browser 'Metering Data > Data Search' pg |  |  | 2021-07-19 | None. | N/A | No Change from current production
R8 | Retail | MSATS Browser 'B2B Browser > Transforms and Protocols' pg |  |  | 2021-07-19 | None. | N/A | None.
R9 | Retail | aseXML Schema r35 no longer supported |  |  | 2021-07-19 | None. | 2022-03-28 | r35 schema no longer supported, r39_p1 moves to superseded version
| Retail | aseXML Schema r42 Available |  |  |  |  | 2022-03-28 | Required for MSDR / MCPI New Fields (Release date to Prep-prod TBC with Market Trial Plan)
R10 | Retail | MSATS Browser 'Participants > Participant Schema' pg |  |  | 2021-07-19 | None. | N/A | None.
R11 | Retail | MSATS Browser 'B2B Browser > B2B Hub Queue' pg |  |  | 2021-07-19 | None. | N/A | None.
R12 | Retail | MSATS Browser 'Reports and Alerts > Queue Monitoring' pg |  |  | 2021-07-19 | None. | N/A | None.
R13 | Retail | Retirement of RM reports: RM7, RM8, RM10, RM12, RM14, RM15, RM18, RM19, SDD and SDR |  |  | 2021-07-19 | None. | N/A | None.
R14 | Retail | CATS report changes : C1, C4, C7, C10, C11 |  |  | 2021-07-19 | None. | N/A | None.
N/A
R15 | Retail | API Pull Functionality for B2M MTRD and MDMT, CATS, NMID |  |  | 2021-07-19 | None. | N/A | None.
R16 | Retail | CATS CR changes to support new NMI classification codes |  |  | 2021-07-19 | None. | N/A | No Change to current production
R17 | Retail | New Standing Data - Meter Installation Type Codes (MITC), Datastream Type 'N' |  |  | 2021-07-19 | None. | N/A | N/A
R18 | Retail | MSATS NMI discovery Display of TNI2 and Vic TUoS |  |  | 2021-07-19 | None. | N/A | No Change to current production
R19 | Retail | MSATS NMI Master/Summary display of TNI2 and VIC TUoS |  |  | 2021-07-19 | None. | N/A | No Change to current production
R20 | Retail | MSATS Browser 'Settlement Data' pg |  |  | 2021-07-19 | None. | N/A | No Change to current production
R21 | Retail | New RM Report Requests: RM37, RM38, RM39 |  |  | 2021-07-19 | None. | N/A | No Change to current production
R22 | Retail | Historic Settlement Runs @ 30 minutes |  |  | 2021-07-19 | None. | N/A | N/A
R23 | Retail | Settlement Run @ 30 minutes |  |  | 2021-07-19 | None. | N/A | N/A
R24 | Retail | Settlement Run @ 5 Minutes Settlement By Difference |  |  | 2021-07-30 | First NEM Settlement run will be executed on TBC | 2022-03-28 | Runs TBC in Market Trial Plan
|  | Settlement Run @ 5 Minutes Global Settlement |  |  |  |  | 2022-03-28 | Runs TBC in Market Trial Plan
R25 | Retail | Existing Meter Data Reports: RM9, RM11, RM13, RM26 |  |  | 2021-07-19 | None. | N/A | No Change to current production
R26 | Retail | Existing Settlements Reports @30-min: RM16, RM17, RM20, RM21, RM22, RM25 |  |  | 2021-07-19 | Up until 30 July 2021 | N/A | N/A
R27 | Retail | Existing Settlements Reports @5-min: RM16, RM17, RM20, RM21, RM22, RM26, RM27 |  |  | 2021-07-30 | None. | 2022-03-28 | inclusion of T1 Metering Data.
R28 | Retail | UFE Reports: RM43, RM46 |  |  | 2021-07-30 | None. | 2022-03-28 | Runs TBC in Market Trial Plan
R29 | Retail | Access to MSATS Browser via Markets Portal |  |  | 2021-07-19 | None. | N/A | No Change to current production
R30 | Retail | B2B Transaction (SORD, CUST, MTRD etc) exchange supported between Participants |  |  | 2021-07-19 | None. | N/A | None.
R31 | Retail | Rejection logic for MDMT for Interval Meters |  |  | 2021-07-19 | None. | N/A | No Change to current production
R32 | Retail | CR rejection logic for CNDS Suffix and Type and Transfer Rejection by NMI Class. |  |  | N/A | N/A | N/A | No Change to current production
R33 | Retail | CR Rejection Logic - LR not GLOPOOL and remove Objection and Notification for LR |  |  | N/A | N/A | 2022-03-28 | Activation Date TBC in Market Trial Plan
R34 | Retail | GS Settlement post LR update |  |  |  | N/A | 2022-03-28 | Runs TBC in Market Trial Plan
R35 | Retail | RM 30 Report |  |  | N/A | None. | N/A | None.
R36 | Retail | Availability of MCPI data item, Shared Isolation Point Flag, for NMI Standing Data at the NMI level. |  |  |  |  | 2022-03-28 | Capability availability TBC on Market Trial plan and deployment
R37 | Retial | Ability to maintain Shared Isolation Point Flag using 2000 and 5000 series CRs. |  |  |  |  | 2022-03-28 | Capability availability TBC on Market Trial plan and deployment
R38 | Retail | 2000 and 5000 series CRs to include validation, processing and notification of Shared Isolation Point Flag. |  |  |  |  | 2022-03-28 | Capability availability TBC on Market Trial plan and deployment
R39 | Retail | Ability to query Shared Isolation Point Flag using existing services: a. NMI Discovery b. MSATS Browser c. CATS Reports (C1, C4, C7) d. MSATS Snapshot |  |  |  |  | 2022-03-28 | Capability availability TBC on Market Trial plan and deployment
S1 | Settlement | 30 and 5 minute reallocations Web UI |  |  | 2021-07-05 | 30 mins up until 30 July 2021. 5 mins from 30 July 2021. | N/A | No Change to current production
S2 | Settlement | Reallocation APIs |  |  | 2021-07-05 | None. | N/A | No Change to current production
S4 | Settlement | Settlements and billing @ 30-min |  |  | 2021-07-05 | None. | N/A | N/A
|  | Settlements and Billing @ 5 MinSettlement by Difference |  |  |  |  | 2022-03-28 | Runs TBC in Market Trial Plan
S5 | Settlement | Prelim, Final, and Revision Settlements - Global Settlement |  |  | 2021-07-05 | None. | 2022-03-28 | Runs TBC in Market Trial Plan
S6 | Settlement | Invoicing (Tax Invoice, RCTI, Adjustment Note, etc) |  |  | 2021-07-05 | None. | 2022-03-28 | UFE $ for all GS Settlement runs
S7 | Settlement | Reconciliation reports (SR, SS, etc) |  |  | 2021-07-05 | None. | 2022-03-28 | UFE $ for all GS Settlement runs
S8 | Settlement | NEM Reports |  |  | 2021-07-05 | None. | 2022-03-28 | UFE $ for all GS Settlement runs
S9 | Settlement | Data Interchange |  |  | 2021-07-05 | None. | 2022-03-28 | UFE $ for all GS Settlement runs
S10 | Settlement | Settlements Direct (Production version, no API’s) |  |  | 2021-07-05 | None. | N/A | No Change
S11 | Settlement | Prudential and settlement estimation @ 30-min |  |  | 2021-07-05 | None. | N/A | N/A
S12 | Settlement | Transition Settlement Statements (30 & 5-min) |  |  | 2021-07-05 | None. | N/A | N/A
|  | Prudential and Settlement estimation @ 5 Minute GS |  |  |  |  | 2022-03-28 | UFE $ for all GS Settlement runs
S13 | Settlement | Settlement Statements @ GS (Financial UFE) |  |  | N/A | N/A | 2022-03-28 | UFE $ for all GS Settlement runs
S14 | Settlement | NEM Prudentials Dashboard |  |  | 2021-07-05 | None. | 2022-03-28 | None.
S15 | Settlement | NEM Prudential Forecast Dashboard @5-min (Web UI) |  |  | 2021-07-05 | None. | 2022-03-28 | No Change
S16 | Settlement | SCADA Data MDFF file @ 5 Min |  |  | N/A | N/A | N/A | N/A

## Q&A
AEMO 5MS Functional Deployment Matrix Q&A
Q&A Ref. # | Date raised | Status | AEMO Functional Matrix ID | Question/Clarification | AEMO Response