## Slide 1: Power of choice (POC) Executive Forum
28 June 2016

## Slide 2: Power of Choice Executive Forum
Agenda
1 Apologies
2 Welcome and Introduction
3 Power of Choice Program overview
3.1 Stakeholder Interaction
3.2 Project Risk and Issue management
3.3 Market Readiness Strategy
4 Transitional IEC Update

## Slide 3: AEMO Power of choice (POC) implementation Program: Program Overview
28 June 2016
Presented BY Ben Healy

## Slide 4
2015 |  |  |  |  |  |  | 2016 |  |  |  |  |  |  |  |  |  |  |  | 2017 |  |  |  |  |  |  |  |  |  |  |  | 2018 | 
JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
Working Groups’
Today
Planned Transitional and New IEC Meetings
Power of Choice (PoC) Program Overview
High Level Program V4.0 – 10 June 16
For Information: poc@aemo.com.au
26 Nov
MC
Final Determination
17 Dec
EN Final Determination
MRP Draft Determination
10 Mar
MRP
Final Determination
1 Sep
EN & MC & MRP
Procedures Published
1 Mar
MC
Registration & EN MSL and Accreditation Documentation Published
1 Dec
EN & MC & MRP & SMP
Effective Date (Go-Live)
EN = Embedded Network, MRP = Meter Replacement Processes
MC = Metering Competition, SMP = Shared Market Protocols
Oct
SMP Advice published
EN/MC/MRP WP 1 Procedure Consultation
EN/MC/MRP Package 2 Development
EN/MC/MRP WP 2
Procedure Consultation
For detailed meeting schedule and agendas, see the 2016 industry meeting schedule.
EN/MC Package 3 Development
WP 3 & ‘As built’ Procedure Consultation (If required)
MC /
EN /
MRP
30 Jun
SMP Final Determination
1 Aug
IEC Election Procedures Finalised
MC B2B Recommendation
1 Sep
IEC Election Complete - IEC Formed
1 May
SMP – IEC recommends B2B Procedures Finalised
07 Apr
SMP Draft Determination
1 Dec
MC & EN Ring fencing and network exemption guidelines
1 Sep
DNSPs to publish standard terms and conditions on which it will act as the initial Metering Coordinator
AEMO Requirements
SMP Conceptual IT Designs
SMP B2B Procedure Consultation
TRANS IEC
IEC Election
Election Procedures
& Operating Manual
Fee methodology (if required)
1 Jun
SMP – AEMO publish B2B Procedures & Accreditation Process
Heightened Support
Procedures
Market Readiness
Supporting Activities
IT Systems
P
P
P
P
Market Readiness Strategy
Industry Training
Industry Testing
Transition / Cut Over
AEMO Design
All - IT Development / Internal Testing
Industry Testing
P
P
SMP Procedure Development
P
EN/MC/MRP Package 1 Development
MC Draft Procedures
P
Publish
SMP
Plan
Execute
Plan
Execute
Plan
Execute
Registration & Accreditation
Pre-Prod Release
Trans
Trans
Prod Release
P
P
P
AER - Electricity ring-fencing guideline 2016
Readiness Reporting Commences
Milestone
Working group meeting
Proposed IEC Meetings (Trans & New)
Program Milestones
10 Sep
MRP Direction paper published
EN Draft Determination

## Slide 5: Power of Choice Milestones
Deliverable / Milestone | Project | Description | Planned date | Expected date | Status
AEMC publish MRP Directions paper & EN draft determination | EN, MRP |  | 10 Sep 15 |  | 
AEMC publish SMP advice paper | SMP |  | Early-Oct 15 | 10 Oct 15 | 
AEMC publish final rule determination | MC |  | 24 Nov 15 | 26 Nov 15 | 
AEMC release final determination | EN |  | 17 Dec 15 |  | 
AEMC release draft determination | MRP |  | 17 Dec 15 |  | 
AEMC publish draft rule determination | SMP |  | Early-Feb 16 | 07 Apr 16 | 
AEMC publish final rule determination | MRP |  | 10 Mar 16 |  | 
AEMO pre-consultation workshops conclude | MC,EN,MRP |  | 11 Mar 16 |  | 
AEMO releases Pre-Consultation Paper | MC,EN,MRP |  | 08 Apr 16 |  | 
AEMO publishes notice of first stage consultation (B2B) | B2B:MC,EN,MRP | Not proceeding | 08 Apr 16 | - | -
AEMO publishes notice first stage consultation | MC,EN,MRP |  | 22 Apr 16 |  | 
AEMC publish final rule determination | SMP |  | 26 May 16 | 30 Jun 16 | 
AEMO concludes first stage consultation | MC,EN,MRP |  | 31 May 16 |  | 
AEMO begins Readiness Workstream engagement | MC,EN,MRP |  | 20 Jun 16 | 21 Jun 16 | 
AEMO publish draft procedure determination | MC,EN,MRP |  | 30 Jun 16 | 29 Jun 16 | 
AEMO concludes second stage consultation | MC,EN,MRP |  | 15 Jul 16 | 20 Jul 16 | 
AEMO seeks IEC recommendation for B2B changes | MC,EN | Not proceeding | 25 Jul 16 | 01 Aug 16 | -
AEMO publishes final procedure determination | B2B:MC,EN,MRP | Not proceeding | 12 Aug 16 | 19 Aug 16 | -
AEMO publishes final procedure determination | MC,EN,MRP | No later than 1 Sep 16 | 26 Aug 16 |  | 
AEMO publishes notice first stage consultation (WP2) | MC,EN,MRP |  | 10 Oct 16 |  | 
AEMO publishes notice first stage consultation | B2B: All |  | 10 Oct 16 |  | 
IEC Election complete – IEC formed | SMP | Noting this is a no later than date. | 31 Oct 16 | 06 Aug 16 | 
AEMO concludes first stage consultation | MC,EN,MRP |  | 15 Nov 16 |  | 
Notes: Intent to Publish

## Slide 6: Power of Choice Milestones
Deliverable / Milestone | Project | Description | Planned date | Expected date | Status
AEMO concludes first stage consultation | B2B: All |  | 15 Nov 16 |  | 
AEMO commences development of Fee Methodology | SMP | If required | Sep 16 |  | 
AER publishes ring fencing & network exemption guidelines | MC,EN |  | 01 Dec 16 |  | 
AEMO publish draft procedure determination | MC,EN,MRP |  | 13 Dec 16 |  | 
AEMO publish draft procedure determination | B2B: All |  | 13 Dec 16 |  | 
System implementation period commences | All |  | Mid Dec 16 |  | 
AEMO concludes second stage consultation | MC,EN,MRP |  | 30 Dec 17 |  | 
AEMO concludes second stage consultation | B2B: All |  | 30 Dec 17 |  | 
AEMO seeks IEC recommendation for B2B changes | B2B: All | TBC Preceding AMEO Feb Boar | 22 Jan 17 |  | 
AEMO publishes final procedure determination | MC,EN,MRP | Obligation is no later than 1 Mar 17 | 01 Mar 17 | 14 Feb 17 | 
AEMO publishes final procedure determination | B2B: All | Obligation is no later than 1 Jun 17 | 01 Mar 17 | 14 Feb 17 | 
AEMO publishes Fee Methodology (participant fee structure) | SMP | If required | 01 Mar 17 |  | 
AEMO commences readiness (registration/accreditation) | All | To be determined in readiness strategy | Mar 17 |  | 
Proposed commencement of industry testing | All | To be determined in test plan | Aug 17 |  | 
DNSPs to publish T&C’s on which it will act as the initial MC | MC |  | 1 Sep 17 |  | 
PoC Effective date | All |  | 1 Dec 17 |  | 
Notes: Intent to Publish

## Slide 7: 3.1 Stakeholder Interactions model
(Refer separate attachment: 3.1 POC Stakeholder Interactions.pdf)
Decision layer
  AEMO (Procedures)
  IEC (B2B Procedures)
Information layer
  Participant Exec Engagement
  Retail Market Consultative Forum (RMCF)
Management layer
  Participant program/project management
  AEMO program/project management
  Power of Choice – Program Consultative Forum (PoC-PCF)
Implementation layer
  Working groups
  “Other”

## Slide 8: 3.1 Stakeholder Interactions model
Power of Choice – Program Consultative Forum (PoC-PCF)
Meet monthly (minimum)
First meeting: Late - July
Terms of Reference (ToR) released in June
  Nominations will be requested shortly thereafter
Main Purpose
Facilitate ‘actions’ – Not a “status update” forum

## Slide 9: 3.2 Risk & Issue Management
(Refer separate attachment: POC Industry Management Plan – Risk and Issue.doc)
Supports the efficient identification, tracking and management of risks/Issues
  Consolidates into a single source for Program Management / visibility
  Inputs into reporting (PoC-PCF, Readiness, SCO etc.)
Facilitates communication, consultation and coordination
  Provides avenues for other bodies to feed-into AEMO’s PoC Program
Updated monthly (minimum)
Published on AEMO website

## Slide 10: AEMO Power of choice (POC) implementation project: Market Readiness Strategy
28 June 2016
Presented BY ben healy

## Slide 11: 3.3 Overview of draft strategy
Definition of “market readiness”
Successful implementation of all necessary activities by AEMO and NEM participants
Seamless transition to procedural arrangements, 1 Dec 2017
  Relevant rule/procedure changes: MC, MRP, EN, B2B/SMP
Purpose of Strategy
Plan for managing, coordinating, monitoring, reporting on AEMO & NEM participants’ business systems preparedness
Help inform development of supporting processes
Seamless transition to new procedural arrangements

## Slide 12: 3.3 Scope of draft strategy
Scope of Strategy
Inside scope
  Market readiness phases (test systems, accred’n, regist’n)
  Stakeholder engagement activities (forums, enquiries, facilitation of “go-live” decision)
  Reporting and monitoring processes (progress reports)
  Education and training activities (information, guidance, w/shops to promote better understanding of POC reforms)
Outside scope
  Consequential activities (changes/testing to supporting business systems and processes)
  Other regulatory obligations (new safety requirements)

## Slide 13: 3.3 Principles for market readiness
To guide development and implementation of Strategy
Collaborative approach to market readiness
Each party is responsible for their own readiness
Report readiness risks/issues as early as possible
Communicate readiness risks/issues in writing to AEMO
True and honest readiness reporting
Handling of confidential/sensitive information by AEMO
AEMO to explain readiness decisions to NEM participants

## Slide 14: 3.3 Market readiness phases
Six phases of market readiness contemplated in Strategy
Planning – Strategy, associated plans, templates
Industry Testing – IT Plan, certification, market trial
Accreditation & Registration – A&R Plan
Industry Transition & Cutover – IT&C Plan
Confirmation of operational preparedness for “go-live”
Post “go-live” heightened support – bed-in operations

## Slide 15: 3.3 Stakeholder engagement activities
How AEMO and NEM participants will engage on market readiness matters throughout POC Implementation Project
POC Readiness Working Group – to be established
Engage with other forums/committees on readiness matters
  POC Executive Forum
  POC Program Consultative Forum (PoC-PCF)
  Retail Market Consultative Forum (RMCF)
  Information Exchange Committee (IEC)

## Slide 16: 5.6 Reporting and monitoring processes
AEMO and NEM participants to prepare regular traffic light and % progress reports on status of readiness activities
Monthly frequency, starting November 2016
Company-level reporting by NEM participants and AEMO
Industry-level aggregated reporting by AEMO
  Report provided to NEM participants, AEMO Board, key industry stakeholders
Template-based reporting against several readiness criteria and metrics (assessment & preparation, legal/regulatory, people, business process, mkt systems, transition planning)

## Slide 17: 4 Transitional IEC Update
28 June 2016
Presented BY Violette Mouchaileh