| Business to Market – MSATS General rules that apply to all CRs: - Need to consider if the CR is prospective or retrospective, for retrospective CRs raised at cutover if it has an actual change date/completion date that is before the cutover date then we do not need to do anything with those CRs. - For any CRs raised prior to the 1 December 2017 that have a current objection logging period of greater than 1 business day, at the time of MSATS’s CR processing on the 1 December 2017 those CRs will move to the next stage in their life cycle. - VICAMI is still under consideration pending order of council expected to be released in May 2017. |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Item no | Process | Sub Process - Brief description of the current process | Cross ref notes to B2M or B2B transactions | Existing regulatory obligation for this process | Volume | State | Market roles impacted | Initial transition plan expectations | Pre-Shutdown activities | During Shutdown activities | Post go-live activities (Rules and Procedures apply) | Other Notes, including any “In flight” arrangements |
| 1 | Transfers | Change of Retailer resulting in the transfer of a NMI from one Retailer to another Retailer. | Change Requests 1000, 1010, 1020, 1030 & 1040 | MSATS Procedures: CATS Procedure Principles and Obligations. |  | NSW, SA, ACT, QLD, TAS, VIC | FRMP MDP MPB MPC MC |  |  |  |  | - Transfers with deleted read type codes (NI, NB) – Cancel CRs On 1 Dec 17 - Transfers assigning FRMP as the RP, or the LNSP as the RP for meters other than 5,6,7 – Cancel CRs on 1 Dec 17 - Transfers assigning MDP and MP roles where there is no valid MC appointed for the NMI – Cancel CRs on 1 Dec 17, this is a consequence of the previous point |
|  |  | Change of Retailer resulting from error corrections of small NMI transfers | Change Requests 1021, 1022, 1023, 1024, 1025, 1026, 1027, 1028, 1029 |  |  |  |  |  |  |  |  |  |
| 2 | Transfers | Change of Retailer where FRMP is not the RP | Change Requests 1050, 1051 | MSATS Procedures: CATS Procedure Principles and Obligations. |  | ALL | FRMP MDP MPB MPC MC |  |  |  |  | Those CRs are disabled from 1 December 2017, as a result CRs will be cancelled on 1 December 2017 |
| 3 | Transfers | Change of Retailer resulting from the transfer of a Child NMI from one retailer to another retailer | Change Requests 1080, 1081, 1082, 1083, 1084 | MSATS Procedures: CATS Procedure Principles and Obligations. |  | ALL | FRMP MDP MPB MPC MC |  |  |  |  | - Transfers with deleted read type codes (NI, NB) – Cancel CRs On 1 Dec 17 - Transfers assigning FRMP as the RP, or the LNSP as the RP for meters other than 5,6,7 – Cancel CRs on 1 Dec 17 - Transfers assigning MDP and MP roles where there is no valid MC appointed for the NMI – Cancel CRs on 1 Dec 17, this is a consequence of the previous point |
| 4 | Transfers | Change of Retailer for Child NMI where FRMP is not the RP | Change Requests 1090, 1091 | MSATS Procedures: CATS Procedure Principles and Obligations. |  | ALL | FRMP MDP MPB MPC MC |  |  |  |  | Those CRs are disabled from 1 December 2017, as a result CRs will be cancelled on 1 December 2017 |
| 5 | Provide Data | Provide Actual Change Date | Change Request 1500 | MSATS Procedures: CATS Procedure Principles and Obligations. |  | ALL | MDP FRMP MC |  |  |  |  | Any CRs cancelled by AEMO on 1 Dec 17, If a CR 1500 is sent as a result of the cancelled CR, the CR1500 will be rejected by the MSATS. |
| 6 | Create NMI | LNSP to create a NMI | Change Requests 2000, 2001 | MSATS Procedures: CATS Procedure Principles and Obligations. |  | ALL | LNSP ROLR MC MPB MPC MDP FRMP |  |  |  |  | - 2000 change request with effective date proposed post 1 December 2017 and has invalid details for RP (RP who is the FRMP, or the LNSP for meters other than 5,6,7 ), and hence it can have invalid details of MPB, MPC, and MDP – Cancel CRs on 1 Dec 17 - Ability for ROLR to object will be disabled from 1 December 2017 – AEMO believes no impact with this change |
| 7 | Create NMI | LNSP to create a Tier 1 NMI | Change Request 2003 | MSATS Procedures: CATS Procedure Principles and Obligations. |  | ALL | LNSP ROLR MC MPB MPC MDP FRMP |  |  |  |  | Those CRs are disabled from 1 December 2017, as a result CRs will be cancelled on 1 December 2017 |
| 8 | Create NMI | ENM to create Child NMIs | Change Requests 2020 2021 | MSATS Procedures: CATS Procedure Principles and Obligations. |  | ALL | LR ROLR MC MPB MPC MDP FRMP ENM |  |  |  |  | - CR 2020 initiated by LR with proposed date after 1 Dec 17 – Cancel CRs On 1 Dec 17 - 2020 change request with effective date proposed post 1 December 2017 and has invalid details for RP (RP who is the FRMP, or the LNSP for meters other than 5,6,7 ), and hence it can have invalid details of MPB, MPC, and MDP – Cancel CRs on 1 Dec 17 - Ability for ROLR to object will be disabled from 1 December 2017 – AEMO believes no impact with this change |
| 9 | Create NMI | LNSP to create NMI, metering installation details, and MDM data stream | Change requests 2500 2501 | MSATS Procedures: CATS Procedure Principles and Obligations. |  | ALL | LNSP ROLR MC MPB MPC MDP FRMP |  |  |  |  | - 2500 change request with effective date proposed post 1 December 2017 and has invalid details for RP (RP who is the FRMP, or the LNSP for meters other than 5,6,7 ), and hence it can have invalid details of MPB, MPC, and MDP – Cancel CRs on 1 Dec 17 - Ability for ROLR to object will be disabled from 1 December 2017 – AEMO believes no impact with this change - Change requests that do not have the MDM contributory suffix provided as this field is mandatory in those CRs post 1 Dec 17 – Cancel CRs on 1 Dec 2017 |
| 10 | Create NMI | ENM to create NMI, metering installation details, and MDM data stream details for Child NMIs | Change requests 2520 2521 | MSATS Procedures: CATS Procedure Principles and Obligations. |  | ALL | LR ROLR MC MPB MPC MDP FRMP ENM |  |  |  |  | - CR 2520 initiated by LR with proposed date after 1 Dec 17 – Cancel CRs On 1 Dec 17 - 2520 change request with effective date proposed post 1 December 2017 and has invalid details for RP (RP who is the FRMP, or the LNSP for meters other than 5,6,7 ), and hence it can have invalid details of MPB, MPC, and MDP – Cancel CRs on 1 Dec 17 - Ability for ROLR to object will be disabled from 1 December 2017 – AEMO believes no impact with this change - Change requests that do not have the MDM contributory suffix provided as this field is mandatory in those CRs post 1 Dec 17 – Cancel CRs on 1 Dec 2017 |
| 11 | Maintain Metering | Creating Metering Installation details Exchange of Metering Information | Change requests 3000 3001 3004 3005 | MSATS Procedures: CATS Procedure Principles and Obligations. |  | ALL | MPB |  |  |  |  | - 3000 and 3004 Change requests that do not have the MDM contributory suffix provided as this field is mandatory in those CRs post 1 Dec 17 – Cancel CRs on 1 Dec 2017 - 3000 and 3004 Change requests that do not have the Network Tariff code as this field is mandatory in those CRs post 1 Dec 2017 - Cancel CRs on 1 Dec 2017 |
| 12 | Maintain Metering | Create tier 1 metering installation details | Change requests 3003 3053 | MSATS Procedures: CATS Procedure Principles and Obligations. |  | ALL | MPB |  |  |  |  | Those CRs are disabled from 1 December 2017, as a result CRs will be cancelled on 1 December 2017 |
| 13 | Maintain Metering | Change Metering Installation details | Change requests 3050 3051 | MSATS Procedures: CATS Procedure Principles and Obligations. |  | ALL | MPB |  |  |  |  | Note: At completion of CRs 3050 and 3051 post 1 Dec 17, if the mandatory fields of MDM contributory suffix and Network Tariff Code do not exists in the standing data in MSATS then the CRs will be rejected by MSATS. |
| 14 | Maintain Metering | Advanced change metering installation details, and advanced exchange of metering | Change requests 3080 3081 3090 3091 | MSATS Procedures: CATS Procedure Principles and Obligations. |  | ALL | MC |  |  |  |  | - CR1500 is required for those CRs post 1 Dec 17, CRs will not complete until CR1500 is submitted post 1 Dec 17 even if no RDAT request was sent – Cancel CRs on 1 Dec 2017 Note: At completion of those CRs post 1 Dec 17, if the mandatory fields of MDM contributory suffix do not exists in the standing data in MSATS then the CRs will be rejected by MSATS. |
| 15 | Maintain Metering | Change network tariff code | Change requests 3100 3101 | MSATS Procedures: CATS Procedure Principles and Obligations. |  | ALL | LNSP ENM |  |  |  |  | No impact |
| 16 | Maintain data stream | Create MDM data stream | Change requests 4000 4001 | MSATS Procedures: CATS Procedure Principles and Obligations. |  | ALL | MDP |  |  |  |  | No impact |
| 17 | Maintain data stream | Exchange of data stream information | Change requests 4004 4005 | MSATS Procedures: CATS Procedure Principles and Obligations. |  | ALL | MDP |  |  |  |  | No impact |
| 18 | Maintain data stream | Create MDM data stream Exchange of data stream information | Change requests 4003 4053 | MSATS Procedures: CATS Procedure Principles and Obligations. |  | ALL | MDP |  |  |  |  | Those CRs are disabled from 1 December 2017, as a result CRs will be cancelled on 1 December 2017 |
| 19 | Maintain data stream | Change NMI Data stream | Change requests 4050 4051 | MSATS Procedures: CATS Procedure Principles and Obligations. |  | ALL | MDP |  |  |  |  | No impact |
| 20 | Maintain NMI | Update Next Scheduled Read Date | Change requests 5070 5071 | MSATS Procedures: CATS Procedure Principles and Obligations. |  | ALL | MDP |  |  |  |  | No impact |
| 21 | Maintain NMI | Backdate a NMI | Change requests 5001 5021 | MSATS Procedures: CATS Procedure Principles and Obligations. |  | ALL | LNSP ENM |  |  |  |  | - CR 5021 initiated by LR with proposed date after 1 Dec 17 – Cancel CRs On 1 Dec 17 - Ability for ROLR to object will be disabled from 1 December 2017 – AEMO believes no impact with this change |
| 22 | Maintain NMI | Change a NMI | Change requests 5050 5051 | MSATS Procedures: CATS Procedure Principles and Obligations. |  | ALL | LNSP |  |  |  |  | No impact |
| 23 | Maintain NMI | Change a 1st tier NMI Standing data | Change request 5053 | MSATS Procedures: CATS Procedure Principles and Obligations. |  | ALL | LNSP |  |  |  |  | Those CRs are disabled from 1 December 2017, as a result CRs will be cancelled on 1 December 2017 |
| 24 | Maintain NMI | Change a NMI – customer classification code | Change requests 5054 5055 | MSATS Procedures: CATS Procedure Principles and Obligations. |  | ALL | FRMP |  |  |  |  | No impact |
| 25 | Maintain NMI | Change NMI embedded network (Child) | Change requests 5060 5061 | MSATS Procedures: CATS Procedure Principles |  | ALL | ENM LR |  |  |  |  | - CR initiated by LR with proposed date after 1 Dec 17 – Cancel CRs On 1 Dec 17 |
| 26 | Maintain NMI | Change parent name | Change requests 5080 5081 | MSATS Procedures: CATS Procedure Principles |  | ALL | FRMP LNSP |  |  |  |  | - CRs that are initiated by current FRMP, as post 1 December it can only be initiated by the current LNSP- cancel CRs raised by FRMP on 1 Dec 2017 |
| 27 | Maintain NMI | Make NMI a child NMI | Change requests 5090 5091 | MSATS Procedures: CATS Procedure Principles |  | ALL | LNSP |  |  |  |  |  |
| 28 | Change Roles | Change LNSP | Change requests 6100 6110 | MSATS Procedures: CATS Procedure Principles |  | ALL | LNSP |  |  |  |  |  |
| 29 | Change Roles | Change MDP | Change requests 6200 6210 | MSATS Procedures: CATS Procedure Principles |  | ALL | FRMP MC MDP |  |  |  |  | - CR1500 is required for those CRs post 1 Dec 17, CRs will not complete until CR1500 is submitted post 1 Dec 17 even if no RDAT request was sent – Cancel CRs on 1 Dec 2017 |
| 30 | Change Roles | Change MC | Change requests 6300 6301 | MSATS Procedures: CATS Procedure Principles |  | ALL | MC MDP |  |  |  |  | - CR1500 is required for those CRs post 1 Dec 17, CRs will not complete until CR1500 is submitted post 1 Dec 17 even if no RDAT request was sent – Cancel CRs on 1 Dec 2017 |
| 31 | Change Roles | Change LR | Change requests 6400 6401 | MSATS Procedures: CATS Procedure Principles |  | ALL | LR |  |  |  |  |  |
| 32 | Change Roles | Change LR Child NMI | Change requests 6421 | MSATS Procedures: CATS Procedure Principles |  | ALL | LR |  |  |  |  |  |
| 33 | Change Roles | Change ROLR | Change requests 6500 6501 | MSATS Procedures: CATS Procedure Principles |  |  | ROLR |  |  |  |  | - Ability for ROLR to object will be disabled from 1 December 2017 – AEMO believes no impact with this change |
| 34 | Change Roles | Change MPB, MPC, or Both | Change requests 6700 6701 | MSATS Procedures: CATS Procedure Principles |  | ALL | MC MDP |  |  |  |  | - CR1500 is required for those CRs post 1 Dec 17, CRs will not complete until CR1500 is submitted post 1 Dec 17 even if no RDAT request was sent – Cancel CRs on 1 Dec 2017 |
| 35 | Change Roles | Change Multiple Roles – MC, MDP, MPC, MPB | Change requests 6800 6801 | MSATS Procedures: CATS Procedure Principles |  | ALL | MC FRMP MDP |  |  |  |  |  |
| 36 | Auto change roles | Change LR – Child NMI – Auto | Change Request ECLR | MSATS Procedures: CATS Procedure Principles |  |  |  |  |  |  |  | No Impact |
| 37 | Auto change roles | Change Secondary FRMP – Parent NMI | Change Request EFPR | MSATS Procedures: CATS Procedure Principles |  |  |  |  |  |  |  | No Impact |
| 38 | AEMO only | Standing data updates | Change requests 5100 5101 | MSATS Procedures: CATS Procedure Principles |  |  |  |  |  |  |  | No Impact |
| 39 | AEMO only | Invoke BCT for ROLR | Change requests ROLR | MSATS Procedures: CATS Procedure Principles |  |  |  |  |  |  |  | No Impact |
| 40 | AEMO only | Invoke BCT Process | Change requests BCxx | MSATS Procedures: CATS Procedure Principles |  |  |  |  |  |  |  | No Impact |

| Business to Business – B2B General rules that apply to all B2B Transactions: - The following B2B transition planning activities relate to the current NEM B2B Service Orders Procedures, version 2.2. - The following planning activities apply to regulated metering sites, I.e. Meter Types 5 & 6. |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Item no | Process | Sub Process - Brief description of the current process | Cross ref notes to B2M or B2B transactions | Existing regulatory obligation for this process | Volume | State | Market roles impacted | Initial transition plan expectations | Pre-Shutdown activities | During Shutdown activities | Post go-live activities (Rules and Procedures apply) | Other Notes, including any specific procedural arrangements or obligations. |
| 1 | Re-Energisation Service Orders | After Disconnection for Non-Payment |  | B2B Procedures: Service Orders v2.2. |  | NSW, SA, ACT, QLD, TAS, VIC | FRMP DNSP | Service order has been received and acknowledged by DB. Stop initiating transaction from current jurisdicational requirements. Tack’s and mack within normal timeframes as per tech guidleines. | If DB received prior will continue to process. | Contingency processes | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation. BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. | Requests prior to 1 Dec, will be sent in R33 with any responses sent post 1 Dec in R36 Same day connections must be received as per jurisdictional timings. Retrospective move in sub types could be a sub type that is not raised on the day of planned shutdown. Sticker removal sub types could be a sub type that is not raised on the day of planned shutdown. May be a slight impact to SDQ data for LNSP NMIST. Prospective Re-ens can be raised as per B2B procedures today.ie 100 calendar days. Cancellations of service orders that have |
|  |  | Sticker Removal |  |  |  |  |  | Service order has been received and acknowledged by DB. Stop initiating transaction from current jurisdicational requirements. Tack’s and mack within normal timeframes as per tech guidleines. | If DB received prior will continue to process. | Contingency processes | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation. BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. |  |
|  |  | Retrospective Move In |  |  |  |  |  | Service order has been received and acknowledged by DB. Stop initiating transaction from current jurisdicational requirements. Tack’s and mack within normal timeframes as per tech guidleines. | If DB received prior will continue to process. | Contingency processes | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation. BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. |  |
|  |  | New Reading Required |  |  |  |  |  | Service order has been received and acknowledged by DB. Stop initiating transaction from current jurisdicational requirements. Tack’s and mack within normal timeframes as per tech guidleines. | If DB received prior will continue to process. | Contingency processes | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation. BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. |  |
|  |  | Blank |  |  |  |  |  | Service order has been received and acknowledged by DB. Stop initiating transaction from current jurisdicational requirements. Tack’s and mack within normal timeframes as per tech guidleines. | If DB received prior will continue to process. | Contingency processes | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation. BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. |  |
| 2 | De-energisation Service Orders | Pillar box, Pit or Pole Top |  | B2B Procedures: Service Orders v2.2 |  | NSW, SA, ACT, QLD, TAS, VIC | FRMP DNSP | Service order has been received and acknowledged by DB. Stop initiating transaction from 1pm. Tack’s and mack within normal timeframes as per tech guidleines. | If DB received prior will continue to process. | Contingency processes | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. | Requests prior to 1 Dec, will be sent in R33 with any responses sent post 1 Dec in R36 De-energisations must be received as per jurisdictional notice period timings. De-energisations must only occur on a permissible/non restricted day. Pillar box, Pit or Pole Top sub type could be a sub type that is not raised on the day of planned shutdown. Pillar box, Pit or Pole Top (disconnect for non payment) sub types could be a sub type that is not raised on the day of planned shutdown. Remove fuse (disconnect for non payment) could be a sub type that is not raised on the day of planned shutdown. Sticker sub type is no longer used |
|  |  | Pillar Box, Pit or Pole Top (non-payment) |  |  |  |  |  | Service order has been received and acknowledged by DB. No raising or scheduling a DNP for the period from 23/11 to 30/11. This will reduce the amount of same day reconnections |  | Contingency not required as no new requests will be raised between 23/11/17 and 30/11/17. | BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. |  |
|  |  | Remove Fuse |  |  |  |  |  | Service order has been received and acknowledged by DB. Stop initiating transaction from 1pm. Tack’s and mack within normal timeframes as per tech guidleines. | If DB received prior will continue to process. | Contingency processes | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation. BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. |  |
|  |  | Remove Fuse (non-payment) |  |  |  |  |  | Service order has been received and acknowledged by DB. No raising or scheduling a DNP for the period from 23/11 to 30/11. This will reduce the amount of same day reconnections |  | Contingency not required as no new requests will be raised between 23/11/17 and 30/11/17. | BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. |  |
|  |  | Sticker |  |  |  |  |  | Service order has been received and acknowledged by DB. Stop initiating transaction from 1pm. Tack’s and mack within normal timeframes as per tech guidleines. | If DB received prior will continue to process. | Contingency processes | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation. BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. |  |
|  |  | Blank |  |  |  |  |  | Service order has been received and acknowledged by DB. Stop initiating transaction from 1pm. Tack’s and mack within normal timeframes as per tech guidleines. | If DB received prior will continue to process. | Contingency processes | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation. BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. |  |
| 3 | Adds & Alts Service Orders | Install Hot water |  | B2B Procedures: Service Orders v2.2. |  | SA, ACT, QLD, TAS, VIC | FRMP DNSP | Service order has been received and acknowledged by DB. Retailers not to raise this sub type later than 1/11/17 for SA & ACT and16/11/17 QLD & TAS No transition for VIC as assumption is that the VIC DB’s will continue to perform this service under the OIC. No transition in NSW as this service order type is not used. | If DB received prior will continue to process. | Contingency not required as no new requests will be raised between 1/11/17 and 30/11/17 for SA & ACT and 16/11/17 and 30/11/17 in QLD and TAS. | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation. BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. | Requests prior to 1 Dec, will be sent in R33 with any responses sent post 1 Dec in R36 |
|  |  | Install Controlled Load |  |  |  |  |  | Service order has been received and acknowledged by DB. Retailers not to raise this sub type later than 1/11/17 for SA & ACT and16/11/17 QLD & TAS No transition for VIC as assumption is that the VIC DB’s will continue to perform this service under the OIC. No transition in NSW as this service order type is not used. | If DB received prior will continue to process. | Contingency not required as no new requests will be raised between 1/11/17 and 30/11/17 for SA & ACT and 16/11/17 and 30/11/17 in QLD and TAS. | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation. BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. |  |
|  |  | Move Meter |  |  |  |  |  | Service order has been received and acknowledged by DB. Retailers not to raise this sub type later than 1/11/17 for SA & ACT and16/11/17 QLD & TAS No transition for VIC as assumption is that the VIC DB’s will continue to perform this service under the OIC. No transition in NSW as this service order type is not used. | If DB received prior will continue to process. | Contingency not required as no new requests will be raised between 1/11/17 and 30/11/17 for SA & ACT and 16/11/17 and 30/11/17 in QLD and TAS. | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation. BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. |  |
|  |  | Install Meter |  |  |  |  |  | Service order has been received and acknowledged by DB. Retailers not to raise this sub type later than 1/11/17 for SA & ACT and16/11/17 QLD & TAS No transition for VIC as assumption is that the VIC DB’s will continue to perform this service under the OIC. No transition in NSW as this service order type is not used. | If DB received prior will continue to process. | Contingency not required as no new requests will be raised between 1/11/17 and 30/11/17 for SA & ACT and 16/11/17 and 30/11/17 in QLD and TAS. | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation. BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. |  |
|  |  | Remove Meter |  |  |  |  |  | Service order has been received and acknowledged by DB. Retailers not to raise this sub type after 1pm on 30/11/17. No transition for VIC as assumption is that the VIC DB’s will continue to perform this service under the OIC. No transition in NSW as this service order type is not used. | If DB received prior will continue to process. | Contingency not required. | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation. BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. |  |
|  |  | Exchange Meter |  |  |  |  |  | Service order has been received and acknowledged by DB. Retailers not to raise this sub type later than 1/11/17 for SA & ACT and16/11 QLD & TAS No transition for VIC as assumption is that the VIC DB’s will continue to perform this service under the OIC. No transition in NSW as this service order type is not used. | If DB received prior will continue to process. | Contingency not required as no new requests will be raised between 1/11/17 and 30/11/17 for SA & ACT and 16/11/17 and 30/11/17 in QLD and TAS. | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation. BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. |  |
| 4 | Allocate NMI Service Order |  |  | B2B Procedures: Service Orders v2.2. |  | NSW, TAS | FRMP DNSP | Service order has been received and acknowledged by DB. Retailers not to raise this service order after 1pm on 30/11. | If DB received prior will continue to process. | Contingency not required On the 1/12 and if the NMI is still a greenfield site then a process will be performed to update the NMI with the correct MC, MDP and MP roles. | DB to send response. BAU processes to continue for macks & tacks. Report to be produced by the DB’s of greenfield NMI’s. BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. | Requests prior to 1 Dec, will be sent in R33 with any responses sent post 1 Dec in R36 5/6: Action:What will the process be for sites that have been created by the NSW DB’s but it is still a greenfield site? Will they be made extinct and a new Allocate NMI is raised with the new roles or will a process be put in place to change the roles upon instruction from the Retailer to update MSATS with the new roles? What is industry’s preferred process? By 15/6 15/6: Meters will be provided to ASP up until the 30/11. NMI will not be made extinct, roles will be updated. ASP’s may still install meters after 1/12. DB’s are in conversation with ASP’s to advise them that they’re not allowed. |
| 5 | New Connection Service Orders | Temporary |  |  |  | SA, ACT, QLD, TAS, VIC | FRMP DNSP | Service order has been received and acknowledged by DB. Retailers not to raise new connection service orders later than 1/11/17 for regulated metering. |  | Contingency processes. Juridictional: Regulated Metering; Each jurisdiction will have their own plan that has been agreed to by Retailers. Non regulated or for new connections that Retailers know will definitely be scheduled to be performed after the 1/12/17; The service will be requested and a response will be sent via email using the new connection email address in the RoCL as the point of contact. This email will consist of a template using the requests and responses as per version 3.0 of the B2B Procedures. | DB to send response. BAU processes to continue for macks & tacks. Any new connections that are inflight with the DB’s after the 1/12/17 and will not be metered and serviced before the 1/1/18 then the NMI a process will be performed to update the NMI with the new MC, MDP and MP roles who will then complete the process. Report to be produced by the DB’s of greenfield NMI’s. BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. | Requests prior to 1 Dec, will be sent in R33 with any responses sent post 1 Dec in R36 On average 40 days for a new connection to complete. 5/6: Action: what is the cut off time for DB’s where service and metering can be guaranteed by the 1/1/18 except NSW & VIC.by 15/6 15/6: SA ok with dates in the action plan. No new connect s/o after 1/11, all DB metering to be done before 1/1/18. Still doing some work internally. NC has its own lifespan. DB to determine whether it can be completed. Roles will updated. Bilateral agreement QLD after 1pm 23/11 for type 6 completed by 30/11. Cant be completed retailer will be notified and new connect will be not completed. Will attempt to meet the original timeframes when a new request comes in. After 1pm on 30/11 for type 4. Roles will be updated by the FRMP for greenfield sites.. ACT accept RFS up until 30/11.accept n/c up until 3/11 5pm 5/6:Action: NSW DB’s what point will you stop allocating meters to ASP’s? by 15/6 Meters will be provided right up until 30/11 5/6: Action:What will the process be for sites that have been created by the DB’s but it is still a greenfield site and will not be metered and serviced by 1/1/18? Will they be made extinct and a new Allocate NMI is raised with the new roles or will a process be put in place to change the roles upon instruction from the Retailer to update MSATS with the new roles? What is industry’s preferred process? By 15/6 Roles will be updated. |
|  |  | Temporary in Permanent |  |  |  |  |  | Service order has been received and acknowledged by DB. Retailers not to raise new connection service orders later than 1/11/17 for regulated metering. |  | Contingency processes. Juridictional: Regulated Metering; Each jurisdiction will have their own plan that has been agreed to by Retailers. Non regulated or for new connections that Retailers know will definitely be scheduled to be performed after the 1/12/17; The service will be requested and a response will be sent via email using the new connection email address in the RoCL as the point of contact. This email will consist of a template using the requests and responses as per version 3.0 of the B2B Procedures. | DB to send response. BAU processes to continue for macks & tacks. Any new connections that are inflight with the DB’s after the 1/12/17 and will not be metered and serviced before the 1/1/18 then the NMI a process will be performed to update the NMI with the new MC, MDP and MP roles who will then complete the process. Report to be produced by the DB’s of greenfield NMI’s. BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. | 15/6: Action: ACT and SA to come back with a position by next meeting or following. |
|  |  | Permanent |  |  |  |  |  | Service order has been received and acknowledged by DB. Retailers not to raise new connection service orders later than 1/11/17 for regulated metering. |  | Contingency processes. Juridictional: Regulated Metering; Each jurisdiction will have their own plan that has been agreed to by Retailers. Non regulated or for new connections that Retailers know will definitely be scheduled to be performed after the 1/12/17; The service will be requested and a response will be sent via email using the new connection email address in the RoCL as the point of contact. This email will consist of a template using the requests and responses as per version 3.0 of the B2B Procedures. | DB to send response. BAU processes to continue for macks & tacks. Any new connections that are inflight with the DB’s after the 1/12/17 and will not be metered and serviced before the 1/1/18 then the NMI a process will be performed to update the NMI with the new MC, MDP and MP roles who will then complete the process. Report to be produced by the DB’s of greenfield NMI’s. BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. |  |
| 6 | Special Read Service Orders | Check Read |  | B2B Procedures: Service Orders v2.2. |  | NSW, SA, ACT, QLD, TAS, VIC | FRMP DNSP | Service order has been received and acknowledged by DB. Stop initiating transaction from 1pm. Tack’s and mack within normal timeframes as per tech guidleines. | If DB received prior will continue to process. | Contingency processes | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation | Requests prior to 1 Dec, will be sent in R33 with any responses sent post 1 Dec in R36. Special Reads must be received as per jurisdictional notice period timings. |
|  |  | Final Read |  |  |  |  |  | Service order has been received and acknowledged by DB. Stop initiating transaction from 1pm. Tack’s and mack within normal timeframes as per tech guidleines. | If DB received prior will continue to process. | Contingency processes | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation |  |
|  |  | Blank |  |  |  |  |  | Service order has been received and acknowledged by DB. Stop initiating transaction from 1pm. Tack’s and mack within normal timeframes as per tech guidleines. | If DB received prior will continue to process. | Contingency processes | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation |  |
| 7 | Meter Reconfiguration Service Orders | Change Controlled Load |  | B2B Procedures: Service Orders v2.2. |  | NSW, SA, ACT, QLD, TAS, VIC | FRMP DNSP | Service order has been received and acknowledged by DB. Stop initiating transaction from 1pm. | If DB received prior will continue to process. | Contingency not required | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation |  |
|  |  | Change Timeswitch |  |  |  |  |  | Service order has been received and acknowledged by DB. Stop initiating transaction from 1pm. | If DB received prior will continue to process. | Contingency not required | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation |  |
|  |  | Change Tariff |  |  |  |  |  | Service order has been received and acknowledged by DB. Stop initiating transaction from 1pm. | If DB received prior will continue to process. | Contingency not required | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation | Ergon want to continue reconfig for solar. Energex will cancel and new meter will need to be installed. |
| 8 | Meter Investigation Service Orders | Tamper |  | B2B Procedures: Service Orders v2.2. |  | NSW, SA, ACT, QLD, TAS, VIC | FRMP DNSP | Service order has been received and acknowledged by DB. Stop initiating transaction from 1pm. | If DB received prior will continue to process. | Contingency not required | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation |  |
|  |  | Inspect |  |  |  |  |  | Service order has been received and acknowledged by DB. Stop initiating transaction from 1pm. | If DB received prior will continue to process. | Contingency not required | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation |  |
|  |  | Meter Test |  |  |  |  |  | Service order has been received and acknowledged by DB. Stop initiating transaction from 1pm. | If DB received prior will continue to process. | Contingency not required | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation |  |
| 9 | Supply Abolishment Service Order |  |  | B2B Procedures: Service Orders v2.2 |  | NSW, SA, ACT, QLD, TAS, VIC | FRMP DNSP | Retailers not to raise this sub type after 1pm on 30/11. No transition for VIC | If DB received prior will continue to process. | Contingency not required | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation |  |
| 10 | Miscellaneous Service Order |  |  | B2B Procedures: Service Orders v2.2 |  | NSW, SA, ACT, QLD, TAS, VIC | FRMP DNSP | Service order has been received and acknowledged by DB. Stop initiating transaction from 1pm. | If DB received prior will continue to process. | Contingency not required | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation | 15/6 Action:retailers to look at reasons for raising. Look at not raising after the 23rd. |
| 11 | Customer and Site Details Notification | Customer Details Request |  | B2B Procedures: Service Orders v2.2 |  | NSW, SA, ACT, QLD, TAS, VIC | FRMP DNSP | Stop initiating transaction from day before cutover. | If RB received prior will continue to process. | Contingency not required | RB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation |  |
|  |  | Customer Details Notification |  |  |  |  |  | Stop initiating transaction from 1pm dayof cutover. | If DB received prior will continue to process. | Contingency not required | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation | Process of ringing and emailing life support will continue. |
|  |  | Customer Details Reconciliation |  |  |  |  |  | Run to your normal schedule. No reconciliations between 1/11/17 to 1/2/18 |  |  |  |  |
|  |  | Site Access Notification |  |  |  |  |  | Stop initiating transaction from 1pmdayof cutover. | If DB received prior will continue to process. | Contingency not required | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation |  |
| 12 | One Way Notification | Meter Exchange Notification |  | B2B Procedures: Service Orders v2.2 |  | NSW, SA, ACT, QLD, TAS, VIC | FRMP DNSP | Stop initiating transaction from 1pmdayof cutover. | If RB received prior will continue to process. | Contingency not required | RB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation |  |
|  |  | Network Tariff Notification |  |  |  |  |  | Stop initiating transaction from 1pmdayof cutover. | If RB received prior will continue to process. | Contingency not required | RB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation |  |
| 13 | Meter Data Process | Provide Meter Request |  | B2B Procedures: Service Orders v2.2 |  | NSW, SA, ACT, QLD, TAS, VIC | FRMP DNSP MDP |  |  |  |  | 15/6:Action: What is the cut off time prior to requesting? What is your catch up time for processing and sending data? When do you start sending meter data and pmd/vmd? |
|  |  | Verify Meter Data Request |  |  |  |  |  |  |  |  |  |  |
|  |  | Meter Data Notification |  |  |  |  |  | 5pm AEST on cutover date to align with MDM data. |  |  |  |  |