## Slide 1: PROGRAM CONSULTATIVE FORUM Meeting pack
DATE: Friday 13 October 2017
TIME: 10.00 AM – 1.00PM (AEST)
VENUE: AEMO OFFICES; MEL, SYD, ADE, BRI
TELECONFERENCE: DIAL IN: 02 8602 3002
CONTACT: poc@aemo.com.au

## Slide 2: Power of Choice PROGRAM UPDATE

## Slide 3: Actions from previous meeting
# | Description | Date due | Status | Owner | Comments/Outcomes
A14 | Bypassing of Meters | 28 Sep 17 | Closed | ActewAGL | • will bypass meters and provide an update to AEMO by Tue 3 Oct
 |  | 28 Sep 17 | Closed | Ausgrid | • will bypass meters – no change
 |  | 28 Sep 17 | Closed | Ausnet | • no change
 |  | 28 Sep 17 | Closed | Endeavour | • no change
 |  | 28 Sep 17 | Closed | Energex | • no change
 |  | 28 Sep 17 | Closed | Ergon | • no change
 |  | 28 Sep 17 | Closed | Essential | • no change
 |  | 28 Sep 17 | Closed | SAPN | • no change
A15 | LNSPs and MCs are to review each scenario provided under a change of role in the attached spreadsheet and notify what action their specific organisation will take, either object (y) or not (n). Refer to attachment: ACT 2 Change Request Objection Clarifications. Responses to 6800 and 6300 messages | 28 Sep 17 | Open | All parties | 
Refer attachment 3.0 PCF Action Summary spreadsheet for A15 responses

## Slide 4: AEMO Program Update
General
Upcoming meetings:
  Executive Forum Tuesday 31 October 2017
AEMO Procedures
Procedures Finalised and published
Any required system changes resulting from WP3 consultation have been included in MSATS
B2B Procedures
IEC met on 26 September to approve the B2B Errata
  This document includes all the corrections agreed by the B2B Working group and will be published by AEMO in the B2B Change Log by Wed18 October
B2BWG met on 27 September to discuss a number of additional items raised to the B2B Change log
  2 x further changes were agreed and on approval by the IEC will be sort by Fri 13 October and will be published by AEMO in the B2B Errata.
B2BWG also discussed an issue involving Jemena and Momentum relating to Service Order paperwork in the Allocate NMI Service Order
  No changes to B2B procedures were agreed, however a process for providing the required detail was agreed - Please refer to the updated B2B Change Log for details
Systems
AEMO system released into pre-production environment 12 October in preparation for Cycle 3 Market Trials

## Slide 5: AEMO Program Update
Communication Plan:
AEMO continues to coordinate discussions on industry PoC communications.
Latest meeting was held on 6 October and included:
  AEMO, officials for the Commonwealth Department of Environment and Energy, the AEMC, the AER, ENA representing networks, the AEC representing its members, a metering representative (Doug Ross) and a small retailer representative (Andrew Mair).
The Industry Communications Overview has been completed
AEMO has released a series of draft fact sheets and led the development of a Joint Industry FAQ document. Feedback on these closes on Fri 13 October
Please work with your representative to engage in the process
If you have any further questions, please contact poc@aemo.com.au
Refer to item 2.0 the Communications Overview for further information

## Slide 6: AEMO Program Update
Readiness:
Readiness Reporting:
  October POC Monthly Readiness Reports were due to 10 October
  AEMO will published the latest POC Monthly Readiness Summary Report 18 October
  Many reports reflecting issues/actions that have been completed – update
  Many participants ‘concerned’ about others
    Self reporting only
Accreditation and Registration:
  Full MCs: 1 registration approved, 11 applications received, 5 in progress/under assessment, awaiting supporting documentation from all others
  Initial MCs: 4 registrations approved, all DNSP applications received, 8 in progress/under assessment
  Type 7 MCs: 4 registrations approved, 1 outstanding DNSP applications, 7 in progress/under assessment
  TNSP MCs: none approved, 4 applications received; 3 outstanding, awaiting support documentation from all others (AEMO proactively pursuing)
  Generator MCs: all have been contacted by AEMO
  ENMs: nil accredited, 20 applications received, 6 in progress/under assessment, awaiting supporting documentation from all others
  20 completed B2B Accreditations. B2B accreditations window remains open

## Slide 7: AEMO Program Update
Readiness (cont):
Industry Testing:
  Cycle 1 - 21 August to 8 September (completed)
  Cycle 2 - 18 September to 6 October (completed)
    36 companies took part in Cycle 2 (40 expected in Cycle 3)
    67% of planned tests executed with 1,935 tests cases in Passed Status, 315 test cases either in Blocked or Failed Status
    No major defects identified - 24 defects assigned to AEMO with 6 confirmed in the defect fix drop due on the 12 October - the remainder are still under investigation
  Cycle 3 - 16 October to 3 November
Transition and Cutover:
  AEMO has published version 1.1 of the POC Industry Transition & Cutover Plan
  The ITCFG are currently focused on dress rehearsal arrangements prior to the commence of system cutover activities on 30 November
Contingency Planning:
  AEMO has finalised the POC industry contingency plan based on feedback from the Contingency Planning Working (CPWG)
  The industry contingency plan has been incorporated into the POC Market Readiness Strategy, with a new version circulated to the Readiness Working Group for broader feedback

## Slide 8: Power of Choice Risk / Issue log updates

## Slide 9: Risk & Issue Update
Refer to attachment
Issues:
I03: Confirm Meter Bridging Approach for Non Vic Jurisdictions
  Proposed to close
I04: assessment being conducted via PCF Action 15.
I05: Treated as meter fault process. DB to bypass & notify FRMP. Propose to close
Other issues by AGL
AGL to detail
Refer to attachment 4.1 AGL raised issues
Additional Risk raised by Momentum
Momentum to discuss
Refer to attachment 4.2 Momentum raised risk

## Slide 10: Power of Choice Other Business

## Slide 11: AEMO Other Business
Availability of Pre-Production for bi-lateral testing
AEMO draft plan – to be confirmed by 27 October:
SMP/MSATS Pre-prod availability |  |  | 
Date | Outage Start | Outage End | Description
9th Oct to 13th Oct | - | - | AEMO performance and load testing - may cause intermittent outages or delays
12th Oct | 10am | 3pm | MSATS maintenance
12th Oct | 5pm | 7pm | Defect release for Market trials - Cycle 3
19th Oct | 5pm | 7pm | Place holder for defect release
26th Oct | 5pm | 7pm | Place holder for defect release
16th Oct to 3rd Nov | - | - | Market trials - Cycle 3
6th Nov to 10th Nov | - | - | AEMO performance and load testing - may cause intermittent outages or delays
9th Nov | 5pm | 7pm | Place holder for defect release
13th Nov to 17th Nov | TBC | TBC | Times to be confirmed - Likely Dress Rehearsal with Batch Handler outages
16th Nov | 5pm | 7pm | Place holder for final pre-prod release

## Slide 12: AEMO Other Business
Commonwealth / Jurisdictional Safety Regs
Next Metering Safety Forum scheduled for Wednesday 18th October
Agenda includes:
  Remote re-en & de-en – Proposal
  Proposal from CMIG in relation to an Industry Code - Proposal
  Tenancy Laws – Discussion
  NSW ASP scheme changes – NSW discuss amendments
  Meter access arrangements – Jurisdictional update
Victoria deferral of metering competition
AMI Obligations Order was made Tue 10 Oct. Published in Special Gazette S342. Can be accessed here or visit www.gazette.vic.gov.au.
Expect remaining NEVA Orders to be published by Special Gazette 12 Oct.
NSW Preparation for Competition in Metering
Held consultation session on Monday 9 October.
Consultation period extended until Wednesday 25 October

## Slide 13: Power of Choice Program Schedule

## Slide 14
2015 |  |  |  |  |  |  | 2016 |  |  |  |  |  |  |  |  |  |  |  | 2017 |  |  |  |  |  |  |  |  |  |  |  | 2018 | 
JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
Today
Power of Choice (PoC) Program Overview
High Level Program V6.7 – 13 Oct 2017
For Information: poc@aemo.com.au
26 Nov
MC
Final Determination
17 Dec
EN Final Determination
MRP Draft Determination
10 Mar
MRP
Final Determination
1 Sep
EN & MC & MRP
Procedures Published
1 Mar
MC
Registration & EN MSL and Accreditation Documentation Published
1 Dec
EN & MC & MRP & B2B
Effective Date (Go-Live)
DNSPs & Retailers to publish amended standard contracts
EN = Embedded Network, MRP = Meter Replacement Processes
MC = Metering Competition, SMP = Shared Market Protocols
Oct
SMP Advice published
EN/MC/MRP WP 1 Procedure Consultation
EN/MC/MRP Package 2 Development
EN/MC/MRP WP 2
Procedure Consultation
For detailed meeting schedule and agendas, see the 2016 industry meeting schedule.
Package 3 ‘As Built’ Development
WP 3 & ‘As built’ Procedure Consultation
MC /
EN /
MRP
30 Jun
SMP Final Determination
1 Aug
IEC Election Procedures Finalised
MC B2B Recommendation
1 Sep
IEC Election Complete - IEC Formed
1 May
B2B – IEC recommends B2B Procedures Finalised
07 Apr
SMP Draft Determination
1 Dec
MC & EN Ring fencing and network exemption guidelines
1 Sep
DNSPs to publish standard terms and conditions on which it will act as the initial Metering Coordinator
AEMO Requirements
SMP Conceptual IT Designs
SMP B2B Procedure Consultation
TRANS IEC
IEC Election
Election Procedures
& Operating Manual
Fee methodology *(if required)
1 Jun
B2B – AEMO publish B2B Procedures & Accreditation Process
Heightened Support
Procedures
Market Readiness
Supporting Activities
IT Systems
P
P
P
P
Market Readiness Strategy
Industry Training
Transition & Cut Over Planning
AEMO Design
All - IT Development / Internal Testing
Industry Testing
P
P
SMP Procedure Development
P
EN/MC/MRP Package 1 Development
MC Draft Procedures
P
Publish
B2B
Plan
Execute
Plan
Registration & Accreditation
Pre-Prod Release
Prod Release
P
P
P
AER - Electricity ring-fencing guideline 2016
Readiness Reporting Commences
Milestone
Working group meeting
Proposed IEC Meetings (Trans & New)
Program Milestones
10 Sep
MRP Direction paper published
EN Draft Determination
P
P
Industry Test Planning
Phase 1
Transition
Phase 2
Market Trial – Phase 3

## Slide 15
2016 |  |  |  |  |  |  |  |  |  |  |  | 2017 | 
JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
Today
Power of Choice (PoC) Program Overview – Readiness Work Stream
High Level Program V6.7 – 13 Oct 2017
For Information: poc@aemo.com.au
EN = Embedded Network, MRP = Meter Replacement Processes
MC = Metering Competition, SMP = Shared Market Protocols
For detailed meeting schedule and agendas, see the 2016 industry meeting schedule.
Industry Test Planning EN/MC
Phase 1 Execution EN/MC
Accreditation & Registration
Transition & Cutover
Transition Planning
P
Publish
Readiness reporting
Industry Testing
1 Dec
Go-live date
17 Nov
Industry Test Report
10 Apr
EN/MC changes in pre-production
06 Mar
B2B Procedures Published
28 Feb
WP2 Procedures Published
Industry Test Planning B2B/Market Trial
Phase 2 Execution B2B
Planning
Accreditation and Registration Period
Phase 3 Market Trial Execution
Transition
Heightened Support
2 Oct
Industry Transition & Cutover Plan Published
5 Jun
Industry Test Plan B2B Published
Readiness Reporting
5 Jun
10 Jul
7 Aug
11 Sep
9 Oct
6 Nov
4 Dec
8 May
3 Apr
6 Mar
8 Feb
16 Aug
Pre-Production system release
22 May
EN/MC patch release
Test Set-up
EN/MC
Cutover Planning
1 Sep
Draft Transition and cutover plan
29 Sep
Final Transition and cutover plan review
Outage Window
11 Aug
Submit entry Criteria checklist
21 Aug
Commence Phase 3 Market Trials
System Cutover
1 Mar
Qualification, registration & accreditation checklists published
24 Mar
Second draft plan published
28 Apr
Registration & Accreditation plan published
9 May
Participant Information Session
31 Oct
Confirmation of registration and accreditation status
14 Aug
Commence daily meetings
16 Aug
E-Hub Certification screens released
28 Jul
Market Trial workbook complete
Cycle 1
Cycle 2
Cycle 3
Contingency Planning

## Slide 16: Power of Choice Milestones
Deliverable / Milestone | Project / Stream | Description | Planned date | Expected date | Status
Phase 1 Test Execution Complete | Industry Testing |  | 30 Jun 17 |  | 
Phase 3 Market Trial Workbook Published | Industry Testing |  | 28 Jul 17 |  | 
Phase 2 Test Execution Complete | Industry Testing |  | 28 Jul 17 |  | 
Transition planning workshops conclude | Trans & Cut Over |  | 08 Aug 17 |  | 
Market Trial daily meetings commence | Industry Testing |  | 14 Aug 17 |  | 
AEMO releases updates systems into pre-production | Systems |  | 16 Aug 17 |  | 
E-Hub Certification screens released | Readiness |  | 21 Aug 17 |  | 
Phase 3 Market Trial cycle 1 commences | Industry Testing |  | 21 Aug 17 |  | 
Transition and cutover plan draft released | Trans & Cut Over |  | 01 Sep 17 |  | 
DNSPs publish T&C’s on which it will act as the initial MC | DNSPs |  | 01 Sep 17 |  | 
Phase 3 Market Trial cycle 1 concludes | Industry Testing |  | 08 Sep 17 |  | 
Phase 3 Market Trial cycle 2 commences | Industry Testing |  | 18 Sep 17 |  | 
Transition and cutover plan published | Trans & Cut Over |  | 02 Oct 17 |  | 
Phase 3 Market Trial cycle 2 concludes | Industry Testing |  | 06 Oct 17 |  | 
Phase 3 Market Trial cycle 3 commences | Industry Testing |  | 16 Oct 17 |  | 
Registration & accreditation confirmation status | Readiness |  | 31 Oct 17 |  | 
Phase 3 Market Trial cycle 3 concludes | Industry Testing |  | 03 Nov 17 |  | 
Transition activities commence | Trans & Cut Over |  | 13 Nov 17 |  | 
Phase 3 Market Trial Report released | Industry Testing |  | 17 Nov 17 |  | 
PoC Effective date | All | Allowance for weekend system cutover | 01 Dec 17 | 04 Dec 17 | 
Cutover Activities commence | Trans & Cut Over | COB Friday 1 Dec 17 | 01 Dec 17 |  | 
Cutover Activities conclude | Trans & Cut Over | OOB Monday 4 Dec 17 | 04 Dec 17 |  | 
Transition activities concludes | Trans & Cut Over |  | 08 Dec |  | 
Heightened Support Period | All |  | 02 Mar 18 | 30 Mar 18 | 
Notes: Intent to Publish

## Slide 17: PoC - Program Overview Version history
This table summarises the changes between the Program Overview as information changes or becomes available.
Version | Date | Amendments
4.3 | 02 Sep 16 | Updated B2B Procedure consultation with AEMO’s proposed dates (pending IEC approval)
4.4 | 10 Oct 16 | Updated terminology – added ‘6 month outlook’ for Procedure development / consultation processes Updated key dates in relation to AEMO WP2 Procedures and B2B Procedure development / consultation Included key dates identified in Readiness strategy
4.5 | 17 Nov 16 | Amended dates for Fee Methodology consultation Updated B2B Procedure Consultation dates
4.6 | 16 Dec 16 | Updated Tracking
4.7 | 21 Dec 16 | Updated Industry Testing and Transition and cut-over activities to commence earlier. Removed achieved milestones (Sep 15 – Nov 16)
4.8 | 25 Jan 17 | Updated Fee Methodology timetable in accordance with AEMO consultation
4.9 | 16 Feb 17 | Removed version control updates prior to 3.5 Removed Industry meeting dates from Program overview (refer to the industry calendar publishes on www.aemo.com.au) Included a draft Readiness overview slide
5.0 | 21 Mar 17 | Removed Procedures Work stream outlook. Updated ‘As Built’ package timeframes
5.1 | 6 Apr 17 | Updated Readiness Work Stream overview following RWG and ITWG (Apr 2017)
5.2 | 19 Apr 17 | Removed Industry Test Box and extended Market Trial Box
6.0 | 19 May 17 | Updated Tracking
6.1 | 26 May 17 | Updated Tracking
6.2 | 18 Jul 17 | Updates Tracking Update WP 3 / As Built consultation dates amended Updated Readiness work stream program overview
6.3 | 14 Aug 17 | Updated Tracking
6.4 | 24 Aug 17 | Updated Tracking
6.5 | 8 Sep 17 | Updated Tracking – Included Contingency planning activity
6.6 | 28 Sep 17 | Updated Tracking
6.7 | 13 Oct 17 | Updated Tracking

## Slide 18
Risk Register Review
See attached Risk Register

## Slide 19: Forward Meeting Plan
POC-PCF meeting dates | Dates
POC-PCF Meeting #13a | 13-Oct-17
POC-PCF Meeting #14 | 26-Oct-17
POC-PCF Meeting #14a | 08-Nov-17
POC-PCF Meeting #15 | 23-Nov-17
POC-PCF Meeting #15a | 08-Dec-17
POC-PCF Meeting #16 | 14-Dec-17
Facilities:
Melbourne, Sydney, Brisbane, Adelaide offices
Video conference
Webinar (when required)