## Slide 1: EXECUTIVE FORUM 8a Meeting pack
MEETING DATE: Tuesday 31 October 2017
TIME: 9.30 AM – 11.00 AM (AEST)
VENUE: AEMO OFFICES; MEL, SYD, ADE, BRI
TELECONFERENCE: DIAL IN: 1800 055 132 MEETING ID: 35928681
CONTACT: poc@aemo.com.au

## Slide 2: Agenda
Accreditation and Registration
Market Trial
Industry Transition and Cutover Plan
Communications Plan
Other Business

## Slide 3: ACCREDITATION & REGISTRATION
Accreditation and Registration:
Metering Coordinators (MC’s):
  Full MCs: 1 registration approved (Active Stream), 11 applications received.
  Initial MCs and Type 7: 7 registrations approved, 13 applications received.
  TNSP MCs: none approved, 4 applications received.
  All Generator MCs have been contacted by AEMO about the NER requirement for them to appoint or become registered as an MC.
  Embedded Network Managers (ENM’s)
  23 applications received, 1 approved.
  AEMO has contacted all Full MC and ENM applicants and requested their full applications by 31 October.
B2B e-Hub
    37 B2B e-Hub accreditations have been approved.
  Click here for a list of Full MC’s and ENM’s that submitted Oct 2017 Market Readiness Reports
  Click here for the NEM Registration and Exemption List

## Slide 4: MARKET TRIAL
    Phase three has been executed in 3 cycles:
      Cycle 1 - 21 August to 8 September (completed)
      Cycle 2 - 18 September to 6 October (completed)
      Cycle 3 - 16 October to 3 November (underway)
    Each cycle has had test cases split into 3 core categories
      Default MC – Day one scenarios designed to test day to day activities where the MC is the default LNSP using B2B r36.
      MC Churn – Tests designed to verify day to activity that results in a new meter and the appointment of an MC or day to day activities where the MC is not the LNSP using B2B r36.
      Base C&I – Test designed to confirm that day to day communications for the current contestable meters are able to be completed with the introduction of a new MC using B2B r36.
    Cycle 1 had x participants made up of 9 distributors, 8 retailers and 5 independent metering companies.
      167 Default MC – 129 completed, 6 failed and 32 moved to the next cycle
      78 MC Churn – 27 completed, 2 failed and 49 moved to the next cycle
      20 Base C&I - 8 completed, and 12 moved to the next cycle
    Workbook Status

## Slide 5: MARKET TRIAL
    Cycle 2 had x participants made up of 12 distributors, 15 retailers and 8 independent metering companies.
      340 Default MC – 105 completed, 26 failed and 209 not executed or completed
      337 MC Churn – 100 completed, 13 failed and 224 not executed or completed
      169 Base C&I - 75 completed, 6 failed and 88 not executed or completed
    Cycle 3 has x participants made up of 12 distributors, 22 retailers and 8 independent metering companies.
      225 Default MC – 18 completed, 15 failed and 192 in progress
      253 MC Churn – 23 completed, 7 failed and 223 in progress
      100 Base C&I – 21 currently completed, 4 failed and 75 in progress

## Slide 6: Industry transition & cutover plan
Version 1.1 of the Industry Transition & Cutover Plan was published 9 October 2017.
Industry Transition Period
Transition activities commence Wednesday, 1 November 2017 to Friday, 30 March 2018 inclusive. *(Staged Approach – New Connections and Ads/Alts concludes 30 Mar 2018).
Industry Cutover Period
The cutover period commences 5pm on Friday, 1 December 2017 to 11:59pm Sunday, 3 December 2017 (AEST) inclusive.
Industry Dress Rehearsal
Dress Rehearsal period commences Wednesday, 15 November 2017 and concludes Friday, 17 December 2017 (inclusive).

## Slide 7: Industry transition & cutover plan
Post Go-Live Heightened Support
Is from Monday, 4 December 2017 till Friday, 30th March 2018 inclusive.
Includes the use of existing AEMO support hub services.
Additional AEMO support includes;
Ongoing AEMO POC project SME support (Incl. technical transaction monitoring and facilitating resolution of system issues or defects experienced by either Participants or AEMO).
Daily phone conference scheduled each morning between Monday 4 December 2017 and Friday 15 December 2017.

## Slide 8: COMMUNICATIONS PLAN
AEMO has been working closely with representatives across the industry on a communications strategy.
Purpose: to communicate as an industry to parties affected by the changes:
  AEMO has prepared fact sheets for jurisdictions and industry to adapt for their use.
  AEMO has prepared frequently asked questions for jurisdictions and market participants to adapt for their use.

## Slide 9: OTHER BUSINESS
8.1 Tier 1 Retailer Top 10 Issues – Stephen Thomson - Spotless