## Slide 1: EXECUTIVE forum
DATE: 27 MARCH 2017
TIME: 2.00 PM – 3.30 PM (AEDT)
VENUE: AEMO OFFICES; MEL, SYD, ADE, BRI

## Slide 2: AEMO Program Update
General:
AEMO held a PCF on 23 March; AEMO to update on the VICAMI metering type watching brief – Verbal update
AEMO Board meeting early March to consider IEC’s recommended B2B Procedures
AEMO Procedures
AEMO published the WP2 final report and determination on 28th February 2017.
Held PWG meeting on 6 March – discussed upcoming ‘As Built’ consultation
B2B Procedures
B2B-WG will be considered amendments and final updates from IEC meeting.
B2B- Procedures published on 6 March
Systems
ASWG has approved the draft B2B related schema (R36) and this draft has been published on the AEMO website
The SWG Focus Group provided feedback to the SMP User Guide/Technical Guide on 15th March
An updated EN/MC MSATS Technical Specification was published on 14th March after review at the Market Systems User Group (MSUG)
Readiness:
Industry readiness reports for March are available on AEMO’s website - project status remains amber.
Participant Information Session held on 24 March – Work Package 2 Procedures and B2B Procedures.
Second drafts released for Industry Accreditation & Registration Plan, Industry Test Strategy, EN/MC Industry Test Plan and EN/MC Industry Test Workbook.

## Slide 3: AEMO Program Update – upcoming tasks
Program:
PCF next session will be 20 April 2017. AEMO to update on the VICAMI metering type watching brief.
AEMO Procedures (Work Package 3 “As built”):
AEMO will be releasing first stage of consultation for WP3 (As built) by 12th April 2017.
B2B Procedures:
B2B-WG will be considering any amendments and final updates from IEC meeting.
B2B-WG / IEC will determine a process for incorporating any updates to Procedures identified as a result of industry testing as part of an ‘As built’ consultation
Systems:
Development of a SMP Systems Guide for delivery to industry in early-March 2017. The SWG focus groups have started gathering member inputs to the guide before publishing to the wider audience.
AEMO continues to define and build market systems in preparation for Industry testing
Upcoming SWG focus meeting is scheduled for Wednesday 31st March with the next full SWG proposed for Friday 21st April
B2M EN & MC MSATS changes will be deployed into Pre-Production on 22nd March for industry testing, starting 10th April
Readiness:
Next Readiness Working Group (RWG) meeting will be 4 April.
Next Industry Testing Working Group (ITWG) meeting will be 5 April.
Next Participant Information Session will be 26 April to outline qualification, accreditation and registration processes.

## Slide 4
2015 |  |  |  |  |  |  | 2016 |  |  |  |  |  |  |  |  |  |  |  | 2017 |  |  |  |  |  |  |  |  |  |  |  | 2018 | 
JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
Today
Power of Choice (PoC) Program Overview
High Level Program V5.0 – 21 March 2017
For Information: poc@aemo.com.au
26 Nov
MC
Final Determination
17 Dec
EN Final Determination
MRP Draft Determination
10 Mar
MRP
Final Determination
1 Sep
EN & MC & MRP
Procedures Published
1 Mar
MC
Registration & EN MSL and Accreditation Documentation Published
1 Dec
EN & MC & MRP & B2B
Effective Date (Go-Live)
DNSPs & Retailers to publish amended standard contracts
EN = Embedded Network, MRP = Meter Replacement Processes
MC = Metering Competition, SMP = Shared Market Protocols
Oct
SMP Advice published
EN/MC/MRP WP 1 Procedure Consultation
EN/MC/MRP Package 2 Development
EN/MC/MRP WP 2
Procedure Consultation
For detailed meeting schedule and agendas, see the 2016 industry meeting schedule.
Package 3 ‘As Built’ Development
WP 3 & ‘As built’ Procedure Consultation (If required)
MC /
EN /
MRP
30 Jun
SMP Final Determination
1 Aug
IEC Election Procedures Finalised
MC B2B Recommendation
1 Sep
IEC Election Complete - IEC Formed
1 May
B2B – IEC recommends B2B Procedures Finalised
07 Apr
SMP Draft Determination
1 Dec
MC & EN Ring fencing and network exemption guidelines
1 Sep
DNSPs to publish standard terms and conditions on which it will act as the initial Metering Coordinator
AEMO Requirements
SMP Conceptual IT Designs
SMP B2B Procedure Consultation
TRANS IEC
IEC Election
Election Procedures
& Operating Manual
Fee methodology *(if required)
1 Jun
B2B – AEMO publish B2B Procedures & Accreditation Process
Heightened Support
Procedures
Market Readiness
Supporting Activities
IT Systems
P
P
P
P
Market Readiness Strategy
Industry Training
Transition & Cut Over Planning
AEMO Design
All - IT Development / Internal Testing
Industry Testing
P
P
SMP Procedure Development
P
EN/MC/MRP Package 1 Development
MC Draft Procedures
P
Publish
B2B
Plan
Execute
Plan
Registration & Accreditation
Pre-Prod Release
Prod Release
P
P
P
AER - Electricity ring-fencing guideline 2016
Readiness Reporting Commences
Milestone
Working group meeting
Proposed IEC Meetings (Trans & New)
Program Milestones
10 Sep
MRP Direction paper published
EN Draft Determination
P
P
Industry Test Planning
Industry Test Execution
Transition

## Slide 5
2016 |  |  |  |  |  |  |  |  |  |  |  | 2017 | 
JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
Today
Power of Choice (PoC) Program Overview – Readiness Work Stream
High Level Program V5.0 – 21 March 2017
For Information: poc@aemo.com.au
EN = Embedded Network, MRP = Meter Replacement Processes
MC = Metering Competition, SMP = Shared Market Protocols
For detailed meeting schedule and agendas, see the 2016 industry meeting schedule.
Industry Test Planning EN/MC
Test Execution EN/MC
Accreditation & Registration
Transition & Cutover
Transition & Cutover Planning
P
Publish
Readiness reporting
Industry Testing
1 Dec
Go-live date
Mid-Nov
Final Industry Test Report
10 Apr
EN/MC changes in pre-production
06 Mar
B2B Procedures Published
28 Feb
WP2 Procedures Published
Industry Test Planning B2B/Market Trial
Test Execution B2B
Connectivity/functionality testing
Planning
Accreditation and Registration Period
Industry
Testing
B2M/B2B
Market Trial Execution
Transition & Cutover
Post Go-Live
Heightened Support
2 Oct
Industry Transition & Cutover Plan Published
5 Jun
Industry Test Plan B2B Published
Readiness Reporting
5 Jun
10 Jul
7 Aug
11 Sep
9 Oct
6 Nov
4 Dec
8 May
3 Apr
6 Mar
8 Feb
Mid-Aug
B2B changes in pre-production
22 May
EN/MC patch release

## Slide 6: Power of Choice Milestones
Deliverable / Milestone | Project / Stream | Description | Planned date | Expected date | Status
AEMO concludes first stage consultation | B2B: All |  | 15 Nov 16 | 02 Dec 16 | 
AEMO commences consultation of Fee Methodology | All |  | Nov 16 | 03 Nov 16 | 
AER publishes ring fencing & network exemption guidelines | - |  | 01 Dec 16 |  | 
AEMO publish draft procedure determination | MC,EN,MRP |  | 13 Dec 16 |  | 
AEMO publish draft procedure determination | B2B: All | No later than 4 January 2017 | 13 Dec 16 | 23 Dec 16 | 
System implementation period commences | All |  | Mid Dec 16 |  | 
AEMO concludes Fee Methodology first stage consultation | All |  | 16 Dec 16 |  | 
AEMO concludes second stage consultation (WP 2) | MC,EN,MRP |  | 30 Dec 16 | 16 Jan 17 | 
AEMO concludes second stage consultation | B2B: All |  | 30 Dec 16 | 20 Jan 17 | 
IEC ‘recommends’ B2B Procedures to AEMO’s Board | B2B: All | TBC Preceding AEMO Feb Board | 22 Jan 17 | 20 Feb 17 | 
AEMO publishes Draft Fee Methodology | All |  | 06 Feb 17 | 23 Feb 17 | 
AEMO concludes second stage consultation Fee Methodology | All |  | 21 Feb 17 | 10 Mar 17 | 
AEMO publishes final procedure determination | MC,EN,MRP | Obligation is no later than 1 Mar 17 | 01 Mar 17 | 28 Feb 17 | 
AEMO publishes final procedure determination | B2B: All | Obligation is no later than 1 Jun 17 | 01 Mar 17 | 06 Mar 17 | 
Commencement of registration / accreditation activities | Readiness | To be determined in readiness strategy | 01 Mar 17 |  | 
AEMO Publishes Final Determination Fee Methodology | All |  | 31 Mar 17 | 21 Apr 17 | 
Industry testing period detailed planning commences | Readiness |  | Mar 17 | Mid-Feb 17 | 
Industry detailed cut-over and transition planning commences | Readiness |  | Apr 17 | Mid -Mar 17 | 
Industry testing and trial period commences | Readiness | To be determined in test plan | Aug 17 |  | 
DNSPs publish T&C’s on which it will act as the initial MC | MC |  | 1 Sep 17 |  | 
Industry Accreditation and Registration activities completed | Readiness |  | Oct 17 |  | 
Industry cut-over and transition plan completed | Readiness |  | Oct 17 |  | 
DNSPs publish distributor deemed standard connection contracts | MC |  | 1 Dec 17 |  | 
Retailers publish Elect & Gas standard retail contracts | MC |  | 1 Dec 17 |  | 
PoC Effective date | All |  | 1 Dec 17 |  | 
Notes: Intent to Publish

## Slide 7: B2B Procedures
B2B Procedures
Published final determination on 6 March
An as-built consultation for B2B Procedures with limited scope will open on 12 April and final determination will be published on 30 November
B2B WG to meet again on 30 March to discuss
  Scope statement for as-built consultation
  Process for logging issues and making changes to the B2B procedures
  Scenario modelling for complex metering installations
AEMO assessed the feasibility of providing a translation table or module for the B2B transactions
  This would allow participants to send Service Orders as they do today and AEMO would translate to the new schema
  AEMO have determined that while technically feasible – the implementation of the translation table will not be possible within the timeframe of 1 December 2017 as the translation module would need to utilise the same AEMO developers current working on or earmarked to work on design and build of the B2B e-hub, Testing environments and transition and cutover.

## Slide 8: Market readiness
Market Readiness
Industry Readiness Reporting – AEMO received 31 participant reports received for March. Market Readiness Reports can be found here Industry Readiness Reporting
Second draft of Industry Accreditation and Registration Plan circulated for industry review and discussion at 4 Apr RWG meeting.
Initial transition and cutover planning discussions to continue at RWG meeting.
Second drafts of Industry Testing Strategy and Industry Test Plan (EN/MC) circulated for industry review and discussion at 5 Apr ITWG meeting.

## Slide 9: Watching briefs
Treatment of Vic AMI meters
  Alterations to Market systems (Meter Type identification codes; ‘MRIM’ & ‘RWD’)
  Updates to substitution methodology ‘labels’ in data provision
  Requirement for VIC DBs to accredit against the MDP Type 4 with consideration to arrangements made under clause 11.86.7
  Other obligations: removal of NSRD
Vic Govt. Consultation on Competition in Metering
  Decision made: Option 4
  Detail to be worked through in a focus group
    Basic principle: in Victoria, the FRMP will be required to appoint the LNSP as the MC
  Potential alterations to Procedures & systems to accommodate outcomes