## Market Readiness Report Page 1
42891
AEMO Power of Choice Implementation Program
|  | Monthly Readiness Report | 2017-06-05
Overall Status |  | Commentary |  |  | Risk Rating |  | # Open Risks - Rating: |  |  | Issues:
|  | The overall project status remains amber - "at risk" of delivery by 1 December 2017 - primarily due to challenging program timeframes. Participants have highlighted challenging timeframes for system build and testing, registration and accreditation activities, and the number and complexity of commercial arrangements to be entered into. Highlighted risk areas include uncertainty associated with the Victorian Government deferral decision, faults and emergency processes, meter churn, jurisdiction safety regulations and transition approach. The overall project risk rating has been increased to High, with a number of participants noting that their timeframes have no tolerance for delays or requirement changes. |  |  |  |  | High | Med | Low | #
[7 empty] | 4 | 3 | 3 | 1
AEMO and NEM Participants Readiness Criteria |  |  | AEMO |  | Retailers |  | Distributors |  | MP and MDP |  | Metering Coordinator |  | Embedded Networks (ENM, ENO) |  | Third party e-hub
# | Category | Criterion | Status | Note | Status | Note | Status | Note | Status | Note | Status | Note | Status | Note | Status | Note
1. Assessment and preparation
1.1 | Assessment and preparation | Consequences of the POC reforms for your business considered, and appropriate implementation plans are in place | [7 empty] | #1 |  | #1
1.2 |  | Key readiness planning documents delivered
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | Updated retail electricity market procedures and associated documents published
2.2 |  | Internal policies updated for consistency with regulatory changes including jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Operationally critical commercial contracts in place |  |  |  | #2 |  |  |  | #2 |  | #2 |  | #2
2.4 |  | Accreditation and registration activities completed | [7 empty] | #3 |  | #3
3. People
3.1 | People | Operational roles specified, assigned to staff, and training delivered
4. Business processes
4.1 | Business processes | Updated, validated and approved business processes in place |  | #4 |  | #5
4.2 |  | Successfully validated critical business processes during industry testing
4.3 |  | Process work‑arounds in place for any issues identified during industry testing
5. Market systems
5.1 | Market systems | Delivery of the re-developed B2B e-hub for industry testing
5.2 |  | Successfully tested market systems capable of being moved into production |  |  |  | #6 |  | #6 |  | #6 |  | #6
5.3 |  | Performance of, and communication between, market systems validated during industry testing |  |  |  | #7 |  | #7 |  | #7 |  | #7
6. Transition planning
6.1 | Transition planning | Transition and cutover plan(s) in place | [5 empty] | #8 |  | #8 |  | #8
6.2 |  | Prerequisite transition and cutover processes completed (e.g. trial data conversions and cutover dress rehearsals) | [7 empty] | #8 |  | #8
Jurisdictional Status
Jurisdiction |  | Comments | AEMO |  | Retailers |  | Distributors |  | MP and MDP |  | Metering Coordinator |  | Embedded Networks (ENM, ENO) |  | Third party e-hub
|  |  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
ACT |  | Jurisdictional risk is a reflection of overall project risk.
NSW |  | Jurisdictional risk is a reflection of overall project risk.
QLD |  | Jurisdictional risk is a reflection of overall project risk.
SA |  | Jurisdictional risk is a reflection of overall project risk.
TAS |  | Jurisdictional risk is a reflection of overall project risk.
VIC |  | Jurisdictional risk is a reflection of overall project risk.

## HIDDEN 25% (hidden)
ü
| 100 | 75 | 50 | 25 | 0
| 0 | 25 | 50 | 75 | 100
WITHIN SCHEDULE | [5 empty] | Risks | Low
Medium
High
AT RISK
NOT WITHIN SCHEDULE

## Market Readiness Report Page 2
AEMO Power of Choice Implementation Program
Monthly Readiness Report
2017-06-05
Variances
Note # | Explanation of Variance |  |  | Mitigating Actions
1 | Variance reported by Participants: Development of detailed Implementation plans on schedule at risk (1) due to requirement to modify plans due to changes in systems development approach (due to aggressive timelines, system procurement issues), and (2) need to iterate plans when consultation outcomes (meter churn – package 3), VIC derogation extension details, faults and emergency processes and transition plans are finalised. |  |  | Participants are increasing internal resources and are developing contingency plans to get back on schedule. Participants are awaiting the Victorian government OIC. [AEMO notes that Package 3 consultation has commenced: http://www.aemo.com.au/Stakeholder-Consultation/Consultations/Power-Of-Choice---AEMO-Procedure-Changes-Package-3]
2 | Variance reported by Participants: Updating commercial arrangements on schedule is at risk due to volume and complexity of contracts that need to be entered into with industry parties. |  |  | Participants are increasing internal resources.
3 | Variance reported by Participants: Fulfilling registration and accreditation activities on schedule is at risk due compressed timeframes for all registration and accreditation activities. |  |  | Participants are increasing internal resources and commencing discussions with AEMO. [AEMO encourages early engagement with AEMO on registration and accreditation requirements - see POC Industry Accreditation & Registration Plan (http://www.aemo.com.au/Electricity/National-Electricity-Market-NEM/Power-of-Choice/Readiness-Work-Stream)]
4 | Variance report by AEMO: The POC platform service and support hub transition are being undertaken within a short timeframe. |  |  | Additional resources are being deployed to address the gap.
5 | Variance reported by Participants: Progress impacted by uncertainty in a number of areas including meter churn, faults and emergencies, jurisdictional requirements. Progress has been impacted by the Victorian Government deferral decision. |  |  | Participants are increasing internal resources, reviewing meter churn impacts under Package 3 and awaiting the Victorian govt. OIC.
6 | Variance reported by Participants: System development at risk due to the complexity and number of changes required within tight timeframes for development and testing. |  |  | Participants are increasing internal resources and working closely with market system vendors.
7 | Variance reported by Participants: Testing timelines are contingent on system design and build. |  |  | Participants are increasing internal resources and working closely with market system vendors.
8 | Variance reported by Participants: Increasing risk reported on transition and cutover planning and implications - timing of cutover, number of inflight transactions, scope of changes required. |  |  | Participants are engaging with the ITCFG. [http://www.aemo.com.au/Electricity/National-Electricity-Market-NEM/Power-of-Choice/Readiness-Work-Stream/Industry-Transition-Cutover-Focus-Group]
Notes
1. The count of open Risk and Issues is based on the POC Industry Risk Register as at 26/05/2017. A PCF Industry Risk Review Meeting is scheduled on 22/6/2017. 2. Explanation of Variance and Mitigating Actions above are based on Participants comments, AEMO's comments are included within square brackets [ ].
Key - Progress and Status | [5 empty] | Key - Risk Rating
Progress |  |  | Status
Harvey balls represent progress towards achieving the criterion |  |  | Colour indicates the readiness status |  |  | Rating
~0% |  | ~50% | Criterion is within agreed schedule and deliverable requirements |  |  | High
~10% |  | ~60% | Criterion is at risk of not meeting requirements and corrective action may be required |  |  | Medium
~20% |  | ~70% | Criterion not meeting requirements. Immediate corrective action required |  |  | Low
~30% |  | ~80% |  |  |  | See POC Industry Risk Register for open risks and issues:
~40% |  | ~90% | Criterion has been achieved |  | ü | POC Industry Register

## Retailer Reports
| 2017-06-05 |  |  | Retailer Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| ActewAGL Retail | Within schedule | Medium | ActewAGL Retail has completed a high level impact assessment of the changes required by PoC on its business operations and systems, requirements have been baselined, business processes in review and detailed system design is nearing completion. A detailed project plan is in place and being tracked against in order to achieve compliance by the "go live" date.
| AGL Retailer Powerdirect | At risk | Medium | AGL is participating in industry testing for EN/MC. Commercial activities are in progress. B2B build is progressing well and on track for market trials commencement in August. Adjusted overall project status to yellow due to commercials complexity and associated dependencies for build and system configuration. Issue raised to AEMO relating to cutover timing being during the week. Still awaiting government decisions for Vic market and varied processes for Victoria add to operational risk. | [7 empty] | Risk rating remains at medium due to the number of parties involved, limited build timeframes, impacts arising from the Victoria competition decision, updated schema timing dependencies, limited industry testing timeframes and significant commercial agreements that must be implemented.
| Alinta Energy | Within schedule | Medium | Project progressing to plan. Impact of Victorian Changes to be determined may impact delivered code and process Metering Partner engagement progressing, however there is no certainty around who will be ready at 1/12 | [7 empty] | Operating in the Queensland market before the end of the year
| Aurora Energy | At risk | Medium | Aurora Energy continues to manage a number of risks with regards to the implementation of the Power of Choice reforms by 1 December 2017. The most significant risk is the aggressive implementation timeline, reflected in Aurora Energy's 'at risk' project status. This risk is also impacting the ability of Aurora Energy's key vendors to meet POC timeframes. This includes, but is not limited to, a prospective Metering Coordinator, which will be required to establish advanced metering service capability in Tasmania where it currently does not exist.
| Energy Australia | At risk | Medium | The Program is making steady progress but we see siginficant risks associated wit: the Vic Government decision to delay PoC; the lack of progress on jurisdictional safety matters; tighness of industry testing schedule; and the progress of industry coordinated activities, such as industry-wide readiness, BCP and Emergency Planning. | [7 empty] | The Program is making steady progress but has risks associated the lack of progress on jurisdictional safety matters. There are also concerns with the progress of industry coordinated activities, such as industry-wide readiness, BCP and Emergency Planning. [VIC]: The Vic decision to delay PoC has a significant impact on B2B processes, which have not been addressed at an industry level. The resulting inconsistencies place a high level of risk on the project. | [5 empty] | Risks associated with industry coordinated activities still exist, such as BCP and Emergency Planning.
| Ergon Energy Queensland (retail) | At risk | Medium | The project risk rating has been maintained at 'medium' due to: - the number of changes required to our retail billing system - the level of complexity of some of these changes - the complexity and number of contracts that need to be negotiated with Initial MC / competitive MC - additional complexities and costs associated with delivering PoC metering changes in a regional setting with no effective competition At this stage no changes have been made to jurisdictional safety requirements which will enable remote re-energisation. This remains a risk that retailers will not achieve the full benefits without these changes. There has also as yet been no resolution of the inconsistencies / issues with Meterology Procedure Part A - Queensland jurisdictional provisions. This has been raised with AEMO and with the Queensland Department of Energy and Water Supply and must be addressed prior to 1 December 2017. | [7 empty] | The project risk rating has been maintained at 'medium' due to: - the number of changes required to our retail billing system - the level of complexity of some of these changes - the complexity and number of contracts that need to be negotiated with Initial MC / competitive MC - additional complexities and costs associated with delivering PoC metering changes in a regional setting where no effective competition At this stage no changes have been made to jurisdictional safety requirements which will enable remote re-energisation. This remains a risk that retailers will not achieve the full benefits without these changes. There has also as yet been no resolution of the inconsistencies / issues with Meterology Procedure Part A - Queensland jurisdictional provisions. This has been raised with AEMO and with the Queensland Department of Energy and Water Supply and must be addressed prior to 1 December 2017.
| ERM Power Retail | At risk | Medium | ERM Power Retail overall POC system and business process development continues to progress. POC Project Risk Rating remains at a 'Medium' level as: - although initial clarification of Victorian meter identification and functionality has been received, uncertainty of the Victorian Government OIC specifying specific details of the Victorian deferment from metering competition may still affect POC development in the short term; - uncertainty of individual distribution business management of Faults and Emergency situations (where a DB asset and/or a contestable asset is installed at a customer premise) is concerning from a customer outcome perspective and clarification is sought by AEMO without delay; - varying interpretations of the AEMO Information regarding Pack 3 and the subject of Meter Churn is concerning as this creates the potential for signifcant variation between commerical agreements with Service Providers which may result in unexpected, complex system design and implementation; - although progress in commercial discussions is occuring, given the number of negotiations and agreements that must be made with counterparties, ERM is now reporting 2.3 At Risk. In addition, as previously noted, the aggressive POC implementation, testing, MC Registration and eHub Accreditation timeframes additionally justify an overall project risk rating of Medium.
| M2 Energy Pty Ltd | Within schedule | Medium | [AEMO Note - Using 8 May Report for M2] Project Scoping by Vendor is 90% complete. Vic related changes are a substantial risk. Business intention is to outsource MC role. Risk considered Medium as few vendors currently available for selection. M2 Energy is maintaining dialogue with potential vendors. | [7 empty] | Vic withdrawl from POC has introduced risk into System Scoping, and increased training and change management requirements.
| Macquarie Bank Limited | Within schedule | Low
| Mojo Power Pty Ltd | Within schedule | Medium | [8 empty] | Treatment of VIC AMI by market. Mojo in application process to be a retailer in Victoria
| Momentum Energy | Within schedule | Low
| Origin Energy | At risk | Medium | Overall project delivery deadline at risk, due to constrained timelines for delivery against overall AEMO Delivery Timelines. During April the program reported Amber internally due to issues around Scope, Schedule and Cost. As of the 1st of May, these issues whee resolved and the program is currently reporting Amber. Project delivery progressing. High number of delivery risks continue to be monitored and mitigated for the duration of the project. Areas of concern include: Delivery • Uncertainty around the details of the VIC derogation extension may delay the delivery of the program (Origin has expressed concerns over proposed deviation from the overall B2B procedures); • Industry Faults and Emergencies process is still not defined (i.e.: R&R for Networks x Retailers x MPs and the comms method and hours of operations); • Meter type 4A E2E process not defined in the Industry - risk of inconsistent processes across participants is high; • Bulk Data conversion for Standing Data (MC/ENM role, Meter Type, NMI/Meter Register Status) across industry participants is still unclear and therefore impacting our planning and implementation of activities; participants updating own data may lead to substantial issues with integrity of information and risk of performance if all participants have to update MSATS at the same time during cutover; • Awaiting delivery from AEMO of a completed Testing Plan inc. Test Data requirements for Market Trial Testing . If a Production Test Data cut is not agreed and published in the next few weeks, the Testing activities of the program will be impacted. Additionally, Origin believes that Phase 3 Market Testing should be seen as a mandatory PoC milestone for all participants to ensure industry readiness is tested / verified. Cutover • Time frame for cutover is not practicable: Thursday night (30th Nov) / Friday morning (1st Dec) - I.e. significant disruption to BAU batch processes and Call centres operations is expected (i.e. we require approx. 20 hours for Cutover and Only 12 hours are available (assuming we shut down systems at 6pm and return to BAU at 6am) • Time frame for cutover coincides with: 1) peak period for numerous BAU teams (New Connections, C&I re-contracting); and 2) Natural Disaster season (bushfire, storm season, etc). Transition & Cutover planning must take this into account; • In-flight Transactions approach are still being developed and may lead to customer impacts & additional costs. The schema change may necessitate a cancel re-raise for open service orders; • There is no Back-out scenario for this implementation given this is an integrated delivery backed by change in legislation. The risk profile is extremely high given statuses of various participants; • AEMO needs to report on the overall readiness assessment. AEMO overall status shows Amber when virtually all participants are showing Amber / Red. This seems to suggest the aggregated risks may not be fully understood. Comms • Communications plan to affected parties (i.e. Electricians, Customers) is still not finalised; expectation that AEMO will lead on this activity. | [7 empty] | Overall project delivery deadline at risk, due to constrained timelines for delivery against overall AEMO Delivery Timelines. | [5 empty] | Areas of concern include: Delivery • Uncertainty around the details of the VIC derogation extension may delay the delivery of the program (Origin has expressed concerns over proposed deviation from the overall B2B procedures); • Industry Faults and Emergencies process is still not defined (i.e.: R&R for Networks x Retailers x MPs and the comms method and hours of operations); • Meter type 4A E2E process not defined in the Industry - risk of inconsistent processes across participants is high; • Bulk Data conversion for Standing Data (MC/ENM role, Meter Type, NMI/Meter Register Status) across industry participants is still unclear and therefore impacting our planning and implementation of activities; participants updating own data may lead to substantial issues with integrity of information and risk of performance if all participants have to update MSATS at the same time during cutover; • Awaiting delivery from AEMO of a completed Testing Plan inc. Test Data requirements for Market Trial Testing . If a Production Test Data cut is not agreed and published in the next few weeks, the Testing activities of the program will be impacted. Additionally, Origin believes that Phase 3 Market Testing should be seen as a mandatory PoC milestone for all participants to ensure industry readiness is tested / verified. Cutover • Time frame for cutover is not practicable: Thursday night (30th Nov) / Friday morning (1st Dec) - I.e. significant disruption to BAU batch processes and Call centres operations is expected (i.e. we require approx. 20 hours for Cutover and Only 12 hours are available (assuming we shut down systems at 6pm and return to BAU at 6am) • Time frame for cutover coincides with: 1) peak period for numerous BAU teams (New Connections, C&I re-contracting); and 2) Natural Disaster season (bushfire, storm season, etc). Transition & Cutover planning must take this into account; • In-flight Transactions approach are still being developed and may lead to customer impacts & additional costs. The schema change may necessitate a cancel re-raise for open service orders; • There is no Back-out scenario for this implementation given this is an integrated delivery backed by change in legislation. The risk profile is extremely high given statuses of various participants; • AEMO needs to report on the overall readiness assessment. AEMO overall status shows Amber when virtually all participants are showing Amber / Red. This seems to suggest the aggregated risks may not be fully understood. Comms • Communications plan to affected parties (i.e. Electricians, Customers) is still not finalised; expectation that AEMO will lead on this activity.
| Pacific Hydro | At risk | Medium | The timing and outcomes of the following outstanding PoC activities have the potential to impact the build, test and implementation phases: 1. MSATS - As Built Consultation 2. B2B - Translation tool technical details yet to be confirmed 3. Meter Churn Issues - recently raised and despite a paper being issued by AEMO, there are still concerns being raised. 4. Vic Government decision not to proceed with PoC. 5. Jurisdictional safety review of the remote Re-en/De-en process. There is also an issue with other Market changes, e.g. Retail Transfer Errors to take effect 3 August 2017, being introduced within the PoC delivery timeframe.
| People Energy | At risk | Medium | The overall project is at a medium risk. VIC withdrawl from POC has introduced risk into System Scoping, Process changes and increased training.
| Pooled Energy | Within schedule | Medium | Project remains on track. Continuing to work through procedural changes. | [7 empty] | Project remains on track. Continuing to work through procedural changes.
| Red Energy & Lumo Energy | At risk | High | Business and customer activity is very high at the targeted cut-over time. Inconsistent approaches across industry creates increased activity and raises risk (eg. new connections, meter churn, faults and emergencies, expected approaches to in-flight transactions). Victorian approach is understood but the detail and specifics is not yet known (Order in Council not released)
| Sumo Power |  |  | [AEMO Note - Only progress was provided on report - see details below]
| Simply Energy | Within schedule | Medium | The program has identified two keys risks: 1. Faults and Emergencies Process not confirmed by Distribution Businesses. 2. VIC Govt decision of deferral of metering competition has opened a few questions that's impacting our design and build, e.g. new connections process in VIC; Plan of approach for VICAMI meters post go-live (type 5 vs type 4 issue), etc.
| Stanwell Corporation Limited | Within schedule | Low | Project progressing as planned.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| ActewAGL Retail | Within schedule | Medium | Within schedule | Medium
| AGL Retailer Powerdirect | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Alinta Energy |  |  | Within schedule | Medium |  |  | Within schedule | Medium |  |  | Within schedule | Medium
| Aurora Energy | [8 empty] | At risk | Medium
| Energy Australia | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | High
| Ergon Energy Queensland (retail) |  |  |  |  | At risk | Medium
| ERM Power Retail | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| M2 Energy Pty Ltd |  |  | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| Macquarie Bank Limited | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Mojo Power Pty Ltd |  |  | Within schedule | Medium | Within schedule | Medium |  |  |  |  | Within schedule | Medium
| Momentum Energy | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Origin Energy | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Pacific Hydro |  |  | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| People Energy |  |  | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | At risk | Medium
| Pooled Energy |  |  | Within schedule | Medium
| Red Energy & Lumo Energy |  |  | At risk | High | At risk | High | At risk | High |  |  | Within schedule | High
Sumo Power
| Simply Energy | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Stanwell Corporation Limited | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  |  |  | Within schedule | Low
0
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | ActewAGL Retail | AGL Retailer Powerdirect | Alinta Energy | Aurora Energy | Energy Australia | Ergon Energy Queensland (retail) | ERM Power Retail | M2 Energy Pty Ltd | Macquarie Bank Limited | Mojo Power Pty Ltd | Momentum Energy | Origin Energy | Pacific Hydro | People Energy | Pooled Energy | Red Energy & Lumo Energy | Sumo Power | Simply Energy | Stanwell Corporation Limited | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Completed (100%) | Completed (100%) | 100% | 61% - 70% | 81% - 99% | 71% - 80% | Completed (100%) | 25% | Completed (100%) | 71% - 80% | 71% - 80% | 81% - 99% | Completed (100%) | 41% - 50% | 51% - 60% | 51% - 60% | 41% - 50% | 31% - 40% | Completed (100%)
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Completed (100%) | 1% - 10% | 75% | 31% - 40% | 71% - 80% | 61% - 70% | 31% - 40% | 25% | 81% - 99% | 21% - 30% | 61% - 70% | 61% - 70% | 51% - 60% | 21% - 30% | 31% - 40% | 11% - 20% | Not started (0%) | Completed (100%) | 61% - 70%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 51% - 60% | Completed (100%) | 50% | 41% - 50% | 71% - 80% | 71% - 80% | 31% - 40% | 25% | 81% - 99% | 61% - 70% | 41% - 50% | 41% - 50% | 51% - 60% | 21% - 30% | Not started (0%) | 81% - 99% | Not started (0%) |  | 71% - 80%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 11% - 20% | 1% - 10% | 25% | 21% - 30% | 51% - 60% | 41% - 50% | 1% - 10% | 0% | 81% - 99% | 61% - 70% | 21% - 30% | 21% - 30% | Not started (0%) | 1% - 10% | 21% - 30% | Not started (0%) | Not started (0%) | 31% - 40% | 1% - 10%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 21% - 30% | 21% - 30% | 25% | 21% - 30% | 41% - 50% | 11% - 20% | 11% - 20% | 0% | Not started (0%) | 61% - 70% | 1% - 10% | Not started (0%) | 1% - 10% | 1% - 10% | 1% - 10% |  | Not started (0%) | Not started (0%) | Not started (0%)
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 21% - 30% | Completed (100%) | N/A | 21% - 30% | 51% - 60% | 1% - 10% | 61% - 70% | 0% | 41% - 50% | 61% - 70% | 61% - 70% | 61% - 70% | 51% - 60% | 1% - 10% | 21% - 30% |  | N/A | Not started (0%) | Completed (100%)
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 11% - 20% | 1% - 10% | N/A | 1% - 10% | 1% - 10% | Not started (0%) | 1% - 10% | N/A | Not started (0%) | Not started (0%) | 41% - 50% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) |  | N/A |  | Not started (0%)
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 61% - 70% | 11% - 20% | 25% | 41% - 50% | 71% - 80% | 11% - 20% | 21% - 30% | 0% | N/A | Completed (100%) | 41% - 50% | 51% - 60% | 41% - 50% | 1% - 10% | 41% - 50% |  | Not started (0%) | 21% - 30% | 41% - 50%
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Not started (0%) | Not started (0%) | 25% | 41% - 50% | 41% - 50% | Not started (0%) | 41% - 50% | N/A | N/A | Completed (100%) | Not started (0%) | 21% - 30% | 41% - 50% | Not started (0%) | 21% - 30% |  | N/A | Not started (0%) | 41% - 50%
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Not started (0%) | Not started (0%) | 0% | 11% - 20% | 21% - 30% | 1% - 10% | 41% - 50% | 0% | Not started (0%) | 31% - 40% | 1% - 10% | 1% - 10% | Not started (0%) | Not started (0%) | 11% - 20% |  | Not started (0%) |  | Not started (0%)
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 81% - 99% | 71% - 80% | 0% | 61% - 70% | 71% - 80% | 51% - 60% | 21% - 30% | 25% | 81% - 99% | 31% - 40% | 21% - 30% | 71% - 80% | 31% - 40% | 11% - 20% | 31% - 40% | 31% - 40% | Not started (0%) | 1% - 10% | 61% - 70%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 71% - 80% | 41% - 50% | 0% | 31% - 40% | 61% - 70% | 31% - 40% | 21% - 30% | 0% | 71% - 80% | Not started (0%) | 11% - 20% | 21% - 30% | Not started (0%) | 1% - 10% | 11% - 20% | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%)
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | 1% - 10% | 0% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 71% - 80% | 61% - 70% | 75% | 61% - 70% | 81% - 99% | 61% - 70% | 41% - 50% | 50% | 71% - 80% | 31% - 40% | 41% - 50% | 71% - 80% | 51% - 60% | 41% - 50% | 1% - 10% | 31% - 40% | 61% - 70% |  | 81% - 99%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Not started (0%) | 51% - 60% | 75% | 11% - 20% | 41% - 50% | 1% - 10% | 41% - 50% | 25% | 41% - 50% | 11% - 20% | 31% - 40% | 21% - 30% | 11% - 20% | 11% - 20% | Not started (0%) | 21% - 30% | 11% - 20% | Not started (0%) | 51% - 60%
5.3 |  | The internal testing of market systems for your business | [5 empty] | Not started (0%) | 51% - 60% | 0% | 11% - 20% | 11% - 20% | Not started (0%) | Not started (0%) | 0% | 41% - 50% | Not started (0%) | 11% - 20% | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not started (0%) | 1% - 10% | 0% | 1% - 10% | 11% - 20% | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) |  | 1% - 10%
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Not started (0%) | 0% | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) |  | Not started (0%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Not started (0%) | 1% - 10% | 0% | 1% - 10% | 1% - 10% | Not started (0%) | 1% - 10% | 0% | 71% - 80% | Not started (0%) | 1% - 10% | 21% - 30% | Not started (0%) | 1% - 10% | Not started (0%) | 1% - 10% | Not started (0%) |  | Not started (0%)
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | Not started (0%) | 0% | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) |  | Not started (0%)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | ActewAGL Retail | AGL Retailer Powerdirect | Alinta Energy | Aurora Energy | Energy Australia | Ergon Energy Queensland (retail) | ERM Power Retail | M2 Energy Pty Ltd | Macquarie Bank Limited | Mojo Power Pty Ltd | Momentum Energy | Origin Energy | Pacific Hydro | People Energy | Pooled Energy | Red Energy & Lumo Energy | Sumo Power | Simply Energy | Stanwell Corporation Limited | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Completed | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Completed |  | Within schedule | At risk | Completed | Within schedule | Within schedule | At risk |  | At risk | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Completed | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule | Within schedule | At risk | Within schedule | At risk |  | Within schedule | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Completed | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk |  |  | Within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Not within schedule | At risk | Within schedule | Within schedule |  | Within schedule | At risk | At risk | At risk | Within schedule | N/A |  | Within schedule | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Completed | Within schedule | At risk | Within schedule | Within schedule | Within schedule | At risk | Within schedule |  | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | N/A |  | Within schedule | Completed
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | N/A | Within schedule |  | Within schedule | At risk | Within schedule | Within schedule | Within schedule | N/A |  |  | Within schedule
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | N/A |  | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | N/A |  | At risk | Within schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | N/A | N/A |  | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | N/A |  | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | At risk | Within schedule | Within schedule | Within schedule | N/A |  |  | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | At risk | Within schedule | Within schedule | At risk | At risk | At risk | At risk | Within schedule | Within schedule |  | Within schedule | At risk | Within schedule | At risk | Within schedule | At risk |  | Within schedule | Within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | At risk | Within schedule | Within schedule |  | Within schedule | Within schedule | At risk | At risk | Within schedule | At risk |  | Within schedule | Within schedule
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule |  | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | At risk | Within schedule | At risk | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule | At risk | At risk | Within schedule | At risk |  |  | Within schedule
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule | At risk | At risk | Within schedule | At risk |  | Within schedule | Within schedule
5.3 |  | The internal testing of market systems for your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule |  |  | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule |  |  | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule |  |  | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | N/A | Within schedule | Within schedule | Within schedule | Within schedule |  |  | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | ActewAGL Retail | AGL Retailer Powerdirect | Alinta Energy | Aurora Energy | Energy Australia | Ergon Energy Queensland (retail) | ERM Power Retail | M2 Energy Pty Ltd | Macquarie Bank Limited | Mojo Power Pty Ltd | Momentum Energy | Origin Energy | Pacific Hydro | People Energy | Pooled Energy | Red Energy & Lumo Energy | Sumo Power | Simply Energy | Stanwell Corporation Limited | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | High level impact assessment has been conducted. |  |  | A high-level assessment of necessary business operational process and systems changes is near completion. | Vic delay may require re-assessment. | [6 empty] | Impact Assessment completed, but will need to be iterated pending consultation outcomes and changes. Procedure and meter type implication due to VIC derogation extension are not yet clear. Faults and Emergencies process not yet finalised | [5 empty] | Meter Churn (Package 3) is causing some issues in finalising high level agreements.
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Program established, Detailed plan in place and being tracked against. |  | .In Progress .Victorian impact not yet avaiable .RFI for metering services is progressing | Detailed requirements have been gathered and vendors engaged to deliver the changes to market messaging. Additional changes to enable all other core operations post 1 December 2017 are being assessed. The aggressive timelines for systems build and testing, combined with contracting and establishment of an MC and the required implementation and testing combined systems is the basis of the 'at risk' status. | Progress has been impacted by the Victorian decision. | Significant changes required to internal systems and processes because of the mangitude of the changes to the final procudures has increased the scope and complexity of the project. Also reliant on contracted parties being ready from go-live date.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | The ACT Government is reviewing the ACT regulatory framework |  |  | A detailed assessment of the revised legal and regulatory is significantly developed. In its current form the detailed assessment has provided the basis of Aurora Energy preparedness to date. The assessment continues to be informed by on-going AEMO market procedure consultation although remaining uncertainty over rule and procedure operations ensures this is still considered 'at risk'. | At risk as there are still unknowns in regards to jurisdictional safety requirements. | Queensland jurisdictional safety requirements are yet to be addressed. There has also as yet been no resolution of the inconsistencies / issues with Meterology Procedure Part A - Queensland jurisdictional provisions |  | scheduled and commenced. |  |  |  | Detailed implementation schedule and program resourcing drafted and aligned to AEMO delivery milestones and timelines |  |  |  | Await Victoria Order in Council and assessment of any potential changes required for Victoria
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [7 empty] | Commenced | Preliminary advice has been sought with regards to regulatory compliance. A key challenge for Aurora Energy is to consider the wider/indirect regulatory implications of metering competition on business-as-usual activities (particularly given the existing regulatory framework was developed in the context of type 6 metering). | Red due to the lack of clarity on safety regulations | Queensland jurisdictional safety requirements are yet to be addressed. There has also as yet been no resolution of the inconsistencies / issues with Meterology Procedure Part A - Queensland jurisdictional provisions. This has been raised with AEMO and with the Queensland Department of Energy and Water Supply and must be addressed prior to 1 December 2017. |  | not yet scheduled. |  |  |  | Policy changes/decisions still being derived through Blueprinting | Vic Government decision on PoC and timing of regulatory changes to reflect the decision not to proceed with PoC.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Contracts and commercial arrangements are being reviewed. | Flagging risk due to the number of commercial agreements required. | Commenced. RFP/Services Agreemnt being developed Review of Customer contracts underway | Activity has commenced for customers and vendors as part of POC implementation. The major challenge is to develop and execute contractual arrangements with a Metering Coordinator, which will have to establish metering service capability in Tasmania where it currently does not exist. |  | These processes have commenced. Significant complexity due to lack of precedent in negotiating agreements of this nature. Contracts not progressing as planned. |  | not yet scheduled. |  |  |  | Overall strategy has been developed and endorsed. Generic Meter provider contract drafted for new providers and contracts in play for current providers. | Requirements/services for various Service Providers yet to be finalised. |  |  | Internal management of this item
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Assessment and planning has commenced. |  | Contractual arrangements to support Accreditation requirements through a nominated MC. | Aurora Energy will be required to receive accreditation for using the B2B e-hub. The newly published B2B E-Hub Accreditation and Revocation process is currently being considered. The timeline and uncertainty for accreditation and registration activities of other participants (specifically, the Metering Coordinator role) also impacts on Aurora Energy's planning. Dialogue with the jurisdictional safety regulator has commenced. |  |  |  | unclear testing registration requirements and impacts at this time. |  |  |  | Underway for new Market Roles |  |  |  | Internal management of this item
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Accrediatation materials review and application submitted. |  |  | Fulfilment of the accreditation obligations is now being considered following AEMO publishing final version of the 'B2B Accreditation and Revocation Process'. | [7 empty] | Planning and preparation in progress |  |  |  | Internal management of this item
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Detailed assessment in progress |  | Operating model development underway | This has commenced and will be finalised following with the detailed assessment of operational and systems changes. |  |  |  | not yet scheduled. |  |  |  | Detailed implementation schedule and program resourcing drafted and aligned to AEMO delivery milestones and timelines |  |  |  | Internal management of this item |  | VIC decision has posed some risk in detailing internal processes; Faults and Emergencies process is not confirmed by the Distribution businesses, posing a bigger risk on retailers to implement end to end process.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [7 empty] | Operating model development underway | The recruitment of specialist human resources to cater for the rule change has commenced. | [7 empty] | Policy changes/decisions identified | PoC Lead Role commenced |  |  | Internal management of this item |  | Due to commence in July 2017
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [8 empty] | Training requirements are currently being assessed as part of the business process, change management and system planning. |  | Training Needs Analysis underway |  | not yet scheduled. |  |  |  | Training requirements and resourcing determined and magnitude of change is understood, change planning started |  |  |  | Internal management of this item
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Awaiting on advice of Fault processes from DB's. Review of Meter Churn impacts from AEMO clarification on 12/5. |  | Continuing | All impacted service order, B2B & B2M and business processes have been identified. Assessment of current and future processes is underway to enable gap analysis and identify process and system changes. Possible future changes puts the delivery scope and timeline at risk. | Lack of consistency in the Victorian processes puts this at risk | The significance of the changes to our billing system and the added complexity of developing a mechanism to address non-PoC areas not subject to the provisions in Chapter 7 of the NER (isolated networks) is challenging in the timeframes. EEQ is also reliant on contracted parties being ready for go-live. Additional complexities and time constraints also as a result of negotiating ring fencing strategy / waivers with the AER which is also impacting contract negotiations. |  | commenced and in schedule |  |  |  | Detailed implementation schedule and program resourcing drafted and aligned to AEMO delivery milestones and timelines. VIC derogation extension not yet clear. Faults and Emergencies process not yet finalised; | [5 empty] | Solution Design workshops have commenced with vendors, functional specs underway
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Key processes have been drafted for CATS and B2B processes and are in review. |  | Continuing | Future business processes are currently being developed using the details from Work Package 1 and 2, as well as the B2B procedures. The timeline for implementation and on-going procedural uncertainty is the basis for Aurora Energy reporting 'at risk'. | As above | [6 empty] | Detailed implementation schedule and program resourcing drafted and aligned to AEMO delivery milestones and timelines. VIC derogation extension not yet clear. Faults and Emergencies process not yet finalised; Engagement with networks is planned to confirm smooth transition. | Pending outcome of availability of B2B Translation Tool. This is further complicated by the Vic Government decision not to proceed with PoC. |  |  |  |  | Scheduled to commence in July 2017
4.3 |  | The validation of business processes during industry testing | [8 empty] | Activity has not yet started. |  |  |  | not yet scheduled. |  |  |  | Test planning commenced, detail on industry testing as yet unclear | [5 empty] | Scheduled to commence in August 2017
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Detailed design in progress. |  | Vendor is looking for final arrangements out of the victorian derrogation and meter classification to finalise requirements and design documents | Detailed requirements have been gathered and vendors engaged to deliver the changes to market messaging systems. The aggressive timeframe impacts on the ability of Aurora Energy's key vendors (including, but not limited to, prospective Metering Coordinators) to deliver the required system changes. | Progress has been impacted by the Victorian decision. | Blueprinting complete. Significant complexity and number of changes to systems is creating challenges in the timeframes. Progress on development of designs slightly behind schedule. |  | Vendor at 47% completion of overall project plan |  |  | System development is reliant on external vendor, delays in final market procedures will impact readiness activities | Detailed impact assessment of system changes has completed. Review of updated B2B procedures in progress. VIC derogation extension impact assessment ongoing. Schema version considered for B2B will be R36 and B2M will be R35. Transaction Acknowledgment to match the version of the request | Pending outcome of availability of B2B Translation Tool. This is further complicated by the Vic Government decision not to proceed with PoC.
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | Underway, refer above. | Aurora Energy has engaged its key market system vendors. System build has commenced for essential market connectivity and system functionality for 1 December 2017. Further priority system functionality is in design phase. Systems changes will still be impacted by the any further changes to the B2B/B2M environment as part of Work Package 3. | There are risks associated with the compressed timeline. |  |  | vendor at 15% of retail sys build plan |  |  |  | Systems development in progress | Business Requirements Specification documents have been finalised. As per 5.1
5.3 |  | The internal testing of market systems for your business | [8 empty] | Aurora Energy has completed a test strategy, on-boarded test resources is in the process of preparing test cases. | At risk, due to tight build and testing timelines to meet Dec 1st. | [6 empty] | Test resources onboarded and test planning started | As per 5.2
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [8 empty] | Aurora Energy was unable to participate in AEMO's first round of testing due to no other participants being available. eHub connectivity will be tested in Phase 1 of AEMO's market interface testing. While Aurora Energy is currently on schedule to meet the timing of AEMO's market system testing opportunities, it is reliant on both key system vendors and other participants to perform testing and therefore continues to consider this to be 'at risk'. | Dependency on AEMO Industry Test Plans and schedules. | [6 empty] | Test resources onboarded and test planning started | As per 5.2
5.5 |  | The validation of performance of market systems during industry testing | [8 empty] | Aurora Energy is separately planning to perform performance testing, as distinct from market interface testing, scheduled for October 2017. Aurora Energy is reliant on key system vendors to perform performance testing and therefore continues to consider this to be 'at risk' | AEMO Industry Test Strategy calls performance testing out of scope. AEMO has indicated it will complete performance testing internally and will not provided outcomes to Participants. | [6 empty] | Test resources onboarded and test planning started | As per 5.2
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [7 empty] | Commenced | A Transition Plan will be completed once AEMO packages and commercial agreements with Metering Coordinator(s) are finalised. Aurora Energy has started discussions with TasNetworks regarding transition and cutover planning. | Transition and Cutover plans are progressing, however AEMO's scope of work is less than has been previously indicated. Significant residual risks still exist. | [6 empty] | Time frame for cutover coincides with: 1) peak period for numerous BAU teams (New Connections, C&I re-contracting); and 2) Natural Disaster season (bushfire, cyclone, etc.). Transition & Cutover planning will take this into account.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [8 empty] | Aurora Energy has started discussions with TasNetworks regarding transition and cutover planning. | [7 empty] | Transition planning and scheduling cannot be accurately determined until Design & Build is completed. Bulk Data conversion for Meter Standing Data (MC/ENM role, NMI/Meter Register Status) across industry participants is still unknown and therefore impacting our Build / Test activities; AEMO's position to leave to participants to update data may lead to substantial issues with integrity of information and risk of performance if all participants have to update MSATS at the same time during cutover;
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | ActewAGL Retail | AGL Retailer Powerdirect | Alinta Energy | Aurora Energy | Energy Australia | Ergon Energy Queensland (retail) | ERM Power Retail | M2 Energy Pty Ltd | Macquarie Bank Limited | Mojo Power Pty Ltd | Momentum Energy | Origin Energy | Pacific Hydro | People Energy | Pooled Energy | Red Energy & Lumo Energy | Sumo Power | Simply Energy | Stanwell Corporation Limited | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [8 empty] | Aurora Energy has implemented a program of work to interpret and implement the POC reforms, within the context of the timeframe and procedural uncertainty. | [7 empty] | Progressing with working assumptions. | [5 empty] | Package 3 scope should hopefully resolve the issues raised by the industry, however we're awaiting for the outcome.
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [8 empty] | Aurora Energy has implemented a program of work to effectively and efficiently work towards market compliance.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [8 empty] | Aurora Energy has implemented a program of work to interpret and implement the POC reforms that factors in the challenging timeframe and procedural uncertainty. |  | Ongoing discussions with the Department of Energy and Water Supply and engagement with the Electrical Safety Office. Lack of jursidictional changes represents a risk to EEQ.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [8 empty] | Aurora Energy is liaising with the Tasmanian Government to identify jurisdictional requirements that require amendment to facilitate metering competition. |  | Ongoing discussions with the Department of Energy and Water Supply and engagement with the Electrical Safety Office. Lack of jursidictional changes represents a risk to EEQ. | [6 empty] | Closely monitor Vic Government's progress on this matter.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [6 empty] | Escalated and added resource to commercial preparations. |  |  |  | Ensure contingencies are in place. | [5 empty] | Origin has onboarded additional Business and Technology resources
2.4 |  | An assessment of the required accreditation and registration activities | [8 empty] | Aurora Energy is proceeding on the assumption that accreditation will be received. |  | Awaiting AEMO publication of retailer e-hub requirements
2.5 |  | The fulfilment of accreditation and registration obligations | [16 empty] | Origin has onboarded additional Business and Technology resources
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [22 empty] | Awaiting VIC Order of Council; Distribution businesses to provide their positions as soon as possible especially around the faults and emergencies processes.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [8 empty] | Aurora Energy continues to invest considerable effort in participating in AEMO procedural consultation. Aurora Energy is proceeding on the basis of the currently available information and must continue to manage the risk of final procedures changing. |  | Increasing internal resources to the project.
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [8 empty] | Aurora Energy is in the process of gathering detailed business and system requirements and engaging with key vendors. |  | Increasing internal resources to the project. | [6 empty] | Engaging with other small retailers and AEMO directly. Closely monitoring Vic Government's progress on the regulatory changes.
5.2 |  | The development and build of appropriate market systems for your business | [8 empty] | Aurora Energy continutes to proactively manage its key market system vendors. | [8 empty] | As per the comment in 5.1 and engaging with our vendor to finalise/agree known changes.
5.3 |  | The internal testing of market systems for your business | [17 empty] | As per 5.2
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [17 empty] | As per 5.2
5.5 |  | The validation of performance of market systems during industry testing | [17 empty] | As per 5.2
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [16 empty] | Transition & Cutover planning will take this into account.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Retailer Participation
References:
[5 empty] | AEMO | http://www.aemo.com.au/Electricity/National-Electricity-Market-NEM/Participant-information/Current-participants/Current-registration-and-exemption-lists
[5 empty] | AER | https://www.aer.gov.au/retail-markets/authorisations/public-register-of-authorised-retailers-and-authorisation-applications
[5 empty] | ESC | http://www.esc.vic.gov.au/project/energy/2075-licensing/
Retailer | On Jun 2017 Report? | On May 2017 Report? | On April 2017 Report? | On March 2017 Report?
1st Energy Pty Ltd | No | No | No | No
ActewAGL Retail | Yes | Yes | Yes | Yes
AGL | Yes | Yes | Yes | Yes
Alinta Energy | Yes | Yes | Yes | Yes
Aurora Energy | Yes | Yes | Yes | Yes
Blue NRG Pty Ltd | No | No | No | No
Click Energy Pty Ltd | No | No | No | No
Covau Pty Limited | No | No | No | No
COzero Energy Retail Pty Ltd | No | No | No | No
Diamond Energy Pty Ltd | No | No | No | No
Energy Locals Pty Ltd | No | No | No | No
EnergyAustralia | Yes | Yes | Yes | Yes
Enova Energy Pty Ltd | No | No | No | No
Ergon Energy Queensland (retail) | Yes | Yes | Yes (using March report) | Yes
ERM Power Retail Pty Ltd | Yes | Yes | No | No
Globird Energy Pty Ltd | No | No | No | No
Lumo Energy (reporting with Red Energy) | Yes | Yes | Yes | Yes
M2 Energy Pty Ltd | Yes (using May report) | Yes | Yes | Yes
Macquarie Bank Limited | Yes | No | No | No
Mojo Power Pty Ltd | Yes | Yes | Yes | Yes
Momentum Energy | Yes | Yes | Yes | Yes
Next Business Energy Pty Ltd | No | No | No | No
Online Power and Gas Pty Ltd | No | No | No | No
Onsite Energy Solutions Pty Ltd | No | No | No | No
Origin Energy | Yes | Yes | Yes | Yes
Pacific Hydro | Yes | Yes | Yes | Yes
People Energy Pty Ltd | Yes | Yes | Yes | Yes
Pooled Energy Pty Ltd | Yes | Yes | Yes | No
Powerdirect Pty Ltd (reporting with AGL) | Yes | No | No | No
Powershop Australia Pty Limited | No | Yes (using April report) | Yes | No
Progressive Green Pty Ltd | No | No | No | No
Qenergy Limited | No | No | No | No
Red Energy | Yes | Yes | Yes | Yes
Sanctuary Energy Pty Ltd | No | No | No | No
Simply Energy | Yes | Yes | Yes | Yes
SparQ Pty Ltd (Sumo Power) | Yes | No | No | No
Stanwell Corporation Limited (Stanwell Energy) | Yes | Yes | Yes | No
WINenergy Pty Ltd (WINenergy) | No | No | No | No

## Distributor Reports
| 2017-06-05 |  |  | Distributor Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| ActewAGL Distribution (AAD) | Within schedule | Medium | [AEMO Note - Using 8 May Report for AAD] AAD has received it's first set of code drops (2 of 17) and is currently testing these releases. Business process review continues with approximately 15% of all business process changes complete and an additional 20% underway. Total project progress is estimated at 17%. | [7 empty] | [Initial MC Risk Rating Low]: AAD has reviewed the registration process to become the initial MC and is currently preparing material for submission to AEMO. Further work is being undertaken to assess the B2B eHub accreditation requirements. | [5 empty] | Accreditation transfer and registration starting 2 March is a risk area and it is noted that AEMO will still be developing systems and processes at the time industry is requested to start this process. AAD received the registration information for initial MC requirements and is currently assessing these requirements. Moreover, the B2B eHub requirements have (at the time of writing) not been fully released and further revisions are being received from AEMO. The readiness of AAD to interface with the AEMO B2B eHub is a significant risk. In the absence of information, the system changes required to facilitate this new data flow is undefined. It is noted AEMO have 12 mths to develop this and Industry only have 3.5 mths to implement. There is a disparate timeframe for Industry to modify, test, put into production and this is noted as a major area of concern for AAD.
| Ausgrid | At risk | Medium | We have established a number of formal ICT projects and assigned resources. A number of significant IT rebuilds are required in order to facilitate the new B2B, CATS and new minimum specification requirements. New interfaces for the customer are under development to assist our customers in operating in the POC space
| AusNet Services | At risk | High | Project in progress. The overall risk rating is a consequence of; 1. Schedule and Scope risk is significant 2. Maturity of strategies for Industry Testing as well as industry cutover and transition. 2. Market System readiness dates not confirmed, including the dates associated with EVM changes. | [7 empty] | The scope of changes to be delivered are greater than anticipated and delivery timeframes are highly compressed. Unable to assess ability to align with Industry Testing and Market Transition phases as strategies for these activities have not been finalised.
| CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | At risk | High | CitiPower/Powercor is continuing to progress its build/test phase and is participating in Phase 1 industry testing. CitiPower/Powercor is also actively participating in industry planning for market trials and 1 December 2017 industry transition and cutover. Following the finalisation of market procedures and business requirements, a re-estimation of effort to complete system changes has identified significantly greater development is required than originally forecasted. A program review is being undertaken in conjunction with our primary vendor to uplift our development and testing velocity to ensure readiness for market trials and achieve a 1 December 2017 go-live compliance. Program timing is challenging with no tolerance for delays or further requirement changes. | [7 empty] | The Victorian Government has decided that distributors will be required to continue to install remotely read interval metering after 1 December 2017 compliant with the Victorian AMI functionality and service levels specifications and that existing and new/replacement AMI metering will be continue to be classified as Type 5 metering. In line with this decision, CitiPower and Powercor will not making any changes to the how we classify either existing or new/replacement AMI meters in MSATS, nor any changes to our meter data validation and/or substitution methodologies. Victorian deferral arrangements are yet to be finalised in Government Orders.
| Endeavour Energy | At risk | Medium | A project risk is the implementation of system and procedural changes to comply with the B2B procedures. The B2B procedures requires significant system and process changes, however there is only 6-7 months to design and develop and to test with the market to achieve accreditation. This short timeframe increases the risk on quality vendor delivery. It is noted that registration as a B2B e-Hub Participants is required before the B2B e-Hub can be used. This registration process is also at risk as there is a dependency to demonstrate system compliance with the B2B procedures. AEMO facilitated a workshop on the meter churn process for participants to highlight issues and more efficient process options. AEMO later clarified that there will be no changes to the procedures for the meter churn process. In addition the MSATS procedure does not allow the existing MP or MDP to object where there is only a change in the MC. This puts Enedeavour Energy in a position where we have no choice but to provide MP and MDP services when a contestable MC is appointed to a NMI. This means that Enedeavour Energy, through no fault of its own, may be noncomplaint with the rules and the ringfencing guideline. The final determination for the "as built" consultation for AEMO procedures will not be published until 30 November 2017 which leaves no time to implement any changes for market start on 1 December 2017. To mitigate this we are actively participating in the various working groups including the PoC-WG, B2BWG, ITWG, RWG and SWG to ensure that AEMO procedures and B2B procedures supports the metering contestability and embedded networks rule changes in the most effective and cost efficient manner, and to only include transactions and obligations required for go live as a priority. We intend to seek clarification from the AER about our obligations with regards to the meter churn process. | [7 empty] | [See project comment] | [5 empty] | This report is for Endeavour Energy as at 30 May 2017. Endeavour Energy will be operating as a LNSP, and as the initial MC, MP and MDP for type 5, 6 & 7 metering installations from 1 December 2017. Endeavour Energy have implemented a project team to manage the impacts of Power of Choice. The activities for the Market Systems testing and cutover are dependent on the development and build of the appropriate market system which is currently at risk.
| Energex Ltd. & Ergon Energy Corporation Ltd. | At risk | Medium | The Distribution project remains slightly behind its planned schedule, however it is recoverable and will meet compliance requirements on 1 December 17. The project is taking a phased implementation approach. Key focus for the project remains on confirming the assumptions with retailers and MC's on mutual interpretation of the B2B procedures. Joint coordination across multiple parties remains a contentious issue which requires mutual agreement to safely ensure continuity of service to the customer. The project is in build and test phase and is progressing the system integration testing of high priorty transactions in priority order. | [7 empty] | The magnitude of change in the final version of the B2B Procedures was larger than expected. The project is currently 'At risk'. It is therefore undertaking a phased implementation approach. Focusing on high priority transactions with manual workarounds for low priority transactions remaining a possibility at go live if build and test does not progress as planned in the compressed timelines.
| Essential Energy | At risk | High | Essential Energy's PoC program is progressing, with system changes on the critical path to deliver compliance by 1 December 2017. Timing is very tight deliver required systems changes to enable Essential Energy to participate in B2B industry testing from August 2017, with no tolerance for delays. Essential Energy is working closely with vendors to ensure required systems are delivered on time with internal testing completed in readiness for industry testing. Additional resources have been assigned to assist in supporting program delivery. | [7 empty] | [Distributor]: Risk rating upgraded to high due risks associated with systems delivery in preparation for industry testing from August 2017. Program schedule is tight and does not provide tolerance for any delays. [Meter Data Provider]: Risk rating is classified as moderate for systems changes to support amended B2B framework, including to receive and process meter exchange information to enable timely publishing of final readings for Type 5 & 6 meters. | [5 empty] | Essential Energy will be an Initial MC, MDP and MP for Type 5 and 6 meter installations connected as at 1 December 2017. Essential Energy is actively participating in AEMO industry groups and NSW jurisdictional workshops associated with Power of Choice.
| Jemena Electricity Networks | Within schedule | Medium | With 6 months to go-live on 1 December 2017, the project is rated at MEDIUM risk this report due to the proposed go-live date of 1 December 2017 at a Financial Month End period prior to the Financial & Regulatory Year End period, and during a period of high volumes for Customer new connections, adds and alts pre-Christmas. | [7 empty] | With 6 months to go-live on 1 December 2017, the project is rated at MEDIUM risk this report due to the proposed go-live date of 1 December 2017 at a Financial Month End period prior to the Financial & Regulatory Year End period, and during a period of high volumes for Customer new connections, adds and alts pre-Christmas.
| SA Power Networks | At risk | Medium | SAPN working towards ensuring minimum market compliance will be met. SAPN are facing significant challenges due to the limited market timeframes, this is impacting the development and build phase of our internal system, which will result in delays to our final state internal business capability. | [7 empty] | Refer to overall project status and Section 5.2
| TasNetworks | At risk | Medium | TasNetworks' market systems build has commenced and current schedule will allow TasNetworks to participate in industry towards the latter part of AEMO's proposed testing window. System build timelines will be challenging to meet. Business and change management activities within schedule.
| United Energy | At risk | Medium | Internal preparations continue to progress well. The amber status reflects the impact of the Vic. Govt. deferral decision, which necessitated revisions to designs and put pressure on the critical path (from which the project has nearly recovered). Risk rating reflects the pending finalisation of the changed Vic Govt Orders and general concerns about industry readiness. | [7 empty] | UE operates in Victoria only. Jurisdictional status reflects overall position. Vic deferral details are yet to be formalised via changed Govt orders. | [5 empty] | Key concerns regarding UE (and industry) readiness are as follows: 1) The Victorian Government has advised that 1: UE's role as MC for new meters after 1 Dec will be on the basis of existing regulated services, 2: New meters after 1 Dec will need to meet only the Vic AMI specifications and 3: New meters after 1 Dec will be classified as Type 5 MRIM, per current practice, and existing meters will remain Type 5 MRIM. On 5 June, the Vic Govt issued an 'AMI Order amendments outline document', which describes the specific changes and the Orders to which they apply. UE is assessing this material for any unexpected impacts and will provide feedback accordingly. Until the amended Orders are finalised, the possibility of unexpected requirements or obligations remains. 2) UE compliance with the ENM rules and ring-fencing is dependent on Embedded Network Managers being accredited, assigned and ready to operate by 1 Dec 2017. UE's compliance in this area may also be dependent on existing child metering services being transitioned to meter providers on or by 1 Dec 2017, although this is yet to be confirmed. If transition is required, it will be an activity over which UE does not have full control, particularly given there are currently no accredited Embedded Network Managers in the market. 3) UE is concerned that the lateness of procedures finalisation and the Victorian deferral details, plus the complexity and scale of testing with the increased number of market participants may ultimately lead to negative impacts on consumers. Strong focus will be required to ensure that connections and supply processes are clear, and industry has a uniform, efficient and reliable approach so the reform is seamless to customers.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| ActewAGL Distribution (AAD) | Within schedule | Medium
| Ausgrid |  |  | At risk | Medium
| AusNet Services | [10 empty] | At risk | High
| CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | [10 empty] | At risk | High
| Endeavour Energy |  |  | At risk | Medium
| Energex Ltd. & Ergon Energy Corporation Ltd. |  |  |  |  | At risk | Medium
| Essential Energy |  |  | At risk | High
| Jemena Electricity Networks | [10 empty] | Within schedule | Medium
| SA Power Networks | [6 empty] | At risk | Medium
| TasNetworks | [8 empty] | At risk | Medium
| United Energy | [10 empty] | At risk | Medium
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | SA Power Networks | TasNetworks | United Energy
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Completed (100%) | 81% - 99% | Completed (100%) | Completed (100%) | 81% - 99% | 61% - 70% | Completed (100%) | Completed (100%) | Completed (100%) | 81% - 99% | Completed (100%)
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 51% - 60% | 81% - 99% | 41% - 50% | Completed (100%) | 71% - 80% | 81% - 99% | 51% - 60% | Completed (100%) | 81% - 99% | 51% - 60% | Completed (100%)
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 51% - 60% | 81% - 99% | 71% - 80% | Completed (100%) | 61% - 70% | 51% - 60% | Completed (100%) | Completed (100%) | 81% - 99% | 31% - 40% | 81% - 99%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 41% - 50% | 21% - 30% | 41% - 50% | 31% - 40% | 41% - 50% | 11% - 20% | 11% - 20% | 81% - 99% | 31% - 40% | 21% - 30% | 81% - 99%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 31% - 40% | 11% - 20% | 21% - 30% | 51% - 60% | 51% - 60% | 21% - 30% | 11% - 20% | 41% - 50% | 21% - 30% | 11% - 20% | 51% - 60%
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 51% - 60% | 81% - 99% | 31% - 40% | 41% - 50% | Completed (100%) | 71% - 80% | Completed (100%) | Completed (100%) | 21% - 30% | 51% - 60% | 71% - 80%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 41% - 50% | 1% - 10% | 1% - 10% | Not started (0%) | 21% - 30% | 51% - 60% | 21% - 30% | 61% - 70% | 1% - 10% | 21% - 30% | 1% - 10%
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 21% - 30% | 51% - 60% | 71% - 80% | Not started (0%) | 71% - 80% | 31% - 40% | 11% - 20% | Completed (100%) | 31% - 40% | 21% - 30% | Completed (100%)
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 11% - 20% | 31% - 40% | 21% - 30% | Not started (0%) | 51% - 60% | 1% - 10% | Not started (0%) | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%)
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | 11% - 20% | 21% - 30% | 11% - 20% | Not started (0%) | 21% - 30% | 11% - 20% | Not started (0%) | 31% - 40% | 1% - 10% | 1% - 10% | 21% - 30%
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 31% - 40% | 51% - 60% | Completed (100%) | 81% - 99% | 71% - 80% | 41% - 50% | 31% - 40% | Completed (100%) | Completed (100%) | 41% - 50% | Completed (100%)
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 31% - 40% | 11% - 20% | 31% - 40% | 61% - 70% | 31% - 40% | 11% - 20% | Not started (0%) | 51% - 60% | 81% - 99% | 1% - 10% | Completed (100%)
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 51% - 60% | Completed (100%) | 81% - 99% | 61% - 70% | 71% - 80% | 51% - 60% | 21% - 30% | Completed (100%) | 41% - 50% | 81% - 99% | Completed (100%)
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 21% - 30% | 11% - 20% | 31% - 40% | 31% - 40% | 1% - 10% | 21% - 30% | 11% - 20% | Completed (100%) | 21% - 30% | 21% - 30% | 81% - 99%
5.3 |  | The internal testing of market systems for your business | [5 empty] | 1% - 10% | Not started (0%) | 11% - 20% | 31% - 40% | Not started (0%) | 11% - 20% | 1% - 10% | 51% - 60% | 21% - 30% | 1% - 10% | 41% - 50%
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not started (0%) | Not started (0%) | 1% - 10% | 1% - 10% | Not started (0%) | 11% - 20% | Not started (0%) | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%)
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 21% - 30% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 1% - 10% | 1% - 10% | 1% - 10% | 1% - 10% | 1% - 10% | 21% - 30% | 1% - 10% | 31% - 40% | 11% - 20% | 1% - 10% | 1% - 10%
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 11% - 20% | Not started (0%) | 1% - 10% | Not started (0%) | 1% - 10% | 1% - 10%
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | SA Power Networks | TasNetworks | United Energy
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | Completed | Completed | Within schedule | At risk | Completed | Completed | Completed | Within schedule | Completed
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule | At risk | Completed | Within schedule | Within schedule | At risk | Completed | Within schedule | Within schedule | Completed
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Completed | Completed | Within schedule | Within schedule | At risk
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | At risk
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Completed | Within schedule | Within schedule | At risk
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Completed
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Completed | Within schedule | Completed
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Completed
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | At risk | Completed | Within schedule | Within schedule | At risk | At risk | At risk | Completed | Within schedule | Within schedule | Completed
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | At risk | At risk | At risk | At risk | At risk | At risk | At risk | Within schedule | At risk | At risk | At risk
5.3 |  | The internal testing of market systems for your business | [5 empty] | At risk | Within schedule | Within schedule | At risk | Within schedule | At risk | At risk | Within schedule | Within schedule | At risk | At risk
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | N/A | Within schedule | At risk | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | At risk | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | SA Power Networks | TasNetworks | United Energy
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | The high level impact assessment is complete. Some gaps may be identified as part of the more detailed program of works to be carried out in the period through to December 2017. | Finalising a number of MC requirements |  |  |  | High-level scope and requirements documents have been signed off by the business. The organisational impact assessment is due for review by the business within the next month. This is slightly behind schedule. |  |  |  | TasNetworks has updated impact assessment for Pack 2 and B2B. Further updates pending Pack 3.
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | AAD is commencing testing on the first round of system changes which will be subject to further review depending on changes to requirements issued by AEMO in future. Business processes and procedures are also undergoing review with all work practices and supporting documentation for two major branches currently underway. | Working with ITCFG to understand impacts before completing planning | Implementation plans for internal systems established and in progress. Development of Industry implementation and market transition plans required to validate internal scope/approach. |  |  |  | Agile delivery methodology has recently been implemented for system changes required to support Power of Choice. This has delayed the finalisation of implementation planning, with amendments required to support the new delivery methodology. |  | Continuous monitoring of established plans | Further planning required for business process and change management.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | A high level assessment of the legal obligations will continue throughout the project as AEMO finalises the program requirements. | Final reviews in place |  |  |  | Ongoing activity - currently under review by organisational specialists. |  |  | Monitor of changes from WP3 for impacts and changes | Still working through AEMO guidelines and jurisdictional safety requirements. | The Vic Govt. has advised that: 1: UE's role as MC for new meters after 1st of Dec will be on the basis of existing regulated services 2: New meters after 1 Dec will need to meet only the Vic AMI specifications. 3: New meters after 1 Dec will be classified as Type 5 MRIM, per current practice, and existing meters will remain Type 5 MRIM. This advice has reduced the risks of not meeting all 1 Dec obligations.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | During the period February - April 2017 AAD has commenced work on legal agreements relating to customer contracts, initial MC agreements with retailers, terms and conditions for provision of data/information to customers, etc. This work will continue until approximately September. | In progress. Will not be finalised until design and early prototypes of user systems are available. |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | While this activity has commenced. The Project is behind schedule in confirming the assumptions with retails and MC's on mutual interpretation of the B2B procedures. Joint coordination across multiple parties remains a contentious issue which requires mutual agreement to ensure continuity of service to the customer. These assumptions are required to be finalised to confirm this documentation and build. |  |  | In progress |  | This work is complete, but is based on the outcomes expected in the Vic Govt Order-in-Council. If these differ from the positions presented to date, rework will be required which may impact readiness.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | As above. | In progress. With Legal team. This is a significant logistical effort to negotiate agrements with each propsective party. |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | Ongoing activity - amendments under consideration by each contract owner, updates will be made using existing procurement and contractual processes. Assessment of new agreements/contracts also ongoing. |  |  | In progress | DNSP T&C's | Plans are in place to address the commercial implications, and resourcing is now in place. Work on the Initial MC Contract (required by 1 Sep) is well progressed. Assuming the Vic Govt Order-in-Council reflects the advice received to date, no other major commercial preparations are required.
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | AAD has reviewed the requirements to register as an initial MC and is preparing the required materials for submission to AEMO. B2B eHub requirements are now being assessed in line with material recently released by AEMO. | In hand. |  | Note: Following the state government decision to defer the introduction of metering competion in Victoria, CitiPower and Powercor will need to further assess our accrediation and registrations requirements. |  | The project is clear on the accreditation activities required to be completed and is well progressed with these obligations. |  |  | In progress |  | Based on Vic Govt advice that existing and new meters are to remain Type 5 MRIM, it is assumed that accreditation as a Type 4 MDP is not required for UE. Once this is confirmed via the Vic Govt Order amendments, this work item will be marked as complete. Accreditation for use of e-Hub is required and preparations are underway.
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | As above. | Letter of intentions provided. Application in draft. ABS acknowledges that a significant effort is required to produce all required procedures in a timely manner. |  | Note: In line with CitiPower/Powercor program delivery schedule. | See above comment | The project is clear on the accreditation activities required to be completed and is well progressed with these obligations. |  |  | In progress |  | Accreditation for use of e-Hub will be completed in accordance with AEMO requirements. The "at risk" flag reflects the remaining uncertainty about accreditation as a Type 4 MDP (which UE is assuming is not required).
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | AAD is recruiting additional resources to back fill operational roles in anticipation of future testing requirements commencing late June 2017. In addition, a detailed assessment of ongoing operational resource requirements has commenced to ready the business for the transition and post PoC go-live activities. | Awaiting outcome of update policies and work instructions to complete. |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | Ongoing activity - currently analysing the human resources impact due to POC implementation. This activity is due for completion by late June. |  |  | In progress
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | AAD is currently recruiting additional people to fulfil the operational duties affected by project specific activities. Other recruitment requirements are being assessed as above. | Relies on the above. |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | An Organisational Impact Assessment is in progress to determine POC recruitment and HR requirements to fulfil operational functions. |  | Not required - out of scope. | No major change from previous status |  | Not required until late 2017
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Identification of training requriements has begun, however, development of this training is yet to commence as it is dependent on other changes (processes, systems, etc.) that are currently underway. | Relies on the above. |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | The Training approach is progressing to plan. |  |  | No major change from previous status | Training Strategy developed | Development of training strategy and training needs analysis for all business units is complete in all but one process area, and is on track. Training delivery will commence in late October 2017.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Detailed reviews of AAD documentation has begun and resourcing for the changes has been completed. AAD is now in the process of carrying out the required reviews, consultation, workshops, etc. required to design and implement the required changes. | In concert with the changes ot policies, priocedures and work instructions. |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | Ongoing activity - currently documenting current and future state processes through development of detailed requirements. Progress on this is less than expected due to required rework, due to the nature of the final B2B Procedure Changes. |  |  | Completed (April 2017) | Core business processes drafted and under review. | Amendments arising from Vic deferral have been completed.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | As above. | In concert with the changes ot policies, priocedures and work instructions. |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | Ongoing activity - currently documenting current and future state processes through development of detailed requirements. Progress on this is less than expected due to required rework, due to the nature of the final B2B Procedure Changes. |  |  | In line with SAPN program delivery schedule |  | Amendments arising from Vic deferral have been completed. Minor updates are expected to be required as integration testing and industry testing progress.
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not yet begun. | Not expected to start until mid-August 2017/ | Subject to finalisation of market procedures & Industry Testing approach. | Note: In line with CitiPower/Powercor program delivery schedule. |  | Test approach is ongoing. The Scope of August industry testing remains unclear. Confirming the scope of industry testing as soon as possible would enable businesses to effectively meet the industry testing date. |  |  | Not started; In line with SAPN delivery schedule |  | Plans are in place to execute industry testing. However the current draft of B2B procedures includes the movement of currently enforceable details into a non-binding "guidance" category. The industry considers some of these details to be necessary for uniform, reliable end-to-end processing in the market. UE remains concerned that varying interpretations and inconsistencies between industry participants will become apparent during industry testing and may threaten its progress.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Final requirements have been received and are being incorporated into the design and development elements of system changes. | System impacts have been assessed in detail. The overall solution design is complete. |  | Note: In line with CitiPower/Powercor program delivery schedule. | See above comment | All requirement specifications are completed. The project is progressing design documentation and build in priority order. Where the highest volume transactions and critical functions have the higest priority. The project is planning for a phased implementation approach. With compliance to be achieved 1 December, and more efficient compliance to be achieved post 1 December. | Agile delivery approach now being applied to system changes, this will extend the timeframe for development of requirements and design for implementation. |  | No major change from previous status |  | Based on Vic Govt advice that existing and new meters are to remain Type 5 MRIM, all solution impacts have been assessed.
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | The first round of system changes entered test in March but will be subject review and possible change depending on further AEMO updates. Further code drops are scheduled from April through June. | The implementation phase is underway. Detailed designs continue to be prepared. Build activities have commenced. Final build estimates will be prepared as the designs complete. | Build process underway. Impact of changes required to support option selected by Vic' Gov't in progress. Awaiting release date for Updated EVM (B2B Validation Module); design and build has now passed internal dependency date of end May. Assessing impact to industry testing timelines. | Note: Program revision of critical path delivery for system changes currently in progress. | See above comment | The build and test phase is progressing. There is very little contingency remaining in the build schedule. Key Risk: changes in retailer / MC assumptions of the interpretation of the B2B procedures may impact the build schedule. | Agile delivery approach now being applied to system changes, with sprints being delivered over a 3 week period. |  | Prioritising internal system development/ build requirements to ensure market compliance. Extended work required post 1 December. | Design activity almost complete and build activity underway. Systems build and testing timelines continue to be challenging. | Based on Vic Govt advice that existing and new meters are to remain Type 5 MRIM, solution development is nearing completion (with the exception of management reporting, which is not time critical). The "at risk" rating reflects the rework required following the Victorian deferral. Solution development is expected to complete by 12 June to allow commencement of Integration Testing.
5.3 |  | The internal testing of market systems for your business | [5 empty] | Testing is underway on the first 2 of 17 code drops received in March 2017. | Not at the stage of testing market systems. |  | Note: Refer above. |  | Test approach is tracking to schedule. Testing timelines are becoming increasingly compressed and therefore 'At risk'. | Agile delivery approach now being applied to system changes, with sprints being delivered every 3 weeks for internal testing. |  | No major change from previous status | Test Strategy complete. Test planning activities underway. | System testing is progressing well but at risk for 12 June completion. Integration testing is expected to commence on 12 June, and if this is achieved, status will be Green.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not yet begun. | Not at the stage of testing market systems. | Timeframe for Industry Testing is very short given complexity, scope and number of participants | Note: In line with CitiPower/Powercor program delivery schedule. |  | On Track to commence Business to Market Industry testing 19th June |  |  | No major change from previous status | TasNetworks to participate in industry towards the latter part of AEMO's proposed testing window | Plans in place and resourcing agreed. Not yet due.
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not yet begun. | Not at the stage of testing market systems. | Market Test Strategy and approach required. Final specifications of hub required. Role of non-functional testing as part of Industry Testing is required. | Note: In line with CitiPower/Powercor program delivery schedule. |  | The Test approach is signed off. The deployment approach will be further progressed on completion of the AEMO transition and cutover working group workshops. |  | Per the industry test plan - this is out of scope. | Monitor of changes from WP3 for impacts and changes | TasNetworks to participate in industry towards the latter part of AEMO's proposed testing window | Plans in place and resourcing agreed. Not yet due.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | AAD is awaiting further information from AEMO relating to focus groups related to this topic. | Working with ITCFG to understand impacts before completing planning | Industry approach has not been defined, therefore ability to meet schedule is unclear. | Note: In line with AEMO schedule of released documentation and CitiPower/Powercor program delivery schedule. |  | The AEMO transition and cutover workshops are very effective. Significant progress has now been made in this area. However, please see the mitigant. |  |  | Phase 1 Industry testing in progress | Commenced planning to understand scope and magnitude of cutover for TasNetworks. This activity is expected to require detailed planning and dedicated resources to manage. Uncertainty at industry level of cutover timeframes and workload. | Early preparation work is underway.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | As above. | Not yet due. | Industry approach has not been defined, therefore ability to meet schedule is unclear. | Note: In line with AEMO schedule of released documentation and CitiPower/Powercor program delivery schedule. |  | Transition planning is on track. With the Go Live Decision making framework going to the Steerco this month. |  |  | In line with SAPN delivery schedule | Commenced data migration strategy and other preliminary planning activities. Preliminary assessment indicates cutover timeframes will exceed a day cutover window. | Early preparation work is underway.
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | SA Power Networks | TasNetworks | United Energy
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | AAD has established risk, issue and decision registers to track and mitigate gaps that are identified as progress is made. | Dedicated resource working on MC engagement and application |  |  |  | Additonal resources are being added to this piece of wrok.
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | AAD is continuing final design and development activities based on information received to date. The degree to which re-work will be required due to changes in final AEMO documentation will be determined in the weeks immediately following release of said documentation. | Member on ITCFG |  |  |  |  | Working closely with systems vendor to update plans aligned with Agile development approach. Additional resources assigned to assist with supporting program outcomes.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [7 empty] | Continued participation in Vic' Gov't Stakeholders Forum | [7 empty] | UE continues to urge prompt finalisation of the changed Vic Govt Orders to ensure that no unexpected requirements or obligations are introduced. On 5 June, the Vic Govt issued an 'AMI Order amendments outline document', which describes the specific changes and the Orders to which they apply. UE is assessing for any unexpected impacts and will provide feedback accordingly.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [15 empty] | As above.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [15 empty] | UE continues to proceed based on Vic Govt advice that DB-provided metering will remain a regulated service. It is also assumed that the current Victorian policy blocking customer opt-out will remain in place.
2.4 |  | An assessment of the required accreditation and registration activities | [15 empty] | As noted above, UE continues to urge prompt finalisation of the changed Vic Govt Orders so that accreditation requirements can be confirmed.
2.5 |  | The fulfilment of accreditation and registration obligations | [9 empty] | See above comment | [5 empty] | As above.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Requirements for additional testers and a business analyst has begun to mitigate risks associated with testing and delivery.
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [9 empty] | See above comment | The Project is reviewing several mitigation strategies; significantly a phased implementation approach. | Prioritised development work associated with industry testing, to deliver early in the sprint releases. Working closely with vendor and business to ensure sprints are delivered on time.
5.2 |  | The development and build of appropriate market systems for your business | [6 empty] | All available resources have been assigned to the design & development tasks. | Communicated dependency on EVM via the SWG, awaiting confirmed delivery date from AEMO |  | See above comment | The Project has implemented a phased implementation approach. | Prioritised development work associated with industry testing, to deliver early in the sprint releases. Working closely with vendor and business to ensure sprints are delivered on time. |  |  |  | Additional resources and weekend work are in place to ensure that the remaining development and system testing work is completed by 12 June, in readiness for integration testing.
5.3 |  | The internal testing of market systems for your business | [11 empty] | Allocated additiona business resources to support Agile testing approach. SME's will work closely with vendor to begin testing as early in process as possible to minimise potential errors. |  |  |  | As above.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [6 empty] | Member on ITCFG |  |  |  | Our organisation continues to urge AEMO to provide a transform capability as usual to mitigate go live risk.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## MP and MDP Reports
| 2017-06-05 |  |  | Metering Provider (MP) and Metering Data Provider (MDP) Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Active Stream | Within schedule | Low | The element of risk is elevating with the delay and/or deferral of the following items: - Package 3 - as built : delayed with inclusive items which need urgent clarification rather than been incorporated in a 6mth consultation process. i.e. Meter Churn, CR6300/800 etc. - Clear communicated date of when the DB's treatment plan on how the Faults and Emergencies will be handled on site and subsequent Market communication of activities undertaken, will be available. | [13 empty] | Active Stream is currently accredited and operating as a Type 4 MDP and MPB/MPC. Systems and processes are currently in place, requiring AS to assess and deliver the delta to comply with the POC requirements. Our approach with the Progress and Traffic Light Status is related to POC specific amendments.
| Acumen Metering | At risk | Medium | Overall project delivery status at risk, due to constrained timelines for delivery for system build and testing coupled with registration and accreditation activities. Clarity and agreement on transition and cutover activities is required, which will determine the impacts (system, process & people). Amber status is maintained due to tight timeframes and project resourcing challenges. Key risk mitigation will be implemented for the duration of the project.
| Ausgrid Business Services | At risk | Medium | We have established a number of formal ICT projects and assigned resources. A number of significant IT rebuilds are required in order to facilitate the new B2B, CATS and new minimum specification requirements. New interfaces for the customer are under development to assist our customers in operating in the POC space
| intelliHUB Pty Ltd | Within schedule | Medium
| Metering Dynamics | Not within schedule | High | There have been a number of key system architecture changes recently due to a change of integration partner working with Metering Dynamics. The project continues to have contingency plans in place that are actively being worked on, however the overall risk of the POC Readiness program has increased as a result. | [7 empty] | System architecture changes being implemented
| Powermetric Metering Pty Ltd | At risk | Medium | Powermetric MDP, MPB & MC overall POC system and business process development is on schedule however, the agressive POC implementation, industry testing, MC Registration and eHub Accreditation timeframes place Powermetric POC development at a Medium risk. Further, uncertainty of individual distribution business management of Faults and Emergency situations (where a contestable asset is installed at a customer premise) is concerning and clarification is sought by AEMO without delay.
| Select Solutions | At risk | High | The overall timeframes for these industry changes are tight. Select Solutions is working to a schedule set by relevant industry deadlines (ie industry testing, accreditation dates etc). Select Solutions overall strategy is to continue to run its existing systems for our Type 1-4 large meters and MP/MDP participant IDs with supporting enhancements to existing systems to form part of our accreditation for Type 4 small meters. The main risks are associated with our readiness for Type 4 small customer to meet the industry testing phase in August 2017. We do not currently see substantial issues impacting our Type 1-4 Large customer accreditation. Process impact and future process mapping is going well and we have a solid understanding of whatis required to ring-fence from Ausnet services appropriately. | [7 empty] | Risk relates to the current status of existing systems modifications.
| VECTORAMS | Within schedule | Medium | Scope of change, tight timeframes, current uncertainty on outstanding matters such as lack of clarity on Emergency Procedures, Meter Churn rules, and transition at cutover leads to a Project risk rating of Medium.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| Active Stream |  |  | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Acumen Metering | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Ausgrid Business Services | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| intelliHUB Pty Ltd | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Metering Dynamics | At risk | High | At risk | High | At risk | High | At risk | High | At risk | High | At risk | High
| Powermetric Metering Pty Ltd | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| Select Solutions | At risk | High | At risk | High | At risk | High | At risk | High | At risk | High | At risk | High
| VECTORAMS | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Powermetric Metering Pty Ltd | Select Solutions | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 71% - 80% | 81% - 99% | 81% - 99% | Completed (100%) | 41% - 50% | 41% - 50% | 75% | 81% - 99%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 81% - 99% | 51% - 60% | 81% - 99% | Completed (100%) | 41% - 50% | 61% - 70% | 75% | 61% - 70%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 81% - 99% | 61% - 70% | 81% - 99% | 81% - 99% | 21% - 30% | 11% - 20% | 75% | 71% - 80%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 81% - 99% | 51% - 60% | 21% - 30% | 61% - 70% | 11% - 20% | 11% - 20% | 75% | 11% - 20%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 61% - 70% | 61% - 70% | 11% - 20% | 81% - 99% | 11% - 20% | 1% - 10% | 25% | 1% - 10%
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 81% - 99% | 71% - 80% | 81% - 99% | 81% - 99% | 61% - 70% | 1% - 10% | 50% | 81% - 99%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 81% - 99% | 1% - 10% | 1% - 10% | 41% - 50% | 31% - 40% | 1% - 10% | 25% | Not started (0%)
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 31% - 40% | 41% - 50% | 51% - 60% | Completed (100%) | 11% - 20% | 41% - 50% | 75% | 11% - 20%
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 11% - 20% | 41% - 50% | 31% - 40% | Completed (100%) | 11% - 20% | 11% - 20% | 25% | Not started (0%)
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Not started (0%) | 11% - 20% | 21% - 30% | 61% - 70% | 1% - 10% | Not started (0%) | 50% | Not started (0%)
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 81% - 99% | 51% - 60% | 51% - 60% | 81% - 99% | 31% - 40% | 21% - 30% | 75% | 61% - 70%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 81% - 99% | 41% - 50% | 11% - 20% | 61% - 70% | 21% - 30% | 21% - 30% | 50% | 21% - 30%
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | 31% - 40% | Not started (0%) | Not started (0%) | 0% | Not started (0%)
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 51% - 60% | 31% - 40% | Completed (100%) | 81% - 99% | 51% - 60% | 21% - 30% | 75% | 31% - 40%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 41% - 50% | 1% - 10% | 11% - 20% | 41% - 50% | 21% - 30% | 1% - 10% | 25% | 11% - 20%
5.3 |  | The internal testing of market systems for your business | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 1% - 10% | 1% - 10% | 1% - 10% | Not started (0%) | 1% - 10% | Not started (0%) | 0% | Not started (0%)
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Powermetric Metering Pty Ltd | Select Solutions | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | At risk | Within schedule | Within schedule | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | Not within schedule | Within schedule | At risk | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | At risk | At risk | Within schedule | At risk | At risk | Not within schedule | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | At risk | At risk | At risk | Within schedule
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | At risk | Within schedule | Within schedule | Within schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | At risk | Within schedule | At risk | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Within schedule | At risk | Completed | Within schedule | Not within schedule | Within schedule | At risk | Within schedule
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | At risk | At risk | Within schedule | Not within schedule | Within schedule | At risk | Within schedule
5.3 |  | The internal testing of market systems for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Not within schedule | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Not within schedule | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Not within schedule | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Not within schedule | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Powermetric Metering Pty Ltd | Select Solutions | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [7 empty] | Finalising a number of MC requirements |  | Due to project and systems changes the reform impact is being reassessed.
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Dependent on Faults/Meter Churn , timely resolution or provisioning of answers from AEMO. |  | Working with ITCFG to understand impacts before completing planning |  | Key system architecture and system integrator changes. |  | At risk due to system procurement program slippage so focus now on ensuring existing systems are compliant for 1 December 2017.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Dependent on jurisdcitional determinations |  | Final reviews in place |  | Continuing uncertainty and changes in jurisdictional rules.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Dependent on jurisdcitional determinations |  | In progress. Will not be finalised until design and early prototypes of user systems are available. |  | Continuing uncertainty and changes in jurisdictional rules.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [7 empty] | In progress. With Legal team. This is a significant logistical effort to negotiate agrements with each propsective party. |  | Complexity of contractual and commercial arrangements under POC. |  | Our internal commercial resources are not as well progressed as had been antcipated but are nonetheless progressing.
2.4 |  | An assessment of the required accreditation and registration activities | [7 empty] | In hand. |  |  |  | Progressing through requirements for MC registration. Schedule challenged.
2.5 |  | The fulfilment of accreditation and registration obligations | [7 empty] | Letter of intentions provided. Application in draft. ABS acknowledges that a significant effort is required to produce all required procedures in a timely manner. |  | Changes required to systems and processes. |  | Progressing through requirements for MC registration. Schedule challenged.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | MC resource requirements have been determined |  | Awaiting outcome of update policies and work instructions to complete. |  | Assessment of contingency plan human resource requirements. |  | This has been done in 2 parts, the resource requirements to deliver the relevant projects and the ongoing resources required to deliver the services.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Resource assessment with respect to the MC role; MC org chart in draft. |  | Relies on the above. |  | Impacted by EQL merger and restructuring activity. |  | Primary changes relate to resourcing around MC function. This work is being progressed but is currently behind schedule.
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [7 empty] | Relies on the above. |  | Due to change in key system components, flow on effect to training development and delivery timing. |  | Workshops are held internally to educate and prepare key staff for the required changes and impacts.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Dependency Pkg 3 content and Faults/Emergencies. |  | In concert with the changes ot policies, priocedures and work instructions. |  | Key system architecture and system integrator changes impacting on business processes. |  | We've had 2 dedicated resources for over 6 months reviewing current processes and planning document changes for the process impacts relating to the PoC changes.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Dependency Pkg 3 content and Faults/Emergencies. |  | In concert with the changes ot policies, priocedures and work instructions. |  | Key system architecture and system integrator changes. |  | Still working with industry release dates to finalise these requirements as AEMO procedures are confirmed.
4.3 |  | The validation of business processes during industry testing | [7 empty] | Not expected to start until mid-August 2017/ |  | Dependant on activities above |  | At risk due to focus on existing systems enhancements.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [7 empty] | System impacts have been assessed in detail. The overall solution design is complete. |  | Key system architecture and system integrator changes. |  | At risk due to focus on existing systems enhancements.
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | The implementation phase is underway. Detailed designs continue to be prepared. Build activities have commenced. Final build estimates will be prepared as the designs complete. |  | Key system architecture and system integrator changes. |  | At risk due to focus on existing systems enhancements.
5.3 |  | The internal testing of market systems for your business | [7 empty] | Not at the stage of testing market systems. |  |  |  | At risk due to focus on existing systems enhancements.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [7 empty] | Not at the stage of testing market systems. |  |  |  | At risk due to focus on existing systems enhancements.
5.5 |  | The validation of performance of market systems during industry testing | [7 empty] | Not at the stage of testing market systems. |  |  |  | At risk due to focus on existing systems enhancements.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [7 empty] | Working with ITCFG to understand impacts before completing planning |  | Planning is dependant on other "At Risk" activities. |  | This action dependent upon finalisation of system changes
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [7 empty] | Not yet due. |  | Being able to manage regulatory compliance, systems cutover and maintaining customer services will be challenging. |  | This action dependent upon finalisation of system changes
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Powermetric Metering Pty Ltd | Select Solutions | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [7 empty] | Dedicated resource working on MC engagement and application |  | Metering Dynamics is moving to contingency plan to manage risks.
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [7 empty] | Member on ITCFG |  | Contingency plans are being worked on to get back on schedule. |  | New dedicated resources have been assigned to our POC Project and will ramp up towards August Industry Testing phase.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [9 empty] | Further reviews of PoC regulatory documentation and jurisdictional information.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [9 empty] | Further reviews of PoC regulatory documentation and jurisdictional information.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [11 empty] | Substantial customer and industry engagement has commenced and agreements are progressing.
2.4 |  | An assessment of the required accreditation and registration activities | [11 empty] | New dedicated resources have been assigned to our POC Project and will ramp up towards August Industry Testing phase.
2.5 |  | The fulfilment of accreditation and registration obligations | [9 empty] | Changes being discussed with AEMO. |  | New dedicated resources have been assigned to our POC Project and will ramp up towards August Industry Testing phase.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [9 empty] | Assessment being completed as part of business and systems work streams and to comply with ring fencing requirements.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [9 empty] | Being completed as part of business and systems work. |  | New dedicated resources have been assigned to our POC Project and will ramp up towards August Industry Testing phase.
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [9 empty] | Contingency plans are being worked on to get back on schedule.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [9 empty] | Working on contingency plans to manage impact.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [9 empty] | Working on contingency plans to manage impact.
4.3 |  | The validation of business processes during industry testing | [11 empty] | New dedicated resources have been assigned to our POC Project and will ramp up towards August Industry Testing phase.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [9 empty] | Working on contingency plans to manage impact. |  | New dedicated resources have been assigned to our POC Project and will ramp up towards August Industry Testing phase.
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | All available resources have been assigned to the design & development tasks. |  | Working on contingency plans to manage impact. |  | Focus is now on making existing systems compliant for 1 December 2017. New dedicated resources have been assigned to our POC Project and will ramp up towards August Industry Testing phase.
5.3 |  | The internal testing of market systems for your business | [11 empty] | Focus is now on making existing systems compliant for 1 December 2017. New dedicated resources have been assigned to our POC Project and will ramp up towards August Industry Testing phase.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [11 empty] | Focus is now on making existing systems compliant for 1 December 2017. New dedicated resources have been assigned to our POC Project and will ramp up towards August Industry Testing phase.
5.5 |  | The validation of performance of market systems during industry testing | [11 empty] | Focus is now on making existing systems compliant for 1 December 2017. New dedicated resources have been assigned to our POC Project and will ramp up towards August Industry Testing phase.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [7 empty] | Member on ITCFG |  | Focus on key deliverables for transition and cutover. |  | New dedicated resources have been assigned to our POC Project and will ramp up towards August Industry Testing phase.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [9 empty] | Focus on key deliverables for transition and cutover. |  | New dedicated resources have been assigned to our POC Project and will ramp up towards August Industry Testing phase.
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Metering Coordinator Reports
| 2017-06-05 |  |  | Metering Coordinator (MC) Readiness Assessment Reports - see Distributors Report tab for initial MC
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Active Stream | Within schedule | Low | The element of risk is elevating with the delay and/or deferral of the following items: - Package 3 - as built : delayed with inclusive items which need urgent clarification rather than been incorporated in a 6mth consultation process. i.e. Meter Churn, CR6300/800 etc. - Clear communicated date of when the DB's treatment plan on how the Faults and Emergencies will be handled on site and subsequent Market communication of activities undertaken, will be available. | [13 empty] | Active Stream is currently accredited and operating as a Type 4 MDP and MPB/MPC. Systems and processes are currently in place, requiring AS to assess and deliver the delta to comply with the POC requirements. Our approach with the Progress and Traffic Light Status is related to POC specific amendments.
| Acumen Metering | At risk | Medium | Overall project delivery status at risk, due to constrained timelines for delivery for system build and testing coupled with registration and accreditation activities. Clarity and agreement on transition and cutover activities is required, which will determine the impacts (system, process & people). Amber status is maintained due to tight timeframes and project resourcing challenges. Key risk mitigation will be implemented for the duration of the project.
| Ausgrid Business Services | At risk | Medium | We have established a number of formal ICT projects and assigned resources. A number of significant IT rebuilds are required in order to facilitate the new B2B, CATS and new minimum specification requirements. New interfaces for the customer are under development to assist our customers in operating in the POC space
| intelliHUB Pty Ltd | Within schedule | Medium
| Metering Dynamics | Not within schedule | High | There have been a number of key system architecture changes recently due to a change of integration partner working with Metering Dynamics. The project continues to have contingency plans in place that are actively being worked on, however the overall risk of the POC Readiness program has increased as a result. | [7 empty] | System architecture changes being implemented
| Powermetric Metering Pty Ltd | At risk | Medium | Powermetric MDP, MPB & MC overall POC system and business process development is on schedule however, the agressive POC implementation, industry testing, MC Registration and eHub Accreditation timeframes place Powermetric POC development at a Medium risk. Further, uncertainty of individual distribution business management of Faults and Emergency situations (where a contestable asset is installed at a customer premise) is concerning and clarification is sought by AEMO without delay.
| Select Solutions | At risk | High | The overall timeframes for these industry changes are tight. Select Solutions is working to a schedule set by relevant industry deadlines (ie industry testing, accreditation dates etc). Select Solutions overall strategy is to continue to run its existing systems for our Type 1-4 large meters and MP/MDP participant IDs with supporting enhancements to existing systems to form part of our accreditation for Type 4 small meters. The main risks are associated with our readiness for Type 4 small customer to meet the industry testing phase in August 2017. We do not currently see substantial issues impacting our Type 1-4 Large customer accreditation. Process impact and future process mapping is going well and we have a solid understanding of whatis required to ring-fence from Ausnet services appropriately. | [7 empty] | Risk relates to the current status of existing systems modifications.
| VECTORAMS | Within schedule | Medium | Scope of change, tight timeframes, current uncertainty on outstanding matters such as lack of clarity on Emergency Procedures, Meter Churn rules, and transition at cutover leads to a Project risk rating of Medium.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| Active Stream |  |  | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Acumen Metering | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Ausgrid Business Services | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| intelliHUB Pty Ltd | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| Metering Dynamics | At risk | High | At risk | High | At risk | High | At risk | High | At risk | High | At risk | High
| Powermetric Metering Pty Ltd | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| Select Solutions | At risk | High | At risk | High | At risk | High | At risk | High | At risk | High | At risk | High
| VECTORAMS | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Powermetric Metering Pty Ltd | Select Solutions | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 71% - 80% | 81% - 99% | 81% - 99% | Completed (100%) | 41% - 50% | 41% - 50% | 75% | 81% - 99%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 81% - 99% | 51% - 60% | 81% - 99% | Completed (100%) | 41% - 50% | 61% - 70% | 75% | 61% - 70%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 81% - 99% | 61% - 70% | 81% - 99% | 81% - 99% | 21% - 30% | 11% - 20% | 75% | 71% - 80%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 81% - 99% | 51% - 60% | 21% - 30% | 61% - 70% | 11% - 20% | 11% - 20% | 75% | 11% - 20%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 61% - 70% | 61% - 70% | 11% - 20% | 81% - 99% | 11% - 20% | 1% - 10% | 25% | 1% - 10%
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 81% - 99% | 71% - 80% | 81% - 99% | 81% - 99% | 61% - 70% | 1% - 10% | 50% | 81% - 99%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 81% - 99% | 1% - 10% | 1% - 10% | 41% - 50% | 31% - 40% | 1% - 10% | 25% | Not started (0%)
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 31% - 40% | 41% - 50% | 51% - 60% | Completed (100%) | 11% - 20% | 41% - 50% | 75% | 11% - 20%
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 11% - 20% | 41% - 50% | 31% - 40% | Completed (100%) | 11% - 20% | 11% - 20% | 25% | Not started (0%)
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Not started (0%) | 11% - 20% | 21% - 30% | 61% - 70% | 1% - 10% | Not started (0%) | 50% | Not started (0%)
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 81% - 99% | 51% - 60% | 51% - 60% | 81% - 99% | 31% - 40% | 21% - 30% | 75% | 61% - 70%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 81% - 99% | 41% - 50% | 11% - 20% | 61% - 70% | 21% - 30% | 21% - 30% | 50% | 21% - 30%
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | 31% - 40% | Not started (0%) | Not started (0%) | 0% | Not started (0%)
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 51% - 60% | 31% - 40% | Completed (100%) | 81% - 99% | 51% - 60% | 21% - 30% | 75% | 31% - 40%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 41% - 50% | 1% - 10% | 11% - 20% | 41% - 50% | 21% - 30% | 1% - 10% | 25% | 11% - 20%
5.3 |  | The internal testing of market systems for your business | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 1% - 10% | 1% - 10% | 1% - 10% | Not started (0%) | 1% - 10% | Not started (0%) | 0% | Not started (0%)
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Powermetric Metering Pty Ltd | Select Solutions | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | At risk | Within schedule | Within schedule | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | Not within schedule | Within schedule | At risk | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | At risk | At risk | Within schedule | At risk | At risk | Not within schedule | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | At risk | At risk | At risk | Within schedule
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | At risk | Within schedule | Within schedule | Within schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | At risk | Within schedule | At risk | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Within schedule | At risk | Completed | Within schedule | Not within schedule | Within schedule | At risk | Within schedule
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | At risk | At risk | Within schedule | Not within schedule | Within schedule | At risk | Within schedule
5.3 |  | The internal testing of market systems for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Not within schedule | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Not within schedule | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Not within schedule | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Not within schedule | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Powermetric Metering Pty Ltd | Select Solutions | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [7 empty] | Finalising a number of MC requirements |  | Due to project and systems changes the reform impact is being reassessed.
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Dependent on Faults/Meter Churn , timely resolution or provisioning of answers from AEMO. |  | Working with ITCFG to understand impacts before completing planning |  | Key system architecture and system integrator changes. |  | At risk due to system procurement program slippage so focus now on ensuring existing systems are compliant for 1 December 2017.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Dependent on jurisdcitional determinations |  | Final reviews in place |  | Continuing uncertainty and changes in jurisdictional rules.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Dependent on jurisdcitional determinations |  | In progress. Will not be finalised until design and early prototypes of user systems are available. |  | Continuing uncertainty and changes in jurisdictional rules.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [7 empty] | In progress. With Legal team. This is a significant logistical effort to negotiate agrements with each propsective party. |  | Complexity of contractual and commercial arrangements under POC. |  | Our internal commercial resources are not as well progressed as had been antcipated but are nonetheless progressing.
2.4 |  | An assessment of the required accreditation and registration activities | [7 empty] | In hand. |  |  |  | Progressing through requirements for MC registration. Schedule challenged.
2.5 |  | The fulfilment of accreditation and registration obligations | [7 empty] | Letter of intentions provided. Application in draft. ABS acknowledges that a significant effort is required to produce all required procedures in a timely manner. |  | Changes required to systems and processes. |  | Progressing through requirements for MC registration. Schedule challenged.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | MC resource requirements have been determined |  | Awaiting outcome of update policies and work instructions to complete. |  | Assessment of contingency plan human resource requirements. |  | This has been done in 2 parts, the resource requirements to deliver the relevant projects and the ongoing resources required to deliver the services.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Resource assessment with respect to the MC role; MC org chart in draft. |  | Relies on the above. |  | Impacted by EQL merger and restructuring activity. |  | Primary changes relate to resourcing around MC function. This work is being progressed but is currently behind schedule.
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [7 empty] | Relies on the above. |  | Due to change in key system components, flow on effect to training development and delivery timing. |  | Workshops are held internally to educate and prepare key staff for the required changes and impacts.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Dependency Pkg 3 content and Faults/Emergencies. |  | In concert with the changes ot policies, priocedures and work instructions. |  | Key system architecture and system integrator changes impacting on business processes. |  | We've had 2 dedicated resources for over 6 months reviewing current processes and planning document changes for the process impacts relating to the PoC changes.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Dependency Pkg 3 content and Faults/Emergencies. |  | In concert with the changes ot policies, priocedures and work instructions. |  | Key system architecture and system integrator changes. |  | Still working with industry release dates to finalise these requirements as AEMO procedures are confirmed.
4.3 |  | The validation of business processes during industry testing | [7 empty] | Not expected to start until mid-August 2017/ |  | Dependant on activities above |  | At risk due to focus on existing systems enhancements.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [7 empty] | System impacts have been assessed in detail. The overall solution design is complete. |  | Key system architecture and system integrator changes. |  | At risk due to focus on existing systems enhancements.
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | The implementation phase is underway. Detailed designs continue to be prepared. Build activities have commenced. Final build estimates will be prepared as the designs complete. |  | Key system architecture and system integrator changes. |  | At risk due to focus on existing systems enhancements.
5.3 |  | The internal testing of market systems for your business | [7 empty] | Not at the stage of testing market systems. |  |  |  | At risk due to focus on existing systems enhancements.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [7 empty] | Not at the stage of testing market systems. |  |  |  | At risk due to focus on existing systems enhancements.
5.5 |  | The validation of performance of market systems during industry testing | [7 empty] | Not at the stage of testing market systems. |  |  |  | At risk due to focus on existing systems enhancements.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [7 empty] | Working with ITCFG to understand impacts before completing planning |  | Planning is dependant on other "At Risk" activities. |  | This action dependent upon finalisation of system changes
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [7 empty] | Not yet due. |  | Being able to manage regulatory compliance, systems cutover and maintaining customer services will be challenging. |  | This action dependent upon finalisation of system changes
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Powermetric Metering Pty Ltd | Select Solutions | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [7 empty] | Dedicated resource working on MC engagement and application |  | Metering Dynamics is moving to contingency plan to manage risks.
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [7 empty] | Member on ITCFG |  | Contingency plans are being worked on to get back on schedule. |  | New dedicated resources have been assigned to our POC Project and will ramp up towards August Industry Testing phase.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [9 empty] | Further reviews of PoC regulatory documentation and jurisdictional information.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [9 empty] | Further reviews of PoC regulatory documentation and jurisdictional information.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [11 empty] | Substantial customer and industry engagement has commenced and agreements are progressing.
2.4 |  | An assessment of the required accreditation and registration activities | [11 empty] | New dedicated resources have been assigned to our POC Project and will ramp up towards August Industry Testing phase.
2.5 |  | The fulfilment of accreditation and registration obligations | [9 empty] | Changes being discussed with AEMO. |  | New dedicated resources have been assigned to our POC Project and will ramp up towards August Industry Testing phase.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [9 empty] | Assessment being completed as part of business and systems work streams and to comply with ring fencing requirements.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [9 empty] | Being completed as part of business and systems work. |  | New dedicated resources have been assigned to our POC Project and will ramp up towards August Industry Testing phase.
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [9 empty] | Contingency plans are being worked on to get back on schedule.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [9 empty] | Working on contingency plans to manage impact.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [9 empty] | Working on contingency plans to manage impact.
4.3 |  | The validation of business processes during industry testing | [11 empty] | New dedicated resources have been assigned to our POC Project and will ramp up towards August Industry Testing phase.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [9 empty] | Working on contingency plans to manage impact. |  | New dedicated resources have been assigned to our POC Project and will ramp up towards August Industry Testing phase.
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | All available resources have been assigned to the design & development tasks. |  | Working on contingency plans to manage impact. |  | Focus is now on making existing systems compliant for 1 December 2017. New dedicated resources have been assigned to our POC Project and will ramp up towards August Industry Testing phase.
5.3 |  | The internal testing of market systems for your business | [11 empty] | Focus is now on making existing systems compliant for 1 December 2017. New dedicated resources have been assigned to our POC Project and will ramp up towards August Industry Testing phase.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [11 empty] | Focus is now on making existing systems compliant for 1 December 2017. New dedicated resources have been assigned to our POC Project and will ramp up towards August Industry Testing phase.
5.5 |  | The validation of performance of market systems during industry testing | [11 empty] | Focus is now on making existing systems compliant for 1 December 2017. New dedicated resources have been assigned to our POC Project and will ramp up towards August Industry Testing phase.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [7 empty] | Member on ITCFG |  | Focus on key deliverables for transition and cutover. |  | New dedicated resources have been assigned to our POC Project and will ramp up towards August Industry Testing phase.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [9 empty] | Focus on key deliverables for transition and cutover. |  | New dedicated resources have been assigned to our POC Project and will ramp up towards August Industry Testing phase.
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Embedded Networks
| 2017-06-05 |  |  | Embedded Networks Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Ausgrid Business Services | At risk | Medium | We have established a number of formal ICT projects and assigned resources. A number of significant IT rebuilds are required in order to facilitate the new B2B, CATS and new minimum specification requirements. New interfaces for the customer are under development to assist our customers in operating in the POC space
| Energy & Plant Management Pty Limited | Within schedule | Low | Preparing for accreditation
| Momentum Energy | Within schedule | Low
| Network Energy Services | Within schedule | Low | Submitted accreditation application | [7 empty] | Getting prepared to implement all aspects
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| Ausgrid Business Services | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| Energy & Plant Management Pty Limited | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Momentum Energy | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Network Energy Services | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | Ausgrid Business Services | Energy & Plant Management Pty Limited | Momentum Energy | Network Energy Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 81% - 99% | 51% - 60% | 71% - 80% | 100%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 81% - 99% | 11% - 20% | 61% - 70% | 100%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 81% - 99% | 21% - 30% | 41% - 50% | 100%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 21% - 30% | 11% - 20% | 21% - 30% | 100%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 11% - 20% | 41% - 50% | 1% - 10% | 25%
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 81% - 99% | 41% - 50% | 61% - 70% | 100%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 1% - 10% | 1% - 10% | 41% - 50% | 50%
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 51% - 60% | 81% - 99% | 41% - 50% | 100%
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 31% - 40% | 61% - 70% | Not started (0%) | 100%
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | 21% - 30% | 41% - 50% | 1% - 10% | 50%
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 51% - 60% | 71% - 80% | 21% - 30% | 100%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 11% - 20% | 11% - 20% | 11% - 20% | 100%
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | 1% - 10% | Not started (0%) | 0%
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Completed (100%) | 41% - 50% | 41% - 50% | 75%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 11% - 20% | 41% - 50% | 31% - 40% | 50%
5.3 |  | The internal testing of market systems for your business | [5 empty] | Not started (0%) | 1% - 10% | 11% - 20% | 50%
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | 0%
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | 1% - 10% | Not started (0%) | 0%
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 1% - 10% | 41% - 50% | 1% - 10% | 75%
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | 11% - 20% | Not started (0%) | 25%
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | Ausgrid Business Services | Energy & Plant Management Pty Limited | Momentum Energy | Network Energy Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | At risk | Within schedule | Within schedule | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | At risk | Within schedule | Within schedule | Within schedule
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Completed | Within schedule | Within schedule | Within schedule
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | At risk | Within schedule | Within schedule | Within schedule
5.3 |  | The internal testing of market systems for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | Ausgrid Business Services | Energy & Plant Management Pty Limited | Momentum Energy | Network Energy Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Finalising a number of MC requirements
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Working with ITCFG to understand impacts before completing planning
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Final reviews in place
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | In progress. Will not be finalised until design and early prototypes of user systems are available.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | In progress. With Legal team. This is a significant logistical effort to negotiate agrements with each propsective party.
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | In hand.
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Letter of intentions provided. Application in draft. ABS acknowledges that a significant effort is required to produce all required procedures in a timely manner.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Awaiting outcome of update policies and work instructions to complete.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Relies on the above.
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Relies on the above.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | In concert with the changes ot policies, priocedures and work instructions.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | In concert with the changes ot policies, priocedures and work instructions.
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not expected to start until mid-August 2017/
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | System impacts have been assessed in detail. The overall solution design is complete. |  | System development is reliant on external vendor, delays in final market procedures will impact readiness activities
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | The implementation phase is underway. Detailed designs continue to be prepared. Build activities have commenced. Final build estimates will be prepared as the designs complete.
5.3 |  | The internal testing of market systems for your business | [5 empty] | Not at the stage of testing market systems.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not at the stage of testing market systems.
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not at the stage of testing market systems.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Working with ITCFG to understand impacts before completing planning
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not yet due.
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | Ausgrid Business Services | Energy & Plant Management Pty Limited | Momentum Energy | Network Energy Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Dedicated resource working on MC engagement and application
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Member on ITCFG
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | All available resources have been assigned to the design & development tasks.
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Member on ITCFG
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Third Party
| 2017-06-05 |  |  | Third Party Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## AEMO
AEMO Readiness Assessment Report
B. Overall project status
| A. Details | [6 empty] | Project status | Project risk rating | Comment
| Date | 2017-06-05 | [5 empty] | Within schedule | Medium | The Vic Govt has released notes on the intent of the Order in Council drafting with a number of questions posed to industry for feedback. Additionally, the treatment of Vic AMI meters will remain consistent with today’s practices. Readiness is the main focus of AEMO’s industry engagement with the establishment of the transition and cut-over focus group who’ve developed a schedule to finalising a plan by the end of September. AEMO encourages early registration and accreditation by all participants requiring to do so as to remove risks associated with late issues.
| Organisation | AEMO
C. Jurisdictional status
# | Organisation | ACT | NSW | QLD | SA | TAS | VIC | Status | Risk | Comment
1 | AEMO | √ | √ | √ | √ | √ | √ | Within schedule | Medium
2
3
4
5
6
D. Detailed status
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%) | Traffic light status | Explanation of variance/Notes | Mitigating actions
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Completed (100%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 81% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
1.3 |  | Delivery of the Market Readiness Strategy and associated plans | [5 empty] | 31% - 40% | Within schedule | Version 1.1 of the POC Industry Test Strategy & Version 1.0 of the POC B2B Industry Test Plan were released on 25 May 2017. The first draft of the POC Market Trial Plan was released on 25 May 2017. The Industry Transition and Cutover Plan will be developed after the ITCFG first draft expected end of August, finalised end of September. |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 81% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.2 |  | The development, documentation and approval of updated internal policies consistent with regulatory changes including jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 1% - 10% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | N/A | N/A |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 81% - 99% | Within schedule | Updated procedures and processes in place for MC registration, MP, MDP and ENM accreditation. Finalising B2B E-Hub accreditation processes. |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | N/A | N/A |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.6 |  | The publication of updated AEMO retail electricity market procedures and associated documentation | [5 empty] | 81% - 99% | Within schedule | Package 3 consultation first stage consultation released on 19 May 2017. |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.7 |  | The publication of updated B2B retail electricity market procedures and associated documentation | [5 empty] | 81% - 99% | Within schedule | On 8 May 2017, the IEC resolved to not undertake a further consultation on the B2B procedures. However a process for error corrections was commenced on 16 May 2017. |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 41% - 50% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 31% - 40% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
3.3 |  | The development and delivery of training to staff in operational roles | [5 empty] | 11% - 20% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 41% - 50% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 21% - 30% | At risk | The POC platform service and support hub transition are being undertaken within a short timeframe. | Additional resources are being deployed to address the gap. |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | Within schedule | End-to-end business processes will be trialled from August. |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4.4 |  | The delivery of POC information sessions to participants | [5 empty] | 81% - 99% | Within schedule | Participant Information Session on industry testing processes still to be scheduled. |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5. Market systems
5.1 | Market systems - MSATS (EN/MC) | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Completed (100%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 81% - 99% | Within schedule | Changes due to work package 3 to be implemented in August release |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.3 |  | The internal testing of market systems for your business | [5 empty] | 81% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | 21% - 30% | Within schedule | Phase 1: EN/MC Testing commenced on 5 Jun 2017 (cycle 1 was cancelled due to participant readiness). |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | 21% - 30% | Within schedule | EN/MC commenced with 5 participants. As at 8 Jun, actual execution was tracking above planned execution. Cycle 2 will commence on 19 June with 6 participants. | All test scenarios will be available in Phase 3: Market Trial. |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.6 | Market systems - B2B e-hub and MSATS | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 51% - 60% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.7 |  | The development and build of appropriate market systems for your business | [5 empty] | 21% - 30% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.8 |  | The internal testing of market systems for your business | [5 empty] | 1% - 10% | Within schedule | On schedule for 13 June: aseXML r36 released in MSATS preproduction, e-Hub API Gateway available for connectivity testing |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.9 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not started (0%) | Within schedule | Phase 2: B2B Industry Testing on schedule to commence on 19 June, to date 13 participants registered. |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.1 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 1% - 10% | Within schedule | The Industry Transition and Cutover Focus Group held their fourth meeting on 5 June 2017. Cut-over plan expected by end of September. |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
7. General notes
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
[12 empty] | 41% - 50% | Retailer
[12 empty] | 51% - 60% | Distributor
[12 empty] | 61% - 70% | Meter Provider
[12 empty] | 71% - 80% | Meter Data Provider
[12 empty] | 81% - 99% | Metering Coordinator
[12 empty] | Completed (100%) | Embedded Network Manager
[12 empty] | N/A | Embedded Network Operator
Third Party B2B Participant
Within schedule
At risk
Not within schedule
N/A
[12 empty] | Completed | √
x
Low
Medium
High
N/A

## Harvey Balls 10% (hidden)
ü
Completed
| 100 | 90 | 80 | 70 |  | 60 | 50 | 40 | 30 | 20 | 10 | 0
| 0 | 10 | 20 | 30 |  | 40 | 50 | 60 | 70 | 80 | 90 | 100
WITHIN SCHEDULE | [12 empty] | Risks | Low
Medium
High
AT RISK
NOT WITHIN SCHEDULE
|  |  | ~0% |  | ~50%
|  |  | ~10% |  | ~60%
|  |  | ~20% |  | ~70%
|  |  | ~30% |  | ~80%
|  |  | ~40% |  | ~90%