## Market Readiness Report Page 1
43045
AEMO Power of Choice Implementation Program
|  | Monthly Readiness Report | 2017-11-06
Overall Status |  | Commentary |  |  | Risk Rating |  | # Open Risks - Rating: |  |  | Issues:
|  | The majority of participants (around 70%) report being on schedule to deliver by 1 December 2017, however the overall project status remains amber - "at risk" of delivery, with a medium risk rating. A critical issue for many participants is their dependency on Metering Coordinator (MC) registration (note as at 14/11 3 MCs have been registered). Participants have also noted that whilst many program risks have now been addressed, there are still a number of open risks and issues (refer to POC Risk and Issue Log). Concerns have been raised about the participation and scope of test coverage in Industry Testing, increasing the risk of issues being raised post go-live. Participants are focusing on preparing for go-live, risk mitigation and post go-live support. |  |  |  |  | High | Med | Low | #
[7 empty] | 2 | 8 | 2 | 2
AEMO and NEM Participants Readiness Criteria |  |  | AEMO |  | Retailers |  | Distributors |  | MP and MDP |  | Metering Coordinator |  | Embedded Network Manager |  | Third party e-hub
# | Category | Criterion | Status | Note | Status | Note | Status | Note | Status | Note | Status | Note | Status | Note | Status | Note
1. Assessment and preparation
1.1 | Assessment and preparation | Consequences of the POC reforms for your business considered, and appropriate implementation plans are in place
1.2 |  | Key readiness planning documents delivered
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | Updated retail electricity market procedures and associated documents published
2.2 |  | Internal policies updated for consistency with regulatory changes including jurisdictional regulations and requirements (e.g. safety) |  |  |  | #1
2.3 |  | Operationally critical commercial contracts in place |  |  |  | #2 |  |  |  | #2 |  | #2 |  | #2
2.4 |  | Accreditation and registration activities completed | [7 empty] | #3 |  | #3
3. People
3.1 | People | Operational roles specified, assigned to staff, and training delivered
4. Business processes
4.1 | Business processes | Updated, validated and approved business processes in place |  |  |  | #4
4.2 |  | Successfully validated critical business processes during industry testing |  |  |  | #5
4.3 |  | Process work‑arounds in place for any issues identified during industry testing
5. Market systems
5.1 | Market systems | Delivery of the re-developed B2B e-hub for industry testing
5.2 |  | Successfully tested market systems capable of being moved into production | [5 empty] | #6
5.3 |  | Performance of, and communication between, market systems validated during industry testing | [5 empty] | #6
6. Transition planning
6.1 | Transition planning | Transition and cutover plan(s) in place
6.2 |  | Prerequisite transition and cutover processes completed (e.g. trial data conversions and cutover dress rehearsals) | [11 empty] | #7
Jurisdictional Status
Jurisdiction |  | Comments | AEMO |  | Retailers |  | Distributors |  | MP and MDP |  | Metering Coordinator |  | Embedded Network Manager |  | Third party e-hub
|  |  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
ACT |  | Jurisdictional risk is a reflection of overall project risk.
NSW |  | Jurisdictional risk is a reflection of overall project risk.
QLD |  | Jurisdictional risk is a reflection of overall project risk.
SA |  | Jurisdictional risk is a reflection of overall project risk.
TAS |  | Jurisdictional risk is a reflection of overall project risk.
VIC |  | Jurisdictional risk is a reflection of overall project risk.

## HIDDEN 25% (hidden)
ü
| 100 | 75 | 50 | 25 | 0
| 0 | 25 | 50 | 75 | 100
WITHIN SCHEDULE | [5 empty] | Risks | Low
Medium
High
AT RISK
NOT WITHIN SCHEDULE

## Market Readiness Report Page 2
AEMO Power of Choice Implementation Program
Monthly Readiness Report
2017-11-06
Variances
Note # | Explanation of Variance |  |  | Mitigating Actions
1 | Variance reported by Retailers, DB and ENMS: Updating internal policies on schedule at risk due to late or yet to be defined jurisdictional changes, including in relation to remote re-en / de-en in non-Vic jurisdictions and clarity on the ENM role in Victoria. |  |  | Participants are monitoring jurisdiction safety discussions and engaging with jurisdictional bodies.
2 | Variance reported by Retailers, MP&MDPs, MCs and ENM): Updating commercial arrangements on schedule is at risk, or not within schedule, due to volume and complexity of contracts that need to be entered into with industry parties. The slow progress of MC registration has also been raised as a risk. |  |  | [As at 14/11, 3 full MCs have been registered and a number of other applications are well advanced.]
3 | Variance reported by Participants: Fulfilment of accreditation and registrations activities on schedule at risk due to tight timeframes and unanticipated time and effort required for the registration process. |  |  | [AEMO is engaging with participants to facilitate registration and accreditation activities.]
4 | Variance reported by Participants: Updating and finalising business processes on schedule is at risk, or not within schedule due to #1 (lack of clarity in processes including remote re-en and de-en) and #2 (dependency on metering partners) and concerns around different interpretations from different market participants Intending ENMs have also highlighted concerns with the ENM NMI discovery process. |  |  | Participants continuing to engage with each other and relevant jurisdictional bodies. Intending ENMs engaging with AEMO and the AER.
5 | Variance reported by Participants: Validation of business processes during Industry Testing at risk or not within schedule due to limited participation and scope in industry testing. |  |  | [Market Trial Cycle 3 concluded on 3 November with 22 Retail companies, 8 independent Metering companies and 12 Distributors taking part. AEMO's pre-production systems remain open for bilateral testing and AEMO's test team is continuing to support participants.]
6 | Variance reported by Participants: Not all end-to-end test cases were able to be completed due to other parties not being ready or able to undertake testing, as such it is likely that some issues will be identified post go-live. |  |  | Participants are continuing to undertake bilateral testing. Participants are increasing post-go-live support.
7 | Variance reported by Participants: Transition and Cutover activities are dependent on timely delivery of earlier program stages.
Notes
1. Please refer to the POC Industry Readiness Reporting Plan for more details on the Readiness Report process: http://www.aemo.com.au/-/media/Files/Electricity/NEM/Power-of-Choice/B2B/AEMO-POC-Industry-Readiness-Reporting-Plan-v20.pdf 2. The count of open Risk and Issues is based on the POC Industry Risk Register as at 15/11/2017. 3. Explanation of Variance and Mitigating Actions above are based on Participants comments, AEMO's comments are included within square brackets [ ].
Key - Progress and Status | [5 empty] | Key - Risk Rating
Progress |  |  | Status
Harvey balls represent progress towards achieving the criterion |  |  | Colour indicates the readiness status |  |  | Rating
~0% |  | ~50% | Criterion is within agreed schedule and deliverable requirements |  |  | High
~10% |  | ~60% | Criterion is at risk of not meeting requirements and corrective action may be required |  |  | Medium
~20% |  | ~70% | Criterion not meeting requirements. Immediate corrective action required |  |  | Low
~30% |  | ~80% |  |  |  | See POC Industry Risk Register for open risks and issues:
~40% |  | ~90% | Criterion has been achieved |  | ü | POC Industry Register

## Retailer Reports
| 2017-11-06 |  |  | Retailer Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Industry risk rating | Overall project comment | [6 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| ActewAGL Retail | Within schedule | Medium | Medium | ActewAGL Retail is currently focused on Regression Testing, Dress Rehearsals, and Operational readiness.A detailed project plan is in place and being tracked against in order to achieve compliance by the "go live" date. One accredited MC (as of end October) is a concern for the Industry Readiness.
| AGL Retailer Powerdirect | At risk | Medium | High | Cycle 3 industry testing has been completed. However, some test scenarios could not be completed due to industry issues and defects. AGL plans to conduct further participant testing in November. Commercial activities are still in progress. Training preparations are underway. Dress rehearsal conducted and another planned. Performance testing and regression testing in progress. Project is now focusing on vendor mobilisation, process tuning and risk management. Project status remains amber due to not yet finalised commercial agreements. Industry risk rating flagged as red due to the significant number of industry tests not completed and MC registration delays that may impact transition and post go-live. | [6 empty] | Risk rating remains amber due to incomplete testing with key participants, a number of open industry issues and commercial agreement risk.
| Alinta Energy | Not within schedule | Low | High | Dependence on Registartion of MCs is a significant concern | [6 empty] | Dependence on Registartion of MCs is a significant concern
| Aurora Energy | At risk | Medium | Medium | Aurora Energy continues to manage a number of risks with regards to the implementation of the Power of Choice reforms by 1 December 2017. The most significant risk is the aggressive implementation timeline, reflected in Aurora Energy's 'at risk' project status. This risk is also impacting the ability of Aurora Energy's key vendors to meet POC timeframes. This includes, but is not limited to, its selected Metering Coordinator, which is required to establish advanced metering service capability in Tasmania where it currently does not exist.
| Diamond Energy | Within schedule | Medium | Medium
| Energy Australia | At risk | Low | Medium | We see significant risks associated with: late participation by some participants in industry and bi-lateral testing. Delays in some industry documentation such as handbooks along with jurisdictional legislative changes still to be finalised is causing some concern. The introduction of the staged new connections process is welcomed however, there are concerns that one participant is not necessarily aligned in interpretation of this process | [6 empty] | The Program is on schedule, but has risks associated with the progress of industry coordinated activities, such as industry-wide readiness, BCP and Emergency Planning.
| Ergon Energy Queensland | Within schedule | Medium | High | Ergon Energy continues to manage a number of system, process and people risks to deliver to the aggressive timeframe of the 1 December 2017. EEQ is focussed on minimising negative impact on customers due to this timeframe. Whilst EEQ believes that it will meet the requirements for 1 December, there remains significant risks for the sector overall from a readiness perspective and the need to develop contingency plans. In particular, MC registrations remain a critical issue. EEQ is aware that AEMO has a delay in processing MC registration, which could impact market readiness in general with less than 4 weeks to go. From a system perceptive, additional clarity is required on the overall readiness assessment of AEMO and the market. In particular reporting is showing that progress for Industry Test Cycle 3 is significantly less than expected. EEQ is seeking to understand what mitigations are being planned should participants not be confident nor accredited to use eHub in readiness for go-live. Greater visibility is required to understand the issue management and resourcing availability of AEMO post go live if issues are experienced, particularly in the lead up to Christmas. | [6 empty] | Refer to above comments
| ERM Power Retail | At risk | Medium | Medium | ERM continues to report at risk for the PoC project, primarily due to remaining uncertainty in areas including 1) Meter Churn processes 2) Impact of these on commercial agreements At this late stage, we are still encountering significant differences between approaches to the same process (e.g. installing a new meter) from our metering providers, impacting on the ability to finalise commercial agreements. Lack of certainty around readiness of ENMs and the impact on our business processes is a new concern. Many previous uncertainties have been resolved, reducing (but not eliminating) risk.
| M2 Energy Pty Ltd | Within schedule | Medium |  | Project Scoping and coding by Vendor is complete, and testing has commenced. Business intention is to fully outsource MC role. Risk considered Medium moving to High as 1 MC accredited, who is a retail competitor. M2 Energy's preferred MC remains un accredited. | [6 empty] | Vic withdrawl from POC has introduced risk into System Scoping, and increased training and change management requirements. | [5 empty] | M2 Energy has achieved E-hub Accreditation.
| Macquarie Bank Limited | Within schedule | Low
| Mojo Power | Within schedule | Medium | Medium | [7 empty] | Mojo in application for licence to enter Victoria.
| Momentum | At risk | Medium | Medium | Currently in negotiations for contractual agreements with potential MC who have not secured their registrations.Progress is slower than planned.Momentum is a subsidiary of Hydro Tas and Legal support is provided as shared services which has been less than ideal and the project cost have been stretched by the charges of the external legal charges.Pricing is the sticking point with most of the proposed business partners. Momentum uses 3 separate Vendors and the delivery of the system requirements was initially not in a coordinated approach but has since been addressed and support during testing has been problematic as one vendor is working for numerous parties. | [6 empty] | Availability of internal legal resources for drafting MC contracts & revamping the T&Cs has been problematic and had to resort to external legal to progress. Business Change Management tasks/ activities and testing [market trials,integration, UAT,regression]are in progress with 60% completed
| Next Business Energy | Within schedule | Low |  | NBE is tracking well with internal processes almost complete for post POC implementation. Bilateral testing is mostly complete with market self accreditation also complete.
| Origin Energy | At risk | Medium |  | Overall project delivery deadline at risk, due to constrained timelines for delivery against overall AEMO Delivery Timelines. Program is currently reporting Amber however remains highly dependant on the readiness of other participants to be successful. A relevant number of delivery risks continue to be monitored and mitigated for the duration of the Project. Main concerns are: • There is no Go / No go option based on overall participant readiness e.g. successful completion of Market Testing. • There is no Back-out scenario for this implementation given this is an integrated delivery backed by change in legislation. The risk profile is extremely high given statuses of various participants. | [6 empty] | Overall project delivery deadline at risk, due to constrained timelines for delivery against overall AEMO Delivery Timelines.
| Pacific Hydro Retail / Tango | At risk | High | Medium | The timing and outcomes of the following outstanding PoC activities have the potential to impact the build, test and implementation phases: 1. MSATS - As Built Consultation 2. B2B - Translation tool delivery and client side implementation & testing; potential new B2B schema changes prior to 1 Dec, and any Errata requiring process workarounds 3. Meter Churn Issues - recently raised and despite a paper being issued by AEMO, there are still concerns being raised. 4. Vic Government decision not to proceed with PoC. 5. Jurisdictional safety review of the remote Re-en/De-en process. 6. Internal Project delay for replacing current systems.
| People Energy Pty Ltd | Within schedule | Medium | Medium | Overall project delivery deadline at low risk, due to constrained timelines for delivery against overall AEMO Delivery Timelines.
| Pooled Energy Pty Ltd | At risk | Medium | Medium | Project status is at risk with a medium risk rating. Pooled Energy are continuing to work through procedural and process changes with its industry partners. Pooled Energy is dependent on external providers meeting timelines - and those providers are also dependent on other providers meeting deadlines. Risk that MCs will not be accredited in time. | [6 empty] | As above - Pooled Energy operates in NSW only currently.
| Powershop | Within schedule | Medium | Medium | Powershop's development team has been making good progress on implementing the required POC changes.
| Red Energy & Lumo Energy | Within schedule | Low | High | Consistent concerns: - Business and customer activity is very high at the targeted cut-over time. Inconsistent approaches across industry creates increased activity and raises risk (eg. new connections, meter churn, faults and emergencies, expected approaches to in-flight transactions). - Other jurisdictional consequential legislative amendments are not yet understood (and some jurisdictions unseen) which is adding further risks to the overall project. We have reduced our overal risk rating as some previous risks and concerns have been mitigated. | [6 empty] | Registration of participants is a significant risk, only one contestable MC is registered | [5 empty] | We remain concerned with the progress of MC registration.
| Simply Energy | Within schedule | Low | Low | NSW Govt. email sent on the 4th of October that may have an impact on the readiness if the new suite of procedures require system or process changes effective 1st December 2017. | [12 empty] | Simply Energy has completed B2B e-hub accreditation testing as well as on track with Market Trial Cycle 3 with more than 95% completion rate and no major defects have been identified.
| Stanwell Corporation Limited | Within schedule | Low |  | Project progressing as planned.
| Sumo | Within schedule
| WINconnect Pty LTD | At risk | Medium |  | [AEMO Note - Using 9-Oct 17 Report for WINconnect]: Working through clarifaction on market design and ENM discovery procedure in MSATS. | [12 empty] | Require guidance from AEMO as to process for ENM discover of MSATS to initiate the custoemr churn process. The ENM is not to be listed against a EN parent in MSATS. Require confirmation on validation in MSATS to ensure only appointed ENMs can perform CR against certain partent NMIS.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| ActewAGL Retail | Within schedule | Medium | Within schedule | Medium
| AGL Retailer Powerdirect | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Alinta Energy |  |  | Not within schedule | Low | Not within schedule | Low | Not within schedule | Low |  |  | Not within schedule | Low
| Aurora Energy | [8 empty] | At risk | Medium
| Diamond Energy |  |  | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| Energy Australia | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | At risk | Medium
| Ergon Energy Queensland |  |  |  |  | Within schedule | Medium
| ERM Power Retail | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| M2 Energy Pty Ltd |  |  | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| Macquarie Bank Limited | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Mojo Power |  |  | Within schedule | Medium | Within schedule | Medium |  |  |  |  | Within schedule | Medium
| Momentum | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Next Business Energy | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Origin Energy | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Pacific Hydro Retail / Tango |  |  | At risk | High | At risk | High | At risk | High |  |  | At risk | High
| People Energy Pty Ltd |  |  | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Pooled Energy Pty Ltd |  |  | At risk | Medium
| Powershop |  |  | Within schedule | Medium | Within schedule | Medium |  |  |  |  | Within schedule | Medium
| Red Energy & Lumo Energy |  |  | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Simply Energy | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Stanwell Corporation Limited | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  |  |  | Within schedule | Low
| Sumo | [10 empty] | Within schedule
| WINconnect Pty LTD |  |  | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | ActewAGL Retail | AGL Retailer Powerdirect | Alinta Energy | Aurora Energy | Diamond Energy | Energy Australia | Ergon Energy Queensland | ERM Power Retail | M2 Energy Pty Ltd | Macquarie Bank Limited | Mojo Power | Momentum | Next Business Energy | Origin Energy | Pacific Hydro Retail / Tango | People Energy Pty Ltd | Pooled Energy Pty Ltd | Powershop | Red Energy & Lumo Energy | Simply Energy | Stanwell Corporation Limited | Sumo | WINconnect Pty LTD | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Completed (100%) | Completed (100%) | Completed (100%) | 91% - 99% | 61% - 70% | 81% - 99% | Completed (100%) | Completed (100%) | 100% | Completed (100%) | Completed (100%) | 91% - 99% | Completed (100%) | Completed (100%) | Completed (100%) | 91% - 99% | 81% - 99% | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%)
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Completed (100%) | Completed (100%) | Completed (100%) | 91% - 99% | 61% - 70% | 81% - 99% | 81% - 90% | 71% - 80% | 75% | Completed (100%) | Completed (100%) | 81% - 90% | 61% - 70% | 91% - 99% | 71% - 80% | 81% - 90% | 71% - 80% | 71% - 80% | Completed (100%) | Completed (100%) | Completed (100%) |  | 71% - 80%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 81% - 90% | Completed (100%) | Completed (100%) | 91% - 99% | Not started (0%) | 81% - 99% | Completed (100%) | 81% - 99% | 25% | Completed (100%) | 81% - 99% | 71% - 80% | 51% - 60% | 81% - 90% | 81% - 90% | 71% - 80% | 71% - 80% | 91% - 99% | 81% - 99% | Completed (100%) | 81% - 99% |  | 41% - 50%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 71% - 80% | 91% - 99% | Completed (100%) | 61% - 70% | Not started (0%) | 71% - 80% | 81% - 90% | 71% - 80% | 0% | Completed (100%) | 71% - 80% | 81% - 90% | 61% - 70% | 71% - 80% | 71% - 80% | 61% - 70% | 51% - 60% | N/A | 61% - 70% | Completed (100%) | 71% - 80% |  | 11% - 20%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 71% - 80% | 81% - 90% | 91% - 99% | 91% - 99% | 51% - 60% | 71% - 80% | 91% - 99% | 41% - 50% | 50% | 61% - 70% | 71% - 80% | 71% - 80% | 41% - 50% | 71% - 80% | 71% - 80% | 61% - 70% | 61% - 70% | 71% - 80% |  | 71% - 80% | 41% - 50% | Completed (100%) | 41% - 50%
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | 81% - 90% | Completed (100%) | Completed (100%) | Completed (100%) | 25% | Completed (100%) | 81% - 99% | 81% - 90% | 41% - 50% | 81% - 90% | Completed (100%) | 91% - 99% | 61% - 70% | Completed (100%) |  | Completed (100%) | Completed (100%) |  | 71% - 80%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | 81% - 90% | Completed (100%) | Completed (100%) | Completed (100%) | N/A | Completed (100%) | 71% - 80% | 81% - 90% | Not started (0%) | Not started (0%) | 41% - 50% | 91% - 99% | 51% - 60% | Completed (100%) |  | N/A | Completed (100%) |  | 71% - 80%
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 91% - 99% | Completed (100%) | Completed (100%) | 61% - 70% | 61% - 70% | Completed (100%) | 91% - 99% | 71% - 80% | 100% | N/A | Completed (100%) | 91% - 99% | Completed (100%) | 81% - 90% | 51% - 60% | 91% - 99% | Completed (100%) | 61% - 70% |  | Completed (100%) | Completed (100%) | Completed (100%) | 71% - 80%
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 81% - 90% | 81% - 90% | Completed (100%) | 71% - 80% | 61% - 70% | 61% - 70% | 81% - 90% | 71% - 80% | N/A | N/A | Completed (100%) | Completed (100%) | Completed (100%) | 61% - 70% | 51% - 60% | N/A | Completed (100%) | Not started (0%) |  | 91% - 99% | 61% - 70% | Completed (100%) | Completed (100%)
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | 61% - 70% | 81% - 90% | 11% - 20% | 31% - 40% | 31% - 40% | 71% - 80% | 51% - 60% | 61% - 70% | 50% | Completed (100%) | 81% - 99% | 71% - 80% | 51% - 60% | 51% - 60% | 31% - 40% | 41% - 50% | 51% - 60% | 21% - 30% |  | 71% - 80% | 51% - 60% | 91% - 99% | Completed (100%)
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 91% - 99% | Completed (100%) | Completed (100%) | Completed (100%) | 51% - 60% | 81% - 99% | 91% - 99% | 61% - 70% | 50% | Completed (100%) | 81% - 99% | 91% - 99% | Completed (100%) | Completed (100%) | Completed (100%) | 61% - 70% | 81% - 99% | 71% - 80% | Completed (100%) | Completed (100%) | 81% - 99% | 91% - 99% | 41% - 50%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Completed (100%) | 91% - 99% | 91% - 99% | 81% - 90% | 41% - 50% | 81% - 99% | 81% - 90% | 61% - 70% | 50% | Completed (100%) | 81% - 99% | 81% - 90% | 71% - 80% | 81% - 90% | 71% - 80% | 51% - 60% | 51% - 60% | 21% - 30% | Completed (100%) | Completed (100%) | 51% - 60% | 91% - 99% | 51% - 60%
4.3 |  | The validation of business processes during industry testing | [5 empty] | 91% - 99% | 81% - 90% | Completed (100%) | 91% - 99% | 41% - 50% | 81% - 99% | 81% - 90% | 21% - 30% | 50% | N/A | 61% - 70% | 91% - 99% | Completed (100%) | 81% - 90% | 71% - 80% | Not started (0%) | 41% - 50% | 51% - 60% | 71% - 80% | 91% - 99% | Completed (100%) | Not started (0%) | Completed (100%)
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) |  | Completed (100%) | Completed (100%) | 71% - 80% | 75% | Completed (100%) | 51% - 60% | 91% - 99% | Completed (100%) | 81% - 99% | Completed (100%) | 81% - 90% | 81% - 99% | 81% - 90% | Completed (100%) | Completed (100%) | Completed (100%) | 91% - 99% | 61% - 70%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Completed (100%) | Completed (100%) | Completed (100%) | 81% - 90% |  | Completed (100%) | Completed (100%) | 71% - 80% | 75% | Completed (100%) | 51% - 60% | 91% - 99% | 71% - 80% | 61% - 70% | 91% - 99% | 81% - 90% | 71% - 80% | 71% - 80% | Completed (100%) | 91% - 99% | Completed (100%) | Completed (100%) | 61% - 70%
5.3 |  | The internal testing of market systems for your business | [5 empty] | 91% - 99% | Completed (100%) | 81% - 90% | 81% - 90% |  | 81% - 99% | 81% - 90% | 71% - 80% | 75% | Completed (100%) | 51% - 60% | 71% - 80% | 51% - 60% | 81% - 90% | 71% - 80% | 81% - 90% | 61% - 70% | 71% - 80% | 71% - 80% | 91% - 99% | Completed (100%) | 71% - 80% | Not started (0%)
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Completed (100%) | Completed (100%) | 91% - 99% | 71% - 80% |  | Completed (100%) | 81% - 90% | 61% - 70% | 100% | Completed (100%) | 41% - 50% | 91% - 99% | Completed (100%) | 81% - 90% | 71% - 80% | 81% - 90% | 51% - 60% | 71% - 80% | 81% - 99% | 91% - 99% | Completed (100%) | Not started (0%) | Not started (0%)
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Completed (100%) | 51% - 60% | Completed (100%) | 51% - 60% |  | 81% - 90% | 71% - 80% | Not started (0%) | 100% | Completed (100%) | 41% - 50% | 91% - 99% | Completed (100%) | 51% - 60% | 71% - 80% | Not started (0%) | 51% - 60% | 71% - 80% | 21% - 30% | 91% - 99% | Completed (100%) | Not started (0%) | Not started (0%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 81% - 90% | Completed (100%) | 61% - 70% | 71% - 80% | Not started (0%) | 61% - 70% | 51% - 60% | 41% - 50% | 50% | 91% - 99% | 41% - 50% | 71% - 80% | 61% - 70% | 91% - 99% | 71% - 80% | 71% - 80% | 71% - 80% | 41% - 50% | 71% - 80% | 81% - 90% | 51% - 60% | 71% - 80% | Not started (0%)
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | 81% - 90% | 61% - 70% | 41% - 50% | 31% - 40% | Not started (0%) | 41% - 50% | 61% - 70% | 41% - 50% | 25% | 91% - 99% | Not started (0%) | 51% - 60% | 11% - 20% | 71% - 80% | 11% - 20% | Not started (0%) | 41% - 50% | 41% - 50% | Not started (0%) | 21% - 30% | Not started (0%) | 51% - 60% | Not started (0%)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | ActewAGL Retail | AGL Retailer Powerdirect | Alinta Energy | Aurora Energy | Diamond Energy | Energy Australia | Ergon Energy Queensland | ERM Power Retail | M2 Energy Pty Ltd | Macquarie Bank Limited | Mojo Power | Momentum | Next Business Energy | Origin Energy | Pacific Hydro Retail / Tango | People Energy Pty Ltd | Pooled Energy Pty Ltd | Powershop | Red Energy & Lumo Energy | Simply Energy | Stanwell Corporation Limited | Sumo | WINconnect Pty LTD | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Completed | Completed | Completed | Within schedule |  | Within schedule |  | Within schedule | Completed | Completed | Within schedule | Within schedule | Within schedule | Completed | Completed | Within schedule | Within schedule | Completed | Within schedule | Completed | Completed | Completed | At risk
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Completed | Completed | Completed | At risk |  | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Completed |  | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Completed | Completed | At risk |  | Within schedule | Completed | Within schedule | Within schedule | Completed | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule |  | At risk
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | Completed | Within schedule |  | At risk | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | N/A | At risk | Completed | Within schedule |  | Not within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | At risk | Not within schedule | At risk | Within schedule |  | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | At risk | At risk | At risk | Not within schedule | At risk | Within schedule | Within schedule | N/A | At risk | Within schedule | Completed | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Completed | Completed | Completed | Completed |  | Completed | Completed | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Completed | N/A | Completed | Completed |  | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Completed | Completed | Completed | Completed |  | Completed | Completed | Within schedule | N/A | Completed | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | At risk | Completed | N/A | N/A | Completed | Within schedule | Within schedule
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Completed | Completed | Within schedule |  | Completed | Within schedule | Within schedule | Completed | N/A | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | N/A | Completed | Completed | Completed | At risk
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Completed | Within schedule |  | Within schedule | Within schedule | Within schedule | N/A | N/A | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Within schedule | Completed | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule |  | At risk | At risk | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | At risk | At risk | At risk | At risk | At risk | N/A | Within schedule | Within schedule | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | At risk | Completed | Completed | Completed |  | At risk | Within schedule | At risk | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Completed | Completed | At risk | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Not within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Completed | At risk | Within schedule | At risk |  | Within schedule | Within schedule | At risk | Within schedule | Completed | Within schedule | Within schedule | Within schedule | At risk | Not within schedule | At risk | Within schedule | At risk | Within schedule | Completed | Within schedule | Within schedule | At risk
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | At risk | Completed | Within schedule |  | Within schedule | Within schedule | At risk | Within schedule | N/A | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Completed |  | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Completed | Completed | Completed | Completed |  | Completed | Completed | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Completed | Within schedule | At risk
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Completed | Completed | Completed | Within schedule |  | Completed | Completed | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule | At risk
5.3 |  | The internal testing of market systems for your business | [5 empty] | Within schedule | Completed | Within schedule | Within schedule |  | Within schedule | At risk | Within schedule | Within schedule | Completed | Within schedule | At risk | Within schedule | At risk | Not within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Completed | Within schedule | At risk
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Completed | Completed | Within schedule | Within schedule |  | Completed | At risk | Within schedule | Completed | Completed | Within schedule | Within schedule | Within schedule | At risk | Not within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Completed |  | At risk
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Completed | Within schedule | Completed | Within schedule |  | At risk | At risk | Within schedule | Completed | Completed | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Completed |  | At risk
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Completed | Within schedule | Within schedule |  | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | ActewAGL Retail | AGL Retailer Powerdirect | Alinta Energy | Aurora Energy | Diamond Energy | Energy Australia | Ergon Energy Queensland | ERM Power Retail | M2 Energy Pty Ltd | Macquarie Bank Limited | Mojo Power | Momentum | Next Business Energy | Origin Energy | Pacific Hydro Retail / Tango | People Energy Pty Ltd | Pooled Energy Pty Ltd | Powershop | Red Energy & Lumo Energy | Simply Energy | Stanwell Corporation Limited | Sumo | WINconnect Pty LTD | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [8 empty] | A high-level assessment of necessary business operational process and systems changes is near 100% completion noting the detailed assessment supporting the high-level view is still incomplete. | [8 empty] | n/a
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [8 empty] | Detailed requirements have been gathered and vendors engaged to deliver the changes to market messaging. Additional changes to enable all other core operations post 1 December 2017 are being assessed. The aggressive timelines for systems build and testing, combined with contracting and establishment of an MC and the required implementation and testing combined systems is the basis of the 'at risk' status. |  |  | As a retailer, EEQ is heavily reliant on contracted parties being ready from go-live date. | [5 empty] | n/a | All necessary project plans are in place and being managed. Detailed cutover plan finalised and Dress Rehearsal #1 executed. Dress Rehearsal #2 planned 10-13 November. It includes lesson learned and identified improvements from DR#1. | At risk due to process and system delays.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [8 empty] | A detailed assessment of the revised legal and regulatory is significantly developed. In its current form the detailed assessment has provided the basis of Aurora Energy preparedness to date. The assessment continues to be informed by on-going AEMO market procedure consultation. The detailed assessment remains 'at risk' as Aurora Energy has identified a small number of areas in the amended rules that produce a sub-optimal outcome for both customers and industry participants. |  |  | With the election in Qld being called, Government agencies are within the caretaker period. No changes will be made to any safety (or other) legislation / regulation in Qld prior to PoC go-live |  | scheduled and commenced. |  |  | Implementing the required changes for legal and regulatory framework is taking more time than scheduled due to unavailability of suitably qualified resources. | n/a |  | Jurisdictional requirements for safety in relation to remote re-en/de-en in non-Vic jurisdictions unconfirmed. NSW decision to not allow remote re-en/de-en for 18 months; uncertainty of remaining jurisdictions. |  |  |  | Awaiting jurisdictional regulatory confirmation and update - due on 18 October
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [8 empty] | Aurora Energy has considered the wider and indirect regulatory implications of metering competition on business-as-usual activities (particularly given the existing regulatory framework was developed in the context of type 6 metering). |  | Progress has been made however late jurisdictional changes have created some schedule risks | EEQ is anticipating finalisation of changes to Metrology Part A following the November COAG Energy Council meeting. |  | not yet scheduled. |  |  |  | n/a | Policy changes/decisions still being derived | Vic Government decision on PoC and timing of regulatory changes to reflect the decision not to proceed with PoC. Potential variance of process by QLD DNSP not accepting Service Orders from an MC. |  |  |  | Jurisdictional regulatory uncertainties remain |  |  |  | Still wating on confirmation on VIC guidance on treatment of embedded network metering.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | All MC contracts received and in review/negotiation. Only 1 MC accredited to date. | Contract delivery is behind revised schedule. | MC Arrangements still to be signed | Activity is well progressed customers and vendors as part of POC implementation. The major challenge is to finalise contractual arrangements with a Metering Coordinator, which will have to establish metering service capability in Tasmania where it currently does not exist. |  |  | Finalisation of commercial and peformance agreement with commercial MC is substantially complete. | The number of contracts and counter-parties put this item at risk. | in progress |  |  | Contractual agreements for MC and ENM are in progress. PoC changes will need to be reflected in the collaterals of the organisations so the same message is available to customers | NBE is still waiting to receive and review contractual arrangements with MCs and MDPs. This places signifiant risk to the business with short timeframes to review and negotiate contracts before 1 December 2017. | Overall strategy has been developed and endorsed. Generic Meter provider contract drafted for new providers and contracts in play for current providers. | Updated customer contract material drafted and under review. MC agreements being finalised, however concerns exist if any existing MPs for C&I customers do not receive their MC accreditation. |  | MC engagement still being reviewed and clarified. |  | Internal management of this item | There is an external dependency where AEMO's MC registration might result in a rejection of some potential MC applications which poses a greater risk on Retailers.
2.4 |  | An assessment of the required accreditation and registration activities | [8 empty] | Aurora Energy has received accreditation for using the B2B e-hub. | [8 empty] | n/a | Request for registration/accreditation submitted as per AEMO deadlines. Awaiting final feedback from AEMO. | Despite 5.2, B2B accreditation is still required and for that purpose we still believe we will be in a position to complete in the required timeframe. |  | In Progress |  | Internal management of this item
2.5 |  | The fulfilment of accreditation and registration obligations | [6 empty] | B2B accreditation completed |  | As per 2.4 |  |  | Email reveived from AEMO confirming EEQ's registration. | [5 empty] | Scheduled for later in 2017. | Planning and preparation in progress | Per 5.2 and the limited timeframes for internal testing and commencement of Market Trial. |  | Relying on external providers for MC and E Hub accreditation. |  | Internal management of this item
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [8 empty] | This is underway and will be finalised following with the detailed assessment of operational and systems changes. |  |  | FTE impact analysis complete. Go-live support is currently being finalised. |  | No resource changes at this time |  |  |  |  | Forecasted workload planning completed for key business areas and socialised to inform recruitment decisions. |  |  |  |  | Internal management of this item
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [8 empty] | The recruitment of specialist human resources to cater for the rule change is progressing as the need to fill key project roles arises. A key challenge is the availability of internal business subject matter experts to assist in change management. Further, total program resources represent a significant portion of Aurora Energy's total staff resource pool, which intensifies resourcing risk. |  |  | Transition Support Team recruitment significantly progressed. | [5 empty] | Procurement of additonal resources complete. | Recruitment for long lead time positions commenced and on track. |  |  |  | Powershop may look to hire temp's to assist with any remediation work that may be required post go live. | Internal management of this item
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Training delivery in progress. |  |  | Training requirements are currently being assessed as part of the business process, change management and system planning. |  | Training development at risk due to delivery of key processes | Face to face training has commenced. |  | Waiting on testing environment to be released, staff have been briefed and aware of industry change |  |  |  | Comprehensive training scheduled for November 2017. | Training requirements and resourcing determined and magnitude of change is understood, change planning started behind schedule. Learning curriculum now finalised and training material development commenced and on track against revised deadlines. | At risk due to 5.2/4.1. |  | Training is being rolled out by providers. | A majority of the changes will not effect front-line operational staff from a workflow perspective due to the processes being embedded into the functionality. But the changes that will impact workflow process still need to be trained. | Internal management of this item
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Awaiting jurisdictional positions on Remote Re-Energisation/De-Energisation. Lack of clarification and certainty has delayed finalising processes and created uncertainty around increased cost of meter reads, by MC's, to customers. |  |  |  |  | Transition and contingency planning have driven some late changes. | End to end process walk through substantially complete. | The scope of change puts this item at risk. | commenced and in schedule | [5 empty] | Business process impact analysis complete. Some non-essential processes to be finalised post 1 Dec. | [7 empty] | In discussion with AEMO, we have concerns about the ENM discovery process in the MSATS market design.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Business Processes completed and Process Owners allocated. Validation continues to be done with MC's (depending on their maturity). Now under formal change control | Completing all work instruction updates has taken longer than planned |  | Future business processes have now been developed using the details from Work Package 1, 2 and 3, as well as the B2B procedures. |  |  | Preparation of Work Instructions substantially complete, some supporting dcoumentation being prepared. | The scope of change puts this item at risk. | commenced and in schedule |  |  |  |  | Business process design mainly completed with 3-4 weeks of delays against baseline plan. | No longer within schedule due to system delay per 5.2 and 4.1. Review & incorporating DB and MC specific variations in progress. |  | Dependent on 4.3 below
4.3 |  | The validation of business processes during industry testing | [5 empty] | All key business processes validated in Industry/Bi-lateral testing - additional bi-lateral testing in progress this week. | Not all processes tested due to participant issues / MC variations |  | UAT has started and the second round industry testing is completed. Aurora Energy is now in the 3rd Round of industry testing and is on track to complete this by 3rd November. |  |  | Treatment of isolated (non PoC) areas in Qld is currently being outworked with our industry partners to determine how service orders and processes will be managed within the new B2B environment. | Validation of business processes will continue during bilateral testing. | [5 empty] | Industry Testing underway with Cycle #3 extended till 9/11. An high number of end-to-end Test Scenarios is not complete, posing a risk on the overall Industry Testing. | At risk due to 5.2/4.1. |  | External billing provider upgrading software for Power of Choice. Information lag from MC.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [13 empty] | Testing completed - Readying for predeployment |  |  |  |  | Mass Market Design activities complete and Large Customers design in progress. Change requests being assessed and planned. | In addition to 4.1, identification of any interim system changes required to be compliant on 1 Dec drafted. | [7 empty] | Confirmation required on proprosed process for ENM discovery in MSATS.
5.2 |  | The development and build of appropriate market systems for your business | [8 empty] | Systems development is on track and it is noted that a code freeze is planned from 15th November |  |  | Build complete with testing continuing. Several change requests being assessed. |  | Testing completed - Readying for predeployment |  |  |  | Being managed by external vendors. | Build progressing on track, including the development of approved change requests. | Updated to 'Not within Schedule' given delays in system changes. Dependent on completed development and implementation of B2B Translation Tool, and any changes per 5.1. Uncertainty regarding B2B Errata process and timelines for potential schema updates.
5.3 |  | The internal testing of market systems for your business | [5 empty] | Last week of regression testing in progress. |  |  | Aurora Energy is progressing through System Test and has started UAT and Industry test activities. |  |  | SIT Cycle 4 complete. UAT cycle 2 complete. Industry Testing Cycle 2 incomplete. UAT cycle 3 and Industry Testing Cycle 3 have substanitally recovered to schedule, with some contingency available if required. |  | Testing completed - Readying for predeployment |  |  | Execution of Market trials and UAT,regression and integration testing has been in 2 different pre-prod environments due to the late delivery of the integrated system,code merge is also in the mix with regression testing being executed twice | Continuing throughout November. | Internal Testing is completed for core solution. Outstanding internal testing re. change requests/variations as outcome of process review and solution enhancements. | As per 5.2 |  | Dependent on 4.3 above
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [8 empty] | Aurora Energy is currently moving through AEMO's third round of testing. eHub connectivity has been tested and established and B2B accreditation testing has been Completed. Some further testing with external participant will continue into November. |  |  | SIT Cycle 4 complete. UAT cycle 2 complete. Industry Testing Cycle 2 incomplete. UAT cycle 3 and Industry Testing Cycle 3 have substanitally recovered to schedule, with some contingency available if required. | [5 empty] | Complete. | Industry Testing progressing through Cycle #2 behind schedule. | As per 5.2 Limited scope of Cycle 3 due to time constraints. |  |  |  |  | Whilst Simply Energy's testing of market system interfaces is progressig extremely well (as evident from the status reports issues by AEMO), there are some issues identified with key participants including a number of Distributors, where the overall status of Industry Testing report shows "Planned" vs "Actual" testing has a signifact variance. As a result, our testing is impacted because the end to end scenario testing is taking longer than expected. If the pattern continues, there is no further window for testing and some participants might go-live with major defects.
5.5 |  | The validation of performance of market systems during industry testing | [8 empty] | Performance testing is underway |  | Completion is dependeant on other market participants | As noted above. | Performance testing will occur separately to industry testing. |  |  |  |  | Complete. | Batch performance and sizing in progress and on track. | As per 5.2 |  |  |  | Not able to validate performance in production environments.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Initial Dress Rehearsal conducted, preparing for Industry DR. |  |  | A Transition Plan will be completed once commercial agreements with Metering Coordinator(s) are finalised. Aurora Energy is progressing discussions with TasNetworks regarding transition and cutover planning. We are now looking to include our Metering Co Ordinator in these meetings. |  | EA's planning is progressing however it is dependent on industry transition and cut-over planning. | Participating in simulated DR2 with AEMO week commencing 13 November. DR1 successfully completed. | [5 empty] | Schedule to occur later in 2017. | Deployment Strategy confirmed. Detailed Cutover Plan finalised and "tested" during DR#1. | Finalisation of detailed cutover plan in progress. |  |  |  | Transition and cut over working group has finalised document. Both brand run sheets are completed. Awaiting further information on the jurisdictional regulatory changes that may impact these outcomes.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [6 empty] | DR1 completed. DR2 planned mid November |  | Data Cleansing completed and BCT request has been sent to AEMO, . |  |  | Data migration BCT list submitted to AEMO. Discussion underway with AEMO relating to exemptions. | [5 empty] | Schedule to occur later in 2017. | Business Transition planning started and on track. Data conversion for Meter Standing Data (MC/ENM role, NMI/Meter Register Status) across industry participants is still unknown and therefore impacting our Build / Test activities; AEMO's position to leave to participants to update data may lead to substantial issues with integrity of information and risk of performance if all participants have to update MSATS at the same time during cutover.
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | ActewAGL Retail | AGL Retailer Powerdirect | Alinta Energy | Aurora Energy | Diamond Energy | Energy Australia | Ergon Energy Queensland | ERM Power Retail | M2 Energy Pty Ltd | Macquarie Bank Limited | Mojo Power | Momentum | Next Business Energy | Origin Energy | Pacific Hydro Retail / Tango | People Energy Pty Ltd | Pooled Energy Pty Ltd | Powershop | Red Energy & Lumo Energy | Simply Energy | Stanwell Corporation Limited | Sumo | WINconnect Pty LTD | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [8 empty] | Aurora Energy has implemented a program of work to interpret and implement the POC reforms, within the context of the timeframe and procedural uncertainty. | [8 empty] | n/a
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [8 empty] | Aurora Energy has implemented a program of work to effectively and efficiently work towards market compliance. |  |  | EEQ continues to work with delivery partners in go-live preparations | [5 empty] | n/a
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Meeting with ACT Government conducted- no expected barriers at this point. NSW Govt has proven to be more challenging to engage. | [5 empty] | EEQ will continue engagement with DEWS and the ESO to facilitate agreement on a national framework for remote re-energisation. |  |  |  |  | External parties onboarded to progess towards completion | n/a |  | Monitor jurisdictional saftey discussion.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Internal documents related to Cth legislation are listed by branch and business unit. Dates for update and review have been set. Code of Practice drafted for Smart Metering and in review. |  |  | Aurora Energy continues to liaise with the Tasmania Government and WorkSafe Tasmanian to identify jurisdictional requirements that require amendment to facilitate metering competition. |  |  | Some finalisation of internal policies based on go-live capabilities of EEQ and partners still occuring. | [5 empty] | n/a |  | Closely review and monitor Vic Government's progress of the OIC. Discussions with DBs ongoing.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [6 empty] | MC contracts submitted and now in review. Sale process also underway. |  | Aurora Energy's procurement process for securing a Metering Coordinator for small customers is at a progressed state with a preferred MC selected but not yet contracted. |  |  | Finalisation is also awaiting AEMO registration of EEQ's proposed commercial MC. |  |  |  |  | Increase level of engagement with Marketing division to finalise before the Go Live dtae | Adopting of staged approach for new connections and adds and alts - still awaiting confirmation that staged approach includes adds and alts. | Origin has onboarded additional Business and Technology resources |  |  | Attempting to clarify with MC |  |  | AEMO to provide more information on pending MC applications and provide transparency on their registration statuses. AEMO to provide a list of registerd MCs by early November so Retailers can take necessary actions in order to comply with the new set of Rules.
2.4 |  | An assessment of the required accreditation and registration activities | [17 empty] | n/a |  | Dependent on AEMO delivery of B2B Translation Tool, and our implementation and testing. Draft B2B Accreditation Guide under review.
2.5 |  | The fulfilment of accreditation and registration obligations | [18 empty] | Origin has onboarded additional Business and Technology resources
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [17 empty] | n/a
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [8 empty] | Aurora Energy has established the core group of its Testing team and will continue to expand its testing resources over the coming months. | [8 empty] | n/a
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [11 empty] | Broader staff training will continue to occur beyond go-live. | [6 empty] | Confirmation of some market transactions and treatments still pending which may impact training timelines given constraints in place. | Reallocation of resources to cover this activity. |  | Dependent on 4.3 below
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [10 empty] | Added additional capacity to process development. | Some manual work arounds will be in place for go-live with more optomised processes to be developed beyond go-live.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [6 empty] | Added resources. Extended timing to complete to late November. |  |  |  |  | Refere to below comment. | [6 empty] | Remaining outstanding clarifications re. Business Process design planned to be addressed by mid-Nov. | Reallocation of resources to cover this activity.
4.3 |  | The validation of business processes during industry testing | [6 empty] | Continue testing key processes throughout November |  |  |  |  | EEQ and its industry partner are continuing to agree approach to delivery. | [6 empty] | Outstanding Test Scenarios at the end of Cycle #3 will be addressed as part of bi-lateral testing. |  |  | Providers are working overtime to achieve testing requirements.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [19 empty] | Assisting AEMO with testing of B2B Translation Tool. Reviewed draft Vic OIC.
5.2 |  | The development and build of appropriate market systems for your business | [19 empty] | Closely monitoring IEC/B2BWG/ASWG discussions and potential for additional B2B Errata/schema changes prior to 1 Dec.
5.3 |  | The internal testing of market systems for your business | [11 empty] | Contingency to use additional testing days 4-8th November which should enable completion of testing. |  |  |  |  | Planning to work during non-business days to progress and also as soon as the MSATS pre-prod environment becomes available after the execution of the industry dress rehearsal |  | Complete internal testing by Fri 17/11 as per revised baseline. | As per 5.2
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [11 empty] | EEQ is working with industry partners to align understanding of new market procedures and facilitate throughput of outstanding industry tests which are all in-flight. | [7 empty] | As per 5.2 Bilateral testing to cover scenarios not sufficiently tested in Market Trial. |  |  |  |  | We understand that AEMO has extended cycle 3 testing window to complete by 9th November 2017 and we will continue to bilaterally test with the market participants who has been unable to fulfil the exit criteria of Market Trial. We also recommend AEMO to work closely with the market participants for a successful go-live market operatability.
5.5 |  | The validation of performance of market systems during industry testing | [11 empty] | As noted above. | [7 empty] | As per 5.2
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [8 empty] | Aurora Energy transition and cutover preparations are being supported by its attendance at AEMO cutover and planning workshops.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 90%
91% - 99%
Completed (100%)
N/A
81% - 99%
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Retailer Participation
References:
[10 empty] | AEMO | http://www.aemo.com.au/Electricity/National-Electricity-Market-NEM/Participant-information/Current-participants/Current-registration-and-exemption-lists
[10 empty] | AER | https://www.aer.gov.au/retail-markets/authorisations/public-register-of-authorised-retailers-and-authorisation-applications
[10 empty] | ESC | http://www.esc.vic.gov.au/project/energy/2075-licensing/
Retailer | On Nov 2017 Report? | On Oct 2017 Report? | On Sep 2017 Report? | On Aug 2017 Report? | On Jul 2017 Report? | On Jun 2017 Report? | On May 2017 Report? | On April 2017 Report? | On March 2017 Report?
1st Energy Pty Ltd | No | No | No | No | No | No | No | No | No
ActewAGL Retail | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
AGL | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Alinta Energy | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Aurora Energy | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Blue NRG Pty Ltd | No | No | No | No | No | No | No | No | No
Click Energy Pty Ltd | No | No | No | No | No | No | No | No | No
Covau Pty Limited | No | No | No | No | No | No | No | No | No
COzero Energy Retail Pty Ltd | No | No | No | No | No | No | No | No | No
Diamond Energy Pty Ltd | Yes | No | No | No | No | No | No | No | No
Energy Locals Pty Ltd | No | No | Yes (using August report) | Yes | No | No | No | No | No
EnergyAustralia | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Enova Energy Pty Ltd | No | No | No | No | No | No | No | No | No
Ergon Energy Queensland (retail) | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes (using March report) | Yes
ERM Power Retail Pty Ltd | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | No
Globird Energy Pty Ltd | No | No | No | No | No | No | No | No | No
Lumo Energy (reporting with Red Energy) | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
M2 Energy Pty Ltd | Yes | Yes | Yes | Yes | Yes | Yes (using May report) | Yes | Yes | Yes
Macquarie Bank Limited | Yes | Yes | Yes | Yes | Yes | Yes | No | No | No
Mojo Power Pty Ltd | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Momentum Energy | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Next Business Energy Pty Ltd | Yes | Yes | Yes | Yes | Yes | No | No | No | No
Online Power and Gas Pty Ltd | No | No | No | No | No | No | No | No | No
Onsite Energy Solutions Pty Ltd | No | No | No | No | No | No | No | No | No
Origin Energy | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Pacific Hydro / Tango | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
People Energy Pty Ltd | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Pooled Energy Pty Ltd | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No
Powerdirect Pty Ltd (reporting with AGL) | Yes | Yes | Yes | Yes | Yes | Yes | No | No | No
Powershop Australia Pty Limited | Yes | Yes (using Sep report) | Yes | Yes (using July report) | Yes | No | Yes (using April report) | Yes | No
Progressive Green Pty Ltd | No | No | No | No | No | No | No | No | No
Qenergy Limited | No | No | No | No | No | No | No | No | No
Red Energy | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Sanctuary Energy Pty Ltd | No | No | No | No | No | No | No | No | No
Simply Energy | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
SparQ Pty Ltd (Sumo Power) | Yes | Yes (using Sep report) | Yes | Yes | Yes (using June report) | Yes | No | No | No
Stanwell Corporation Limited (Stanwell Energy) | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No
WINenergy Pty Ltd (WINenergy) | Yes (using Oct report) | Yes | Yes | Yes | Yes | No | No | No | No

## Distributor Reports
| 2017-11-06 |  |  | Distributor Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Industry risk rating | Overall project comment | [6 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| ActewAGL Distribution (AAD) | Within schedule | Medium |  | AAD has completed internal testing with industry and bilateral testing continuing. Rollout plans and schedules are now being finalised. Business plans are being implemented and internal training of staff is underway. Total progress is estimated at 86%. | [12 empty] | AAD has submitted the required information for accreditation as the initial MC for type 5, 6 and 7 metering installations and is responding to additional AEMO queries. Type 3-4 metering accreditation has now been received and AAD is continuing work on systems development to maintain compliance with the PoC reforms. Registration as an MC for these latter meter types has been submitted. While industry testing has revealed no significant issues to date, AAD has reservations about the level of participation to date.
| Ausgrid DB | At risk | Medium | Medium | Awaiting resolution of NSW legislative changes in order to finalise staged transitional process requirements. Also awaiting finalisation of AEMO MC registration. Internal system testing continues, however, timeframes remain tight. | [6 empty] | [Refer to overall project comment]
| AusNet Services | Within schedule | Low | Medium | On track for 1st December cutover and go-live. Other participant readiness across the NEM remains a risk, the majority of contributing concerns are not relevant within Victoria given metering exclusivity. | [6 empty] | Refer to overall comment.
| CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | At risk | Medium |  | CitiPower/Powercor is continuing to progress its internal and external test phase and defect rectification process for 1 December 2017 go-live. Additional build is being undertaken to account for recent B2B errata changes published by the IEC. Go-live dress rehearsal activities are being undertaken and transition/deployment planning is complete. | [6 empty] | The Victorian Government has gazetted Orders in Council that require distributors to continue to install remotely read interval metering after 1 December 2017 compliant with the Victorian AMI functionality and service levels specifications and that existing and new/replacement AMI metering will be continue to be classified as Type 5 metering.
| Endeavour Energy | Within schedule | Medium | Medium | A project risk is the implementation of system and procedural changes to comply with the B2B procedures, which require significant system and process changes over a period of only 6-7 months to design, develop and test. Early testing indicates that the short timeframe is having an impact on the quality of our vendor's delivery. We are working closely with our vendors to prioritise and manage the quality. A key dependency for our PoC project, which is technical currency of our core system, has been successfully implemented. Another project risk is that different interpretations from each market participant of the Rules, procedures and jurisdictional obligations may result in ineffective or unworkable processes between businesses. To mitigate this we are actively engaging with retailers and metering service providers to foster an open dialog on managing key processes. These engagements are proving beneficial as they have highlighted differences in our assumptions and approaches to some of the processes at an early point of the project. To help industry and to provide us better confidence that our solution will work effectively with other market participants, we are participating in the industry testing and additional bi-lateral testing with other participants. We are also actively participating in various industry working groups to ensure an effective transition and cutover to the new Rules with minimal customer impacts. To assist the industry mitigate go-live risks that can impact on the customers, we are participating in the Staged Approach. | [6 empty] | [Refer to overall project comment] | [5 empty] | This report is for Endeavour Energy as at 31 October 2017. Endeavour Energy will be operating as a LNSP, and as the initial MC, MP and MDP for type 5, 6 & 7 metering installations from 1 December 2017. Endeavour Energy have implemented a project team to manage the impacts of Power of Choice. The activities for the Market Systems testing and cutover are dependent on the development and build of the appropriate market system which is currently at risk.
| Energex Ltd. & Ergon Energy Corporation Ltd. | Within schedule | Medium | Medium | The Distribution project is tracking to its intended schedule and is confident in meeting 1 December 2017 compliance requirements. The project is currently undertaking User Acceptance Testing in priority order. Industry Testing concluded on 3 November 2017 without the identification of any significant issues. A small number of defects, differing interpretations of rules and their implementation were found and resolved. Flaws recognised within the Industry Test process meant the inability to recognise all issues during the testing cycles. As such these issues are likely to be identified Post Go Live. The project has increased its resourcing to support this and hopes that other businesses do the same. Market registration and the required accreditation activates are now complete. | [6 empty] | The Distribution project is tracking to its intended schedule and is confident in meeting 1 December 2017 compliance requirements. The project is currently undertaking User Acceptance Testing in priority order.
| Essential Energy | At risk | Medium | High | Essential Energy's PoC program is progressing, with system changes on the critical path to deliver compliance by 1 December 2017. The program has delivered all systems changes and completed industry testing - completing all transactions that we received requests for. A number of business efficiency system changes have been deferred for delivery post 1 December. A significant issue exists with Essential Energy's Initial MC registration, this is being worked through with AEMO. | [6 empty] | [Distributor]:Risk downgraded to medium. Internal testing complete. Market testing complete. Some business efficiency items deferred for delivery post 1 December [Meter Data Provider]: Risk rating is classified as moderate for systems changes to support amended B2B framework, including to receive and process meter exchange information to enable timely publishing of final readings for Type 5 & 6 meters. | [5 empty] | Essential Energy will be an Initial MC, MDP and MP for Type 5 and 6 meter installations connected as at 1 December 2017. Essential Energy is actively participating in AEMO industry groups and NSW jurisdictional workshops associated with Power of Choice.
| Jemena Electricity Network | Within schedule | Low | High | Jemena's preparations are on track for go-live, however the post implementation risk to customer experience is rated HIGH due to: 1. Limited industry e2e testing scope with Retailers - only 9% of e2e test scope was executed with Retailer partners. In addition, the testing experience demonstrated the knowledge gap industry has with the operations of the new PoC processes; 2. We have no visibility of which retailers have achieved e-hub accreditation; and 3. Industry performance testing was not performed; 4. Industry testing of the LVI & TT contingency solution was not performed; and 5. The lack of harmonisation across the electricity market procedures will cause retailers considerable confusion and a high level of error both in process and in training people in call centres etc. As a result of these industry program limitations, Jemena is now preparing contingency in order to mitigate customer experience impact during the 'Transition period' from 3 Dec to end March 18, particularly during the period 3 December - 15 December where we receive and execute the highest volumes of customer new connections, additions, alterations, abolishments, re-energistations and de-energisations. | [6 empty] | All activities within Jemena's control are on track for go-live.
| SA Power Networks | At risk | Medium | N/A | SAPN is still facing significant project challenges particularly with the development/ defect resolution of the market system. At this point we still believe that we will be in a position to achieve minimum market compliance. Project team is working closely with the impacted Business Units, including CitiPower/PowerCor, to ensure manual work arounds are in place especially during the transition period. | [6 empty] | See overall project status comment
| TasNetworks | Within schedule | Medium | Medium | TasNetworks will be ready for the 1st December 2017. TasNetworks is taking a risk based approach on the delivery of the Market Systems functionality which may have a flow on effect to market processes, training activities and potentially other market participants. TasNetworks has now been asked to undertake a number of transitional activities which will impact readiness. Some program activities will need to be completed post 1st December.
| United Energy | Within schedule | Low | Medium | Preparations are on track. UE participated in all cycles of market trials and bi-lateral testing , with generally positive results and no open defects, although noting that not all retailers participated. The amber industry risk rating reflects general concerns about industry readiness and the possible operational impact of market disruption after go-live. | [12 empty] | Key concerns regarding UE (and industry) readiness are as follows: 1) UE compliance with the ENM rules and ring-fencing is dependent on Embedded Network Managers being accredited, assigned and ready to operate by 1 Dec 2017. This appears to be at risk. UE intends to progressively exit its role as MC, MP and MDP for a small number of second-tier customers by 1 Dec 2018 in accordance with the Victorian deferral Orders, however this requires the current FRMPs to take action to appoint a new MC and for access to the metering to be provided to allow a new MP to replace existing metering. 2) UE is concerned that the complexity and scale of changes may ultimately lead to negative impacts on consumers. Strong focus will be required to ensure that connections and supply processes are clear, and industry has a uniform, efficient and reliable approach so the reform is seamless to customers. It is important that participants that were unable to complete industry testing during the formal cycles continue to test on a bi-lateral basis during November 2017.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| ActewAGL Distribution (AAD) | Within schedule | Medium
| Ausgrid DB |  |  | At risk | Medium
| AusNet Services | [10 empty] | Within schedule | Medium
| CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | [10 empty] | At risk | Medium
| Endeavour Energy |  |  | Within schedule | Medium
| Energex Ltd. & Ergon Energy Corporation Ltd. |  |  |  |  | Within schedule | Medium
| Essential Energy |  |  | At risk | Medium
| Jemena Electricity Network | [10 empty] | Within schedule | Low
| SA Power Networks | [6 empty] | At risk | Medium
| TasNetworks | [8 empty] | At risk | Medium
| United Energy | [10 empty] | Within schedule | Low
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid DB | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Network | SA Power Networks | TasNetworks | United Energy
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | 91% - 99% | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%)
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 81% - 99% | 81% - 99% | Completed (100%) | Completed (100%) | 91% - 99% | Completed (100%) | 81% - 90% | Completed (100%) | Completed (100%) | 81% - 99% | Completed (100%)
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 71% - 80% | 81% - 99% | Completed (100%) | Completed (100%) | 81% - 90% | 91% - 99% | Completed (100%) | Completed (100%) | Completed (100%) | 81% - 99% | Completed (100%)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 81% - 99% | 61% - 70% | 91% - 99% | Completed (100%) | 51% - 60% | 81% - 90% | 81% - 90% | Completed (100%) | 81% - 90% | 71% - 80% | Completed (100%)
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 81% - 99% | 81% - 90% | Completed (100%) | 91% - 99% | 81% - 90% | 81% - 90% | 71% - 80% | Completed (100%) | 71% - 80% | 81% - 99% | Completed (100%)
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 81% - 99% | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%)
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 81% - 99% | 91% - 99% | 81% - 90% | 91% - 99% | Completed (100%) | 91% - 99% | 71% - 80% | Completed (100%) | 81% - 90% | 81% - 99% | Completed (100%)
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 71% - 80% | 81% - 90% | Completed (100%) | Completed (100%) | 81% - 90% | Completed (100%) | Completed (100%) | Completed (100%) | 91% - 99% | 81% - 99% | Completed (100%)
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 71% - 80% | 81% - 90% | Completed (100%) | N/A | 81% - 90% | Completed (100%) | Completed (100%) | N/A | N/A | 71% - 80% | Completed (100%)
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | 71% - 80% | 71% - 80% | 91% - 99% | 71% - 80% | 21% - 30% | 71% - 80% | 51% - 60% | 91% - 99% | 51% - 60% | 51% - 60% | 81% - 90%
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 71% - 80% | 71% - 80% | Completed (100%) | Completed (100%) | 91% - 99% | 91% - 99% | Completed (100%) | Completed (100%) | Completed (100%) | 71% - 80% | Completed (100%)
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 71% - 80% | 71% - 80% | Completed (100%) | Completed (100%) | 91% - 99% | 91% - 99% | Completed (100%) | Completed (100%) | 91% - 99% | 61% - 70% | Completed (100%)
4.3 |  | The validation of business processes during industry testing | [5 empty] | 71% - 80% | 71% - 80% | 81% - 90% | 81% - 90% | 41% - 50% | 81% - 90% | Completed (100%) | Completed (100%) | 61% - 70% | 61% - 70% | 91% - 99%
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 81% - 99% | Completed (100%) | Completed (100%) | Completed (100%) | 81% - 90% | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%)
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 81% - 99% | Completed (100%) | 91% - 99% | 91% - 99% | 81% - 90% | 91% - 99% | Completed (100%) | Completed (100%) | 81% - 90% | 71% - 80% | Completed (100%)
5.3 |  | The internal testing of market systems for your business | [5 empty] | 71% - 80% | 61% - 70% | 81% - 90% | 81% - 90% | 91% - 99% | 81% - 90% | Completed (100%) | Completed (100%) | 71% - 80% | 71% - 80% | 91% - 99%
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | 71% - 80% | 91% - 99% | 81% - 90% | 61% - 70% | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | 91% - 99% | 61% - 70% | 91% - 99%
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | 71% - 80% | 91% - 99% | 81% - 90% | Completed (100%) | 21% - 30% | Completed (100%) | Completed (100%) | N/A | 91% - 99% | 61% - 70% | Completed (100%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 71% - 80% | 81% - 99% | 91% - 99% | Completed (100%) | 41% - 50% | 81% - 90% | 51% - 60% | Completed (100%) | 91% - 99% | 61% - 70% | Completed (100%)
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | 21% - 30% | 41% - 50% | 41% - 50% | 61% - 70% | 41% - 50% | 81% - 90% | Not started (0%) | 91% - 99% | 51% - 60% | 61% - 70% | Completed (100%)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid DB | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Network | SA Power Networks | TasNetworks | United Energy
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | Completed | Completed | Within schedule | Completed | Completed | Completed | Completed | Within schedule | Completed
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule | Completed | Completed | Within schedule | Completed | Within schedule | Completed | Completed | At risk | Completed
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | At risk | Completed |  | Within schedule | Within schedule | Completed | Completed | Completed | Within schedule | Completed
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Completed | Within schedule | At risk | Completed
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Completed
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Within schedule | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Within schedule | Completed
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | At risk | Within schedule | Within schedule | Completed | Completed | At risk | Completed | Within schedule | Within schedule | Completed
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Completed | Completed | Within schedule | Completed | Completed | Completed | Within schedule | Within schedule | Completed
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Completed | N/A | Within schedule | Completed | Completed | N/A | N/A | Within schedule | Completed
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Within schedule | Within schedule | Completed | Completed | Within schedule | Within schedule | Completed | Completed | Completed | At risk | Completed
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | Within schedule | Completed | Completed | Within schedule | Within schedule | Completed | Completed | Within schedule | At risk | Completed
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | N/A | Completed | Completed | Within schedule | At risk | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Within schedule | Completed | Completed | Completed | At risk | Completed | Completed | Completed | Completed | Within schedule | Completed
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | Completed | Within schedule | At risk | At risk | Within schedule | Completed | Completed | At risk | At risk | Completed
5.3 |  | The internal testing of market systems for your business | [5 empty] | At risk | At risk | Within schedule | At risk | At risk | At risk | Completed | Completed | At risk | At risk | Within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | At risk | Within schedule | Within schedule | At risk | Completed | Completed | Completed | Completed | Within schedule | At risk | At risk
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | At risk | Within schedule | At Risk | Completed | Within schedule | N/A | Completed | N/A | Within schedule | At risk | Completed
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Completed | Within schedule | At risk | Completed
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Completed
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid DB | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Network | SA Power Networks | TasNetworks | United Energy
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | The high level impact assessment is complete. Some gaps may be identified as part of the more detailed program of works to be carried out in the period through to December 2017. | Impact assessment undertaken in line with staged transitional process |  |  |  | Organisational Impact Assessment is complete. |  | n/a | Completed
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Deployment plans are being finalised in preparation for dress rehearsal #2 in accordance with industry plans. | Planning for final elements of staged transitional process underway |  |  |  | The Business Readiness Framework has been finalised and has received formal approval. |  | n/a | Completed ( July 2017) | TasNetworks is facing some challenges in completing all Market Systems changes and testing before 1 December. TasNetworks is taking a risk based approach on the delivery of the Market Systems functionality
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | AAD is finalising model standing offers | No jurisdictional safety requirements in place yet. Awaiting NSW legislative changes for staged transitional process. |  |  |  | As issues are identified in UAT and Industry Test their Legal and Regulatory impacts are being investigated. |  | n/a | Completed | Initial MC (Type 6) T&C's finalised and provided to Retailers.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | All legal frameworks have been finalised with the exception of the model standing offers. Final review of initial MC contracts is underway in response to retailer feedback | In progress. No jurisdictional safety requirements in place yet. |  |  |  | Ongoing activity - the project is working with the internal regulatory team to ensure all regulatory requirements are met. |  | n/a | Pending final approval and publication of all internal policies. | Late change requests to transitional activities by retailers have created extra work
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | As above. | Initial MC T&Cs now issued. Ring-fenced service agreements in progress. |  | MC standard agreements have been published in accordance with Rules and Victorian Order in Council requirements. Updates to Model standing offers are in progress |  | Ongoing activity - amendments under consideration by each contract owner, updates will be made using existing procurement and contractual processes. Assessment of new agreements/contracts also ongoing. |  | n/a | Work in progress with the business. | Initial MC (Type 6) T&C's finalised and provided to Retailers.
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | AAD is finalising repsonses to recent AEMO clarification questions. | Appropriate applications have been submitted |  |  |  | All of the required Accreditation and registration documentation and the associated activities have been completed and confirmation of accreditation for eHub and registration for MC has been received from AEMO. |  | n/a | Completed
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | As above. | Appropriate applications have been submitted - registration not yet achieved |  | CitiPower/Powercor have received their respective Metering Coordinator registrations from AEMO. eHub accreditation activities are more than 95% complete |  | The project has developed an updated Standard Ts&Cs document to be re-issued to the market based on retailer feedback. This is in the approval stage. | Signficant issue with Essential Energy's Intial MC registration | n/a | B2B Accreditation in final stages and Awaiting final MC Registration Approval. |  | All accreditation and registration obligations met. Initial MC contract issued.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | AAD is awaiting clarification on the number of meters due to be installed during the transition period in order to finalise field staff requirements. All other requirements have been met or are being recruited for. | Planning for final elements of staged transitional process underway |  |  |  | Ongoing activity - Impact assessment is approved. |  | n/a | Work in progress with the business | TasNetworks is facing some challenges in completing all Market Systems changes and testing before 1 December. TasNetworks is taking a risk based approach on the delivery of the Market Systems functionality
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | See above. | Planning for final elements of staged transitional process underway | [5 empty] | n/a | Not Applicable | Late change requests to transitional activities by retailers have created extra work
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | AAD is training internal staff. External training to contractors and other third parties is planned for the final week of November and early December. | Operational staff participating in system testing & training. Contact centre scripting & training underway. |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | Training is progressing to plan across the impacted groups within the business |  | n/a | Finalisation of training content (dependent on defect resolution). Training scheduled for mid to late November. | Late change requests to transitional activities by retailers have created extra work | Development complete. Delivery underway.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Rollout of new processes is underway. | Business process development being finalised |  |  |  | Any business process changes being identified as part of UAT or training are being documented and rolled out to the businesses. |  | n/a | Completed (April 2017) | Late change requests to transitional activities by retailers have created extra work
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Final approval process is underway. | Planning for final elements of staged transitional process + other processes underway |  |  |  | Any business process changes being identified as part of UAT or training are being documented and rolled out to the businesses. |  | n/a | Finalisation of all business processes. | To-be business processes well understood, intend to document the processes toward the backend of the project for approval.
4.3 |  | The validation of business processes during industry testing | [5 empty] | Processes relevant to industry testing completed to date have been validated. | Cycle 1 & 2 of industry testing successfully completed. |  | Note: In line with CitiPower/Powercor program delivery schedule. | See above comment | Industry Test has concluded. Analysis is underway of any tests no completed during this cycle as these represent a risk that the business process/systems have not been fully tested. At the end of that review, the project will organise further bi-lateral testing if it is believed that there is a material risk. Concerns with industry test: • Not a minimum suite of tests that participants had to complete. Therefore varying levels of testing across the industry. • Some participants that planned to test with EQL did not participate. • Some participants deleted test steps that they felt were not applicable and this is not how the market works. Overall - it is likely that there are issues that are yet to be discovered that will be found in the weeks and months post go live. Traffic light status has been set to N/A while Industry Test is completed. The coverage of testing may not be. Therefore a completed status would be misleading. |  | n/a | Industry testing is still underway; Unable to successfully test all industry scenarios due to defects. Some tests are blocked which in turn affected the ability to validate minor business processes. | TasNetworks is participating in industry testing during Cycle 2. | Additional bi-lateral testing will be completed with a subset of retailers during November 2017.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | AAD has a change request process underway for several minor amendments to system design. Changes are at various stages ranging from conceptual design through to development. | All solution designs are complete. |  |  | See above comment | Requirement specifications and high priority designs are complete. The projects phased implementation approach ensures the achievement of compliance in release 1 and further efficiencies in release 2 of which will occur post 1 December 2017. The Proposed Transitional Approach is now The risk of misalignment of assumptions between participants, remains due to concerns with the industry test process. See 4.3 |  |  | Completed
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | All initial code has been received by AAD. System updates relating to change requests (see above) are resulting in ongoing development efforts. | The implementation phase is complete. All software builds are in testing. |  | Late changes from recently published B2B errata are being incorporated into product build | See above comment | The development phase is complete with all releases in User Acceptance Testing as planned. |  |  | Defects for Day 1 requirements are still being fixed. | TasNetworks is facing some challenges in completing all Market Systems changes and testing before 1 December. TasNetworks is taking a risk based approach on the delivery of the Market Systems functionality
5.3 |  | The internal testing of market systems for your business | [5 empty] | AAD has concerns around industry testing based on the participation rates to date. | Testing is well advanced. 15 testers are working across all solution components. Timeframes remain tight. This task remains "At Risk" given the volume of required testing. |  | Critical path has little remaining contingency. | See above comment | Testing is currently progressing well. However, due to compressed timelines and the addition of the transitional approach, user acceptance testing is under pressure to complete. |  |  | Refer to Section 5.2 comment | Testing progress has been impacted by the level of defects identified to-date. | Integration and user acceptance testing have been completed. Additional regression and performance testing will be carried out in Nov 2017 as an additional safeguard.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | As above. | Testing with Market systems is in the final week. No defects have been raised against Ausgrid internal systems. |  | Critical path has little remaining contingency. |  | eHub Accreditation confirmed. Connectivity testing confirmed during industry testing. |  | Industry testing was limited to the scope allocated to Jemena (9% of the e2e tests that should have been executed with Retailers) and the number of Retailer partners available to test. | Participated in Industry Testing. Testing of all scenarios and connectivity. | TasNetworks is participating in industry testing during Cycle 2. | Some retailers were not able to complete agreed tests. UE plans to complete outstanding tests on a bi-lateral basis during Nov 2017.
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | As above. | Testing with market systems is nearing completion. | Continuing difficulties with retailers not being available / ready for industry and bi-lateral testing |  |  | Industry test has completed. We are doing an analysis of any tests not completed during this cycle that represent a risk that the business process / systems have not been fully tested. At the end of that review, the project will organise further bi-lateral testing if it is believed that there is a material risk. Concerns with industry test: Not a minimum suite of tests that participants had to complete. Therefore varying levels of testing across the industry. Some participants that planned to test with EQL did not participate. Some participants deleted test steps that they felt were not applicable and this is not how the market works. Overall - it is likely that there are issues that are yet to be discovered that will be found in the weeks and months post go live. Traffic light status has been set to N/A as while industry test is completed. The coverage of testing may not be. Therefore a completed status would be misleading. | Performance not validated as full integration did not exist in test environment | Not in scope in the AEMO Program | Last week of industry testing. Defects are still being fixed to complete Industry testing. | TasNetworks is participating in industry testing during Cycle 2.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | AAD is on schedule to participate in industry wide dress rehearsal #2. | Working with ITCFG. Cutover planning is in final review and adjustment to align with market advice |  |  |  | The transitional approach is in User Acceptance Testing. The second of two go live dress rehearsals is in progress. |  |  | Pending final approval of the Business Transition plan. Technical Deployment plan has been approved. | This activity is under pressure due to the competing priorities and compressed timelines. This activity is also dependant on other market participants. | Cutover Plan, Stabilisation Plan, IT Transition Plan and In-flight Treatment Plan all in place.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Will continue until go live. | Particpated in cutover rehearsal; 3 walk throughs complete of internal cutover plan. |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | A Cutover Plan and Inflight Management Plan has been completed. A dry-run Dress Rehearsal (DR) was performed in early October to test the cutover and inflight management. A further DR exercise is currently in progress. |  |  | Dress Rehearsal #1 underway. Dress Rehearsal # 2 and Industry Dress Rehearsal to commence in a couple of weeks. | Data migration strategy complete. Cutover Planning activities underway. | Two dress rehearsals completed successfully. No major data migrations required.
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid DB | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Network | SA Power Networks | TasNetworks | United Energy
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | AAD has established risk, issue and decision registers to track and mitigate gaps that are identified as progress is made. | [6 empty] | n/a
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Weekend work and additional test resources have been approved to mitigate the risks associated with slower than expected progress. | [6 empty] | n/a
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [12 empty] | n/a
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [12 empty] | n/a
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [12 empty] | n/a
2.4 |  | An assessment of the required accreditation and registration activities | [12 empty] | n/a
2.5 |  | The fulfilment of accreditation and registration obligations | [11 empty] | This is being worked through with AEMO | n/a
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [12 empty] | n/a
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [12 empty] | n/a
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [12 empty] | n/a
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [12 empty] | n/a
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [12 empty] | n/a
4.3 |  | The validation of business processes during industry testing | [9 empty] | See above comment |  |  | n/a | Mitigate by doing regression testing and further business process testing during UAT (cycle 4) with bilateral arrangement with market participants ( 7/11- 24/11) | Validation of business processes may be done outside of industry testing and during UAT
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [9 empty] | See above comment
5.2 |  | The development and build of appropriate market systems for your business | [9 empty] | See above comment |  |  |  | Manual work arounds are being documented to mitigate risks associated with Day 1 requirements.
5.3 |  | The internal testing of market systems for your business | [9 empty] | See above comment
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [6 empty] | Certification of Ausgrids' five participants against AEMO's eHub has successfully completed. |  | Additional bi lateral testing to be scheduled in Cycle 4 |  |  |  | Retailer bilateral testing attempted to mitigate the limited industry testing, however not all Retailers who have customers on the Jemema Electricity Network were available to test, and those Retailers that were available could not execute the full e2e test set.
5.5 |  | The validation of performance of market systems during industry testing | [11 empty] | Accepting the risk - assessed as very low | Jemena performed full performance testing of our Power of Choice solution, however this does not mititage e2e performance across the elecricity market.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [6 empty] | Member on ITCFG
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 90%
91% - 99%
Completed (100%)
N/A
81% - 99%
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## MP and MDP Reports
| 2017-11-06 |  |  | Metering Provider (MP) and Metering Data Provider (MDP) Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Industry risk rating | Overall project comment | [6 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Active Stream | Within schedule | Low | Low
| Acumen Metering | Within schedule | Medium | Medium | Project risk remains as Acumen continues to progress through significant testing activities, defect resolution, change and business readiness preparation. However the primary development enabling PoC change has been completed and the level of confidence of deploying into systems and across the business in time for cutover is now highly probable. Activities ahead of cutover include Industry and Bi-lateral testing, last stages of system, user acceptance and regression testing as well as business change and training. Plans in place for execution of the above activities and ongoing support plans underway. Cutover preparation is on track and negotiation of commercial agreements with other stakeholders continues.
| Ausgrid Business Services | Within schedule | Low | Low | Test scripts continue to be executed internally and bilaterally to supplement Industry Testing. New interfaces for the customer to assist our customers in operating in the POC space with the second phase release continuing in UAT. Cycle 1 & 2 of industry testing have completed successfully Cycle 3 progressing well, however, further internal system testing is still underway.
| Intellihub | Within schedule | Low | Low
| Metering Dynamics | At risk | Medium | Medium | Accreditation and registration process requirements are taking much longer than originally planned. MP/MDP accreditation audit scheduled and contingency plans have been prepared. | [6 empty] | Accreditation and registration activities taking longer than originally planned, and MD providing additional information to address AEMO requested clarifications. MP/MDP accreditation audit scheduled.
| Metropolis Metering Services Pty Ltd | Within schedule | Low |  | [AEMO Note - Using 9-Oct 17 Report for Metropolis]: Metropolis has allocated July-November 2017 to complete systems enhancements and testing activities with a particular focus on Service Order, CSDN and Metering Data processes, with supporting MSATS Metering Coordinator transactions and change request processes.
| Powermetric Metering Pty Ltd | At risk | Medium | Medium | Powermetric MDP, MPB & MC overall POC system and business process development is on schedule however, the aggressive POC implementation, industry testing and MC Registration timeframes place Powermetric POC development at a Medium risk.
| Select Solutions GLOBALM, EASTENMP, EASTENMC | Within schedule | Medium | Medium | The summary project status and risk rating relate to the activities as Metering Coordinator. Select Solutions overall PoC strategy is to continue to run its existing systems for our Type 1-4 large meters and MP/MDP participant IDs with supporting enhancements to existing systems to form part of our accreditation for MC Services. Our MC Registration has been submitted and clarifications provided to AEMO as requested. We are currently waiting on confirmation of MC Registration from AEMO. There are currently no substantial risks or issues impacting our existing Type 1-4 Large MP and MDP accreditations. Select Solutions system development, testing and business readiness activities are progressing to plan in readiness for 1 December 2017 Go Live. Project risks predominantly relate to the substantial volume of commercial updates to be undertaken (scoped, negotiated and executed) prior to 1 December 2017.
| Spotless Advanced Metering | Within schedule | Low | Low | [7 empty] | Accrediation Audit completed early August. Minor actions still to be completed by SAM to finalise accredition.
| VECTORAMS | Within schedule | Medium | Medium | Overall project is within schedule and is expected to be operationally ready for POC Go-live.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| Active Stream | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Acumen Metering | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| Ausgrid Business Services | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Intellihub | Completed | Low | Completed | Low | Completed | Low | Completed | Low | Completed | Low
| Metering Dynamics | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| Metropolis Metering Services Pty Ltd | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Powermetric Metering Pty Ltd | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| Select Solutions GLOBALM, EASTENMP, EASTENMC | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Spotless Advanced Metering | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| VECTORAMS | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | Intellihub | Metering Dynamics | Metropolis Metering Services Pty Ltd | Powermetric Metering Pty Ltd | Select Solutions GLOBALM, EASTENMP, EASTENMC | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Completed (100%) | 81% - 99% | Completed (100%) | Completed (100%) | Completed (100%) | 81% - 99% | 71% - 80% | Completed (100%) | Completed (100%) | 91% - 99%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Completed (100%) | 81% - 99% | Completed (100%) | Completed (100%) | 91% - 99% | 71% - 80% | 71% - 80% | Completed (100%) | Completed (100%) | 91% - 99%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Completed (100%) | 71% - 80% | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | 71% - 80% | Completed (100%) | Completed (100%) | 81% - 99%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Completed (100%) | 81% - 99% | 61% - 70% | Completed (100%) | 91% - 99% | 81% - 99% | 71% - 80% | Completed (100%) | Completed (100%) | 81% - 99%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 91% - 99% | 41% - 50% | 81% - 90% | Completed (100%) | 91% - 99% | 61% - 70% | 21% - 30% | 71% - 80% | Completed (100%) | 71% - 80%
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Completed (100%) | 81% - 99% | Completed (100%) | Completed (100%) | 91% - 99% | Completed (100%) | 71% - 80% | Completed (100%) | Completed (100%) | Completed (100%)
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Completed (100%) | 81% - 99% | 91% - 99% | Completed (100%) | 91% - 99% | 61% - 70% | 61% - 70% | 91% - 99% | 91% - 99% | 81% - 99%
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Completed (100%) | 81% - 99% | 81% - 90% | Completed (100%) | Completed (100%) | Completed (100%) | 71% - 80% | Completed (100%) | Completed (100%) | 81% - 99%
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Completed (100%) | 81% - 99% | 61% - 70% | Completed (100%) | 91% - 99% | 81% - 99% | 31% - 40% | Completed (100%) | Completed (100%) | 61% - 70%
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | 91% - 99% | 41% - 50% | 51% - 60% | Completed (100%) | 71% - 80% | 71% - 80% | Not started (0%) | 71% - 80% | Completed (100%) | 71% - 80%
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Completed (100%) | 81% - 99% | 81% - 90% | Completed (100%) | Completed (100%) | 71% - 80% | 61% - 70% | Completed (100%) | Completed (100%) | 91% - 99%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Completed (100%) | 71% - 80% | 51% - 60% | Completed (100%) | 91% - 99% | 61% - 70% | 61% - 70% | Completed (100%) | Completed (100%) | 91% - 99%
4.3 |  | The validation of business processes during industry testing | [5 empty] | 91% - 99% | 71% - 80% | 71% - 80% | Completed (100%) | 81% - 90% | 31% - 40% | Not started (0%) | 91% - 99% | Completed (100%) | 91% - 99%
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Completed (100%) | 81% - 99% | Completed (100%) | Completed (100%) | Completed (100%) | 71% - 80% | 61% - 70% | Completed (100%) | Completed (100%) | 81% - 99%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Completed (100%) | 71% - 80% | Completed (100%) | Completed (100%) | 91% - 99% | 61% - 70% | 41% - 50% | Completed (100%) | Completed (100%) | 81% - 99%
5.3 |  | The internal testing of market systems for your business | [5 empty] | Completed (100%) | 81% - 99% | 71% - 80% | Completed (100%) | 81% - 90% | 41% - 50% | 11% - 20% | Completed (100%) | 91% - 99% | 81% - 99%
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | 91% - 99% | 81% - 99% | 81% - 90% | Completed (100%) | Completed (100%) | 41% - 50% | 41% - 50% | Completed (100%) | 91% - 99% | Completed (100%)
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | 91% - 99% | 81% - 99% | 81% - 90% | Completed (100%) | Completed (100%) | 41% - 50% | Not started (0%) | Completed (100%) | Completed (100%) | 81% - 90%
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 91% - 99% | 71% - 80% | 81% - 90% | Completed (100%) | 81% - 90% | 71% - 80% | 11% - 20% | 81% - 90% | Completed (100%) | 41% - 50%
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | 91% - 99% | 31% - 40% | 41% - 50% | 81% - 90% | 41% - 50% | 71% - 80% | 1% - 10% | 51% - 60% | Completed (100%) | 11% - 20%
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | Intellihub | Metering Dynamics | Metropolis Metering Services Pty Ltd | Powermetric Metering Pty Ltd | Select Solutions GLOBALM, EASTENMP, EASTENMC | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Completed | Within schedule | Completed | Completed | Completed | Within schedule | Within schedule | Completed | Completed | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Completed | Within schedule | Completed | Completed | Within schedule | Within schedule | Within schedule | Completed | Completed | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Completed | Within schedule | Completed | Completed | Completed | Within schedule | Within schedule | Completed | Completed | Within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Completed | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Completed | Completed | Within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | At risk | Within schedule | Completed | Within schedule | Within schedule | At risk | At risk | Completed | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Completed | At risk | Completed | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Completed | At risk | Within schedule | Completed | At risk | Within schedule | At risk | At risk | Within schedule | At risk
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Completed | Within schedule | Within schedule | Completed | Completed | Within schedule | Within schedule | Completed | Completed | Within schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Completed | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Completed | Completed | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Completed | Within schedule | Within schedule | Completed | Completed | Within schedule | Within schedule | Completed | Completed | Within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Completed | Within schedule | Within schedule | Completed | Within schedule | Within schedule | At risk | Completed | Completed | Within schedule
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | At risk | Within schedule | Within schedule | Within schedule | Completed | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Completed | Within schedule | Completed | Completed | Completed | Within schedule | Within schedule | Completed | Completed | Within schedule
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Completed | Within schedule | Completed | Completed | At risk | Within schedule | Within schedule | Completed | Completed | Within schedule
5.3 |  | The internal testing of market systems for your business | [5 empty] | Completed | Within schedule | Within schedule | Completed | At risk | Within schedule | Within schedule | Completed | Within schedule | Within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | Completed | Within schedule | Within schedule | Completed | Within schedule | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | Completed | Within schedule | Within schedule | Completed | Completed | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | At risk | Within schedule | Within schedule | Within schedule | Completed | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Completed | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | Intellihub | Metering Dynamics | Metropolis Metering Services Pty Ltd | Powermetric Metering Pty Ltd | Select Solutions GLOBALM, EASTENMP, EASTENMC | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [7 empty] | MC Application Checklist has been submitted
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [7 empty] | Reviewing ITCFG plan document |  |  | Implemetation plans to be revised in line with industry testing results.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [7 empty] | Final reviews completed.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [7 empty] | In progress. Final reviews and updates in progress.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [7 empty] | Campaigns well underway to reach each relationship type for new or amended agreements |  |  | Metering Coordinator contractual arrangements being finalised with several major retailers. |  | Select Solutions is continuing to work through the review and update to a large volume of indivdual I&C customer contracts in readiness for 1 December commencement of MC services and PoC changes. Commercial activities include the addition of new services, transactions, fees and charges, each to be individually negotiated and agreed. There is a risk that protracted negiotiation timeframes will impact arranagements for POC Go Live on 1 December 2017. This has been registered as part of our Risk Management framework and a risk treatment plan is currently being worked through to ensure readiness for 01/12.
2.4 |  | An assessment of the required accreditation and registration activities | [7 empty] | In hand.
2.5 |  | The fulfilment of accreditation and registration obligations | [7 empty] | M&DS continues to progress with required procedures in a timely manner. Supporting documentation for registration of new role ENM has been completed. MC Checklist has been resubmitted. Applications for reaccreditation of MPB and MDP roles for the new categories have been submitted. |  | Accreditation and registration activities taking longer than originally planned, with policies being modified to satisfy AEMO requirements. | Metering Coordinator registration application submitted to AEMO. |  | Our MC Registration has been submitted and clarifications provided to AEMO as requested. We are currently waiting for confirmation of our MC Registration from AEMO. |  | Unanticipated time and effort required to attain MC registration has caused this variance.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [7 empty] | Awaiting final updates to policies and work instructions.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [7 empty] | Relies on the above.
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [7 empty] | Relies on the above. |  |  | Training to be developed inline with industry testing. |  | Change Management and Training Activities in progress.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [7 empty] | Policies, priocedures and work instructions have been idenitfied and are in update/generation.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [7 empty] | Policies, priocedures and work instructions have been idenitfied and are in update/generation.
4.3 |  | The validation of business processes during industry testing | [7 empty] | Cycle 1 & 2 Industry Testing successful. |  | Not all test cases could be executed as part of Industry Test Cycle 3 due to blocked test cases by other parties. | Industry testing not completed. |  | We have participated in Industry Testing Cycle 2 and Cycle 3 as well as Bilateral Testing to validate business processes.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [7 empty] | All solution designs are complete.
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | The implementation phase is complete with internal testing in progress. |  | Development activities to cater for requirements (e.g. MC) have taken longer than originally planned.
5.3 |  | The internal testing of market systems for your business | [7 empty] | Testing is well advanced. 15 testers are working across all solution components. Timeframes remain tight. This task remains "At risk (Low)" given the volume of testing required. |  | Testing of any late arriving functionality need to be executed.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [7 empty] | Configuration of the AEMO links to connect Ausgrid's file based and SMP gateways is complete.
5.5 |  | The validation of performance of market systems during industry testing | [7 empty] | Testing with market systems is underway for Cycle 3.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [7 empty] | Working with ITCFG. Cutover planning is in final review and adjustment to align with market advice |  | Transaction volume limits may cause delays at cutover. |  |  | Detailed Transition and Cutover plans have been developed in line with the Industry Transition plan.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [7 empty] | Particpated in cutover rehearsal; 3 walk throughs complete of internal cutover plan. |  | Some activities are taking longer than originally planned. |  |  | We have successfully completed an internal Dress Rehersal 1 and are preparing for Dress Rehersal 2 activities as part of our detailed Transition and Cutover plans.
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | Intellihub | Metering Dynamics | Metropolis Metering Services Pty Ltd | Powermetric Metering Pty Ltd | Select Solutions GLOBALM, EASTENMP, EASTENMC | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [7 empty] | Member on ITCFG
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [12 empty] | Contract amendments have been drafted, issued and a significant customer engagement activity is currently underway with a number of responses received. Commercial activities are progressing to plan and are also being closely monitored in our governance framework as a key project risk.
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations | [9 empty] | Actively working with AEMO to finalise. |  |  |  |  | Responding to AEMO requests as fast as possible but turn around time by both Vector and AEMO's is impacting the schedule.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing | [9 empty] | Additional bilateral end to end testing planned.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | All available resources have been assigned to the design & development tasks. |  | Additional focus provided to mitigate the risk.
5.3 |  | The internal testing of market systems for your business | [9 empty] | Increased focus provided to mitigate the risk.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [7 empty] | Certification of M&DS's four participants against AEMO's eHub is complete.
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [7 empty] | Member on ITCFG |  | Working with AEMO to increase limits and manage transaction and notification volumes. Coordination with retailers to ensure limits are not exceeded.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [9 empty] | Increased focus on data migration and cutover to production systems.
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 90%
91% - 99%
Completed (100%)
N/A
81% - 99%
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Metering Coordinator Reports
Metering Coordinator (MC) Readiness Assessment Reports - see Distributors Report tab for initial MC
| 2017-11-06 |  |  | Please note that the below organisations are voluntarily self-reporting readiness as intending MCs. This is not a reflection of their registration status or a complete list of all intending Metering Coordinators. The list of Registered Metering Coordinators can be found here:
http://www.aemo.com.au/-/media/Files/Electricity/NEM/Participant_Information/NEM-Registration-and-Exemption-List.xls
| Organisation | Project status | Project risk rating | Industry risk rating | Overall project comment | [6 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Active Stream | Within schedule | Low | Low
| Acumen Metering | Within schedule | Medium | Medium | Project risk remains as Acumen continues to progress through significant testing activities, defect resolution, change and business readiness preparation. However the primary development enabling PoC change has been completed and the level of confidence of deploying into systems and across the business in time for cutover is now highly probable. Activities ahead of cutover include Industry and Bi-lateral testing, last stages of system, user acceptance and regression testing as well as business change and training. Plans in place for execution of the above activities and ongoing support plans underway. Cutover preparation is on track and negotiation of commercial agreements with other stakeholders continues.
| Ausgrid Business Services | Within schedule | Low | Low | Test scripts continue to be executed internally and bilaterally to supplement Industry Testing. New interfaces for the customer to assist our customers in operating in the POC space with the second phase release continuing in UAT. Cycle 1 & 2 of industry testing have completed successfully Cycle 3 progressing well, however, further internal system testing is still underway.
| Intellihub | Within schedule | Low | Low
| Metering Dynamics | At risk | Medium | Medium | Accreditation and registration process requirements are taking much longer than originally planned. MP/MDP accreditation audit scheduled and contingency plans have been prepared. | [6 empty] | Registration nearing completion.
| Metropolis Metering Services Pty Ltd | Within schedule | Low |  | [AEMO Note - Using 9-Oct 17 Report for Metropolis]: Metropolis has allocated July-November 2017 to complete systems enhancements and testing activities with a particular focus on Service Order, CSDN and Metering Data processes, with supporting MSATS Metering Coordinator transactions and change request processes.
| Origin Energy | At risk | Medium |  | Overall project delivery deadline at risk, due to constrained timelines for delivery against overall AEMO Delivery Timelines. Program is currently reporting Amber however remains highly dependant on the readiness of other participants to be successful. A relevant number of delivery risks continue to be monitored and mitigated for the duration of the Project. Main concerns are: • There is no Go / No go option based on overall participant readiness e.g. successful completion of Market Testing. • There is no Back-out scenario for this implementation given this is an integrated delivery backed by change in legislation. The risk profile is extremely high given statuses of various participants. | [6 empty] | Request for registration submitted to AEMO on 25/9. AEMO's feedback received and addressed by Origin. Accreditation expected by Oct-end, now targeting mid-November..
| Powermetric Metering Pty Ltd | At risk | Medium | Medium | Powermetric MDP, MPB & MC overall POC system and business process development is on schedule however, the aggressive POC implementation, industry testing and MC Registration timeframes place Powermetric POC development at a Medium risk.
| Select Solutions GLOBALM, EASTENMP, EASTENMC | Within schedule | Medium | Medium | The summary project status and risk rating relate to the activities as Metering Coordinator. Select Solutions overall PoC strategy is to continue to run its existing systems for our Type 1-4 large meters and MP/MDP participant IDs with supporting enhancements to existing systems to form part of our accreditation for MC Services. Our MC Registration has been submitted and clarifications provided to AEMO as requested. We are currently waiting on confirmation of MC Registration from AEMO. There are currently no substantial risks or issues impacting our existing Type 1-4 Large MP and MDP accreditations. Select Solutions system development, testing and business readiness activities are progressing to plan in readiness for 1 December 2017 Go Live. Project risks predominantly relate to the substantial volume of commercial updates to be undertaken (scoped, negotiated and executed) prior to 1 December 2017. | [6 empty] | Risk relates to the remaining timeframe to complete updated commercial arrangements by 1 Dec 2017 and the unplanned extended timeframe for the MC Registration clarification activities with AEMO.
| Spotless Advanced Metering | Within schedule | Low | Low | [7 empty] | AEMO have advised that all requirements for registration have been met and that Participant Readiness Committee meeting is all that is required to complete registration.
| VECTORAMS | Within schedule | Medium | Medium | Overall project is within schedule and is expected to be operationally ready for POC Go-live. | [6 empty] | Unanticipated time and effort required to attain MC registration has caused some level of concern.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| Active Stream | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Acumen Metering | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Ausgrid Business Services | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Intellihub | Completed | Low | Completed | Low | Completed | Low | Completed | Low | Completed | Low
| Metering Dynamics | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium
| Metropolis Metering Services Pty Ltd | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Origin Energy | At risk | Low | At risk | Low | At risk | Low | At risk | Low |  |  | At risk | Low
| Powermetric Metering Pty Ltd | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| Select Solutions GLOBALM, EASTENMP, EASTENMC | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium
| Spotless Advanced Metering | Completed | N/A | Completed | N/A | Completed | N/A | Completed | N/A | Completed | N/A | Completed | N/A
| VECTORAMS | At risk | Low | At risk | Low | At risk | Low | At risk | Low | At risk | Low
0
0
0
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | Intellihub | Metering Dynamics | Metropolis Metering Services Pty Ltd | Origin Energy | Powermetric Metering Pty Ltd | Select Solutions GLOBALM, EASTENMP, EASTENMC | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Completed (100%) | 81% - 99% | Completed (100%) | Completed (100%) | Completed (100%) | 81% - 99% | Completed (100%) | 71% - 80% | Completed (100%) | Completed (100%) | 91% - 99%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Completed (100%) | 81% - 99% | Completed (100%) | Completed (100%) | 91% - 99% | 71% - 80% | 91% - 99% | 71% - 80% | Completed (100%) | Completed (100%) | 91% - 99%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Completed (100%) | 71% - 80% | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | 81% - 90% | 71% - 80% | Completed (100%) | Completed (100%) | 81% - 99%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Completed (100%) | 81% - 99% | 61% - 70% | Completed (100%) | 91% - 99% | 81% - 99% | 71% - 80% | 71% - 80% | Completed (100%) | Completed (100%) | 81% - 99%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 91% - 99% | 41% - 50% | 81% - 90% | Completed (100%) | 91% - 99% | 61% - 70% | 71% - 80% | 21% - 30% | 71% - 80% | Completed (100%) | 71% - 80%
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Completed (100%) | 81% - 99% | Completed (100%) | Completed (100%) | 91% - 99% | Completed (100%) | 81% - 90% | 71% - 80% | Completed (100%) | Completed (100%) | Completed (100%)
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Completed (100%) | 81% - 99% | 91% - 99% | Completed (100%) | 91% - 99% | 61% - 70% | Not started (0%) | 61% - 70% | 91% - 99% | 91% - 99% | 81% - 99%
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Completed (100%) | 81% - 99% | 81% - 90% | Completed (100%) | Completed (100%) | Completed (100%) | 81% - 90% | 71% - 80% | Completed (100%) | Completed (100%) | 81% - 99%
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Completed (100%) | 81% - 99% | 61% - 70% | Completed (100%) | 91% - 99% | 81% - 99% | 61% - 70% | 31% - 40% | Completed (100%) | Completed (100%) | 61% - 70%
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | 91% - 99% | 41% - 50% | 51% - 60% | Completed (100%) | 71% - 80% | 71% - 80% | 51% - 60% | Not started (0%) | 71% - 80% | Completed (100%) | 71% - 80%
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Completed (100%) | 81% - 99% | 81% - 90% | Completed (100%) | Completed (100%) | 71% - 80% | Completed (100%) | 61% - 70% | Completed (100%) | Completed (100%) | 91% - 99%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Completed (100%) | 71% - 80% | 51% - 60% | Completed (100%) | 91% - 99% | 61% - 70% | 81% - 90% | 61% - 70% | Completed (100%) | Completed (100%) | 91% - 99%
4.3 |  | The validation of business processes during industry testing | [5 empty] | 91% - 99% | 71% - 80% | 71% - 80% | Completed (100%) | 81% - 90% | 31% - 40% | 81% - 90% | Not started (0%) | 91% - 99% | Completed (100%) | 91% - 99%
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Completed (100%) | 81% - 99% | Completed (100%) | Completed (100%) | Completed (100%) | 71% - 80% | 81% - 99% | 61% - 70% | Completed (100%) | Completed (100%) | 81% - 99%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Completed (100%) | 71% - 80% | Completed (100%) | Completed (100%) | 91% - 99% | 61% - 70% | 61% - 70% | 41% - 50% | Completed (100%) | Completed (100%) | 81% - 99%
5.3 |  | The internal testing of market systems for your business | [5 empty] | Completed (100%) | 81% - 99% | 71% - 80% | Completed (100%) | 81% - 90% | 41% - 50% | 81% - 90% | 11% - 20% | Completed (100%) | 91% - 99% | 81% - 99%
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | 91% - 99% | 81% - 99% | 81% - 90% | Completed (100%) | Completed (100%) | 41% - 50% | 81% - 90% | 41% - 50% | Completed (100%) | 91% - 99% | Completed (100%)
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | 91% - 99% | 81% - 99% | 81% - 90% | Completed (100%) | Completed (100%) | 41% - 50% | 51% - 60% | Not started (0%) | Completed (100%) | Completed (100%) | 81% - 90%
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 91% - 99% | 71% - 80% | 81% - 90% | Completed (100%) | 81% - 90% | 71% - 80% | 91% - 99% | 11% - 20% | 81% - 90% | Completed (100%) | 41% - 50%
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | 91% - 99% | 31% - 40% | 41% - 50% | 81% - 90% | 41% - 50% | 71% - 80% | 71% - 80% | 1% - 10% | 51% - 60% | Completed (100%) | 11% - 20%
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | Intellihub | Metering Dynamics | Metropolis Metering Services Pty Ltd | Origin Energy | Powermetric Metering Pty Ltd | Select Solutions GLOBALM, EASTENMP, EASTENMC | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Completed | Within schedule | Completed | Completed | Completed | Within schedule | Completed | Within schedule | Completed | Completed | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Completed | Within schedule | Completed | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Completed | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Completed | Within schedule | Completed | Completed | Completed | Within schedule | Within schedule | Within schedule | Completed | Completed | Within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Completed | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Completed | Within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | At risk | Within schedule | Completed | Within schedule | Within schedule | At risk | At risk | At risk | Completed | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Completed | At risk | Completed | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Completed | At risk | Within schedule | Completed | At risk | Within schedule | At risk | At risk | At risk | Within schedule | At risk
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Completed | Within schedule | Within schedule | Completed | Completed | Within schedule | Within schedule | Within schedule | Completed | Completed | Within schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Completed | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Completed | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Completed | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Completed | Within schedule | Within schedule | Completed | Completed | Within schedule | Completed | Within schedule | Completed | Completed | Within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Completed | Within schedule | Within schedule | Completed | Within schedule | Within schedule | At risk | At risk | Completed | Completed | Within schedule
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | At risk | Within schedule | At risk | Within schedule | Within schedule | Completed | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Completed | Within schedule | Completed | Completed | Completed | Within schedule | Within schedule | Within schedule | Completed | Completed | Within schedule
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Completed | Within schedule | Completed | Completed | At risk | Within schedule | Within schedule | Within schedule | Completed | Completed | Within schedule
5.3 |  | The internal testing of market systems for your business | [5 empty] | Completed | Within schedule | Within schedule | Completed | At risk | Within schedule | At risk | Within schedule | Completed | Within schedule | Within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | Completed | Within schedule | At risk | Within schedule | Completed | Within schedule | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | Completed | Within schedule | Within schedule | Within schedule | Completed | Completed | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule | Completed | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | Intellihub | Metering Dynamics | Metropolis Metering Services Pty Ltd | Origin Energy | Powermetric Metering Pty Ltd | Select Solutions GLOBALM, EASTENMP, EASTENMC | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [7 empty] | MC Application Checklist has been submitted
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [7 empty] | Reviewing ITCFG plan document |  |  | Implemetation plans to be revised in line with industry testing results. | All necessary project plans are in place and being managed. Detailed cutover plan finalised and Dress Rehearsal #1 executed. Dress Rehearsal #2 planned 10-13 November. It includes lesson learned and identified improvements from DR#1.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [7 empty] | Final reviews completed.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [7 empty] | In progress. Final reviews and updates in progress. |  |  |  | Policy changes/decisions still being derived
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [7 empty] | Campaigns well underway to reach each relationship type for new or amended agreements |  |  | Metering Coordinator contractual arrangements being finalised with several major retailers. | Overall strategy has been developed and endorsed. Generic Meter provider contract drafted for new providers and contracts in play for current providers. |  | Select Solutions is continuing to work through the review and update to a large volume of indivdual I&C customer contracts in readiness for 1 December commencement of MC services and PoC changes. Commercial activities include the addition of new services, transactions, fees and charges, each to be individually negotiated and agreed. There is a risk that protracted negiotiation timeframes will impact arranagements for POC Go Live on 1 December 2017. This has been registered as part of our Risk Management framework and a risk treatment plan is currently being worked through to ensure readiness for 01/12.
2.4 |  | An assessment of the required accreditation and registration activities | [7 empty] | In hand. |  |  |  | Request for registration/accreditation submitted as per AEMO deadlines. Awaiting final feedback from AEMO.
2.5 |  | The fulfilment of accreditation and registration obligations | [7 empty] | M&DS continues to progress with required procedures in a timely manner. Supporting documentation for registration of new role ENM has been completed. MC Checklist has been resubmitted. Applications for reaccreditation of MPB and MDP roles for the new categories have been submitted. |  | Accreditation and registration activities taking longer than originally planned, with policies being modified to satisfy AEMO requirements. | Metering Coordinator registration application submitted to AEMO. | Planning and preparation in progress |  | Our MC Registration has been submitted and clarifications provided to AEMO as requested. We are currently waiting for confirmation of our MC Registration from AEMO. |  | Unanticipated time and effort required to attain MC registration has caused this variance.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [7 empty] | Awaiting final updates to policies and work instructions. |  |  |  | Forecasted workload planning completed for key business areas and socialised to inform recruitment decisions.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [7 empty] | Relies on the above. |  |  |  | Recruitment for long lead time positions commenced and on track.
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [7 empty] | Relies on the above. |  |  | Training to be developed inline with industry testing. | Training requirements and resourcing determined and magnitude of change is understood, change planning started behind schedule. Learning curriculum now finalised and training material development commenced and on track against revised deadlines. |  | Change Management and Training Activities in progress.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [7 empty] | Policies, priocedures and work instructions have been idenitfied and are in update/generation.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [7 empty] | Policies, priocedures and work instructions have been idenitfied and are in update/generation. |  |  |  | Business process design mainly completed with 3-4 weeks of delays against baseline plan.
4.3 |  | The validation of business processes during industry testing | [7 empty] | Cycle 1 & 2 Industry Testing successful. |  | Not all test cases could be executed as part of Industry Test Cycle 3 due to blocked test cases by other parties. | Industry testing not completed. | Industry Testing underway with Cycle #3 extended till 9/11. An high number of end-to-end Test Scenarios is not complete, posing a risk on the overall Industry Testing. |  | We have participated in Industry Testing Cycle 2 and Cycle 3 as well as Bilateral Testing to validate business processes.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [7 empty] | All solution designs are complete. |  |  |  | Mass Market Design activities complete and Large Customers design in progress. Change requests being assessed and planned.
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | The implementation phase is complete with internal testing in progress. |  | Development activities to cater for requirements (e.g. MC) have taken longer than originally planned. |  | Build progressing on track, including the development of approved change requests.
5.3 |  | The internal testing of market systems for your business | [7 empty] | Testing is well advanced. 15 testers are working across all solution components. Timeframes remain tight. This task remains "At risk (Low)" given the volume of testing required. |  | Testing of any late arriving functionality need to be executed. |  | Internal Testing is completed for core solution. Outstanding internal testing re. change requests/variations as outcome of process review and solution enhancements.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [7 empty] | Configuration of the AEMO links to connect Ausgrid's file based and SMP gateways is complete. |  |  |  | Industry Testing progressing through Cycle #2 behind schedule.
5.5 |  | The validation of performance of market systems during industry testing | [7 empty] | Testing with market systems is underway for Cycle 3. |  |  |  | Batch performance and sizing in progress and on track.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [7 empty] | Working with ITCFG. Cutover planning is in final review and adjustment to align with market advice |  | Transaction volume limits may cause delays at cutover. |  | Deployment Strategy confirmed. Detailed Cutover Plan finalised and "tested" during DR#1. |  | Detailed Transition and Cutover plans have been developed in line with the Industry Transition plan.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [7 empty] | Particpated in cutover rehearsal; 3 walk throughs complete of internal cutover plan. |  | Some activities are taking longer than originally planned. |  | Business Transition planning started and on track. Data conversion for Meter Standing Data (MC/ENM role, NMI/Meter Register Status) across industry participants is still unknown and therefore impacting our Build / Test activities; AEMO's position to leave to participants to update data may lead to substantial issues with integrity of information and risk of performance if all participants have to update MSATS at the same time during cutover. |  | We have successfully completed an internal Dress Rehersal 1 and are preparing for Dress Rehersal 2 activities as part of our detailed Transition and Cutover plans.
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | Intellihub | Metering Dynamics | Metropolis Metering Services Pty Ltd | Origin Energy | Powermetric Metering Pty Ltd | Select Solutions GLOBALM, EASTENMP, EASTENMC | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [7 empty] | Member on ITCFG
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [11 empty] | Origin has onboarded additional Business and Technology resources |  | Contract amendments have been drafted, issued and a significant customer engagement activity is currently underway with a number of responses received. Commercial activities are progressing to plan and are also being closely monitored in our governance framework as a key project risk.
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations | [9 empty] | Actively working with AEMO to finalise. |  | Origin has onboarded additional Business and Technology resources |  |  |  | Responding to AEMO requests as fast as possible but turn around time by both Vector and AEMO's is impacting the schedule.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [11 empty] | Confirmation of some market transactions and treatments still pending which may impact training timelines given constraints in place.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [11 empty] | Remaining outstanding clarifications re. Business Process design planned to be addressed by mid-Nov.
4.3 |  | The validation of business processes during industry testing | [9 empty] | Additional bilateral end to end testing planned. |  | Outstanding Test Scenarios at the end of Cycle #3 will be addressed as part of bi-lateral testing.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | All available resources have been assigned to the design & development tasks. |  | Additional focus provided to mitigate the risk.
5.3 |  | The internal testing of market systems for your business | [9 empty] | Increased focus provided to mitigate the risk. |  | Complete internal testing by Fri 17/11 as per revised baseline.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [7 empty] | Certification of M&DS's four participants against AEMO's eHub is complete.
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [7 empty] | Member on ITCFG |  | Working with AEMO to increase limits and manage transaction and notification volumes. Coordination with retailers to ensure limits are not exceeded.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [9 empty] | Increased focus on data migration and cutover to production systems.
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 90%
91% - 99%
Completed (100%)
N/A
81% - 99%
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Embedded Networks
Embedded Network Manager (ENM) Readiness Assessment Reports
| 2017-11-06 |  |  | Please note that the below organisations are voluntarily self-reporting readiness as intending ENMs. This is not a reflection of their accreditation status or a complete list of all intending Embedded Network Managers. The list of Accredited Embedded Networks Managers can be found here:
http://www.aemo.com.au/-/media/Files/Electricity/NEM/Retail_and_Metering/Metering-Procedures/National-Electricity-Market-Accredited-Embedded-Network-Managers.pdf
| Organisation | Project status | Project risk rating | Industry risk rating | Overall project comment | [6 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Active Utilities Pty Ltd | Within schedule | Medium |  | [AEMO Note - Using 9-Oct 17 Report for Active Utilities]: Completion of system access occurred 04/10/2017, process documentation completed and ready for testing. Migration plan for existing fleet developed and ready for submission to AEMO along with accreditation documentation. Resources trained and clients updated on pending industry changes. Final 3 weeks from 09/10/20178 is completing final testing and all documentation and having ready all required elements for submission to AEMO for ENM Accreditation review/feedback/approval. | [6 empty] | Currently Operating as an ENO. ENM: Currently in final stages of draft documentation and readiness for process testing.
| Ausgrid Business Services | Within schedule | Low | Low | Test scripts continue to be executed internally and bilaterally to supplement Industry Testing. New interfaces for the customer to assist our customers in operating in the POC space with the second phase release continuing in UAT. Cycle 1 & 2 of industry testing have completed successfully Cycle 3 progressing well, however, further internal system testing is still underway.
| Choice Metering | Within schedule | Medium | Medium | Site management system near completion, 1 week left ENM Procedures 70% completed, Policies development 40% completed. ISO9001 Accreditation process to commenced, 15% completed MSATS Access gained.
| Energy & Plant Management Pty Limited | Within schedule | Low | Low | Attended Pre-Application Meeting 4/8/17 ENM Accreditation Application Forms submitted 7/8/17 Received access credentials for MarketNet Connection 9/10/17 Submitted Accreditation Checklists completing application 31/10/17
| Energy Intelligence | Within schedule | Low | Low | Attended Pre-Application Meeting 24/8/17 ENM Accreditation Application Forms submitted 15/9/17 Final stages of resubmission; preparing for audit, waiting on MarketNet 08/10/2017. MarketNet access granted, Preproduction testing completed, Audit completed. 09/11/17
| Energy On | Completed | Low
| ENM Solutions | Within schedule | Low | Low
| Locality Embedded Networks Pty Limited | Within schedule | Low |  | Waiting for AEMO feedback on application.
| Metropolis Metering Services Pty Ltd | Within schedule | Low |  | [AEMO Note - Using 9-Oct 17 Report for Metropolis]: Metropolis has allocated July-November 2017 to complete systems enhancements and testing activities with a particular focus on Service Order, CSDN and Metering Data processes, with supporting MSATS Metering Coordinator transactions and change request processes.
| Momentum | At risk | Medium | Medium | Currently in negotiations for contractual agreements with potential MC who have not secured their registrations.Progress is slower than planned.Momentum is a subsidiary of Hydro Tas and Legal support is provided as shared services which has been less than ideal and the project cost have been stretched by the charges of the external legal charges.Pricing is the sticking point with most of the proposed business partners. Momentum uses 3 separate Vendors and the delivery of the system requirements was initially not in a coordinated approach but has since been addressed and support during testing has been problematic as one vendor is working for numerous parties.
| WINconnect Pty LTD | At risk | Medium |  | [AEMO Note - Using 9-Oct 17 Report for WINconnect]: Working through clarifaction on market design and ENM discovery procedure in MSATS. | [6 empty] | Issues are arising in discussion with AEMO in regards to market design. | [5 empty] | Require guidance from AEMO as to process for ENM discover of MSATS to initiate the custoemr churn process. The ENM is not to be listed against a EN parent in MSATS. Require confirmation on validation in MSATS to ensure only appointed ENMs can perform CR against certain partent NMIS.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| Active Utilities Pty Ltd | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium
| Ausgrid Business Services | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Choice Metering | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium
| Energy & Plant Management Pty Limited | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Energy Intelligence | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Energy On |  |  | Completed | Low | Completed | Low | Completed | Low |  |  | Completed | Low
| ENM Solutions | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Locality Embedded Networks Pty Limited | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Metropolis Metering Services Pty Ltd | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium
| Momentum |  |  | Within schedule | Low |  |  | Within schedule | Low |  |  | Within schedule | Low
| WINconnect Pty LTD | Not within schedule | Medium | Not within schedule | Medium | Not within schedule | Medium | Not within schedule | Medium |  |  | Not within schedule | Medium
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | Active Utilities Pty Ltd | Ausgrid Business Services | Choice Metering | Energy & Plant Management Pty Limited | Energy Intelligence | Energy On | ENM Solutions | Locality Embedded Networks Pty Limited | Metropolis Metering Services Pty Ltd | Momentum | WINconnect Pty LTD | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 71% - 80% | Completed (100%) | 91% - 99% | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | 81% - 99% | 91% - 99% | Completed (100%)
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 71% - 80% | Completed (100%) | Completed (100%) | 91% - 99% | 91% - 99% | Completed (100%) | Completed (100%) | Completed (100%) | 71% - 80% | 81% - 90% | 71% - 80%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 71% - 80% | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | 71% - 80% | 41% - 50%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 71% - 80% | 61% - 70% | 61% - 70% | 91% - 99% | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | 81% - 99% | 81% - 90% | 11% - 20%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 31% - 40% | 81% - 90% | 51% - 60% | 61% - 70% | 91% - 99% | Completed (100%) | Completed (100%) | Completed (100%) | 61% - 70% | 71% - 80% | 41% - 50%
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | 81% - 90% | Completed (100%) | 81% - 90% | 71% - 80%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 71% - 80% | 91% - 99% | 51% - 60% | 91% - 99% | 91% - 99% | 91% - 99% | Completed (100%) | 41% - 50% | 61% - 70% | 81% - 90% | 71% - 80%
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Completed (100%) | 81% - 90% | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | 91% - 99% | 71% - 80%
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Completed (100%) | 61% - 70% | Completed (100%) | 71% - 80% | Completed (100%) | N/A | Completed (100%) | Completed (100%) | 81% - 99% | Completed (100%) | Completed (100%)
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | 81% - 90% | 51% - 60% | 11% - 20% | 71% - 80% | 91% - 99% | 91% - 99% | Completed (100%) | Completed (100%) | 71% - 80% | 71% - 80% | Completed (100%)
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 71% - 80% | 81% - 90% | 41% - 50% | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | 71% - 80% | 91% - 99% | 41% - 50%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 61% - 70% | 51% - 60% | 61% - 70% | 71% - 80% | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | 61% - 70% | 81% - 90% | 51% - 60%
4.3 |  | The validation of business processes during industry testing | [5 empty] | 31% - 40% | 71% - 80% | Not started (0%) | 81% - 90% | 91% - 99% | Completed (100%) | Completed (100%) | 81% - 90% | 31% - 40% | 91% - 99% | Completed (100%)
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 81% - 90% | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | 71% - 80% | 91% - 99% | 61% - 70%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 81% - 90% | Completed (100%) | 71% - 80% | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | 81% - 90% | 61% - 70% | 91% - 99% | 61% - 70%
5.3 |  | The internal testing of market systems for your business | [5 empty] | Completed (100%) | 71% - 80% | 41% - 50% | 91% - 99% | 91% - 99% | Completed (100%) | Completed (100%) | 81% - 90% | 41% - 50% | 71% - 80% | Not started (0%)
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | 81% - 90% | 81% - 90% | 61% - 70% | 91% - 99% | 91% - 99% | Completed (100%) | Completed (100%) | 71% - 80% | 41% - 50% | 91% - 99% | Not started (0%)
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | 41% - 50% | 81% - 90% | Not started (0%) | 81% - 90% | 91% - 99% | Completed (100%) | Completed (100%) | 71% - 80% | 41% - 50% | 91% - 99% | Not started (0%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 71% - 80% | 81% - 90% | 61% - 70% | 71% - 80% | 91% - 99% | N/A | Completed (100%) | 71% - 80% | 71% - 80% | 71% - 80% | Not started (0%)
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | 11% - 20% | 41% - 50% | 21% - 30% | 71% - 80% | 81% - 90% | N/A | Completed (100%) | 71% - 80% | 71% - 80% | 51% - 60% | Not started (0%)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | Active Utilities Pty Ltd | Ausgrid Business Services | Choice Metering | Energy & Plant Management Pty Limited | Energy Intelligence | Energy On | ENM Solutions | Locality Embedded Networks Pty Limited | Metropolis Metering Services Pty Ltd | Momentum | WINconnect Pty LTD | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Within schedule | Within schedule | At risk
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Completed | Completed | Within schedule | Within schedule | Completed | Completed | Completed | Within schedule | Within schedule | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Completed | Within schedule | Completed | Completed | Completed | Completed | Completed | Within schedule | At risk | At risk
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Completed | Completed | Completed | Within schedule | Within schedule | Not within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Not within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Completed | Completed | Within schedule | At risk | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Within schedule | Within schedule | Within schedule | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Within schedule
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Completed | Within schedule | Within schedule | Completed | Completed | Completed | Completed | Completed | Within schedule | Within schedule | At risk
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Completed | Within schedule | Within schedule | Within schedule | Completed | N/A | Completed | Completed | Within schedule | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Completed | Within schedule | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | Completed | Completed | Completed | Completed | Within schedule | Within schedule | Not within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Completed | Completed | Completed | Within schedule | Within schedule | At risk
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Completed | Within schedule | Within schedule | Within schedule | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Within schedule | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Within schedule | Within schedule | At risk
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | Completed | Within schedule | Completed | Completed | Completed | Completed | Within schedule | Within schedule | Within schedule | At risk
5.3 |  | The internal testing of market systems for your business | [5 empty] | Completed | Within schedule | At risk | Within schedule | Within schedule | Completed | Completed | Within schedule | Within schedule | At risk | At risk
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Completed | Within schedule | Within schedule | Within schedule | At risk
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Completed | Within schedule | Within schedule | Within schedule | At risk
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | N/A | Completed | Within schedule | Within schedule | Within schedule | At risk
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | At risk | Within schedule | At risk | Within schedule | Within schedule | N/A | Completed | Within schedule | Within schedule | Within schedule | At risk
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | Active Utilities Pty Ltd | Ausgrid Business Services | Choice Metering | Energy & Plant Management Pty Limited | Energy Intelligence | Energy On | ENM Solutions | Locality Embedded Networks Pty Limited | Metropolis Metering Services Pty Ltd | Momentum | WINconnect Pty LTD | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [6 empty] | MC Application Checklist has been submitted
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Process flows and systems are at final stage of completion. Testing to commence 09/10/17. | Reviewing ITCFG plan document | [6 empty] | Implemetation plans to be revised in line with industry testing results.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Compliance monitoring against regulatory requirements now completed and in place. | Final reviews completed. | [7 empty] | Implementing the required changes for legal and regulatory framework is taking more time than scheduled due to unavailability of suitably qualified resources.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Process flows and systems are at final stage of completion. Testing to commence 09/10/17. | In progress. Final reviews and updates in progress. | [8 empty] | Still wating on confirmation on VIC guidance on treatment of embedded network metering.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Initial discussions had with all impacted customers. Final pricing and cost impact to be submitted for review and acceptance by clients. | Campaigns well underway to reach each relationship type for new or amended agreements | [6 empty] | Metering Coordinator contractual arrangements being finalised with several major retailers. | Contractual agreements for MC and ENM are in progress. PoC changes will need to be reflected in the collaterals of the organisations so the same message is available to customers
2.4 |  | An assessment of the required accreditation and registration activities | [6 empty] | In hand.
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Final testing to commence 09/10/17 ready for AEMO submission end of October 17. | M&DS continues to progress with required procedures in a timely manner. Supporting documentation for registration of new role ENM has been completed. MC Checklist has been resubmitted. Applications for reaccreditation of MPB and MDP roles for the new categories have been submitted. |  |  |  | At audit stage w/c 20/11/2017 |  |  | Metering Coordinator registration application submitted to AEMO.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [6 empty] | Awaiting final updates to policies and work instructions.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [6 empty] | Relies on the above.
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Final stages of training to be completed post testing and final tweaks of new systems and processes initial training completed. | Relies on the above. |  |  |  | Completion scheduled w/c 13/11/2017 |  |  | Training to be developed inline with industry testing.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [6 empty] | Policies, priocedures and work instructions have been idenitfied and are in update/generation. | [8 empty] | In discussion with AEMO, we have concerns about the ENM discovery process in the MSATS market design.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [6 empty] | Policies, priocedures and work instructions have been idenitfied and are in update/generation.
4.3 |  | The validation of business processes during industry testing | [5 empty] | To commence week 09/10/2017. | Cycle 1 & 2 Industry Testing successful. | [6 empty] | Industry testing not completed.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [6 empty] | All solution designs are complete. | [8 empty] | Confirmation required on proprosed process for ENM discovery in MSATS.
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Final connectivity established testing to commence 09/10/2017. | The implementation phase is complete with internal testing in progress.
5.3 |  | The internal testing of market systems for your business | [6 empty] | Testing is well advanced. 15 testers are working across all solution components. Timeframes remain tight. This task remains "At risk (Low)" given the volume of testing required. |  |  | Only valid for Preproduction |  |  |  |  | Execution of Market trials and UAT,regression and integration testing has been in 2 different pre-prod environments due to the late delivery of the integrated system,code merge is also in the mix with regression testing being executed twice
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Final connectivity established testing to commence 09/10/2017 | Configuration of the AEMO links to connect Ausgrid's file based and SMP gateways is complete. |  |  | Only valid for Preproduction
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Final connectivity established testing to commence 09/10/2017. | Testing with market systems is underway for Cycle 3. |  |  | Only valid for Preproduction
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Plan developed to be confirmed post final testing. | Working with ITCFG. Cutover planning is in final review and adjustment to align with market advice
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | To commence post final Testing. | Particpated in cutover rehearsal; 3 walk throughs complete of internal cutover plan.
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | Active Utilities Pty Ltd | Ausgrid Business Services | Choice Metering | Energy & Plant Management Pty Limited | Energy Intelligence | Energy On | ENM Solutions | Locality Embedded Networks Pty Limited | Metropolis Metering Services Pty Ltd | Momentum | WINconnect Pty LTD | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [6 empty] | Member on ITCFG
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [14 empty] | External parties onboarded to progess towards completion
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [14 empty] | Increase level of engagement with Marketing division to finalise before the Go Live dtae
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business | [6 empty] | All available resources have been assigned to the design & development tasks.
5.3 |  | The internal testing of market systems for your business | [14 empty] | Planning to work during non-business days to progress and also as soon as the MSATS pre-prod environment becomes available after the execution of the industry dress rehearsal
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [6 empty] | Certification of M&DS's four participants against AEMO's eHub is complete.
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [6 empty] | Member on ITCFG
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 90%
91% - 99%
Completed (100%)
N/A
81% - 99%
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Third Party
| 2017-11-06 |  |  | Third Party Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Industry risk rating | Overall project comment | [6 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 90%
91% - 99%
Completed (100%)
N/A
81% - 99%
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## AEMO
AEMO Readiness Assessment Report
B. Overall project status
| A. Details | [6 empty] | Project status | Project risk rating | Comment
| Date | 2017-11-06 | [5 empty] | Within schedule | Low | Industry and AEMO concluded cycle 3 of Market trial. AEMO completed system performance testing. AEMO Pre-Prod system remains available for industry bilateral testing to occur. Registration and accreditation windows remain open. Three full MC’s have completed registration. AEMO has notified parties which are currently undertaking the process to complete outstanding actions by mid-November.
| Organisation | AEMO
C. Jurisdictional status
# | Organisation | ACT | NSW | QLD | SA | TAS | VIC | Status | Risk | Comment
1 | AEMO | √ | √ | √ | √ | √ | √ | Within schedule | Low
2
3
4
5
6
D. Detailed status
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%) | Traffic light status | Explanation of variance/Notes | Mitigating actions
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Completed (100%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Completed (100%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
1.3 |  | Delivery of the Market Readiness Strategy and associated plans | [5 empty] | Completed (100%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Completed (100%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.2 |  | The development, documentation and approval of updated internal policies consistent with regulatory changes including jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 91% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | N/A | N/A |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Completed (100%) | Completed |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | N/A | N/A |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.6 |  | The publication of updated AEMO retail electricity market procedures and associated documentation | [5 empty] | Completed (100%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.7 |  | The publication of updated B2B retail electricity market procedures and associated documentation | [5 empty] | Completed (100%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Completed (100%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Completed (100%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
3.3 |  | The development and delivery of training to staff in operational roles | [5 empty] | 81% - 90% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 91% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 91% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4.3 |  | The validation of business processes during industry testing | [5 empty] | 91% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4.4 |  | The delivery of POC information sessions to participants | [5 empty] | Completed (100%) | Completed |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5. Market systems
5.1 | Market systems - MSATS (EN/MC) | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Completed (100%) | Completed |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Completed (100%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.3 |  | The internal testing of market systems for your business | [5 empty] | Completed (100%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Completed (100%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Completed (100%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.6 | Market systems - B2B e-hub and MSATS | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Completed (100%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.7 |  | The development and build of appropriate market systems for your business | [5 empty] | 91% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.8 |  | The internal testing of market systems for your business | [5 empty] | 91% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.9 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | 91% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.1 |  | The validation of performance of market systems during industry testing | [5 empty] | 91% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 91% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | 41% - 50% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
7. General notes
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
[12 empty] | 41% - 50% | Retailer
[12 empty] | 51% - 60% | Distributor
[12 empty] | 61% - 70% | Meter Provider
[12 empty] | 71% - 80% | Meter Data Provider
[12 empty] | 81% - 90% | Metering Coordinator
[12 empty] | 91% - 99% | Embedded Network Manager
[12 empty] | Completed (100%) | Embedded Network Operator
[12 empty] | N/A | Third Party B2B Participant
81% - 99%
Within schedule
At risk
Not within schedule
N/A
[12 empty] | Completed | √
x
Low
Medium
High
N/A

## Harvey Balls 10% (hidden)
ü
Completed
| 100 | 90 | 80 | 70 |  | 60 | 50 | 40 | 30 | 20 | 10 | 0
| 0 | 10 | 20 | 30 |  | 40 | 50 | 60 | 70 | 80 | 90 | 100
WITHIN SCHEDULE | [12 empty] | Risks | Low
Medium
High
AT RISK
NOT WITHIN SCHEDULE
|  |  | ~0% |  | ~50%
|  |  | ~10% |  | ~60%
|  |  | ~20% |  | ~70%
|  |  | ~30% |  | ~80%
|  |  | ~40% |  | ~90%