## Market Readiness Report Page 1
42751
AEMO Power of Choice Implementation Program
|  | Monthly Readiness Report | 2017-01-16
Overall Status |  | Summary |  |  | Risk Rating |  | # Open Risks - Rating: |  |  | Issues:
|  | Overall AEMO and the majority of participants are on schedule to meet the program deliverables. However the risk rating of the program overall is Medium, due to schedule constraints associated with the scope and timing of the B2B Procedure development and subsequent compressed timeframes system development and testing. A Medium to High risk rating has also been highlighted in Victoria due to ongoing uncertainty associated with the Victorian Government Transition to Metering Competition in Victoria decision timing in March 2017. |  |  |  |  | High | Med | Low | #
[7 empty] | 1 | 4 | 2 | 0
AEMO and NEM Participants Readiness Criteria |  |  | AEMO |  | Retailers |  | Distributors |  | MP and MDP |  | Metering Coordinator |  | Embedded Networks (ENM, ENO) |  | Third party e-hub
# | Category | Criterion | Status | Note | Status | Note | Status | Note | Status | Note | Status | Note | Status | Note | Status | Note
1. Assessment and preparation
1.1 | Assessment and preparation | Consequences of the POC reforms for your business considered, and appropriate implementation plans are in place
1.2 |  | Key readiness planning documents delivered
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | Updated retail electricity market procedures and associated documents published
2.2 |  | Internal policies updated for consistency with regulatory changes including jurisdictional regulations and requirements (e.g. safety) | [5 empty] | #1
2.3 |  | Operationally critical commercial contracts in place
2.4 |  | Accreditation and registration activities completed
3. People
3.1 | People | Operational roles specified, assigned to staff, and training delivered
4. Business processes
4.1 | Business processes | Updated, validated and approved business processes in place
4.2 |  | Successfully validated critical business processes during industry testing
4.3 |  | Process work‑arounds in place for any issues identified during industry testing
5. Market systems
5.1 | Market systems | Delivery of the re-developed B2B e-hub for industry testing
5.2 |  | Successfully tested market systems capable of being moved into production | [5 empty] | #2
5.3 |  | Performance of, and communication between, market systems validated during industry testing | [5 empty] | #3
6. Transition planning
6.1 | Transition planning | Transition and cutover plan(s) in place
6.2 |  | Prerequisite transition and cutover processes completed (e.g. trial data conversions and cutover dress rehearsals)
Jurisdictional Status
Jurisdiction |  | Comments | AEMO |  | Retailers |  | Distributors |  | MP and MDP |  | Metering Coordinator |  | Embedded Networks (ENM, ENO) |  | Third party e-hub
|  |  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
ACT |  | Jurisdicational risk is a reflection of overall project risk.
NSW |  | Jurisdicational risk is a reflection of overall project risk.
QLD |  | Jurisdicational risk is a reflection of overall project risk.
SA |  | Jurisdicational risk is a reflection of overall project risk.
TAS |  | Jurisdicational risk is a reflection of overall project risk.
VIC |  | Jurisdicational risk is a reflection of overall project risk, with additional risk noted due to the uncertainty associated with the Victorian Government Transition to Metering Competition in Victoria decision timing in March 2017, and the treatment of VICAMI meters.

## HIDDEN 25% (hidden)
ü
| 100 | 75 | 50 | 25 | 0
| 0 | 25 | 50 | 75 | 100
WITHIN SCHEDULE | [5 empty] | Risks | Low
Medium
High
AT RISK
NOT WITHIN SCHEDULE

## HIDDEN 10% (hidden)
ü
Completed
| 100 | 90 | 80 | 70 |  | 60 | 50 | 40 | 30 | 20 | 10 | 0
| 0 | 10 | 20 | 30 |  | 40 | 50 | 60 | 70 | 80 | 90 | 100
WITHIN SCHEDULE | [12 empty] | Risks | Low
Medium
High
AT RISK
NOT WITHIN SCHEDULE
|  |  | ~0% |  | ~50%
|  |  | ~10% |  | ~60%
|  |  | ~20% |  | ~70%
|  |  | ~30% |  | ~80%
|  |  | ~40% |  | ~90%

## Market Readiness Report Page 2
AEMO Power of Choice Implementation Program
Monthly Readiness Report
2017-01-16
Variances
Note # | Explanation of Variance |  |  | Mitigating Actions
1 | The assessment of legal and regulatory frameworks cannot be completed until the Victorian government decision is made (expected around March 2017). |  |  | Continued engagement with Victorian Government and the ESC/ECS.
2 | Business processes in certain areas are dependent on, or heavily impacted by, the B2B procedures. These processes cannot be fully designed until procedures are published in Mar 2017. |  |  | Business process design is continuing based on draft material. This involves risk of re-work and wasted effort if the final B2B procedures differ from the drafts.
3 | System design is dependent on B2B procedures and the scope of changes to be delivered is greater than anticipated and delivery timeframes are highly compressed. |  |  | As with business design - system design is being progressed based on draft material. This involves risk of re-work and wasted effort if the final B2B procedures differ from the drafts.
Notes
Key - Progress and Status | [5 empty] | Key - Risk Rating
Progress |  |  | Status
Harvey balls represent progress towards achieving the criterion |  |  | Colour indicates the readiness status |  |  | Rating
~0% |  | ~50% | Criterion is within agreed schedule and deliverable requirements |  |  | High
~10% |  | ~60% | Criterion is at risk of not meeting requirements and corrective action may be required |  |  | Medium
~20% |  | ~70% | Criterion not meeting requirements. Immediate corrective action required |  |  | Low
~30% |  | ~80% |  |  |  | See POC Industry Risk Register for open risks and issues:
~40% |  | ~90% | Criterion has been achieved |  | ü | POC Industry Register

## Retailer Reports
| 2017-01-16 |  |  | Retailer Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| ActewAGL Retail | Within schedule | Medium | ActewAGL Retail is currently undertaking a high level impact assessment of the changes required by PoC on its business operations and systems and a project plan is being devised to achieve compliance by the "go live" date.
| AGL | Within schedule | Medium | Project currenly tracking to plan for Dec 2017 delivery. Risk rating increased from low to medium due to key project dependencies such as B2B procedure timing and limited industry testing timeframes. | [7 empty] | Risk rating medium due to the number of project interdependencies, B2B impacts and delivery risks such as aggressive industry testing timeframes.
| Aurora Energy | At risk | Medium | Based on detailed planning completed since the most recent AEMO Readiness Report, Aurora Energy has identified a number of risks associated with achieving full rule compliance on 1 December 2017. These risks are predominately based on the aggressive timelines combined with the uncertainty of rule and procedural operation. This is reflected in Aurora Energy's 'at risk' project status. These risks are also impacting on the ability of Aurora Energy's key vendors (including, but not limited to, prospective Metering Coordinators) to meet POC timeframes, as confirmed to Aurora Energy in its recent market engagement.
| Energy Australia | Within schedule | Medium | Overall, on track to be ready from a build point of but with B2B Procedures and Regulatory Changes have not been finalised, there is still a risk that this may result in rework. | [7 empty] | Overall, on track to be ready from a build point of but with B2B Procedures and Regulatory Changes have not been finalised, there is still a risk that this may result in rework.
| Ergon Energy Queensland (retail) | Within schedule | Medium | Due to the high number of changes to our retail billing system due to procedural and B2B changes, overall this project remains as a 'medium risk'. At this stage no changes have been made to jurisdictional safety requirements which will enable remote re-energisation. This remains a risk that retailers will not achieve the full benefits without these changes. | [7 empty] | Due to the high number of changes to our retail billing system due to procedural and B2B changes, overall this project remains as a 'medium risk'. At this stage no changes have been made to jurisdictional safety requirements which will enable remote re-energisation. This remains a risk that retailers will not achieve the full benefits without these changes.
| M2 Energy Pty Ltd | Within schedule | Low | Project planning and build by vendor has commenced and is on schedule. Business operations impact scoping has not commenced. Business intention is to outsource MC role. M2 Energy is maintaining dialogue with potential vendors. | [7 empty] | M2 Energy to Outsource MC Role. Software Vendor is within Schedule.
| Mojo Power Pty Ltd | Within schedule | Medium
| Momentum Energy | Within schedule | Medium | Work packages and final B2B procedure documentation is not due until March 2017. All current scoping and impact assessments have been based on draft procedures. Any significant changes from draft procedures will have a direct project impact due to constrained timelines for project.
| Origin Energy | At risk | Medium | Overall project delivery status at risk, due to constrained timelines for delivery against overall AEMO Delivery Timelines. Business and Systems impact assessments arecompleted and Project Blueprinting has commenced on schedule and is progressing well. Amber status is maintained due to high number of delivery risks that will need to be monitored and mitigated on an ongoing basis | [7 empty] | Overall project delivery status at risk, due to constrained timelines for delivery against overall AEMO Delivery Timelines. Business and Systems impact assessments are completed and Project Blueprinting has commenced on schedule and is progressing well. Project Delivery Team is onboarded and internal QA and Governance measures are established. Amber status is maintained due to high number of delivery risks that will need to be monitored and mitigated on an ongoing basis
| Pacific Hydro | Within schedule | Medium | Although the current MSATS and B2B Consultations are within the planned timeframes, there is a risk the MSATS CATS Procedures may need to be revisited as a result of the outcomes of the B2B Consultation. The proposed change to B2B Procedures to enable the management of transactions to notified parties and agreement by all members of the System Working Group on the technical solution to facilitate this are still yet to be confirmed. The result of these outcomes has the potential to add onerous complexity to market communications; impacting the build test and implementation phases.
| People Energy Pty Ltd | Within schedule | Medium | Overall project is currently at a Medium stage risk level as the final B2B procedures may impact the scope.
| Simply Energy | Within schedule | Low | [14 empty] | Simply Energy has initiated multiple internal projects under the Power of Choice Program of Work, since last reported. The program has not yet identified any internal risks however their is an outstanding risk of variances between draft and final Procedures, that can pose a significant market readiness issue because the internal business requirements have been based on draft Procedures.
| Powershop | Within schedule | Medium | [AEMO Note - no report submitted in January 2017: Advised that there are no material updates from November 2016 report. Refer to November report for details]
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| ActewAGL Retail | Within schedule | Low | Within schedule | Low
| AGL |  |  | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| Aurora Energy | [8 empty] | At risk | Medium
| Energy Australia | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| Ergon Energy Queensland (retail) |  |  |  |  | Within schedule | Medium
| M2 Energy Pty Ltd |  |  | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Mojo Power Pty Ltd |  |  | Within schedule | Medium | Within schedule | Medium
| Momentum Energy | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| Origin Energy | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Pacific Hydro |  |  | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| People Energy Pty Ltd |  |  | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Simply Energy | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
Powershop
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | ActewAGL Retail | AGL | Aurora Energy | Energy Australia | Ergon Energy Queensland (retail) | M2 Energy Pty Ltd | Mojo Power Pty Ltd | Momentum Energy | Origin Energy | Pacific Hydro | People Energy Pty Ltd | Simply Energy | Powershop | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 11% - 20% | 71% - 80% | 21% - 30% | 61% - 70% | 41% - 50% | 1% - 10% | 51% - 60% | 71% - 80% | 50% | Completed (100%) | 11% - 20% | 51% - 60%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 1% - 10% | 1% - 10% | 21% - 30% | 51% - 60% | 31% - 40% | 1% - 10% | 1% - 10% | 21% - 30% | 50% | 51% - 60% | 1% - 10% | 31% - 40%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 1% - 10% | 61% - 70% | 1% - 10% | 21% - 30% | 41% - 50% | Not started (0%) | 51% - 60% | 11% - 20% | 25% | 51% - 60% | 1% - 10% | 21% - 30%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Not started (0%) | Not started (0%) | 11% - 20% | Not started (0%) | 11% - 20% | Not started (0%) | 51% - 60% | Not started (0%) | 25% | Not started (0%) | 1% - 10% | Not started (0%)
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Not started (0%) | 1% - 10% | 1% - 10% | Not started (0%) |  | Not started (0%) | 51% - 60% | Not started (0%) | 0% | Not started (0%) | 1% - 10% | 21% - 30%
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Not started (0%) | N/A | N/A | Not started (0%) |  | Not started (0%) | N/A | 1% - 10% | 25% | 21% - 30% | Not started (0%) | 1% - 10%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Not started (0%) | N/A | N/A | Not started (0%) |  | Not started (0%) | N/A | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%)
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Not started (0%) | Not started (0%) | 1% - 10% | 41% - 50% |  | Not started (0%) | 21% - 30% | Not started (0%) | 50% | 21% - 30% | 1% - 10% | 21% - 30%
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Not started (0%) | Not started (0%) | 11% - 20% | Not started (0%) |  | N/A | 71% - 80% | Not started (0%) | 25% | Not started (0%) | Not started (0%) | Not started (0%)
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | 1% - 10% |  | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%)
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 11% - 20% | 21% - 30% | 21% - 30% | 51% - 60% | 31% - 40% | Not started (0%) | Not started (0%) | Not started (0%) | 50% | 21% - 30% | 1% - 10% | 21% - 30%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Not started (0%) | 1% - 10% | 21% - 30% | 11% - 20% | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | 25% | Not started (0%) | 1% - 10% | Not started (0%)
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) |  | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%)
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 1% - 10% | 21% - 30% | 21% - 30% | 51% - 60% | 31% - 40% | 1% - 10% | Not started (0%) | 31% - 40% | 25% | 1% - 10% | 11% - 20% | 1% - 10%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%) |  | 1% - 10% | Not started (0%) | Not started (0%) | 25% | Not started (0%) | 11% - 20% | Not started (0%)
5.3 |  | The internal testing of market systems for your business | [5 empty] | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%) |  | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%) | 11% - 20% | Not started (0%)
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) |  | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%) | 11% - 20% | Not started (0%)
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) |  | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%) | 1% - 10% | Not started (0%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) |  | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%) | 1% - 10% | Not started (0%)
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) |  | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | ActewAGL Retail | AGL | Aurora Energy | Energy Australia | Ergon Energy Queensland (retail) | M2 Energy Pty Ltd | Mojo Power Pty Ltd | Momentum Energy | Origin Energy | Pacific Hydro | People Energy Pty Ltd | Simply Energy | Powershop | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Within schedule | N/A | Within schedule |  | Within schedule | N/A | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule | N/A | Within schedule |  | N/A | N/A | Within schedule | At risk | Within schedule | N/A | N/A
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule |  | N/A | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule | Within schedule | N/A | Within schedule | At risk | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | Within schedule | At risk | Within schedule |  | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
5.3 |  | The internal testing of market systems for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Within schedule | Within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Within schedule | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Within schedule | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | At risk | Within schedule |  | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Within schedule | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule | Within schedule | N/A | Within schedule | At risk | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | ActewAGL Retail | AGL | Aurora Energy | Energy Australia | Ergon Energy Queensland (retail) | M2 Energy Pty Ltd | Mojo Power Pty Ltd | Momentum Energy | Origin Energy | Pacific Hydro | People Energy Pty Ltd | Simply Energy | Powershop | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Impact assessment is underway |  | Aurora Energy has implemented a project to understand, prepare and implement the POC reforms. The current focus of this project is a detailed assessment of necessary business operational process and systems changes. This continues to be informed by on-going AEMO market procedure consultation. Given the uncertainty of rule and procedure operation, this is considered 'at risk'. | [5 empty] | Impact Assessment completed, but will need to be iterated pending consultation outcomes and changes
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | A project plan is being devised and will be finalised after the impact assessment has been completed, see 4.1 and 5.1 below |  | A project plan has been prepared for Aurora Energy to effectively and efficiently work towards market compliance. A draft estimate of business change impacts, required investment and ability to comply with rule at commencement has been prepared. The aggressive timelines for systems build combined with the uncertainty of rule and procedural operation is the basis of the 'at risk' status. | [5 empty] | Detailed implementation schedule and program resourcing drafted and aligned to AEMO delivery milestones and timelines
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Consultation required with the ACT regulator |  | Activity has commenced as part of POC impact assessment. | Assessment in progress and on track but there are still unknowns in regards to jurisdictional safety requirements, and associated obligations on Retailers and MCs. | Queensland jurisdictional safety requirements are yet to be addressed. | not yet scheduled. |  |  | Detailed implementation schedule and program resourcing drafted and aligned to AEMO delivery milestones and timelines |  |  | Awaiting jurisdictional safety regulators to publish requirements
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [7 empty] | Preliminary advice has been sough with regards to regulatory compliance. In addition to direct metering competition regulatory changes, a key challenge for Aurora Energy is to consider the wider (/indrect) regulatory implications of metering competition on business-as-usual activities. | Waiting on finalised procedures in order to lock down the requirements which may result in re-work | Queensland jurisdictional safety requirements are yet to be addressed. | not yet scheduled. |  |  | Policy changes/decisions still being derived through Blueprinting
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [7 empty] | Activity has commenced. |  |  | not yet scheduled. |  |  | Unable to commence until Blueprinting and overall strategy has been developed and endorsed
2.4 |  | An assessment of the required accreditation and registration activities | [10 empty] | not yet scheduled. |  |  | Underway for new Market Roles
2.5 |  | The fulfilment of accreditation and registration obligations | [13 empty] | Unable to commence until Blueprinting and overall strategy has been developed and endorsed |  |  | Pending outcome from 2.4
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Will commence after impact assessment has been completed |  | This has commenced and will be finalised following with the detailed assessment of operational and systems changes. |  |  | not yet scheduled. |  |  | Detailed implementation schedule and program resourcing drafted and aligned to AEMO delivery milestones and timelines
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [7 empty] | The recruitment of specialist human resources to cater for the rule change has commenced. | [5 empty] | Policy changes/decisions still being derived through Blueprinting |  | This task is yet to commence
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [7 empty] | Pending above. |  |  | not yet scheduled. |  |  | Training requirements and resourcing unable to be accurately determined until High Level Requirements and Blueprint is completed and magnitude of change is understood |  | This task is yet to commence | Scheduled to commence in mid 2017
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Dependent on B2B procedures which will determine the scope of required changes to business processes |  | All impacted service order, B2B & B2M and business processes have been identified. Assessment of current and future processes is underway to enable gap analysis and identify process and system changes. However as there are likely to be further changes to B2B and possibly B2M procedures, this introduces considerable planning uncertainty for Aurora Energy (and consequently puts the delivery scope and timelines at risk). |  |  | not yet scheduled. |  |  | Detailed implementation schedule and program resourcing drafted and aligned to AEMO delivery milestones and timelines
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [7 empty] | Future business processes are currently being developed using the details from Work package 1 and 2, as well as the B2B draft procedures. However as there are likely to be further changes to B2B and possibly B2M final published document this is considered by Aurora Energy to be 'at risk'. |  |  | not yet scheduled. |  |  | Detailed implementation schedule and program resourcing drafted and aligned to AEMO delivery milestones and timelines
4.3 |  | The validation of business processes during industry testing | [7 empty] | Activity has not yet started. |  |  | not yet scheduled. |  |  | Not Commenced |  | not yet scheduled.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Scoping of changes to systems to be conducted in conjunction with the external vendor |  | Aurora Energy is undertaking a gap analysis to inform required market systems of technical and business process change effort. Based on this, detailed system and business change requirements are currently being gathered. However as advised previously due to possible further changes to B2B procedures this puts Aurora Energy's delivery scope and timelines 'at risk'. |  |  |  |  | System development is reliant on external vendor, delays in final market procedures will impact readiness activities | Detailed impact assessment of system changes has only just commenced, and is highly dependent on decisions, outcomes and information provided in Systems and B2B Working Groups | A full assessment cannot be undertaken until the technical solution for B2B is known and the Final Determination on the B2B Procedures is released. |  | High level assessment is complete, detailed assessment will require final set of Procedures
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | Aurora Energy is awaiting clarity on the final full set of changes to the B2B/B2M environment. This activity will be completed once these are provided by AEMO. | [5 empty] | Systems development commencement is dependent on the outcomes and conclusions of the Systems IA and Requirements being understood |  |  | Scheduled to commence in 2017
5.3 |  | The internal testing of market systems for your business | [7 empty] | This has not started and not due to start until 2017. | [5 empty] | Not Commenced |  |  | Scheduled to commence in 2017
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [7 empty] | This has not started and not due to start until mid-2017. | [5 empty] | Not Commenced |  |  | Scheduled to commence in 2017
5.5 |  | The validation of performance of market systems during industry testing | [7 empty] | This has not started and not due to start until mid-2017. | [5 empty] | Not Commenced |  |  | Scheduled to commence in 2017
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [7 empty] | Transition Plans will be completed once AEMO packages and commercial agreements with metering coordinator(s) are finalised. |  |  | not yet scheduled. |  |  | Transition planning and scheduling cannot be accurately determined until Design & Build is completed
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [7 empty] | Activity has not yet started. |  |  | not yet scheduled. |  |  | Transition planning and scheduling cannot be accurately determined until Design & Build is completed |  | not yet scheduled.
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | ActewAGL Retail | AGL | Aurora Energy | Energy Australia | Ergon Energy Queensland (retail) | M2 Energy Pty Ltd | Mojo Power Pty Ltd | Momentum Energy | Origin Energy | Pacific Hydro | People Energy Pty Ltd | Simply Energy | Powershop | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [13 empty] | Origin has onboarded additional Business and Technology resources
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [9 empty] | Ongoing discussions with the Department of Energy and Water Supply and engagement with the Electrical Safety Office. |  |  |  | Origin has onboarded additional Business and Technology resources |  |  | Internal assessments have commenced
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [9 empty] | Ongoing discussions with the Department of Energy and Water Supply and engagement with the Electrical Safety Office.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [13 empty] | Origin has onboarded additional Business and Technology resources
2.4 |  | An assessment of the required accreditation and registration activities | [13 empty] | Origin has onboarded additional Business and Technology resources
2.5 |  | The fulfilment of accreditation and registration obligations | [13 empty] | Origin has onboarded additional Business and Technology resources
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [13 empty] | Origin has onboarded additional Business and Technology resources
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [13 empty] | Origin has onboarded additional Business and Technology resources
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [13 empty] | Origin has onboarded additional Business and Technology resources
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [13 empty] | Origin has onboarded additional Business and Technology resources
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [13 empty] | Origin has onboarded additional Business and Technology resources
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [13 empty] | Origin has onboarded additional Business and Technology resources
5.2 |  | The development and build of appropriate market systems for your business | [13 empty] | Origin has onboarded additional Business and Technology resources
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Distributor Reports
| 2017-01-16 |  |  | Distributor Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| ActewAGL Distribution (AAD) | Within schedule | N/A | Within the constraints and information provided by AEMO, AAD are on schedule. Critical enablers are yet to be released by AEMO to substantiate this position with a suitable level of confidence. Significant concerns remain over the undetermined POC procedure changes, issues register outcomes and the potential need for substantial system changes. AAD is presently reviewing the Ring Fencing Guidelines released in December to assess the business impacts of the new policy. | [13 empty] | Accreditation transfer and registration starting 2 March is a risk area and it is noted that AEMO will still be developing systems and processes at the time industry is requested to start this process. The readiness of AAD to interface with the AEMO B2B hub is a significant risk. In the absence of information, the system changes required to facilitate this new data flow is undefined. It is noted AEMO have 12 mths to develop this and Industry only have 3.5 mths to implement. There is a disparate timeframe for Industry to modify, test, put into production and this is noted as a major area of concern for AAD.
| Ausgrid | At risk | Medium | We have established a formal ICT project and assigned resources. A number of significant IT rebuilds are expected to be required in order to facilitate the new B2B requirements. | [7 empty] | [See overall project comment]
| AusNet Services | At risk | High | Project mobilised and development in progress, however the overall risk rating of 'High' is a consequence of; 1. Continuing development and change to B2B Procedures. 2. Scope of the current draft of the changes is significant, with some key positions including the new Schema yet to be drafted or finalised. The extent of changes requires development resources/effort/cost beyond initial estimates. 3. Schedule and Scope risk is significant given the definition of strategies for Industry Testing, Industry Systems Implementation and Market Transition has not commenced, 4. The potential impact if the outcome of the Victorian Government options assessment is delayed, 5. Uncertainty about the agreed market treatment of Vic AMI Meters as Type 4 or Type 5. | [7 empty] | The scope of changes to be delivered is greater than anticipated and delivery timeframes are highly compressed. (i.e.; ~5 months between the planned publication of final B2B Procedures on March 6th and the commencement of Industry Testing in early August). Unable to assess ability to align with Industry Testing and Market Transition phases as strategies for these activities have not been drafted. | [5 empty] | The scope of changes to be delivered is greater than anticipated and delivery timeframes are highly compressed. (i.e.; ~5 months between the planned publication of final B2B Procedures on March 6th and the commencement of Industry Testing in early August). Currently unable to reasonably assess ability to align with Industry Testing and Market Transition phases as strategies for these activities have not been drafted.
| CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Within schedule | Medium | CitiPower/Powercor continues to progress its analysis and build phase to schedule. | [7 empty] | CitiPower/Powercor are intending to only be the initial Metering Co-ordinator/Metering Provider/Meter Data Provider for CitiPower and Powercor's legacy metering fleet. Our assessment of the jurisdictional risk rating is based on Victorian government determining final transitional metering arrangements by the end of Q1, 2017. Similarly, the jurisdictional industry operating model is yet to be agreed amongst jurisdictional participants for key activities such as new connections and metering faults.
| Endeavour Energy | At risk | Medium | A project risk is the implementation of system and procedural changes to comply with the B2B procedures. The initial draft of the B2B procedures suggests that there will be significant system and process changes, however the B2B procedures are not expected to be finalised until early March 2017. This only leaves 8 months to analyse the impacts, specify the requirements and design, develop and build, test internal and with the market, and train impacted staff. It is noted that registration as a B2B e-Hub Participants is required before the B2B e-Hub can be used. This registration process is also at risk as there is a depenedency to demonstrate system compliance with the B2B procedures. To mitigate this we are actively participating in the various working groups including the PoC-WG, B2BWG and SWG to ensure that AEMO procedures and B2B procedures supports the metering contestability and embedded networks rule changes in the most effective and cost efficient manner, and to only include transactions and obligations required for go live as a priority. | [7 empty] | [See overall project comment] | [5 empty] | This report is for Endeavour Energy as at 31 December 2016. Endeavour Energy will be operating as a LNSP, and as the initial MC, MP and MDP for type 5 and 6 metering installations from 1 December 2017. Endeavour Energy have implemented a project team to manage the impacts of Power of Choice. Most activities are at early stages because there are still a number of pending decisions such as the B2B procedures, AEMO procedure changes pack 2, jurisdictional obligations, AER's classification of network services etc. The activities for the Market Systems testing and cutover are dependent on the development and build of the appropiate market system which is currently at risk.
| Energex Ltd. & Ergon Energy Corporation Ltd. | Within schedule | Medium | The project is progressing as planned. However, ring-fencing, new B2B Procedures and new system requirements are collectively proving to make planning and delivery challenging in such a tight timeframe. | [7 empty] | Proposed changes to B2B Procedures have impacted planning activities and the associated schedule. The project is currently tracking within schedule, however potentially at risk. | [5 empty] | Please note that the progress % on each category may appear less that the last reporting period. This is due to the change in progress % ranges from 25% to 10%.
| Essential Energy | Within schedule | Medium | Essential Energy's PoC program is underway and progressing to schedule. Risk rating is classified as moderate associated with the implementation of system and procedural changes to comply with the updated B2B procedures, recognising the B2B procedures are not expected to be finalised until early March 2017. This will leave only 5 months for implementation prior to industry testing. Systems changes will need to be specified on draft procedures, as released for consultation on 23 December 2016, to enable Essential Energy to meet delivery timeframes, which comes with inherant risk that the final procedures may vary from the draft. | [7 empty] | Essential Energy will be an initial MC for Type 5 and 6 meter installations connected as at 1 December 2017. Risk rating is classified as moderate due to commencement of systems build prior to receipt of finalised procedures. [Meter Provider - Type 5 &6 basic meters only. Risk rating of low] [Meter Data Provider - Type 5 & 6 basic meters only. Risk rating is classified as moderate due to commencement of systems build prior to receipt of finalised procedures.] | [5 empty] | Essential Energy is actively participating in AEMO industry groups and NSW jurisdictional workshops associated with Power of Choice.
| Jemena Electricity Networks | Within schedule | Medium | The project is rated at Medium risk this report due to 1. the uncertainty associated with the Victorian Government Transition to Metering Competition in Victoria decision timing in March 2017; 2. the adequacy of the proposed industry testing scope and timeframe; 3. the proposed go-live date of 1 December 2017 causing a need to cutover mid week, at a Financial Month End period prior to the Financial & Regulatory Year End period, and during a period of high volumes for Customer new connections, adds and alts pre-Christmas. | [7 empty] | The project is rated at Medium risk this report due to 1. the uncertainty associated with the Victorian Government Transition to Metering Competition in Victoria decision timing in March 2017; 2. the adequacy of the proposed industry testing scope and timeframe; 3. the proposed go-live date of 1 December 2017 causing a need to cutover mid week, at a Financial Month End period prior to the Financial & Regulatory Year End period, and during a period of high volumes for Customer new connections, adds and alts pre-Christmas.
| Sa Power Networks | Within schedule | Medium | Currently on schedule
| TasNetworks | At risk | Medium | TasNetworks plan is to be ready business preparations and the development of specifications with vendors is progressing well, TasNetworks' market systems build schedule could propose a delivery timeline post the industry testing dates, not allowing TasNetworks to fully participate in industry testing before the scheduled go live.
| United Energy | At risk | Medium | Internal preparations are progressing well. Process and solution designs are nearing completion in areas not affected by shared market protocol (SMP), in accordance with schedule. System development will commence in January. Amber status reflects uncertainty over jurisdictional adoption of Metering Competition, timing of SMP details and other readiness factors. | [7 empty] | UE operates in Victoria only. Jurisdictional status refects overall position. [Note: Initial MC, MP and MDP only (for existing meters)] | [5 empty] | Key concerns for UE (and industry) readiness are as follows: 1) The Victorian Government approach to "Transition to Metering Competition" is not finalised, with the options paper still under consideration and a decision not expected until March 2017 or later. Until the Govt. provide a final position, UE's project will continue on the assumption of full adoption in Victoria in Dec 2017. Regulatory changes in Victoria at that point, or later, have the potential to result in changes to project scope and requirements, and may negatively impact readiness. 2) Publication of Package 2 Procedures at the start of Mar 2017 necessitates design of business processes and functionality based on assumptions and draft B2B/SMP documents. Delayed publication of the procedures, failed assumptions and/or any major changes between draft and final procedures will impact project timelines and therefore readiness preparations. 3) Lack of definitive direction on whether VICAMI meters can remain as Type 5 MRIM is creating uncertainty around whether system changes, data changes and accreditation for Type 4 meters will be required in this area. Continuing to seek confirmation from AEMO, AER and Victorian Government. 4) UE compliance with the ENM rules and ring-fencing is dependent on Embedded Network Managers being accredited, assigned and ready to operate by 1 Dec 2017. UE's compliance in this area may also dependent on existing child metering services being transitioned to non-regulated meter providers on or by 1 Dec 2017, although this is yet to be confirmed. If transition is required, it will be an activity over which UE does not have full control. 5) After 1 Dec 2017, UE may not be able to avoid temporarily providing regulated metering services (via its Initial MP and MDP roles) under a competitive MC if the new MC is unable to organise timely meter exchanges after a churn event. 6) UE is concerned that the lateness of procedures finalisation and the complexity and scale of testing with the increased number of market participants may ultimately lead to negative impacts on consumers. Strong focus will be required to ensure that connections, supply and supply restoration processes are clear, and industry has a uniform, efficient and reliable approach so the reform is seamless to customers. Supply restoration includes faults, damaged meters, unplanned replacement and associated communication steps for Consumers.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| ActewAGL Distribution (AAD) | Within schedule | N/A
| Ausgrid |  |  | At risk | Medium
| AusNet Services | [10 empty] | At risk | High
| CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | [10 empty] | Within schedule | Medium
| Endeavour Energy |  |  | At risk | Medium
| Energex Ltd. & Ergon Energy Corporation Ltd. |  |  |  |  | Within schedule | Medium
| Essential Energy |  |  | Within schedule | Medium
| Jemena Electricity Networks | [10 empty] | Within schedule | Medium
| Sa Power Networks | [6 empty] | Within schedule | Medium
| TasNetworks | [8 empty] | At risk | Medium
| United Energy | [10 empty] | At risk | Medium
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | Sa Power Networks | TasNetworks | United Energy | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 61% - 70% | 41% - 50% | Completed (100%) | Completed (100%) | 11% - 20% | 41% - 50% | 71% - 80% | 21% - 30% | Completed (100%) | 71% - 80% | Completed (100%)
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 41% - 50% | 21% - 30% | 21% - 30% | Completed (100%) | 11% - 20% | 61% - 70% | 31% - 40% | Not started (0%) | 41% - 50% | 41% - 50% | Completed (100%)
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 21% - 30% | 21% - 30% | 21% - 30% | Completed (100%) | 1% - 10% | 1% - 10% | 61% - 70% | 21% - 30% | 31% - 40% | 31% - 40% | 51% - 60%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 11% - 20% | 21% - 30% | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 21% - 30% | Not started (0%)
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 11% - 20% | 1% - 10% | Not started (0%) | 11% - 20% | 1% - 10% | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | 1% - 10% | Not started (0%)
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 1% - 10% | Not started (0%) | Not started (0%) | 21% - 30% | Not started (0%) | 11% - 20% | Not started (0%) | Not started (0%) | Not started (0%) | 41% - 50% | Not started (0%)
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 21% - 30% | Not started (0%)
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 21% - 30% | 31% - 40% | 11% - 20% | Not started (0%) | 11% - 20% | 1% - 10% | 1% - 10% | 11% - 20% | Not started (0%) | 21% - 30% | Completed (100%)
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Not started (0%) | 31% - 40% | Not started (0%) | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | 1% - 10% | 21% - 30% | Not started (0%) | Not started (0%) | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 21% - 30% | 21% - 30% | 11% - 20% | 21% - 30% | 1% - 10% | 21% - 30% | 31% - 40% | 21% - 30% | 21% - 30% | 41% - 50% | Completed (100%)
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 1% - 10% | 1% - 10% | 11% - 20% | 21% - 30% | Not started (0%) | 11% - 20% | Not started (0%) | Not started (0%) | 21% - 30% | Not started (0%) | 61% - 70%
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 21% - 30% | 11% - 20% | 11% - 20% | 21% - 30% | 1% - 10% | 11% - 20% | Not started (0%) | 21% - 30% | 11% - 20% | 71% - 80% | 61% - 70%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 1% - 10% | Not started (0%) | 1% - 10% | 21% - 30% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
5.3 |  | The internal testing of market systems for your business | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | 11% - 20% | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | 1% - 10% | Not started (0%)
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | Sa Power Networks | TasNetworks | United Energy | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | Completed | Completed | Within schedule | Within schedule | At risk | Within schedule | Completed | Within schedule | Completed
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule | At risk | Completed | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Completed
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule | At risk | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Not within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule |  | Within schedule | Within schedule | Within schedule | Within schedule | Not within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk |  | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Completed
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Completed
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | At risk
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | N/A | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | At risk | At risk | At risk | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | At risk
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | At risk | At risk | At risk | Within schedule | At risk |  | Within schedule | Within schedule | Within schedule | At risk | At risk
5.3 |  | The internal testing of market systems for your business | [5 empty] | At risk | N/A | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | At risk | N/A | At risk | Within schedule | Within schedule |  | Within schedule | Within schedule | Within schedule | At risk | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | At risk | N/A | At risk | Within schedule | Within schedule |  | Within schedule | Within schedule | Within schedule | At risk | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule |  | Within schedule | Within schedule | Within schedule | At risk | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | Sa Power Networks | TasNetworks | United Energy | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Known released and approved POC change requirements have been scoped. Unknown changes may have unforeseen impacts. Plans are being developed. 12 mths of AEMO development of IT Systems (particularly the B2B Hub) and only 3.5 mths for industry testing before committing to production is disparate. |  |  |  |  | High-level scope and requirements documents have been signed off by the business. Currently scoping business transformation activities and reviewing B2B Procedures. | Unable to finalise impact assessment until final B2B procedures are distributed. Risk significant variations may occur between the 2nd draft of procedures and the final. |  |  | Will be completed with the finalisation of pack 2 and a review of the impact assessment
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Known released and approved POC change requirements have been scoped. Unknown changes may have unforeseen impacts. Plans are being developed. |  | Implementation plans for internal systems established. Development of Industry implementation and market transition plans required to validate internal scope/approach. |  |  | Ongoing activity - the Project Management Plan and critical path have been drafted. The Project is currently reviewing against market timeframes. The business transformation plan is being progressed. The volume (over 500) and type of B2B Procedure changes continue to put pressure on the critical path to industry testing and 1 December 'Go Live'. A significant example impacting our market systems is our requested change that was not accepted, i.e. that an EWR is submitted to a Distributor prior to a Retailer. Queensland Legislation sections 226 and 231 of the Electrical Safety Regulation 2013 support our position.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | The AAD PoC team continues to hold regular meetings with the legal / regulatory team to ensure compliance with all regulatory requirements. Assessment of impacts is underway with clarity around unknown changes affecting the ability of the business to fully understand the final impacts. In addition to this AAD holds regular forums with external stakeholders including the ACT Govt. to ensure a smooth transition takes place. |  | Impact of possible delay in Victorian Government Options assessment and subsequent changes to Vic Regulatory Codes and safety requirements. Uncertain framework for maintaining Vic AMI Meters Type 5 after 1 December. | Note: This assessment excludes AEMO procedures that remain in draft. |  | Ongoing activity - currently under review by organisational specialists. |  |  |  |  | Vic. Govt. is considering options for "transition to metering competition". The assessment of legal and regulatory frameworks cannot be completed until a decision is made (expected around March 2017). Once the Govt. position is clear, the ESC can also make amendments to reflect the NERR type obligations within Victoria. There are also a number of points of clarification required in regards to on-site safety obligations, particularly for connections work. A number of Vic. Govt. instruments and contracts will also need amendment. This remains well behind UE schedule and has the potential to impact business process and market systems work referenced in the rows below.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Final POC procedure changes remain unknown. The ACT is undergoing substantial transformation to accommodate increased contestability in the metering sphere and significant uncertainty still remains. |  | Impact of possible delay in Victorian Government Options assessment and subsequent changes to Vic Regulatory Codes and safety requirements. Uncertain framework for maintaining Vic AMI Meters Type 5 after 1 December. | Note: In line with CitiPower/Powercor program delivery schedule. | [6 empty] | As noted above, Vic. Govt. is considering options for "transition to metering competition". Internal documentation and policies cannot be finalised until a decision is made (expected around March 2017). This is well behind UE schedule.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Consultation is underway with existing and potential business partners to establish appropriate arrangements for the post PoC operating model. |  | Definition of B2B Procedures and finalisation of Market Roles required to establish associated commercial arrangements | Note: In line with CitiPower/Powercor program delivery schedule. |  | Ongoing activity - currently meeting with contract owners and associated business subject matter experts. |  |  |  |  | Plans are in place to address the commercial implications, and resourcing is now in place. Work will commence before end of Jan 2017.
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Registration procedures are yet to be finalised by AEMO. The business is working on the basis of incomplete information and will review and adjust accordingly as more information comes to hand. There is a concern that AEMO have only allowed 8 months for existing businesses to transition to new accredited businesses that are required under the new rule structure. |  | Accreditation procedures not published | Note: We have completed our assessment of the required accreditations and registrations. The activities to achieve these are related to AEMO procedures which remain in draft. |  | Initial discussions with AEMO representative on the approach that the existing LNSP, MPB and MDP accreditations will continue. MC will be a registration process given our current RP role. Formal confirmations to follow. |  |  |  |  | Accreditation requirements for UE are not yet confirmed, due to lack of clarity on whether VICAMI meters will have to be reclassified as Type 4. Also the registration process for metering competition is not yet clear.
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | AAD remains compliant with its current obligations and will review and assess any future requirements as AEMO makes more information available. |  | Accreditation procedures not published | Note: In line with CitiPower/Powercor program delivery schedule. | See above comment | [5 empty] | Plans and funding are in place to cover UE accreditation if it is necessary. The draft accreditation requirements and checklist are being reviewed. Time and effort will be required to assess the requirements when they are finalised and to ensure that internal processes & policies meet the accreditation criteria. This is expected to take several months, leading to accreditation occurring in late Q3/Q4 2017.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | AAD has begun assessing future requirements. Finalisation by AEMO of procedures and IT Systems will require that this position is reassessed. |  | Has started, however may be impacted by Victorian Government Options assessment and subject to finalisation of market procedures. | Note: In line with CitiPower/Powercor program delivery schedule. |  | Ongoing activity - currently analysing the human resources impact due to Power of Choice implementation.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Not yet begun. Noting PoC removes current functions from existing businesses which may result in staff reductions in some areas while the increased volume of interval metering data may result in increases to staff numbers elsewhere (TBC). |  |  | Note: In line with CitiPower/Powercor program delivery schedule. | [6 empty] | Not required until late 2017
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Not yet begun. |  |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | Training approach has commenced. |  |  |  |  | Development of training strategy and plan will commence during Jan '17.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Final POC procedure changes remain unknown. AAD has assessed impacts on its current business practices based on the available knowledge and will revise as more information becomes available. |  | Subject to finalisation of market procedures and Vic Gov't approach | Note: In line with AEMO schedule of released documentation and CitiPower/Powercor program delivery schedule. |  | Ongoing activity - currently documenting current and future state processes through development of detailed requirements. Less than expected progress due to rework as a result of the nature of the latest B2B Procedure changes. |  |  |  | Will be completed with the finalisation of pack 2 and a review of the impact assessment
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Final POC procedure changes remain unknown. AAD has assessed impacts on its current business practices based on the available knowledge and will revise as more information becomes available. |  | Subject to finalisation of market procedures and Vic Gov't approach | Note: In line with AEMO schedule of released documentation and CitiPower/Powercor program delivery schedule. |  | Ongoing activity - currently working with subject matter experts to verify current and future state processes. Less than expected progress due to rework as a result of the volume (over 500) and nature of the latest B2B Procedure changes. |  |  |  |  | Business processes in certain areas are dependent on, or heavily impacted by, the SMP/B2B procedures. These processes cannot be fully designed until procedures are published in Mar 2017. This delays the design and development of system changes, putting readiness at risk. Any delay to the release of the procedures will increase the risk.
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not yet begun. |  | Subject to finalisation of market procedures and Vic Gov't approach and Industry Testing approach | Note: In line with AEMO schedule of released documentation and CitiPower/Powercor program delivery schedule. |  | Test approach is ongoing. Scope of industry testing is unclear. Confirming the scope of industry testing prior to 30 January 2017 would enable businesses to effectively meet the industry testing date. |  |  |  |  | Plans are in place to execute industry testing. However the current draft of B2B procedures includes the movement of currently enforceable details into a non-binding "guidance" category. The industry considers some of these details to be necessary for uniform, reliable end-to-end processing in the market. UE is concerned that varying interpretations and inconsistencies between industry participants will become apparent during industry testing and may threaten its progress.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Final requirements are yet to be released by AEMO, however, those requirements that are known have been scoped and are in design (we estimate that approximately 10% of requirements are known). | Not all system impacts have been assessed in detail | Subject to finalisation of market procedures and Vic Gov't approach. Schedule for delivery of market system changes likely to be impacted by late definition of market procedures and extent of changes required.. | Note: In line with AEMO schedule of released documentation and CitiPower/Powercor program delivery schedule. | See above comment | Ongoing activity - currently developing market systems detailed requirements documents leading into detailed design activities. The type of change in this release of the B2B Procedures indicates that there will be significant changes in the next (final) release of the B2B Procedures in March 2017. |  |  |  |  | Business requirements have been completed and approved. Design is nearing completion in some areas, but is being undertaken "at risk" in those areas that might be impacted by the publication of final B2B procedures in Mar 2017.
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Design is in progress for B2B system processes. Limited information is known about the new AEMO B2B hub. This is a major risk area for success. | Waiting for finalisation of the B2B changes. | Finalisation of build plans is subject to completion of consultation process, due March 6th. Current scope of proposed changes is assessed as greater than the minimum required to support market operation. | Note: In line with CitiPower/Powercor program delivery schedule. | See above comment |  |  |  |  | The plan is to be ready development of specifications with vendors is progressing well, the build schedule could be passed the industry testing dates, limiting industry testing participation | System development is on track to commence in Jan 2017, with preparations commenced. Some areas of development will not be able to commence until after March 2017 due to the timing of final B2B procedures (or later, depending on the timing of the Victorian policy and clarity of regulatory changes).
5.3 |  | The internal testing of market systems for your business | [5 empty] | Not yet begun. | Not at the stage of testing market systems. | Definition of internal Test Strategy is subject to finalisation of delivery scope and Industry Testing approach. | Note: In line with CitiPower/Powercor program delivery schedule. |  | Test approach is tracking to schedule. |  |  |  | The plan is to be ready development of specifications with vendors is progressing well, the build schedule could be passed the industry testing dates, limiting industry testing participation | Plans in place and resourcing agreed. Not yet due.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not yet begun. | Not at the stage of testing market systems. | Definition of Industry Test Strategy has not commenced. Timeframe for Industry Testing is very short given complexity, scope and number of participants | Note: In line with CitiPower/Powercor program delivery schedule. |  | Requested changes to B2B Procedures that have not occurred relating to EWRs (i.e. the submission to a Distributor prior to a Retailer). This will significantly impact our market systems and the ability for our readiness by the industry testing date. Scope of industry testing is unclear. Confirming the scope of industry testing prior to 30 January 2017 would enable businesses to effectively meet the industry testing date. |  |  |  | The plan is to be ready development of specifications with vendors is progressing well, the build schedule could be passed the industry testing dates, limiting industry testing participation | Plans in place and resourcing agreed. Not yet due.
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not yet begun. | Not at the stage of testing market systems. | Final specifications of hub required. Role of non-functional testing as part of Industry Testing is required. | Note: In line with CitiPower/Powercor program delivery schedule. | [5 empty] | The plan is to be ready development of specifications with vendors is progressing well, the build schedule could be passed the industry testing dates, limiting industry testing participation | Plans in place and resourcing agreed. Not yet due.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Not yet begun. |  | Industry approach has not been defined, therefore ability to meet schedule is unclear | Note: In line with CitiPower/Powercor program delivery schedule. |  | Discussions are continuing with impacted groups and information gathering to inform transition plans. |  |  |  |  | Plans in place and resourcing agreed. Not yet due.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not yet begun. |  | Industry approach has not been defined, therefore ability to meet schedule is unclear | Note: In line with CitiPower/Powercor program delivery schedule. | [5 empty] | The AEMO schedule is challenging to deliver in the current timeframe. | Plans in place and resourcing agreed. Not yet due.
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | Sa Power Networks | TasNetworks | United Energy | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Stage Gates built into Schedule based on AEMO identified key milestones. Implementation approach that develops solutions as best as practical now and change later when AEMO formally releases information.
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | As above. |  | Provide support for early definition of market procedures |  |  | Currently working through the B2B Procedure changes to understand impacts on detailed requirements, design and build. B2B configuration changes occurring in parallel to mitigate timeframe constraints.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [15 empty] | UE continues to actively participate in the consultation process, and is encouraging a prompt decision. UE is also encouraging Vic. Govt. to develop a programme plan for the industry and to create a regulatory working group to develop the necessary instrument amendments. UE will actively participate in the working group and any Vic. Govt., ESC and/or ESV consultation processes.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | First pass review of all impacted procedures to identified anticipated level of change required (Hi, Med, Low). | [9 empty] | As above.
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Stage Gate milestone of 1 March 2017 included in schedule (for submission to AEMO) | [9 empty] | Continuing to seek confirmation from AEMO, AER and Victorian Government on whether UE's meters can remain as Type 5 MRIM.
2.5 |  | The fulfilment of accreditation and registration obligations | [9 empty] | See above comment
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [10 empty] | Additional experienced resources and subject matter experts have been sourced as a preventative mitigation strategy.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [10 empty] | Additional experienced resources and subject matter experts have been sourced to support ongoing business process activity and as a preventative mitigation strategy. |  |  |  |  | Business process design is continuing within UE, based on a combination of assumptions and draft material from the B2B working group and AEMO. This involves risk of re-work and wasted effort if the final B2B procedures differ from the drafts, but that risk is lower than waiting until Mar 2017 before commencing process design.
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | AAD is developing system designs in the absence of finalised requirements being issued by AEMO. | A formal ICT project has been established and additional resources have been assigned. The project is tracking to its' timeline. | Requirement to provision additional resources to be assessed in order to deliver scope within timeframes. |  | See above comment | Additional experienced resources and subject matter experts have been sourced to support ongoing market systems activity and as a preventative mitigation strategy. |  |  |  |  | Solution design is continuing within UE, based on a combination of assumptions and final draft B2B procedures. This involves risk of re-work and wasted effort if the final B2B procedures differ from the drafts, but that risk is lower than waiting until Mar 2017 before commencing solution design.
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Stage Gates built into Schedule based on AEMO identified key milestones. Implementation approach that develops solutions as best as practical now and change later when AEMO formally releases information. |  | Some development is proceeding based on assumed outcome. Impact of variances between current draft and final processes will be undertaken when these are published on March 6th. |  | See above comment | [5 empty] | System development will commence in Jan 2017 for areas not impacted by B2B procedures. Development for B2B-related functionality will commence as soon as there is sufficient confidence in the B2B procedures and associated process and solution designs.
5.3 |  | The internal testing of market systems for your business | [7 empty] | Strategy to be validated when Industry testing Strategy has been defined.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [7 empty] | Strategy to be validated when Industry testing Strategy has been defined.
5.5 |  | The validation of performance of market systems during industry testing | [7 empty] | Internal non-functional testing to be undertaken.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [7 empty] | Support development of industry approach.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [7 empty] | Support development of industry approach.
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## MP and MDP Reports
| 2017-01-16 |  |  | Metering Provider (MP) and Metering Data Provider (MDP) Readiness Assessment Reports - see Distributors Report tab for initial MP and MDP
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Active Stream | Within schedule | Low | [14 empty] | Active Stream is currently accredited and operating as an Type 4 MDP and MPB/MPC. Systems and processes are currently in place, requiring AS to assess and deliver the delta to comply with the POC requirements. Our approach with the Progress and Traffic Light Status is related to POC specific amendments.
| Metering Dynamics (MD) | Within schedule | Medium | Ring fencing, new POC procedures, new systems, merger of Energex, Ergon and Sparq into Energy Queensland are all combining to make planning and delivery difficult given the very tight timeframe. | [7 empty] | MP: MD have experience and capability as MP - risk rating low MDP: MD have experience and capability as MDP - risk rating medium
| VectorAMS | Within schedule | Medium | Scope of change, tight timeframes, current uncertainty on transition at cutover and approach to Industry testing leads to a Project risk rating of Medium.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| Active Stream |  |  | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Metering Dynamics (MD) | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium
| VectorAMS | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | Active Stream | Metering Dynamics (MD) | VectorAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 71% - 80% | 31% - 40% | 61% - 70%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 81% - 99% | 21% - 30% | 31% - 40%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 51% - 60% | 11% - 20% | 51% - 60%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 51% - 60% | 1% - 10% | Not started (0%)
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 51% - 60% | 1% - 10% | Not started (0%)
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 71% - 80% | 21% - 30% | 11% - 20%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 71% - 80% | 1% - 10% | Not started (0%)
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 31% - 40% | 11% - 20% | Not started (0%)
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%)
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%)
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 21% - 30% | 31% - 40% | 1% - 10%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 21% - 30% | 11% - 20% | Not started (0%)
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%)
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 21% - 30% | 41% - 50% | Not started (0%)
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Not started (0%) | 11% - 20% | Not started (0%)
5.3 |  | The internal testing of market systems for your business | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%)
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%)
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Not started (0%) | 1% - 10% | Not started (0%)
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | Active Stream | Metering Dynamics (MD) | VectorAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | Within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | Within schedule | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Within schedule | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule | Within schedule
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Within schedule | Within schedule | Within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | Within schedule | Within schedule
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Within schedule | Within schedule | Within schedule
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | Within schedule | Within schedule
5.3 |  | The internal testing of market systems for your business | [5 empty] | Within schedule | Within schedule | Within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | Active Stream | Metering Dynamics (MD) | VectorAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities | [6 empty] | On track assuming the accreditation requirements will not materially change from the drafts provided.
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Dependent on the finalisation of associated industry documentation.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [6 empty] | Ring fencing, restructure and merger are requiring additional business process effort and approvals.
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | Active Stream | Metering Dynamics (MD) | VectorAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [6 empty] | Full-time program manager appointed and additional resources are being sourced.
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Metering Coordinator Reports
| 2017-01-16 |  |  | Metering Coordinator (MC) Readiness Assessment Reports - see Distributors Report tab for initial MC
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Active Stream | Within schedule | Low | [14 empty] | Active Stream is currently accredited and operating as an Type 4 MDP and MPB/MPC. Systems and processes are currently in place, requiring AS to assess and deliver the delta to comply with the POC requirements. Our approach with the Progress and Traffic Light Status is related to POC specific amendments.
| Energy Australia | Within schedule | Medium | Overall, on track to be ready from a build point of but with B2B Procedures and Regulatory Changes have not been finalised, there is still a risk that this may result in rework. | [7 empty] | Overall, on track to be ready from a build point of but with B2B Procedures and Regulatory Changes have not been finalised, there is still a risk that this may result in rework.
| Metering Dynamics (MD) | Within schedule | Medium | Ring fencing, new POC procedures, new systems, merger of Energex, Ergon and Sparq into Energy Queensland are all combining to make planning and delivery difficult given the very tight timeframe. | [7 empty] | New role and procedures not finalised in B2B and MSATS
| Momentum Energy | Within schedule | Medium | Work packages and final B2B procedure documentation is not due until March 2017. All current scoping and impact assessments have been based on draft procedures. Any significant changes from draft procedures will have a direct project impact due to constrained timelines for project. | [7 empty] | In early stages of scoping and analysis
| VectorAMS | Within schedule | Medium | Scope of change, tight timeframes, current uncertainty on transition at cutover and approach to Industry testing leads to a Project risk rating of Medium.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| Active Stream |  |  | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Energy Australia | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| Metering Dynamics (MD) | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium
| Momentum Energy | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| VectorAMS | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | Active Stream | Energy Australia | Metering Dynamics (MD) | Momentum Energy | VectorAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 71% - 80% | 61% - 70% | 31% - 40% | 71% - 80% | 61% - 70%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 81% - 99% | 51% - 60% | 21% - 30% | 21% - 30% | 31% - 40%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 51% - 60% | 21% - 30% | 11% - 20% | 11% - 20% | 51% - 60%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 51% - 60% | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%)
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 51% - 60% | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%)
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 71% - 80% | Not started (0%) | 21% - 30% | 1% - 10% | 11% - 20%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 71% - 80% | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%)
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 31% - 40% | 41% - 50% | 11% - 20% | Not started (0%) | Not started (0%)
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%)
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 21% - 30% | 51% - 60% | 31% - 40% | Not started (0%) | 1% - 10%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 21% - 30% | 11% - 20% | 11% - 20% | Not started (0%) | Not started (0%)
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 21% - 30% | 51% - 60% | 41% - 50% | 31% - 40% | Not started (0%)
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Not started (0%) | Not started (0%) | 11% - 20% | Not started (0%) | Not started (0%)
5.3 |  | The internal testing of market systems for your business | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Not started (0%) | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%)
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | Active Stream | Energy Australia | Metering Dynamics (MD) | Momentum Energy | VectorAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | At risk | Within schedule | Within schedule | Within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | At risk | Within schedule | Within schedule | Within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
5.3 |  | The internal testing of market systems for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | Active Stream | Energy Australia | Metering Dynamics (MD) | Momentum Energy | VectorAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [6 empty] | Assessment in progress and on track but there are still unknowns in regards to jurisdictional safety requirements, and associated obligations on Retailers and MCs.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [6 empty] | Waiting on finalised procedures in order to lock down the requirements which may result in re-work
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities | [7 empty] | On track assuming the accreditation requirements will not materially change from the drafts provided.
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Dependent on the finalisation of associated industry documentation.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [7 empty] | Ring fencing, restructure and merger are requiring additional business process effort and approvals.
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [8 empty] | System development is reliant on external vendor, delays in final market procedures will impact readiness activities
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | Active Stream | Energy Australia | Metering Dynamics (MD) | Momentum Energy | VectorAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [7 empty] | Full-time program manager appointed and additional resources are being sourced.
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Embedded Networks
| 2017-01-16 |  |  | Embedded Networks Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Momentum Energy | Within schedule | Medium | Work packages and final B2B procedure documentation is not due until March 2017. All current scoping and impact assessments have been based on draft procedures. Any significant changes from draft procedures will have a direct project impact due to constrained timelines for project. | [7 empty] | In early stages of scoping and analysis
| Network Energy Services | Within schedule | Low | Getting prepared to implement all aspects
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| Momentum Energy | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| Network Energy Services | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | Momentum Energy | Network Energy Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 71% - 80% | 1% - 10%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 21% - 30% | Not started (0%)
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 11% - 20% | Not started (0%)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Not started (0%) | Not started (0%)
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Not started (0%) | Not started (0%)
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 1% - 10% | Not started (0%)
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Not started (0%) | Not started (0%)
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Not started (0%) | Not started (0%)
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Not started (0%) | Not started (0%)
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Not started (0%) | Not started (0%)
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Not started (0%) | Not started (0%)
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Not started (0%) | Not started (0%)
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | Not started (0%)
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 31% - 40% | Not started (0%)
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Not started (0%) | Not started (0%)
5.3 |  | The internal testing of market systems for your business | [5 empty] | Not started (0%) | Not started (0%)
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not started (0%) | Not started (0%)
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Not started (0%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Not started (0%) | Not started (0%)
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | Not started (0%)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | Momentum Energy | Network Energy Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Within schedule | Within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | Within schedule
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Within schedule | Within schedule
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | Within schedule
5.3 |  | The internal testing of market systems for your business | [5 empty] | Within schedule | Within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Within schedule | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | Momentum Energy | Network Energy Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [6 empty] | Getting prepared to implement all aspects
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [6 empty] | Getting prepared to implement all aspects
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [6 empty] | Getting prepared to implement all aspects
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [6 empty] | Getting prepared to implement all aspects
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | System development is reliant on external vendor, delays in final market procedures will impact readiness activities | Getting prepared to implement all aspects
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [6 empty] | Getting prepared to implement all aspects
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | Momentum Energy | Network Energy Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Third Party
| 2017-01-16 |  |  | Third Party Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
0
0
0
0
0
0
0
0
0
0
0
0
0
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## AEMO
AEMO Readiness Assessment Report
B. Overall project status
| A. Details | [6 empty] | Project status | Project risk rating | Comment
| Date | 2017-01-16 | [5 empty] | Within schedule | Medium | The pending Vic Govt decision and the instruments that are chosen to implement the decision could impact the delivery program. A decision and formal notification in Q1 2017 will be required. System build and scenario based transition and cut-over planning are dependent on the final B2B Procedures being publish on schedule. Delays to this process could impact downstream timeframes.
| Organisation | AEMO
C. Jurisdictional status
# | Organisation | ACT | NSW | QLD | SA | TAS | VIC | Status | Risk | Comment
1 | AEMO | √ | √ | √ | √ | √ | √ | Within schedule | Medium
2
3
4
5
6
D. Detailed status
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%) | Traffic light status | Explanation of variance/Notes | Mitigating actions
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 71% - 80% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 71% - 80% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
1.3 |  | Delivery of the Market Readiness Strategy and associated plans | [5 empty] | 11% - 20% | Within schedule | AEMO finalised first version on Market Readiness Strategy and Industry Readiness Plan in collaboration with Industry. First drafts of Industry Test Strategy and Accreditation and Registration Plans on schedule for Industry review in February 2017 |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 71% - 80% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.2 |  | The development, documentation and approval of updated internal policies consistent with regulatory changes including jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Not started (0%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Not started (0%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 61% - 70% | Within schedule | Undertaking detailed planning for AEMO activities during the accreditation and registration phase based on draft procedures |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Not started (0%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.6 |  | The publication of updated AEMO retail electricity market procedures and associated documentation | [5 empty] | 81% - 99% | Within schedule | Final determination due on 28 February 2017 |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.7 |  | The publication of updated B2B retail electricity market procedures and associated documentation | [5 empty] | 71% - 80% | Within schedule | Expected to publish final B2B procedures on 6 March 2017 |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 21% - 30% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 31% - 40% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
3.3 |  | The development and delivery of training to staff in operational roles | [5 empty] | Not started (0%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 21% - 30% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 11% - 20% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4.4 |  | The delivery of POC information sessions to participants | [5 empty] | 31% - 40% | Within schedule | First two sessions (out of 6) held on 28 November 2016. Next sessions scheduled for March 2017 |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5. Market systems
5.1 | Market systems - MSATS (B2M) | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 81% - 99% | Within schedule | R35 schema was approved and published on 16 January 2017 |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 51% - 60% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.3 |  | The internal testing of market systems for your business | [5 empty] | 41% - 50% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not started (0%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.6 | Market systems - B2B e-hub | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 31% - 40% | Within schedule | Reviewing feedback in relation to the Technical design specification. |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.7 |  | The development and build of appropriate market systems for your business | [5 empty] | 11% - 20% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.8 |  | The internal testing of market systems for your business | [5 empty] | Not started (0%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.9 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not started (0%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.1 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 1% - 10% | Within schedule | Initial planning and strawman development commenced. Industry engagement in March 2017 |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
7. General notes
AEMO has issued a call for nominations to establish the industry testing working group. AEMO will establish a Transition and cut-over group in March 2017. The key industry focus for much of 2017 includes the building of systems, the establishment of bi-lateral agreements (where required) and the development of transition and cut-over options.B26
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
[12 empty] | 41% - 50% | Retailer
[12 empty] | 51% - 60% | Distributor
[12 empty] | 61% - 70% | Meter Provider
[12 empty] | 71% - 80% | Meter Data Provider
[12 empty] | 81% - 99% | Metering Coordinator
[12 empty] | Completed (100%) | Embedded Network Manager
[12 empty] | N/A | Embedded Network Operator
Third Party B2B Participant
Within schedule
At risk
Not within schedule
N/A
[12 empty] | Completed | √
x
Low
Medium
High
N/A