## Slide 1: AEMO ‘Power of choice’ Readiness Working Group (POC-RWG)
28 November 2016

## Slide 2: Agenda
Welcome and introduction (14:00-14:10)
November Readiness Report (14:10-14:30)
Readiness Reporting Debrief (14:30-15:00)
EN & MC system changes update (15:00-15:10)
Forward meeting plan (15:10-15:20)
Closing – Actions & next steps (15:20-15:30)

## Slide 3: 2. November readiness report
Number of submissions:
25 reports received in total:
  9 retailers
  11 distribution businesses (initial MC)
    7 of these also MP and MPD
  4 metering companies (MPD, MP, MC)
  1 tentative ENM
Other responses:
2 retailers intend to commence reporting in Q1 2017
1 metering company has not formally submitted a report:
  Green across board
  May engage if risk increases significantly

## Slide 4: 2. NOVEMBER READINESS REPORT
Summary:
Overall rating of “within schedule” with a “medium” risk rating
Risks relate to timing of Procedure development and subsequent impact:
  Business processes
  System development, build and testing
  Registration and accreditation
“Medium” to “high” risk rating highlighted in Victoria due to:
  Uncertainty associated with the Victorian Government Transition to Metering Competition in Victoria decision timing in March 2017
  VICAMI meter type
Program progress approximately 25%

## Slide 5: 3. Readiness report debrief
AEMO changes (to AEMO’s participant template)
Separated Procedure development:
  AEMO Procedures
  IEC (B2B) Procedures
Separated Market systems development:
  EN/MC changes (B2M)
  E-hub (B2B)
AEMO changes (to Monthly Summary)
Changed 2.1:
  From “Internal policies updated for consistency with jurisdictional regulations and requirements (e.g. safety)”
  To “Internal policies updated for regulatory changes including jurisdictional regulations and requirements (e.g. safety)”

## Slide 6: 3. Readiness report debrief
Feedback received to date:
Change progress to categories, eg:
  Not started
  1% - 25%
  26%-50%
  51%-75%
  76%-99%
  Completed
Feedback discussion:
  On reporting - process, reporting criteria, etc.?
  On summary report – criteria, summarising, usefulness, etc.?

## Slide 7: 3. Readiness report NexT STEPS
Next round of reporting due by 16 January 2017:
Additional feedback due by 5 December 2016
POC-RWG to email comments to POC@aemo.com.au
Depending on nature and scale of feedback AEMO will either:
  Call a POC-RWG to discuss feedback and version 2.0
  Circulate an version 2.0 to be used for January report by 16 December 2016
AEMO will continue to engage with participants yet to report, and new participants (ENM) as they come on-board.

## Slide 8: 4. EN & MC SYSTEM UPDATE
This is split into 9 deliverables
  NMI Ranges and related items (New screen, Validation, C1 Report)
  Required CR/OBJ Changes
  Exception (PMS) reporting configuration
  Additional info against Embedded Networks
  New Status codes (NMI status and meter register)
  New Meter install codes
  C7 report changes
  aseXML Schema change
  Batch handler Update
All system changes, including schema change in pre-production by Monday 3 April 2017

## Slide 9: 5. DRAFT INDUSTRY MEETING SCHEDULE
POC-RWG meetings (TBC)
13 February – First draft of Registration and Accreditation Plan and discussion on testing for EN/MC changes
8 March – First draft of Industry Testing Plan for e-hub (Market Trial)
24 March – Q1 Readiness update
5 April – First draft of Transition and Cutover Plan

## Slide 10: 4. Industry readiness reporting plan – FEEDBACK AND CHANGES
Other
Reporting on the number of open risks and issues
Added specific criteria on readiness of B2B e-hub for industry testing
Notes field for general comments included
Contingency plans
No specific criteria asking participants if they have contingency measures in place
Implementation and Transition plans expected to have contingency planning incorporated
Purpose of reporting is to highlight areas where industry may need to develop industry-wide contingency measures

## Slide 11: 6. Closing
Actions
POC-RWG comments to POC@aemo.com.au by 5 Dec on:
  Readiness reporting
AEMO to prepare summary note of today’s meeting
Next steps
AEMO to distribute meeting summary note to POC-RWG
AEMO to distribute version 2.0 of reporting to POC-RWG
Next meeting
13 February 2017 (tbc)