## Market Readiness Report Page 1
2016-11-14
AEMO Power of Choice Implementation Program
|  | Monthly Readiness Report | 2016-11-14
Overall Status |  | Commentary |  |  | Risk Rating |  | # Open Risks - Rating: |  |  | Issues:
|  | Overall AEMO and the majority of participants are on schedule to meet the program deliverables. However the risk rating of the program overall is Medium, due to schedule constraints associated with Procedure development and subsequent system development and testing. A Medium to High risk rating has also been highlighted in Victoria due to uncertainty associated with the Victorian Government Transition to Metering Competition in Victoria decision timing in March 2017. |  |  |  |  | High | Med | Low | #
[7 empty] | 1 | 3 | 3 | 0
AEMO and NEM Participants Readiness Criteria |  |  | AEMO |  | Retailers |  | Distributors |  | MP and MDP |  | Metering Coordinator |  | Other (3rd party, ENM)
# | Category | Criterion | Status | Note | Status | Note | Status | Note | Status | Note | Status | Note | Status | Note
1. Assessment and preparation
1.1 | Assessment and preparation | Consequences of the POC reforms for your business considered, and appropriate implementation plans are in place
1.2 |  | Key readiness planning documents delivered
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | Updated retail electricity market procedures and associated documents published |  | #1
2.2 |  | Internal policies updated for regulatory changes including jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Operationally critical commercial contracts in place
2.4 |  | Accreditation and registration activities completed
3. People
3.1 | People | Operational roles specified, assigned to staff, and training delivered
4. Business processes
4.1 | Business processes | Updated, validated and approved business processes in place
4.2 |  | Successfully validated critical business processes during industry testing
4.3 |  | Process work‑arounds in place for any issues identified during industry testing
5. Market systems
5.1 | Market systems | Delivery of the re-developed B2B e-hub for industry testing |  | #2
5.2 |  | Successfully tested market systems capable of being moved into production |  | #3 |  | #4 |  | #4 |  | #4
5.3 |  | Performance of, and communication between, market systems validated during industry testing
6. Transition planning
6.1 | Transition planning | Transition and cutover plan(s) in place
6.2 |  | Prerequisite transition and cutover processes completed (e.g. trial data conversions and cutover dress rehearsals)
Jurisdictional Status
Jurisdiction |  | Comments | AEMO |  | Retailers |  | Distributors |  | MP and MDP |  | Metering Coordinator |  | Other (3rd party, ENM)
|  |  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
ACT |  | Jurisdicational risk is a reflection of overall project risk.
NSW |  | Jurisdicational risk is a reflection of overall project risk.
QLD |  | Jurisdicational risk is a reflection of overall project risk.
SA |  | Jurisdicational risk is a reflection of overall project risk.
TAS |  | Jurisdicational risk is a reflection of overall project risk.
VIC |  | Jurisdicational risk is a reflection of overall project risk, with additional risk noted due to the uncertainty associated with the Victorian Government Transition to Metering Competition in Victoria decision timing in March 2017.

## HIDDEN (hidden)
ü
| 100 | 75 | 50 | 25 | 0
| 0 | 25 | 50 | 75 | 100
WITHIN SCHEDULE | [5 empty] | Risks | Low
Medium
High
AT RISK
NOT WITHIN SCHEDULE

## Market Readiness Report Page 2
AEMO Power of Choice Implementation Program
Monthly Readiness Report
2016-11-14
Variances
Note # | Explanation of Variance |  | Mitigating Actions
1 | B2B procedures at risk due to legal and Technical issues coupled with a reduced period for review and 2nd stage drafting |  | Directive on Legal Drafting, Technical Delivery Specification drafted by 30 Nov, B2B WG/AEMO Workplan for 2nd stage consultation
2 | B2B e-hub development dependent on B2B procedures (Refer to #1) |  | Refer to #1
3 | Development of system changes due to the Embedded Network and Metering in Competition (EN/MC) well advanced, however B2B e-hub development changes at risk as per #1 and #2 |  | Refer to #1
4 | Retailers and Distributors, MP and MDPs highlighted that delivery of their updated market systems are at risk due to the dependency on B2B procedures |  | Participants are engaging with POC-SWG and designing solutions based on draft materials.
Notes
Please note that the number of open risks and issues is based on the POC Risk and Issue log from 5 Sep 2016. The POC-PCF is holding a Risk Session on 25 November 2016 to update the register.
Key - Progress and Status |  |  |  |  | Key - Risk Rating
Progress |  | Status
Harvey balls represent progress towards achieving the criterion |  | Colour indicates the readiness status |  |  | Rating
~100% |  | Criterion is within agreed schedule and deliverable requirements |  |  | High
~75% |  | Criterion is at risk of not meeting requirements and corrective action may be required |  |  | Medium
~50% |  | Criterion not meeting requirements. Immediate corrective action required |  |  | Low
~25%
~0% |  | Criterion has been achieved |  | ü | See POC Industry Risk Register for open risks and issues:
POC Industry Register

## Retailer Reports
| 2016-11-14 |  |  | Retailer Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| AGL Retailer | Within schedule | Low | Project currenly tracking to plan for Dec 2017 delivery | [7 empty] | Project currenly tracking to plan for Dec 2017 delivery
| Aurora Energy | Within schedule | Low | Aurora Energy is currently in the process of understanding the impact of market changes on its operations. This will form the basis of its plans to efficiently and effectively work towards market compliance. The on-going uncertainty regarding market operation under the rule is the most significant risk.
| EnergyAustralia | Within schedule | Medium | Work packages and final B2B documentation is not due until March 2017. Any significant changes from B2B Procedures/Work packages will have a direct project impact
| Ergon Energy Queensland | Within schedule | Medium | Due to the high number of procedural and B2B procedures still under consultation in the market, overall this project remains as a 'medium risk' | [7 empty] | Due to the high number of procedural and B2B procedures still under consultation in the market, overall this project remains as a 'medium risk'
| Lumo and Red Energy |  |  | Will commence reporting in 2017
| M2 Energy Pty Ltd | Within schedule | Medium | Project Scoping by Vendor has commenced. Business operations impact scope has not commenced. Business intention is to outsource MC role. Risk considered Medium as no vendor currently available for selection. M2 Energy is maintaining dialogue with potential vendors. | [7 empty] | Business intention is to outsource MC role. No vendor currently available.
| Mojo Power Pty Ltd | Within schedule | Medium | [8 empty] | Mojo Power will be entering Victroian market in early 2017
| Momentum Energy |  |  | Under development
| Origin Energy | At risk | Medium | Overall project delivery status at risk, due to constrained timelines for delivery against overall AEMO Delivery Timelines. Business and Systems impact assessments are having to be conducted with high degree of assumption of how B2B, SMP and systems designs will be agreed. If there is significant variance or change to these assumptions during consultation process, there is a high risk that Origin Energy may not have sufficient time and resources available to complete the requisite changes. | [7 empty] | Overall project delivery status at risk, due to constrained timelines for delivery against overall AEMO Delivery Timelines. Business and Systems impact assessments are having to be conducted with high degree of assumption of how B2B, SMP and systems designs will be agreed. If there is significant variance or change to these assumptions during consultation process, there is a high risk that Origin Energy may not have sufficient time and resources available to complete the requisite changes.
| Pacific Hydro | Within schedule | Medium | Although the current MSATS and B2B Consultations are within the planned timeframes, there is a risk the MSATS CATS Procedures may need to be revisited as a result of the outcomes of the B2B Consultation and the technical solution agreed by the System Working Group will add onerous complexity to market communications; both outcomes impacting the build test and implementation phases.
| People Energy |  |  | Will commence reporting in 2017
| Powershop | Within schedule | Medium | Without B2B and SMP finalised the system build is at its earliest stage of scoping.
| Simply Energy | Within schedule | Low | [14 empty] | Simply Energy is running an internal Power of Choice Program of Work. The program has not yet identified any internal risks. The key risk identified is due to external factors. This is the risk that published Procedures differ significantly from draft Procedures. Significant differences will pose a significant market readiness risk because the internal business requirements have been based on draft Procedures.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| AGL Retailer |  |  | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Aurora Energy | [8 empty] | Within schedule | Low
| EnergyAustralia | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Ergon Energy Queensland |  |  |  |  | Within schedule | Medium
Lumo and Red Energy
| M2 Energy Pty Ltd |  |  | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| Mojo Power Pty Ltd |  |  | Within schedule | Medium | Within schedule | Medium |  |  |  |  | Within schedule | Medium
Momentum Energy
| Origin Energy | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Pacific Hydro |  |  | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
People Energy
| Powershop |  |  | Within schedule | Low | Within schedule | Low |  |  |  |  | Within schedule | Low
| Simply Energy | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | AGL Retailer | Aurora Energy | EnergyAustralia | Ergon Energy Queensland | Lumo and Red Energy | M2 Energy Pty Ltd | Mojo Power Pty Ltd | Momentum Energy | Origin Energy | Pacific Hydro | People Energy | Powershop | Simply Energy | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 75% | 25% | 50% | 25% |  | 25% | 50% |  | 50% | 100% |  | 75% | 50%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 25% | 25% | 25% | 25% |  | 25% | 0% |  | 25% | 50% |  | 50% | 25%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 50% | 0% | 25% | 25% |  | 0% | 50% |  | 50% | 50% |  | 75% | 25%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 0% | 0% | 0% | 0% |  | 0% | 50% |  | 25% | 0% |  | 0% | 0%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 0% | 0% | 25% | 0% |  | 0% | 50% |  | 0% | 0% |  | 25% | 25%
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 25% | N/A | 0% | 0% |  | 0% | N/A |  | 0% | 25% |  | 25% | 0%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 0% | N/A | 0% | 0% |  | N/A | N/A |  | 0% | 0% |  | 0% | 0%
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 0% | 0% | 25% | 0% |  | 0% | 25% |  | 50% | 25% |  | 50% | 25%
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 0% | 0% | 0% | 0% |  | N/A | 75% |  | 0% | 0% |  | 0% | 0%
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | 0% | 0% | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0%
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 25% | 25% | 25% | 25% |  | 0% | 0% |  | 50% | 25% |  | 25% | 25%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 25% | 25% | 25% | 0% |  | 0% | 0% |  | 25% | 0% |  | 0% | 0%
4.3 |  | The validation of business processes during industry testing | [5 empty] | 0% | 0% | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0%
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 25% | 25% | 50% | 0% |  | 25% | 0% |  | 25% | 0% |  | 25% | 0%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 0% | 0% | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0%
5.3 |  | The internal testing of market systems for your business | [5 empty] | 0% | 0% | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0%
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | 0% | 0% | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0%
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | 0% | 0% | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0%
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 0% | 0% | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0%
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | 0% | 0% | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0%
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | AGL Retailer | Aurora Energy | EnergyAustralia | Ergon Energy Queensland | Lumo and Red Energy | M2 Energy Pty Ltd | Mojo Power Pty Ltd | Momentum Energy | Origin Energy | Pacific Hydro | People Energy | Powershop | Simply Energy | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule |  | Within schedule | Within schedule |  | Within schedule | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule |  | At risk | Within schedule |  | Within schedule | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule | At risk | Within schedule |  | Within schedule | Within schedule |  | At risk | Within schedule |  | Within schedule | Within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule |  | At risk | Within schedule |  | Within schedule | Within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule |  | At risk | Within schedule |  | Within schedule | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | N/A | Within schedule | Within schedule |  | Within schedule | N/A |  | At risk | Within schedule |  | Within schedule | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | N/A | Within schedule | Within schedule |  | N/A | N/A |  | At risk | Within schedule |  | Within schedule | N/A
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule |  | At risk | Within schedule |  | Within schedule | Within schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule |  | N/A | Within schedule |  | At risk | Within schedule |  | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule |  | At risk | Within schedule |  | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Within schedule | Within schedule | At risk | Within schedule |  | Within schedule | Within schedule |  | At risk | Within schedule |  | Within schedule | Within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule |  | At risk | Within schedule |  | Within schedule | Within schedule
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule |  | At risk | Within schedule |  | Within schedule | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule |  | At risk | Within schedule |  | Within schedule | Within schedule
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule |  | Not within schedule | Within schedule |  | Within schedule | Within schedule
5.3 |  | The internal testing of market systems for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule |  | At risk | Within schedule |  | Within schedule | Within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule |  | At risk | Within schedule |  | Within schedule | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule |  | At risk | Within schedule |  | Within schedule | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule |  | At risk | Within schedule |  | Within schedule | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule |  | At risk | Within schedule |  | Within schedule | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | AGL Retailer | Aurora Energy | EnergyAustralia | Ergon Energy Queensland | Lumo and Red Energy | M2 Energy Pty Ltd | Mojo Power Pty Ltd | Momentum Energy | Origin Energy | Pacific Hydro | People Energy | Powershop | Simply Energy | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [6 empty] | Aurora Energy has implemented a project to understand, prepare and implement the POC reforms. The current focus of this project is a detailed assessment of necessary business operational and systems changes. | [6 empty] | Impact Assessment being conducted against assumed consultation outcomes and changes
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [6 empty] | A project plan is currently being prepared for Aurora Energy to effectively and efficiently work towards market compliance. A draft estimate of business change impacts, required investment and ability to comply with rule at commencement is planned for December 2016. The on-going uncertainty regarding market operation under the rule is the most significant risk. | [6 empty] | Detailed implementation schedule and program resourcing cannot be accurately determined until impact assessment is completed
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [6 empty] | Activity has not yet started. | Have commenced assessment work. Jurisdictional safety regulations have not been defined by the safety regulators- This is a dependency. Conversations and forums have commenced however the regulations needed to inform the assessment have not been finalised. |  |  | not yet scheduled. |  |  | Detailed implementation schedule and program resourcing cannot be accurately determined until impact assessment is completed |  |  |  | Awaiting jurisdictional safety regulators to publish requirements
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [6 empty] | Activity has not yet started. | Consultation on procedures still occurring. Updates would commence once final procedures published. Also safety regulations not finalised |  |  | not yet scheduled. |  |  | Policy changes/decisions cannot be endorsed until IA completed |  |  |  | Scheduled to commence in 2017
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [6 empty] | Activity has not yet started. | Work on this item has commenced based on contracts created as part of the NSW SBS rollout |  |  | not yet scheduled. |  |  | Detailed implementation schedule and program resourcing cannot be accurately determined until impact assessment is completed
2.4 |  | An assessment of the required accreditation and registration activities | [7 empty] | Procedures for this section have only just been released for consultation – Assessment would commence once final procedures published |  |  | not yet scheduled. | Mojo not seeking to attain new accreditations |  | Detailed implementation schedule and program resourcing cannot be accurately determined until impact assessment is completed |  |  |  | Scheduled to commence in 2017
2.5 |  | The fulfilment of accreditation and registration obligations | [7 empty] | Procedures for this section have only just been released for consultation – Assessment would commence once final procedures published |  |  |  | Mojo not seeking to attain new accreditations |  | Detailed implementation schedule and program resourcing cannot be accurately determined until impact assessment is completed |  |  |  | Depends on outcome of 2.4
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [6 empty] | To be completed in following with the detailed assessment of operational and systems changes. |  |  |  | not yet scheduled. |  |  | Detailed implementation schedule and program resourcing cannot be accurately determined until impact assessment is completed
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [6 empty] | Pending above. | [6 empty] | Detailed implementation schedule and program resourcing cannot be accurately determined until impact assessment is completed |  |  |  | Scheduled to commence in 2017
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [6 empty] | Pending above. |  |  |  | not yet scheduled. |  |  | Training requirements and resourcing unable to be accurately determined until impact assessment is completed and magnitude of change is understood |  |  |  | Scheduled to commence in 2017
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [6 empty] | All impacted service order, B2B & B2M and business processes have been identified. Assessment of current and future processes is underway to enable gap analysis and identify process and system changes. | B2B procedures are not finalised which has impacts on business processes |  |  | not yet scheduled. |  |  | Detailed implementation schedule and program resourcing cannot be accurately determined until impact assessment is completed; a high degree of assumption has had to be made in order for this work to progress
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [6 empty] | Future business processes are currently being developed using the details from Work package 1 and 2, as well as the B2B draft procedures. |  |  |  | not yet scheduled. |  |  | Detailed implementation schedule and program resourcing cannot be accurately determined until impact assessment is completed |  |  |  | Scheduled to commence in 2017
4.3 |  | The validation of business processes during industry testing | [6 empty] | Activity has not yet started. |  |  |  | not yet scheduled. |  |  | Detailed implementation schedule and program resourcing cannot be accurately determined until impact assessment is completed |  |  |  | Scheduled to commence in 2017
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [6 empty] | An impact assessment is underway which includes a business process and system gap analysis. The gap analysis will drive system and business change requirements. |  |  |  | external vendor has commenced scoping. |  |  | Detailed impact assessment of system changes has only just commenced, and is highly dependent on decisions, outcomes and information provided in Systems and B2B Working Groups | A full assessment cannot be made until the Systems Working Group resolve the technical solution for B2B. |  |  | High level assessment is complete, detailed assessment will required concrete set of Procedures
5.2 |  | The development and build of appropriate market systems for your business | [6 empty] | Aurora Energy is awaiting clarity on the final full set of changes to the B2B/B2M environment. This activity will be completed once these are provided by AEMO. In tandem with this, Aurora Energy is undertaking a gap analysis to inform required market systems of technical and business process change effort. | [6 empty] | Systems development commencement is dependent on the outcomes and conclusions of the Systems IA and Requirements being understood |  |  |  | Scheduled to commence in 2017
5.3 |  | The internal testing of market systems for your business | [6 empty] | This has not started and not due to start until 2017. | [6 empty] | Systems testing is dependent on the outcomes and conclusions of the Systems IA and Requirements being understood |  |  |  | Scheduled to commence in 2017
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [6 empty] | This has not started and not due to start until mid-2017. | [6 empty] | Systems integration is dependent on the outcomes and conclusions of the Systems IA and Requirements being understood |  |  |  | Scheduled to commence in 2017
5.5 |  | The validation of performance of market systems during industry testing | [6 empty] | This has not started and not due to start until mid-2017. | [6 empty] | Dependent on the outcomes and conclusions of the Systems IA and Requirements being understood |  |  |  | Scheduled to commence in 2017
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [6 empty] | Transition Plans will be completed once AEMO packages and commercial agreements with metering coordinator(s) are finalised. | [6 empty] | Transition planning and scheduling cannot be accurately determined until impact assessment is completed |  |  |  | Scheduled to commence in 2017
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [6 empty] | Activity has not yet started. | [6 empty] | Unable to commence at this point in the project schedule |  |  |  | Scheduled to commence in 2017
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | AGL Retailer | Aurora Energy | EnergyAustralia | Ergon Energy Queensland | Lumo and Red Energy | M2 Energy Pty Ltd | Mojo Power Pty Ltd | Momentum Energy | Origin Energy | Pacific Hydro | People Energy | Powershop | Simply Energy | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [13 empty] | Origin has onboarded additional Business and Technology resources to expedite Impact Assessment completion
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [7 empty] | Raised with AEC to progress | [5 empty] | Origin has onboarded additional Business and Technology resources to expedite Impact Assessment completion |  |  |  | Internal assessments have commenced
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [13 empty] | Origin has onboarded additional Business and Technology resources to expedite Impact Assessment completion
2.4 |  | An assessment of the required accreditation and registration activities | [13 empty] | Origin has onboarded additional Business and Technology resources to expedite Impact Assessment completion
2.5 |  | The fulfilment of accreditation and registration obligations | [13 empty] | Origin has onboarded additional Business and Technology resources to expedite Impact Assessment completion
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [13 empty] | Origin has onboarded additional Business and Technology resources to expedite Impact Assessment completion
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [13 empty] | Origin has onboarded additional Business and Technology resources to expedite Impact Assessment completion
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [13 empty] | Origin has onboarded additional Business and Technology resources to expedite Impact Assessment completion
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [7 empty] | Workshops have commenced, working through business scenarios to identify process and impacts | [5 empty] | Origin has onboarded additional Business and Technology resources to expedite Impact Assessment completion
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [13 empty] | Origin has onboarded additional Business and Technology resources to expedite Impact Assessment completion
4.3 |  | The validation of business processes during industry testing | [13 empty] | Origin has onboarded additional Business and Technology resources to expedite Impact Assessment completion
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [13 empty] | Origin has onboarded additional Business and Technology resources to expedite Impact Assessment completion
5.2 |  | The development and build of appropriate market systems for your business | [13 empty] | Origin has onboarded additional Business and Technology resources to expedite Impact Assessment completion
5.3 |  | The internal testing of market systems for your business | [13 empty] | Origin has onboarded additional Business and Technology resources to expedite Impact Assessment completion
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [13 empty] | Origin has onboarded additional Business and Technology resources to expedite Impact Assessment completion
5.5 |  | The validation of performance of market systems during industry testing | [13 empty] | Origin has onboarded additional Business and Technology resources to expedite Impact Assessment completion
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [13 empty] | Origin has onboarded additional Business and Technology resources to expedite Impact Assessment completion
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [13 empty] | Origin has onboarded additional Business and Technology resources to expedite Impact Assessment completion
0%
25%
50%
75%
100%
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Distributor Reports
| 2016-11-14 |  |  | Distributor Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| ActewAGL Distribution (AAD) | Within schedule |  | Within the constraints and information provided by AEMO, AAD are on schedule and in a proactive state of preparedness. Critical enablers are yet to be released by AEMO to substantiate this position with a suitable level of confidence. Significant concerns are held over the undetermined POC procedure changes, issues register outcomes and the potential need for substantial system changes. | [13 empty] | Accreditation transfer and registration starting 2 March is a risk area and it is noted that AEMO will still be developing systems and processes at the time industry is requested to start this process. The readiness of AAD to interface with the AEMO B2B hub is a significant risk. In the absence of information, the system changes required to facilitate this new data flow is undefined. It is noted AEMO have 12 mths to develop this and Industry only have 3.5 mths to implement. There is a disparate timeframe for Industry to modify, test, put into production and this is noted as a major area of concern for AAD.
| Ausgrid | At risk | Medium | A number of significant IT rebuilds are expected to be required in order to facilitate the new B2B requirements. However, the final B2B procedures are not expected to be established until well into next year, allowing only an extremely tight timeframe to specify, built and test the required systems and processes. | [7 empty] | As per project
| AusNet Services | At risk | Medium | Initial impact assessment complete and delivery project mobilisation underway. | [7 empty] | Our project is subject to following external risks - Vic Govt policy uncertainty - lack of certainty about B2B and eHub including the B2B Technical Specification Procedure - the scope of proposed procedural change is greater than anticipated - Uncertainty over whether and when VICAMI meters will need to be reclassified as Type 4
| CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Within schedule | High | CitiPower/Powercor has completed the mobilisation phase of its program. All resources required have been identified and the program is in the analysis and build phase. This assessment is applicable to roles of: 1. Distribution Network Service Provider (DNSP) 2. Initial Metering Coordinator (MC) for CitiPower and Powercor's legacy metering fleet as of 1 December 2017 3. Metering Provider (MP) 4. Metering Data Provider (MDP). Our assessment of the project risk rating is High primarily because industry procedure releases are currently in very early stages. This risk rating will be reassessed as procedures mature. Our assessment of jurisdictional risk is discussed in Table C below. [see to right] | [7 empty] | Our assessment of the jurisdictional risk rating is High primarily because the Victorian Government has advised that the Victorian transitional metering arrangements will be determined by the end of Q1, 2017. In addition, the Victorian Working Group to review and amend jurisdictional instruments is yet to convene. Similarly, the jurisdictional industry operating model is yet to be agreed amongst jurisdictional participants for key activities such as new connections and metering faults.
| Endeavour Energy | At risk | Medium | A project risk is the implementation of system and procedural changes to comply with the B2B procedures. The initial draft of the B2B procedures suggests that there will be significant system and process changes, however the B2B procedures are not expected to be finalised until early March 2016. This only leaves 8 months to analyse the impacts, specify the requirements and design, develop and build, test internal and with the market, and train impacted staff. It is noted that the initial draft of the B2B technical specification will not be released until late December 2016 which prevents us from making early impact assessments. Another project risk is AEMO's mandate to reuse a NMI when a connection point moves from a distribution network to an embedded network, and vice versa. This has system impacts and the final decision is not expected until late February 2017. This only leaves 9 months to update our a number of our core systems. To mitigate this we are actively participating in the various working groups including the PoC-WG, B2BWG and SWG to ensure that the AEMO procedures and B2B procedures supports the metering contestability and embedded networks rule changes in the most effective and cost efficient manner, and to only include transactions and obligations required for go live as a priority. | [7 empty] | As per project | [5 empty] | Endeavour Energy will be operating as a LNSP, and as the initial MC, MP and MDP for type 5 and 6 metering installations from 1 December 2017. We have highlighted to AEMO that the progress scale could be improved to indicate a range instead of a milestone to allow for better reporting. In the interim we have taken the progress scale to indicate progress up to the percentage milestone e.g. 25% indicates that we have started and have progressed between 1% to 25%. Endeavour Energy have implemented a project team to manage the impacts of Power of Choice. Most activities are at early stages because there are still a number of pending decisions such as the B2B procedures, the ring fencing guideline, AEMO procedure changes pack 2, jurisdictional obligations, AER's classification of network services etc.
| Energex Ltd. & Ergon Energy Corporation Ltd. | Within schedule | Medium | Progressing as planned however ring fencing, new POC procedures and new systems are all combining to make planning and delivery challenging given the very tight timeframe. | [13 empty] | Full business case has been submitted for approval by the board in December 2016. Organisation wide engagement on the changes to the Distribution business operating model as a result of Power of Choice have commenced.
| Essential Energy | Within schedule | Medium | Essential Energy's PoC program is underway and progressing to schedule. Risk rating is classified as moderate due to commencement of systems build prior to receipt of finalised procedures. | [7 empty] | Essential Energy will be an initial MC for Type 5 and 6 meter installations connected as at 1 December 2017. Risk rating is classified as moderate due to commencement of systems build prior to receipt of finalised procedures. | [5 empty] | Essential Energy is actively participating in AEMO industry groups and NSW jurisdictional workshops associated with Power of Choice.
| Jemena Electricity Networks | Within schedule | Medium | The project is rated at Medium risk this report due to 1. the uncertainty associated with the Victorian Government Transition to Metering Competition in Victoria decision timing in March 2017; 2. industry procedures development is in early stages; and 3. the Victorian Working Group to review and amend jurisdictional instruments is yet to convene. | [7 empty] | The project is rated at Medium risk this report due to 1. the uncertainty associated with the Victorian Government Transition to Metering Competition in Victoria decision timing in March 2017; 2. industry procedures development is in very early stages; and 3. the Victorian Working Group to review and amend jurisdictional instruments is yet to convene.
| SA Power Networks | Within schedule | Medium | Currently on schedule
| United Energy | At risk | Medium | Internal preparations are progressing well. The United Energy (UE) team and key IT vendor are in place and progress is in accordance with schedule. Process and solution design are progressing well. Amber status reflects uncertainty over jurisdictional adoption of Metering Competition, timing of shared market protocol details and a number of other readiness factors. | [7 empty] | UE operates in Victoria only. Jurisdictional status reflects overall position. Note: Initial MC, MP and MDP only (for existing meters) | [5 empty] | 1Key concerns for UE (and industry) readiness are as follows: 1) The Victorian Government approach to "Transition to Metering Competition" is not finalised, with the options paper still under consideration and a decision not expected until March 2017 or later. Until the Govt. provide a final position, UE's project will continue on the assumption of full adoption in Victoria in Dec 2017. Regulatory changes in Victoria at that point, or later, have the potential to result in changes to project scope and requirements, and may negatively impact readiness. 2) Publication of Package 2 Procedures at the end of Feb 2017 necessitates design of business processes and functionality based on assumptions and draft B2B/SMP documents. Delayed publication of the procedures, failed assumptions and/or any major changes between draft and final procedures will impact project timelines and therefore readiness preparations. 3) Lack of definitive direction on whether VICAMI meters can remain as Type 5 MRIM is creating uncertainty around whether system changes, data changes and accreditation for Type 4 meters will be required in this area. 4) UE compliance with the ENM rules and ring-fencing is dependent on Embedded Network Managers being accredited, assigned and ready to operate by 1 Dec 2017. UE's compliance in this area is also dependent on existing child metering services being transitioned to non-regulated meter providers on or by 1 Dec 2017, an activity over which UE does not have full control. 5) After 1 Dec 2017, UE may not be able to avoid temporarily providing regulated metering services (via its Initial MP and MDP roles) under a competitive MC if the new MC is unable to organise timely meter exchanges after a churn event. 6) UE is concerned that the lateness of procedures finalisation and the complexity and scale of testing with the increased number of market participants may ultimately lead to negative impacts on consumers. Strong focus will be required to ensure that connections, supply and supply restoration processes are clear, and industry has a uniform, efficient and reliable approach so the reform is seamless to customers.
| TasNetworks DNSP | Within schedule | Medium | TasNetworks strategy is to modify process & extend the current IT systems
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| ActewAGL Distribution (AAD) | Within schedule
| Ausgrid |  |  | At risk | Medium
| AusNet Services | [10 empty] | At risk | Medium
| CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | [10 empty] | Within schedule | High
| Endeavour Energy |  |  | At risk | Medium
| Energex Ltd. & Ergon Energy Corporation Ltd. |  |  |  |  | Within schedule | Medium
| Essential Energy |  |  | Within schedule | Medium
| Jemena Electricity Networks | [10 empty] | Within schedule | Medium
| SA Power Networks | [6 empty] | Within schedule | Medium
| United Energy | [10 empty] | At risk | Medium
| TasNetworks DNSP | [8 empty] | Within schedule | Medium
0
0
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | SA Power Networks | United Energy | TasNetworks DNSP | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 25% | 50% | 100% | 100% | 25% | 50% | 50% | 25% | 100% | 100% | 75%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 0% | 25% | 25% | 100% | 25% | 25% | 25% | 25% | 50% | 100% | 25%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 25% | 25% | 25% | 100% | 25% | 25% | 50% | 25% | 0% | 50% | 25%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 0% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 25%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | N/A
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 0% | 0% | 0% | 25% | 0% | 0% | 0% | 25% | 0% | 0% | 50%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 25%
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 25% | 25% | 25% | 0% | 0% | 25% | 0% | 0% | 0% | 75% | 25%
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 0% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | 0% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 25% | 25% | 0% | 25% | 25% | 50% | 25% | 0% | 25% | 100% | 50%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 0% | 0% | 0% | 25% | 0% | 0% | 0% | 0% | 25% | 50% | 0%
4.3 |  | The validation of business processes during industry testing | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 25% | 25% | 25% | 25% | 25% | 25% | 0% | 25% | 0% | 50% | 75%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 0% | 0% | 0% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 25%
5.3 |  | The internal testing of market systems for your business | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 0% | 0% | 0% | 0% | 0% | 25% | 0% | 0% | 0% | 0% | 0%
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | SA Power Networks | United Energy | TasNetworks DNSP | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Completed | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Completed | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | At risk
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | N/A | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | At risk | At risk | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | At risk | At risk | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | At risk | At risk
5.3 |  | The internal testing of market systems for your business | [5 empty] | At risk | N/A | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | At risk | N/A | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | At risk | N/A | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | SA Power Networks | United Energy | TasNetworks DNSP | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Known released and approved POC change requirements have been scoped. Unknown changes may have unforeseen impacts. Plans are being developed. 12 mths of AEMO development of IT Systems (particularly the B2B Hub) and only 3.5 mths for industry testing before committing to production is disparate. |  | Initial assessment completed based on available information |  |  | Procedures and guidelines are not finalised. B2B timeline is on critical path and does not leave any room for delays. |  |  |  |  | TasNetworks progress is on track, waiting for pack 2 consolation before this task can be complete
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Known released and approved POC change requirements have been scoped. Unknown changes may have unforeseen impacts. Plans are being developed. |  | At risk due to lack of certainty about B2B and eHub Specification |  |  | Procedures and guidelines are not finalised. B2B timeline is on critical path and does not leave any room for delays. |  |  |  |  | TasNetworks progress is on track, waiting for pack 2 consolation before this task can be complete
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | The AAD PoC team has regular meetings with the legal / regulatory team to ensure compliance with all regulatory requirements. Assessment of impacts is underway with clarity around unknown changes affecting the ability of the business to fully understand the final impacts. In addition to this AAD holds regular forums with external stakeholders including the ACT Govt. to ensure a smooth transition takes place. |  | Accreditation procedures not yet published and lack of certainty about B2B Procedures | Note: This assessment excludes AEMO procedures that remain in draft. |  | Procedures and guidelines are not finalised. B2B timeline is on critical path and does not leave any room for delays. |  |  |  | Vic. Govt. is considering options for "transition to metering competition". The assessment of legal and regulatory frameworks cannot be completed until a decision is made (expected around March 2017). Once the Govt. position is clear, the ESC can also make amendments to reflect the NERR type obligations within Victoria. A number of Vic. Govt. instruments and contracts will also need amendment. This is well behind UE schedule and has the potential to impact business process and market systems work referenced in the rows below. | On track
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Final POC procedure changes remain unknown |  | Accreditation procedures not yet published and lack of certainty about B2B Procedures | Note: In line with CitiPower/Powercor program delivery schedule. | [5 empty] | As noted above, Vic. Govt. is considering options for "transition to metering competition". Internal documentation and policies cannot be finalised until a decision is made (expected around March 2017). This is well behind UE schedule. | On track
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Not yet begun. |  | Accreditation procedures not yet published and lack of certainty about B2B Procedures | Note: In line with CitiPower/Powercor program delivery schedule. | [5 empty] | Plans are in place to address the commercial implications, and resourcing has been agreed. Not due to commence. | On track
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Registration procedures are yet to be finalised by AEMO. The business is working on the basis of incomplete information and will review and adjust accordingly as more information comes to hand. There is a concern that AEMO have only allowed 8 months for existing businesses to transition to new accredited businesses that are required under the new rule structure. |  | Accreditation procedures not yet published and lack of certainty about B2B Procedures | Note: We have completed our assessment of the required accreditations and registrations. The activities to achieve these are related to AEMO procedures which remain in draft. | [5 empty] | Accreditation requirements for UE are not yet confirmed, due to lack of clarity on whether VICAMI meters will have to be reclassified as Type 4. Also the registration process for metering competition is not yet clear. | On track
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | AAD remains compliant with its current obligations and will review and assess any future requirements as AEMO makes more information available. |  | Accreditation procedures not yet published and lack of certainty about B2B Procedures | Note: In line with CitiPower/Powercor program delivery schedule. | [5 empty] | Plans and funding are in place to cover UE accreditation if it is necessary. The accreditation requirements and checklist are being/will be reviewed and UE understands these will be changed significantly from current requirements. Time and effort will be required to review the requirements when they are finalised and to ensure that internal processes & policies meet the accreditation criteria. This is expected to take several months, leading to accreditation occurring in late Q3/Q4 2017. | On track
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | AAD has begun assessing future requirements. Finalisation by AEMO of procedures and IT Systems will require that this position is reassessed. |  | Initial assessment completed based on available information | Note: In line with CitiPower/Powercor program delivery schedule. |  | Currently developing a workforce strategy for impacted employees. |  |  |  | Change impact assessments are well progressed. | On track
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Not yet begun. Noting PoC removes current functions from existing businesses, this may result in reductions to staff (TBC). |  | Initial assessment completed based on available information | Note: In line with CitiPower/Powercor program delivery schedule. | [5 empty] | Plans in place. Not yet due. | On track
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Not yet begun. |  | Initial assessment completed based on available information | Note: In line with CitiPower/Powercor program delivery schedule. | [5 empty] | Plans in place. Not yet due. | On track
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Final POC procedure changes remain unknown. AAD has assessed impacts on its current business practices based on the available knowledge and will revise as more information becomes available. |  | Requires confirmationm of B2B and Work Practices | Note: In line with AEMO schedule of released documentation and CitiPower/Powercor program delivery schedule. |  | Currently completing detailed business requirements, including current and future state processes. |  |  |  |  | TasNetworks progress is on track, waiting for pack 2 consolation before this task can be complete
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Final POC procedure changes remain unknown. AAD has assessed impacts on its current business practices based on the available knowledge and will revise as more information becomes available. |  | Requires confirmationm of B2B and Work Practices | Note: In line with AEMO schedule of released documentation and CitiPower/Powercor program delivery schedule. | [5 empty] | Business processes in certain areas are dependent on, or heavily impacted by, the SMP/B2B procedures. These processes cannot be fully designed until procedures are published in Feb 2017. This delays the design and development of system changes, putting readiness at risk. Any delay to the release of the procedures will increase the risk. | Timeframes are tight with the release of the B2B in March 2107
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not yet begun. | Too early in the process for industry testing | Requires confirmationm of B2B and Work Practices | Note: In line with AEMO schedule of released documentation and CitiPower/Powercor program delivery schedule. | [5 empty] | Plans are in place to execute industry testing. However it is worth noting that the review of existing B2B Procedures may result in details that are currently enforceable being moved into a non-binding "guidance" category. The industry considers some of these details to be necessary for uniform, reliable end-to-end processing in the market. If these are moved to non-binding guidelines, varying interpretations and inconsistencies between industry participants will become apparent during industry testing and may threaten its progress. | Timeframes are tight with the release of the B2B in March 2107
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Final requirements are yet to be released by AEMO, however, those requirements that are known have been scoped and are in design (we estimate that approximately 10% of requirements are known). | Not all system impacts have been assessed in detail | Requires confirmationm of B2B and Work Practices | Note: In line with AEMO schedule of released documentation and CitiPower/Powercor program delivery schedule. | As per project | Currently completing detailed business requirements, including current and future state processes. |  |  |  | Business requirements have been completed and approved. Design is progressing well in most areas, but is being undertaken "at risk" in those areas that might be impacted by the publication of final B2B procedures in Feb 2017. | Timeframes are tight with the release of the B2B in March 2107
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Design is in progress for B2B system processes. Limited information is known about the new AEMO B2B hub. This is a major risk area for success. | Should be starting to build B2B market systems but finalised requirements will not be known for some while. | Requires confirmationm of B2B and Work Practices | Note: In line with CitiPower/Powercor program delivery schedule. | As per project |  |  |  |  | System development is on track to commence in Jan 2017. Some areas of development will not be able to commence until after March 2017 due to the timing of final B2B procedures (or later, depending on the timing of the Victorian policy and clarity of regulatory changes). | Timeframes are tight with the release of the B2B in March 2107
5.3 |  | The internal testing of market systems for your business | [5 empty] | Not yet begun. | Not yet at the stage of testing market systems. (B2B standards yet to be defined.) | Requires confirmationm of B2B and Work Practices | Note: In line with CitiPower/Powercor program delivery schedule. | [5 empty] | Plans in place. Not yet due. | Timeframes are tight with the release of the B2B in March 2107
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not yet begun. | Not yet at the stage of testing external interfaces. (B2B standards yet to be defined.) | Requires confirmationm of B2B and Work Practices | Note: In line with CitiPower/Powercor program delivery schedule. | [5 empty] | Plans in place. Not yet due. | Timeframes are tight with the release of the B2B in March 2107
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not yet begun. | Not yet at the stage of building market systems. (B2B standards yet to be defined.) | Requires confirmationm of B2B and Work Practices | Note: In line with CitiPower/Powercor program delivery schedule. | [5 empty] | Plans in place. Not yet due. | Timeframes are tight with the release of the B2B in March 2107
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Not yet begun. |  | To be assessed when Market Procedures published | Note: In line with CitiPower/Powercor program delivery schedule. |  | Initial discussions with impacted groups and information gathering to inform tranisition plans has begun. |  |  |  | Plans in place. Not yet due. | Timeframes are tight with the release of the B2B in March 2107, Industry cutover requirements are not know yet
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not yet begun. |  | To be assessed when Market Procedures published | Note: In line with CitiPower/Powercor program delivery schedule. | [5 empty] | Plans in place. Not yet due. | Timeframes are tight with the release of the B2B in March 2107, Industry cutover requirements are not know yet
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | SA Power Networks | United Energy | TasNetworks DNSP | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Stage Gates built into Schedule based on AEMO identified key milestones. Implementation approach that develops solutions as best as practical now and change later when AEMO formally releases information. |  | Assesment underway based on available information |  |  | Working with drafts and scenarios. Completing submissions and work as quickly as possible.
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | As above. |  | Assesment underway based on available information |  |  | Working with drafts and scenarios. Completing submissions and work as quickly as possible.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [7 empty] | Assesment underway based on available information |  |  | Attending working group and forums to determine what is required. |  |  |  | UE is actively participating in the consultation process, and is encouraging a prompt decision. UE is also encouraging Vic. Govt. to develop a programme plan for the industry and to create a regulatory working group to develop the necessary instrument amendments. UE will actively participate in the working group and any Vic. Govt., ESC and/or ESV consultation processes.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | First pass review of all impacted procedures to identified anticipated level of change required (Hi, Med, Low). |  | Assesment underway based on available information | [6 empty] | As above.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [7 empty] | Assesment underway based on available information
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Stage Gate milestone of 1 March 2017 included in schedule (for submission to AEMO) |  | Assesment underway based on available information | [6 empty] | Continuing to seek confirmation from AEMO on whether UE's meters can remain as Type 5 MRIM.
2.5 |  | The fulfilment of accreditation and registration obligations | [7 empty] | Assesment underway based on available information
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [7 empty] | N/A |  |  | Ongoing interaction with required stakeholders and SME's.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [7 empty] | N/A
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [7 empty] | N/A
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [7 empty] | Assesment underway based on available information |  |  | Ongoing interaction with required stakeholders and SME's.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [7 empty] | Assesment underway based on available information | [6 empty] | Business process design is continuing within UE, based on a combination of assumptions and draft material from the B2B working group and AEMO. This involves risk of re-work and wasted effort if the final B2B procedures differ from the drafts, but that risk is lower than waiting until Feb 2017 before commencing process design.
4.3 |  | The validation of business processes during industry testing | [7 empty] | Assesment underway based on available information
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [6 empty] | Additional resources to be put into assessment of market systems. | Participation in SWG and assessment of options |  | As per project | Ongoing interaction with required stakeholders and SME's. |  |  |  | Solution design is continuing within UE, based on a combination of assumptions and draft material from the B2B working group and AEMO. This involves risk of re-work and wasted effort if the final B2B procedures differ from the drafts, but that risk is lower than waiting until Feb 2017 before commencing solution design.
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Stage Gates built into Schedule based on AEMO identified key milestones. Implementation approach that develops solutions as best as practical now and change later when AEMO formally releases information. | Work with various industry groups in an attempt to expedite this. | Participation in SWG and assessment of options |  | As per project |  |  |  |  | System development will commence in Jan 2017 for areas not impacted by B2B procedures. Development for B2B-related functionality will commence as soon as there is sufficient confidence in the B2B procedures and associated process and solution designs.
5.3 |  | The internal testing of market systems for your business | [7 empty] | Participation in SWG and assessment of options
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [7 empty] | Participation in SWG and assessment of options
5.5 |  | The validation of performance of market systems during industry testing | [7 empty] | Participation in SWG and assessment of options
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [7 empty] | Assessment of options and risks as part of delivery planning |  |  | Ongoing interaction with required stakeholders and SME's.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [7 empty] | Assessment of options and risks as part of delivery planning
0%
25%
50%
75%
100%
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## MP and MDP Reports
| 2016-11-14 |  |  | Metering Provider (MP) and Metering Data Provider (MDP) Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| ActewAGL Distribution (AAD) | Within schedule |  | Within the constraints and information provided by AEMO, AAD are on schedule and in a proactive state of preparedness. Critical enablers are yet to be released by AEMO to substantiate this position with a suitable level of confidence. Significant concerns are held over the undetermined POC procedure changes, issues register outcomes and the potential need for substantial system changes. | [13 empty] | Accreditation transfer and registration starting 2 March is a risk area and it is noted that AEMO will still be developing systems and processes at the time industry is requested to start this process. The readiness of AAD to interface with the AEMO B2B hub is a significant risk. In the absence of information, the system changes required to facilitate this new data flow is undefined. It is noted AEMO have 12 mths to develop this and Industry only have 3.5 mths to implement. There is a disparate timeframe for Industry to modify, test, put into production and this is noted as a major area of concern for AAD.
| Ausgrid | At risk | Medium | A number of significant IT rebuilds are expected to be required in order to facilitate the new B2B requirements. However, the final B2B procedures are not expected to be established until well into next year, allowing only an extremely tight timeframe to specify, built and test the required systems and processes. | [7 empty] | As per project
| CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Within schedule | High | CitiPower/Powercor has completed the mobilisation phase of its program. All resources required have been identified and the program is in the analysis and build phase. This assessment is applicable to roles of: 1. Distribution Network Service Provider (DNSP) 2. Initial Metering Coordinator (MC) for CitiPower and Powercor's legacy metering fleet as of 1 December 2017 3. Metering Provider (MP) 4. Metering Data Provider (MDP). Our assessment of the project risk rating is High primarily because industry procedure releases are currently in very early stages. This risk rating will be reassessed as procedures mature. Our assessment of jurisdictional risk is discussed in Table C below. [see to right] | [7 empty] | Our assessment of the jurisdictional risk rating is High primarily because the Victorian Government has advised that the Victorian transitional metering arrangements will be determined by the end of Q1, 2017. In addition, the Victorian Working Group to review and amend jurisdictional instruments is yet to convene. Similarly, the jurisdictional industry operating model is yet to be agreed amongst jurisdictional participants for key activities such as new connections and metering faults.
| Endeavour Energy | At risk | Medium | A project risk is the implementation of system and procedural changes to comply with the B2B procedures. The initial draft of the B2B procedures suggests that there will be significant system and process changes, however the B2B procedures are not expected to be finalised until early March 2016. This only leaves 8 months to analyse the impacts, specify the requirements and design, develop and build, test internal and with the market, and train impacted staff. It is noted that the initial draft of the B2B technical specification will not be released until late December 2016 which prevents us from making early impact assessments. Another project risk is AEMO's mandate to reuse a NMI when a connection point moves from a distribution network to an embedded network, and vice versa. This has system impacts and the final decision is not expected until late February 2017. This only leaves 9 months to update our a number of our core systems. To mitigate this we are actively participating in the various working groups including the PoC-WG, B2BWG and SWG to ensure that the AEMO procedures and B2B procedures supports the metering contestability and embedded networks rule changes in the most effective and cost efficient manner, and to only include transactions and obligations required for go live as a priority. | [7 empty] | As per project | [5 empty] | Endeavour Energy will be operating as a LNSP, and as the initial MC, MP and MDP for type 5 and 6 metering installations from 1 December 2017. We have highlighted to AEMO that the progress scale could be improved to indicate a range instead of a milestone to allow for better reporting. In the interim we have taken the progress scale to indicate progress up to the percentage milestone e.g. 25% indicates that we have started and have progressed between 1% to 25%. Endeavour Energy have implemented a project team to manage the impacts of Power of Choice. Most activities are at early stages because there are still a number of pending decisions such as the B2B procedures, the ring fencing guideline, AEMO procedure changes pack 2, jurisdictional obligations, AER's classification of network services etc.
| Essential Energy | Within schedule | Medium | Essential Energy's PoC program is underway and progressing to schedule. Risk rating is classified as moderate due to commencement of systems build prior to receipt of finalised procedures. | [7 empty] | Meter Provider - Type 5 and 6 only - risk rating of low Meter Data Provider - Risk rating is classified as moderate due to commencement of systems build prior to receipt of finalised procedures. | [5 empty] | Essential Energy is actively participating in AEMO industry groups and NSW jurisdictional workshops associated with Power of Choice.
| SA Power Networks | Within schedule | Medium | Currently on schedule
| Active Stream | Within schedule | Low | [14 empty] | Active Stream is currently accredited and operating as an Type 4 MDP and MPB/MPC. Systems and processes are currently in place, requiring AS to assess and deliver the delta to comply with the POC requirements. Our approach with the Progress and Traffic Light Status is related to POC specific amendments.
| Metering Dynamics - ENERGXMP | Within schedule | Medium | Ring fencing, new POC procedures, new systems, merger of Energex, Ergon and Sparq into Energy Queensland are all combining to make planning and delivery difficult given the very tight timeframe. | [7 empty] | MD have experience and capability as MP and MPD, [Note: Risk status for MP is Low, Risk status for MDP is Medium]
| Select Solutions | Within schedule | Medium | The overall timeframes for these industry changes are tight. Select Solutions are working to a schedule set by relevant industry deadlines (ie industry testing, accreditation dates etc). Select Solutions overall strategy is to continue to run our existing systems for our Type 1-4 large meters and MP/MDP participant Ids and under separate participant Ids procure a new system to form part of our accreditation for Type 4 small meters. Process impact and future process mapping is going well and we have a solid understanding of what is required to ring-fence from Ausnet services appropriately. We are currently within schedule but there are risks relating to our procurement and final implementation of the new systems. We have significant resources focussing on delivering this part of the project. | [7 empty] | Medium risk relates to the current status of new system implementation
| Vector Advanced Metering Services | Within schedule | Low
| TasNetworks MDP type 6 & 7 | Within schedule | Medium | TasNetworks strategy is to modify process & extend the current IT systems
| TasNetworks MP type 6 | Within schedule | Medium | TasNetworks strategy is to modify process & extend the current IT systems
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| ActewAGL Distribution (AAD) | Within schedule
| Ausgrid |  |  | At risk | Medium
| CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | [10 empty] | Within schedule | High
| Endeavour Energy |  |  | At risk | Medium
| Essential Energy |  |  | Within schedule | Medium
| SA Power Networks | [6 empty] | Within schedule | Medium
| Active Stream |  |  | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Metering Dynamics - ENERGXMP | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium
| Select Solutions | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium
| Vector Advanced Metering Services | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| TasNetworks MDP type 6 & 7 | [8 empty] | Within schedule | Medium
| TasNetworks MP type 6 | [8 empty] | Within schedule | Medium
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Essential Energy | SA Power Networks | Active Stream | Metering Dynamics - ENERGXMP | Select Solutions | Vector Advanced Metering Services | TasNetworks MDP type 6 & 7 | TasNetworks MP type 6 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 25% | 50% | 100% | 25% | 50% | 100% | 50% | 25% | 75% | 50% | 75% | 75%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 0% | 25% | 100% | 25% | 25% | 50% | 25% | 25% | 50% | 25% | 25% | 25%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 25% | 25% | 100% | 25% | 50% | 0% | 50% | 25% | 75% | 25% | N/A | 25%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 0% | 25% | 0% | 0% | 0% | 0% | 50% | 25% | 25% | 0% | N/A | 25%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 0% | 0% | 0% | N/A | 0%
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 0% | 0% | 25% | 0% | 0% | 0% | 25% | 25% | 50% | 0% | 50% | 50%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 25% | 0% | 0% | 25%
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 25% | 25% | 0% | 0% | 0% | 0% | 0% | 25% | 50% | 0% | 25% | 25%
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 0% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 25% | 0% | 0% | 0%
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | 0% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 25% | 0% | 0% | 0%
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 25% | 25% | 25% | 25% | 25% | 25% | 0% | 25% | 50% | 0% | 50% | 50%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 0% | 0% | 25% | 0% | 0% | 25% | 0% | 0% | 25% | 0% | 0% | 0%
4.3 |  | The validation of business processes during industry testing | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 25% | 25% | 25% | 25% | 0% | 0% | 0% | 25% | 75% | 25% | 75% | 75%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 0% | 0% | 25% | 0% | 0% | 0% | 0% | 0% | 25% | 0% | 25% | 25%
5.3 |  | The internal testing of market systems for your business | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Essential Energy | SA Power Networks | Active Stream | Metering Dynamics - ENERGXMP | Select Solutions | Vector Advanced Metering Services | TasNetworks MDP type 6 & 7 | TasNetworks MP type 6 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | N/A | Within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | N/A | Within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | N/A | N/A
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | At risk
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | N/A | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | At risk
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | At risk | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | At risk | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule
5.3 |  | The internal testing of market systems for your business | [5 empty] | At risk | N/A | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | At risk
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | At risk | N/A | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | At risk
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | At risk | N/A | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | At risk
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | At risk
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | At risk
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Essential Energy | SA Power Networks | Active Stream | Metering Dynamics - ENERGXMP | Select Solutions | Vector Advanced Metering Services | TasNetworks MDP type 6 & 7 | TasNetworks MP type 6 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Known released and approved POC change requirements have been scoped. Unknown changes may have unforeseen impacts. Plans are being developed. 12 mths of AEMO development of IT Systems (particularly the B2B Hub) and only 3.5 mths for industry testing before committing to production is disparate. | [6 empty] | Procedures and guidelines are not finalised |  |  | TasNetworks progress is on track, waiting for pack 2 consolation before this task can be complete | TasNetworks progress is on track, waiting for pack 2 consolation before this task can be complete
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Known released and approved POC change requirements have been scoped. Unknown changes may have unforeseen impacts. Plans are being developed. | [6 empty] | Procedures and guidelines are not finalised. B2B timeline is on critical path and does not leave any room for delays. | Select Solutions has its strategy in place. A key variable is confirming delivery of the systems which will form the final part of our delivery plan. |  | TasNetworks progress is on track, waiting for pack 2 consolation before this task can be complete | TasNetworks progress is on track, waiting for pack 2 consolation before this task can be complete
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | The AAD PoC team has regular meetings with the legal / regulatory team to ensure compliance with all regulatory requirements. Assessment of impacts is underway with clarity around unknown changes affecting the ability of the business to fully understand the final impacts. In addition to this AAD holds regular forums with external stakeholders including the ACT Govt. to ensure a smooth transition takes place. |  | Note: This assessment excludes AEMO procedures that remain in draft. |  |  |  |  | Procedures and guidelines are not finalised |  |  | N/A | On track
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Final POC procedure changes remain unknown |  | Note: In line with CitiPower/Powercor program delivery schedule. |  |  |  |  | Waiting on safety regulators |  |  | N/A | On track
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Not yet begun. |  | Note: In line with CitiPower/Powercor program delivery schedule. | [7 empty] | N/A | N/A
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Registration procedures are yet to be finalised by AEMO. The business is working on the basis of incomplete information and will review and adjust accordingly as more information comes to hand. There is a concern that AEMO have only allowed 8 months for existing businesses to transition to new accredited businesses that are required under the new rule structure. |  | Note: We have completed our assessment of the required accreditations and registrations. The activities to achieve these are related to AEMO procedures which remain in draft. |  |  |  |  | Procedures and guidelines are not finalised |  |  | On track | On track
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | AAD remains compliant with its current obligations and will review and assess any future requirements as AEMO makes more information available. |  | Note: In line with CitiPower/Powercor program delivery schedule. |  |  |  | Dependent on the finalisation of associated industry documentation. |  |  |  | On track | On track
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | AAD has begun assessing future requirements. Finalisation by AEMO of procedures and IT Systems will require that this position is reassessed. |  | Note: In line with CitiPower/Powercor program delivery schedule. |  |  |  | Dependent on the details of 'inprogress' industry documents/procedures to assess the magnitude of change to current state. | Need to develop and build systems to ascertain human resource requirements | This has been done in 2 parts, the resource requirements to deliver the relevant projects and the ongoing resources required to deliver the services. |  | On track | On track
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Not yet begun. Noting PoC removes current functions from existing businesses, this may result in reductions to staff (TBC). |  | Note: In line with CitiPower/Powercor program delivery schedule. | [7 empty] | On track | On track
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Not yet begun. |  | Note: In line with CitiPower/Powercor program delivery schedule. | [5 empty] | Workshops are held internally to educate and prepare key staff for the required changes and impacts. |  | On track | On track
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Final POC procedure changes remain unknown. AAD has assessed impacts on its current business practices based on the available knowledge and will revise as more information becomes available. |  | Note: In line with AEMO schedule of released documentation and CitiPower/Powercor program delivery schedule. |  |  |  | Dependent on the details of 'inprogress' industry documents/procedures to assess the magnitude of change to current state. | Currently completing detailed functional requirements, including current and future state processes. | We've had 2 dedicated resources for over 6 months reviewing current processes and planning document changes for the process impacts relating to the PoC changes. |  | TasNetworks progress is on track, waiting for pack 2 consolation before this task can be complete | TasNetworks progress is on track, waiting for pack 2 consolation before this task can be complete
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Final POC procedure changes remain unknown. AAD has assessed impacts on its current business practices based on the available knowledge and will revise as more information becomes available. |  | Note: In line with AEMO schedule of released documentation and CitiPower/Powercor program delivery schedule. | [5 empty] | Still working with industry release dates to finalise these requirements as AEMO procedures are confirmed. |  | Timeframes are tight with the release of the B2B in March 2107 | Timeframes are tight with the release of the B2B in March 2107
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not yet begun. | Too early in the process for industry testing | Note: In line with AEMO schedule of released documentation and CitiPower/Powercor program delivery schedule. | [7 empty] | Timeframes are tight with the release of the B2B in March 2107 | Timeframes are tight with the release of the B2B in March 2107
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Final requirements are yet to be released by AEMO, however, those requirements that are known have been scoped and are in design (we estimate that approximately 10% of requirements are known). | Not all system impacts have been assessed in detail | Note: In line with AEMO schedule of released documentation and CitiPower/Powercor program delivery schedule. | As per project |  |  | Dependent on the details of 'inprogress' industry documents/procedures to assess the magnitude of change to current state. | Currently completing detailed business requirements, including current and future state processes. | A significant "blue print process" has been completed highlighting requirements. We are finalising our RFP requirements for selection of a systems vendor based on over 12 months of investigating options. |  | Timeframes are tight with the release of the B2B in March 2107 | Timeframes are tight with the release of the B2B in March 2107
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Design is in progress for B2B system processes. Limited information is known about the new AEMO B2B hub. This is a major risk area for success. | Should be starting to build B2B market systems but finalised requirements will not be known for some while. | Note: In line with CitiPower/Powercor program delivery schedule. | As per project |  |  |  |  | Build phase is looking to begin in early 2017 and will have the usual IT project risks associated with it. |  | Timeframes are tight with the release of the B2B in March 2107 | Timeframes are tight with the release of the B2B in March 2107
5.3 |  | The internal testing of market systems for your business | [5 empty] | Not yet begun. | Not yet at the stage of testing market systems. (B2B standards yet to be defined.) | Note: In line with CitiPower/Powercor program delivery schedule. | [5 empty] | Due in mid 2017, dependant on progress of system build. |  | Timeframes are tight with the release of the B2B in March 2107 | Timeframes are tight with the release of the B2B in March 2107
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not yet begun. | Not yet at the stage of testing external interfaces. (B2B standards yet to be defined.) | Note: In line with CitiPower/Powercor program delivery schedule. | [5 empty] | Due in mid 2017, dependant on progress of system build. |  | Timeframes are tight with the release of the B2B in March 2107 | Timeframes are tight with the release of the B2B in March 2107
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not yet begun. | Not yet at the stage of building market systems. (B2B standards yet to be defined.) | Note: In line with CitiPower/Powercor program delivery schedule. | [5 empty] | Due in mid 2017, dependant on progress of system build. |  | Timeframes are tight with the release of the B2B in March 2107 | Timeframes are tight with the release of the B2B in March 2107
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Not yet begun. |  | Note: In line with CitiPower/Powercor program delivery schedule. | [7 empty] | Timeframes are tight with the release of the B2B in March 2107, Industry cutover requirements are not know yet | Timeframes are tight with the release of the B2B in March 2107, Industry cutover requirements are not know yet
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not yet begun. |  | Note: In line with CitiPower/Powercor program delivery schedule. | [7 empty] | Timeframes are tight with the release of the B2B in March 2107, Industry cutover requirements are not know yet | Timeframes are tight with the release of the B2B in March 2107, Industry cutover requirements are not know yet
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Essential Energy | SA Power Networks | Active Stream | Metering Dynamics - ENERGXMP | Select Solutions | Vector Advanced Metering Services | TasNetworks MDP type 6 & 7 | TasNetworks MP type 6 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Stage Gates built into Schedule based on AEMO identified key milestones. Implementation approach that develops solutions as best as practical now and change later when AEMO formally releases information. | [6 empty] | Working with drafts and scenarios
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | As above. | [6 empty] | Working with drafts and scenarios. Completing submissions and work as quickly as possible. | Dedicated resources and strong business focus on the systems delivery project.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [12 empty] | Attending working group and forums to determine what is required
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | First pass review of all impacted procedures to identified anticipated level of change required (Hi, Med, Low). | [6 empty] | Attending working group and forums to determine what is required
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Stage Gate milestone of 1 March 2017 included in schedule (for submission to AEMO) | [6 empty] | Attending working group and forums to determine what is required
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [12 empty] | Ongoing interaction with required stakeholders.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [12 empty] | Ongoing interaction with required stakeholders.
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [6 empty] | Additional resources to be put into assessment of market systems. |  | As per project |  |  |  | Ongoing interaction with required stakeholders.
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Stage Gates built into Schedule based on AEMO identified key milestones. Implementation approach that develops solutions as best as practical now and change later when AEMO formally releases information. | Work with various industry groups in an attempt to expedite this. |  | As per project |  |  |  |  | Dedicated resources and strong business focus on the systems delivery project.
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
0%
25%
50%
75%
100%
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Metering Coordinator Reports
| 2016-11-14 |  |  | Metering Coordinator (MC) Readiness Assessment Reports - see Distributors Report tab for initial MC
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Active Stream | Within schedule | Low | [14 empty] | Active Stream is currently accredited and operating as an Type 4 MDP and MPB/MPC. Systems and processes are currently in place, requiring AS to assess and deliver the delta to comply with the POC requirements. Our approach with the Progress and Traffic Light Status is related to POC specific amendments.
| Metering Dynamics - ENERGXMP | Within schedule | Medium | Ring fencing, new POC procedures, new systems, merger of Energex, Ergon and Sparq into Energy Queensland are all combining to make planning and delivery difficult given the very tight timeframe. | [7 empty] | New role and procedures not finalised B2B and MSATS
| Select Solutions | Within schedule | Medium | The overall timeframes for these industry changes are tight. Select Solutions are working to a schedule set by relevant industry deadlines (ie industry testing, accreditation dates etc). Select Solutions overall strategy is to continue to run our existing systems for our Type 1-4 large meters and MP/MDP participant Ids and under separate participant Ids procure a new system to form part of our accreditation for Type 4 small meters. Process impact and future process mapping is going well and we have a solid understanding of what is required to ring-fence from Ausnet services appropriately. We are currently within schedule but there are risks relating to our procurement and final implementation of the new systems. We have significant resources focussing on delivering this part of the project.
| Vector Advanced Metering Services | Within schedule | Low
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| Active Stream |  |  | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Metering Dynamics - ENERGXMP | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium
| Select Solutions | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Vector Advanced Metering Services | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | Active Stream | Metering Dynamics - ENERGXMP | Select Solutions | Vector Advanced Metering Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 50% | 25% | 75% | 50%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 25% | 25% | 50% | 25%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 50% | 25% | 75% | 25%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 50% | 25% | 25% | 0%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 50% | 0% | 0% | 0%
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 25% | 25% | 50% | 0%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 0% | 0% | 25% | 0%
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 0% | 25% | 50% | 0%
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 0% | 0% | 25% | 0%
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | 0% | 0% | 25% | 0%
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 0% | 25% | 50% | 0%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 0% | 0% | 25% | 0%
4.3 |  | The validation of business processes during industry testing | [5 empty] | 0% | 0% | 0% | 0%
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 0% | 25% | 75% | 25%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 0% | 0% | 25% | 0%
5.3 |  | The internal testing of market systems for your business | [5 empty] | 0% | 0% | 0% | 0%
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | 0% | 0% | 0% | 0%
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | 0% | 0% | 0% | 0%
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 0% | 0% | 0% | 0%
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | 0% | 0% | 0% | 0%
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | Active Stream | Metering Dynamics - ENERGXMP | Select Solutions | Vector Advanced Metering Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | At risk | At risk | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | Within schedule | At risk | Within schedule
5.3 |  | The internal testing of market systems for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | Active Stream | Metering Dynamics - ENERGXMP | Select Solutions | Vector Advanced Metering Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [6 empty] | Procedures and guidelines are not finalised
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [6 empty] | Procedures and guidelines are not finalised. B2B timeline is on critical path and does not leave any room for delays. | Select Solutions has its strategy in place. A key variable is confirming delivery of the systems which will form the final part of our delivery plan.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [6 empty] | Procedures and guidelines are not finalised
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [6 empty] | Waiting on safety regulators
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities | [6 empty] | Procedures and guidelines are not finalised
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Dependent on the finalisation of associated industry documentation.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Dependent on the details of 'inprogress' industry documents/procedures to assess the magnitude of change to current state. | Need to develop and build systems to ascertain human resource requirements | This has been done in 2 parts, the resource requirements to deliver the relevant projects and the ongoing resources required to deliver the services.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [7 empty] | Workshops are held internally to educate and prepare key staff for the required changes and impacts.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Dependent on the details of 'inprogress' industry documents/procedures to assess the magnitude of change to current state. | Currently completing detailed functional requirements, including current and future state processes. | We've had 2 dedicated resources for over 6 months reviewing current processes and planning document changes for the process impacts relating to the PoC changes.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [7 empty] | Still working with industry release dates to finalise these requirements as AEMO procedures are confirmed.
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Dependent on the details of 'inprogress' industry documents/procedures to assess the magnitude of change to current state. | Currently completing detailed business requirements, including current and future state processes. | A significant "blue print process" has been completed highlighting requirements. We are finalising our RFP requirements for selection of a systems vendor based on over 12 months of investigating options.
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | Build phase is looking to begin in early 2017 and will have the usual IT project risks associated with it.
5.3 |  | The internal testing of market systems for your business | [7 empty] | Due in mid 2017, dependant on progress of system build.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [7 empty] | Due in mid 2017, dependant on progress of system build.
5.5 |  | The validation of performance of market systems during industry testing | [7 empty] | Due in mid 2017, dependant on progress of system build.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | Active Stream | Metering Dynamics - ENERGXMP | Select Solutions | Vector Advanced Metering Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [6 empty] | Working with drafts and scenarios
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [6 empty] | Working with drafts and scenarios. Completing submissions and work as quickly as possible. | Dedicated resources and strong business focus on the systems delivery project.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [6 empty] | Attending working group and forums to determine what is required
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [6 empty] | Attending working group and forums to determine what is required
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities | [6 empty] | Attending working group and forums to determine what is required
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [6 empty] | Ongoing interaction with required stakeholders.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [6 empty] | Ongoing interaction with required stakeholders.
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [6 empty] | Ongoing interaction with required stakeholders.
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | Dedicated resources and strong business focus on the systems delivery project.
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
0%
25%
50%
75%
100%
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Other Parties Reports
| 2016-11-14 |  |  | Other Parties Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Select Solutions | Within schedule | Low | [See Select Solutions report on Metering Coordinator Reports tab for details] | [7 empty] | Select Solutions is still confirming a final decision to pursue this accreditation
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| Select Solutions | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
0
0
0
0
0
0
0
0
0
0
0
0
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | Select Solutions | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | Select Solutions | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | Select Solutions | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | Select Solutions | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
0%
25%
50%
75%
100%
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## AEMO
AEMO Readiness Assessment Report
B. Overall project status
| A. Details | [6 empty] | Project status | Project risk rating | Comment
| Date | 2016-11-14 | [5 empty] | Within schedule | Medium | AEMO are continuing to meet program deliverables. Medium risk rating refers to schedule constraints associated with the B2B Procedure development and subsequent system builds.
| Organisation | AEMO
C. Jurisdictional status
# | Organisation | ACT | NSW | QLD | SA | TAS | VIC | Status | Risk | Comment
1 | AEMO | √ | √ | √ | √ | √ | √ | Within schedule | Medium
2
3
4
5
6
D. Detailed status
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%) | Traffic light status | Explanation of variance/Notes | Mitigating actions
1. Assessment and preparation | [11 empty] | 0% | Retailer
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 75% | Within schedule | System impacts resulting from updates to the B2B e-Hub currently being assessed. |  | 25% | Distributor | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 75% | Within schedule | Final detailed planning associated with system updates is underway. |  | 50% | Meter Provider | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
1.3 |  | Delivery of the Market Readiness Strategy and associated plans | [5 empty] | 25% | Within schedule | AEMO has finalised the first versions of the Market Readiness Strategy and Industry Readiness Reporting Plan in collaboration with Industry |  | 75% |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy | [11 empty] | 100% | Meter Data Provider
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 75% | Within schedule |  |  | N/A | Metering Coordinator | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 0% | Within schedule |  |  |  | Embedded Network Manager | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 0% | Within schedule |  |  |  | Embedded Network Operator | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 50% | Within schedule | Dependant on work package two consultation. |  | Within schedule | Third Party B2B Participant | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 0% | Within schedule |  |  | At risk |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.6 |  | The publication of updated AEMO retail electricity market procedures and associated documentation | [5 empty] | 75% | Within schedule | Consultation has finished for the Package 1 Procedures and final versions were published on 31 August 2016. Consultation has started for the Package 2 Procedures and will be completed by 28 February 2017. |  | Not within schedule |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.7 |  | The publication of updatedB2B retail electricity market procedures and associated documentation | [5 empty] | 50% | At risk | Legal and Technical issues coupled with a reduced period for review and 2nd stage drafting | IEC Directive on Legal Drafting, Technical Delivery Specification drafted by 30 Nov, B2B WG/AEMO Workplan for 2nd stage consultation | N/A |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
3. People | [11 empty] | Completed
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 25% | Within schedule |  |  |  | √ | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 0% | Within schedule |  |  |  | x | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
3.3 |  | The development and delivery of training to staff in operational roles | [5 empty] | 0% | Within schedule |  |  | Low |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4. Business processes | [11 empty] | Medium
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 25% | Within schedule |  |  | High |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 0% | Within schedule |  |  | N/A |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4.3 |  | The validation of business processes during industry testing | [5 empty] | 0% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4.4 |  | The delivery of POC information sessions to participants | [5 empty] | 25% | Within schedule | Consolidated sessions 1 and 2 scheduled for 28 November. |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5. Market systems
5.1 | Market systems - MSATS | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 75% | Within schedule | System work stream have developed a detailed plan for the implementation of the changes from the Embedded Network and Metering in Competition (EN/MC). EN/MC requirements documents and detailed design are mostly complete. |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 50% | Within schedule | Staged IT development of changes from the EN/MC rule changes are progressing |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.3 |  | The internal testing of market systems for your business | [5 empty] | 25% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | 0% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | 0% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.6 | Market systems - B2B | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 25% | At risk | Refer B2B Procedure Development |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.7 |  | The development and build of appropriate market systems for your business | [5 empty] | 25% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.8 |  | Completion of internal testing of the e-hub and readiness for industry testing | [5 empty] | 0% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.9 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | 0% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.1 |  | The validation of performance of market systems during industry testing | [5 empty] | 0% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
6. Transition planning | [13 empty] | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 0% | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | 0% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
7. General notes | [13 empty] | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date