## Sheet1
WEM Reform Cutover Plan - Level 2 Milestones (DRAFT - published for consultation 15/05/23)
Function | Category | Core Milestone Description | Milestone Type | Start |  | End/Milestone |  | Transitional Schedule?
|  |  |  | Time | Date | Time | Date
Registration | Registration | Publish registration templates. Note: These are excel templates that AEMO will accept as formal registration data submissions prior to [New WEM Commencement Day or earlier date TBD] | Operational |  |  |  | 2023-05-03 | Yes
|  | Phase 1 - Pre-Production (MKT) Deployment | Deployment |  |  |  | 2023-05-31 | No
|  | Deadline for facility class assessment submissions for facilities or aggregations to be registered before 1 October 2023 with an effective date after New WEM Commencement Day | Participant |  |  |  | 2023-06-20 | Yes
|  | WEM Procedure for Transitional Processes Published | Operational |  |  |  | 2023-07-01 | Yes
|  | Deadline for submission of newly required Intermittent Load data | Participant |  |  |  | 2023-07-01 | Yes
|  | Phase 1 - Production Deployment | Deployment |  |  |  | 2023-07-03 | No
|  | Registrations User Interface available for users to submit registration applications and data for registration to apply after New WEM Commencement Day | Participant |  |  |  | 2023-07-03 | Yes
|  | Phase 2 - Pre-Production (Market Trial) Deployment | Deployment |  |  |  | 2023-07-31 | No
|  | Deadline for requests to change Facility Standing Data for periods before New WEM Commencement Day | Participant |  |  |  | 2023-08-01 | Yes
|  | Deadline for registration applications for NTDL load facilities. | Participant |  |  |  | 2023-08-08 | Yes
|  | Phase 2 - Production Deployment | Deployment |  |  |  | 2023-08-14 | No
|  | Deadline for registration applications for non-NTDL load facilities. | Participant |  |  |  | 2023-08-25 | Yes
|  | Deadline for MPs to submit Load Associations for DSPs and Interruptible Loads | Participant |  |  |  | 2023-08-25 | Yes
|  | Complete review and approval or rejection of facility registration data to apply from New WEM Commencement Da | Operational |  |  |  | 2023-09-01 | Yes
|  | Provide each Market Participant responsible for a Pre-Amending Rules Interruptible Load with a list of their Interruptible Loads which will become NDLs on New WEM Commencement Day, the relevant NMIs, and AEMO’s assessment of which Post-Amending Rules Interruptible Load each NMI should be associated with (if any). | Operational |  |  |  | 2023-09-01 | Yes
|  | Deadline to confirm AEMO’s assessment of Associated Loads for post-amending rule Interruptible Loads, or provide an alternative set of Load Associations. | Operational |  |  |  | 2023-09-16 | Yes
|  | Transition from Balancing to SCED APIs (‘back end’ to retain ability to provide existing Rego data to PaSS) | Deployment |  |  |  | 2023-10-01 | No
|  | PDS Participant/Facility registration reports switch from Balancing to SCED framework | Deployment |  |  |  | 2023-10-01 | No
|  | ‘Final’ cutover milestones to cease backend integration with existing Settlements functionality | Deployment |  |  |  | 2024-09-30 | No
Dispatch | Balancing & LFAS | Last NBDMO (and push) | Operational |  |  | 1300 | 2023-09-29 | No
|  | Last Balancing horizon extension, noting BMO / LFMO calculation continues to work with shortened horizon | Operational |  |  | 1300 | 2023-09-29 | No
|  | Deadline for last LFAS submissions | Participant |  |  | 0030 | 2023-10-01 | No
|  | Deadline for last Balancing Submissions | Participant |  |  | 06000 | 2023-10-01 | No
|  | Last BMO / LFMO calculations (for dispatch) | Operational |  |  | 0700 | 2023-10-01 | No
|  | Last dispatch instruction under pre-amending rules | Operational |  |  | 0750 | 2023-10-01 | No
|  | Last BMO calculation (for provisional pricing) | Operational |  |  | 1100 | 2023-10-01 | No
|  | Last BMO calculation (for final pricing) - including validation review by Market Ops Team | Operational |  |  | 0100 | 2023-10-03 | No
|  | Publish last provisional TES Calculations under pre-amending rules | Operational |  |  | 0830 | 2023-10-03 | No
|  | Publish final BMO under pre-amending Rules | Operational |  |  | 1100 | 2023-10-03 | No
|  | Publish last final TES results under pre-amending Rules | Operational |  |  | 1415 | 2023-10-20 | No
| SCED/RTMS | Deploy to Pre-Production Environment | Deployment |  |  |  | 2023-08-30 | No
|  | Publish the Real-Time Market Schedule | Operational |  |  |  | 2023-09-01 | Yes
|  | Deploy to Production Environment | Deployment |  |  |  | 2023-09-06 | No
|  | Market participants can start making Real-Time Market Submissions for 'system proving' purposes (AEMO to provide further details in due course) | Participant | 0800 | 2023-09-08 |  |  | No
|  | Market participants may choose to make (and AEMO must accept) RTM Submissions and Standing RTM Submissions for periods within the Real-Time Market Submission Acceptance Horizon | Participant | 0800 | 2023-09-16 |  |  | Yes
|  | Market participants must start making Real-Time Market Submissions, and must make submissions for all intervals in the Week-Ahead Schedule Horizon | Participant | 0800 | 2023-09-23 |  |  | Yes
|  | AEMO may start issuing market advisories under the post-amending rules | Operational |  | 2023-09-23 |  |  | Yes
|  | Participants must start complying with Market Advisories issued under the post-amending rules | Participant |  | 2023-09-23 |  |  | Yes
|  | Start publishing the Operational System Load Estimate calculated under the post-amending rules | Operational | 0800 | 2023-09-23 |  |  | Yes
|  | Start publishing Week Ahead Schedules Start publishing information about Week Ahead Schedules | Operational | 0730 | 2023-09-24 |  |  | Yes
|  | Start publishing Pre-Dispatch Schedules Start publishing information about Pre-Dispatch Schedules | Operational | 0730 | 2023-09-29 |  |  | Yes
|  | Start publishing Dispatch Schedules Start publishing information about Dispatch Schedules | Operational | 0605 | 2023-10-01 |  |  | Yes
|  | Start making Dispatch Instruction information (recorded under 7.6.8, 7.6.11A) available to Market Participants, as if those Dispatch Schedules had been used to generate Dispatch Instructions | Operational | 0605 | 2023-10-01 |  |  | Yes
|  | Start publishing Reference Trading Prices | Operational | 0635 | 2023-10-01 |  |  | Yes
|  | Last dispatch instruction from RTDE | Operational |  |  | 0750 | 2023-10-01 | No
|  | First dispatch instruction (WEMDE) under post-amending rules | Operational |  |  | 0759 | 2023-10-01 | No
|  | Removal of constraints and inhibits for NWCD cutover fleet | Operational |  |  | TBC | 2023-10-01 | No
|  | Continue publishing the Operational System Load Estimate calculated under the pre-amending rules until this time | Operational |  |  | 0800 | 2023-10-08 | Yes
|  | Last date for 'first WEMDE' dispatch of a facility | Operational |  |  | TBC | 2023-10-31 | No
STEM (and Bilaterals) | STEM and Bilaterals | Deploy STEM to Pre-PRD | Deployment |  |  |  | 2023-07-31 | No
|  | Deploy STEM tp PRD | Deployment |  |  |  | 2023-08-14 | No
|  | Market Participants may choose to make (and AEMO must accept) STEM Standing Submissions and Bilateral Standing Submissions for Scheduling Days after New WEM Commencement Date | Participant | 0800 | 2023-09-15 |  |  | Yes
|  | Last Bilateral Standing Submission under pre-amending Rules | Participant |  |  | 1550 | 2023-09-21 | Yes
|  | Start publishing information required to inform STEM Submissions | Operational | 0800 | 2023-09-23 |  |  | Yes
|  | Market Participants may make (and AEMO must accept) Bilateral Submissions and STEM Submissions for intervals on or after New WEM Commencement Day under post-amending rules. | Participant | 0800 | 2023-09-23 |  |  | Yes
|  | Last STEM Standing Submissions under pre-amending rules | Participant |  |  | 1550 | 2023-09-28 | No
|  | Last Bilateral Submission under pre-amending rules | Participant |  |  | 0850 | 2023-09-29 | No
|  | Last STEM Submission under pre-amending rules | Participant |  |  | 1050 | 2023-09-29 | No
|  | Last STEM Auction under pre-amending rules | Operational |  |  | 1115 | 2023-09-29 | No
|  | Market Participants may make (and AEMO must accept) Bilateral Submissions and STEM Submissions for intervals on or after New WEM Commencement Day under post-amending rules. | Participant |  |  | 0800 | 2023-09-23 | Yes
|  | First STEM Auction under post-amending rules. | Operational |  |  | 1100 | 2023-09-30 | No
PASA | ST PASA | Deploy to Pre-Production Environment | Deployment |  |  |  | 2023-08-30 | No
|  | Deploy to Production Environment | Deployment |  |  |  | 2023-09-06 | No
|  | Commence running and publishing ST-PASA under the post-amending rules. | Operational |  |  |  | 2023-09-23 | Yes
|  | Last ST PASA Publication under pre-amending rules | Operational |  |  |  | 2023-09-28 | No
| MT PASA | Publish the PASA WEM Procedure on the WEM Website | Operational |  |  |  | 2023-08-18 | Yes
|  | Provide PASA data to AEMO as required by the PASA WEM Procedure . Participants can provide data earlier if they would like to | Participant |  |  |  | 2023-09-01 | Yes
|  | Deploy to Pre-Production Environment | Deployment |  |  |  | 2023-08-30 | No
|  | Deploy to Production Environment | Deployment |  |  |  | 2023-09-06 | No
|  | Last current MT PASA | Operational |  |  |  | 2023-09-15 | No
|  | Commence running and publishing MT-PASA under the post-amending rules. | Operational |  |  |  | 2023-09-23 | Yes
Outage Management | Outage Management | Publish the final Outage Data Conversion Procedure | Operational |  |  |  | 2023-07-01 | Yes
|  | Deploy to Pre-Production Environment | Deployment |  |  |  | 2023-07-31 | No
|  | Deploy to Production Environment | Deployment |  |  |  | 2023-08-14 | No
|  | Undertake the Outage Data Conversion for Market Participant Outages that exist at this time | Operational |  |  |  | 2023-08-14 | Yes
|  | Publish the Equipment List that will apply for the Post-Amending Rules | Operational |  |  |  | 2023-09-01 | Yes
|  | Publish the Self-Scheduling Outage Facility List that will apply for the Post-Amending Rules | Operational |  |  |  | 2023-09-01 | Yes
|  | If a Market Participant requests Approval of an Accepted outage before this time, AEMO must assess it under the pre-amending rules before 23 September. | Participant |  |  |  | 2023-09-16 | Yes
|  | Where a market participant requests Approval of an Accepted outage before 16 September, AEMO must assess the outage under the pre-amending rules, and either approve or reject the outage by this date. | Operational |  |  |  | 2023-09-23 | Yes
|  | Send CAPO/CAFO data to STEM/Bilaterals | Deployment |  |  | 0800 | 2023-09-23 | No
|  | Data Migration for REPO Count Daily | Operational |  |  |  | 2023-10-01 | No
|  | Perform the Outage Data Conversion for Network Operator Outages as they exist at this time | Deployment |  |  | 0800 | 2023-10-01 | Yes
|  | Continue to report Forced Outages for periods before New WEM Commencement Day under the pre-amending rules until this date. | Participant |  |  |  | 2023-10-15 | No
|  | Re-deployment (of existing MPI) to Production Environment | Deployment |  |  |  | 2023-10-15 | No
Settlements & Prudentials | Overall | Deploy PaSS to Pre-Production environment | Deployment |  |  |  | 2023-07-31 | No
|  | Deploy PaSS tp Production environment | Deployment |  |  |  | 2023-08-14 | No
|  | Validate integration with wider Architecture | Deployment |  |  |  | 2023-09-06 | No
| CCA | Last Capacity Credit Allocation submissions under pre-amending rules | Particpant | 0800 | 2023-08-18 | 1700 | 2023-11-01 17:00 | No
| NTDL | Deadline for NTDL submissions for Sep 2023 under pre-amending rules | Participant |  |  | 1700 | 2023-07-28 | No
|  | Deadline for NTDL submissions for Oct 2023 under post-amending rules | Participant |  |  | 1700 | 2023-08-28 | No
| IRCR | Last Individual Reserve Capacity Requirement (Adjustments) published under pre-amending rules | Operational |  | 14-Aug-24 |  | 2024-09-18 | No
|  | First Individual Reserve Capacity Requirement (Indicative) published under post-amending rules | Operational |  |  | 1700 | 2023-09-15 | No
| Prudentials | First Prudential calculations under post-amending rules (incl STEM/Non-STEM cumulative estimated exposure) | Operational |  |  | 0000 | 2023-10-01 | No
| Metering | Last Interval Meter Deadline under legacy rules | Participant |  |  |  | 2023-11-01 | No
|  | First Interval Meter Deadline under new rules | Participant |  |  | 1700 | 2023-10-25 17:00 | No
| Settlements | Last STEM Invoices published under pre-amending rules | Operational |  |  |  | 2023-10-02 | No
|  | Last Non-STEM Invoices (Adjustments) published under legacy rules | Operational |  |  |  | 2024-09-18 | No
|  | First WEM Invoices published under post-amending rules | Operational |  |  |  | 2023-10-31 | No
RCM | Phase 2 (NAQ) | Pre-PRD Deployment (Portal Modifications) | Deployment |  |  |  | 2023-03-29 | No
|  | NAQ Deployment (VDI via laptop and RCM Portal pre-processing function) | Deployment |  |  |  | 2023-04-12 | No
|  | Deadline for Trade Decs to AEMO | Participant |  |  |  | 2023-04-28 | No
|  | Integration/data migration to RCM DB | Deployment |  |  |  | 2023-06-01 | No
|  | Assign NAQ quantitites and Capacity Credits | Operational |  |  |  | 2023-06-28 | No
| Phase 3 | Deploy to Pre-Production Environment | Deployment |  |  |  | 2023-07-31 | No
|  | Deploy to Production Environment | Deployment |  |  |  | 2023-08-14 | No
|  | Participants may start making daily Capacity Credit Allocations for times after New WEM Commencement Day under the post-amending rules | Participant | 0800 | 2023-09-10 | 1700 | 2023-09-30 17:00 | Yes
|  | Validate integration with wider Architecture in Pre-PRD | Deployment |  |  |  | 2023-08-07 | No
|  | Validate integration with wider Architecture in PRD | Deployment |  |  |  | 2023-09-06 | No
|  | First RCOQ calculation under post amending rules (1-8 Oct Period) | Operational |  |  |  | 2023-09-30 | Yes
|  | First RC Testing, Verification Test and Relevant Level Calcs | Operational |  |  |  | 2023-10-01 | No
|  | Deadline for Consumption Deviation Applications for the Capacity Year starting 1 Oct 2023 | Participant |  |  |  | 2023-10-31 | Yes
Compliance & Monitoring | Data Website Publication | Draft Transition Schedule Published | Operational |  |  |  | 2023-05-15 | No
|  | Transition Schedule Published | Operational |  |  |  | 2023-06-30 | No
|  | Final Market Pulse & Data Site Updates | Operational |  |  |  | 2023-10-01 | No
GPS | GPS | Deploy updated GPS solution with revised API endpoints (Registration) into Pre-Production Environment | Deployment |  |  |  | 2023-05-31 | No
|  | Deploy updated GPS solution with revised API endpoints (Registration) into Production Environment | Deployment |  |  |  | #REF! | No
Formulas:
Date = [Date, row below]-14
Date = [Date, row above]