## Slide 1: Cutover Plan|WEM Reform Cutover Plan
Dispatch (e.g. RTMS, WEMDE) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Settlement & Prudentials1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Registration1 (& GPS) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
STEM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
RCM1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Outage Management (& CTP) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PASA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Website and Regulatory Publications |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Week Commencing | 27-Mar | 3-Apr | 10-Apr | 17-Apr | 24-Apr | 1-May | 8-May | 15-May | 22-May | 29-May | 5-Jun | 12-Jun | 19-Jun | 26-Jun | 3-Jul | 10-Jul | 17-Jul | 24-Jul | 31-Jul | 7-Aug | 14-Aug | 21-Aug | 28-Aug | 4-Sep | 11-Sep | 18-Sep | 25-Sep | 2-Oct | 9-Oct | 16-Oct | 23-Oct | 30-Oct | 25-Dec
1
Participant milestone
1 Settlements, RCM and Registrations timeframes run through to Sep 2024 as AEMO as existing Settlement periods are 12 months from Trading Day
PRD
PRD
PRD
PRD (Ph 2)
PRD
PRD
6
Go Live Hypercare
SIT/Coordinated Market Trial/UAT/RFM
Go Live Gates
PPD
PPD
PPD
PPD (MKT)
PPD (MKT)
PRD (Ph 3)
PPD
Operational milestone
Deployment milestone
Hypercare milestone
PRD
PPD (MKT)
SIT
SIT
SIT
5
8
7
SIT
New RTM, STEM & Bilateral Subs
7
9
‘New’ CCA Subs
First ‘new’ indicative IRCR
5
Standing Data & Facility Info Deadlines
Standing Data Deadline & Registration Approvals
Facility Aggregation & Class Assessment Deadline
Excel Templates Available
2
3
New STEM Subs
New STEM Auction
6
7
3
Trade Decs Deadline
Assign NAQ & CC
4
6
SIT
MT
MT
MT PASA Data Input Deadline
First ‘new’ ST & MT PASA
Data Migration and IPP Review Commences
CAPO/CAFO to STEM
Forced Outage Subs Deadline
PPD (MKT)
R2
SIT
SIT
‘New’ Interval Meter Data
Final TES
Final ‘managed’ WEMDE dispatch
‘New’ WEM Invoices
PP
SIT
SIT Exit
SIT
Data Migration
NTDL Subs
27 June
31 July
11 Aug
Transition Schedule Published
28 Sep
First ‘New’ RCOQ Calc
Toggle On New Func.
R1
Go Live
Market Pulse & Data Site Updated
Procedure Published
IL Data Deadline
Load Assoc. Assessment
Procedure Published
Procedure Published
Equipment & SS Outage Facility Lists
Draft Transition Schedule Published
First ‘new’ Prudential calc
API Transition
NO Data Conversion