# Introduction

In February 2012, the GRCF endorsed the testing approach as outlined in “2012 Gas Retail Market Changes – Testing Scope”. This paper proposed that AEMO would monitor the certification activities for the Queensland, South Australia and Victorian jurisdictions to ensure all participants complete their certification effort within the agreed window of 1 April 2012 to 1 June 2012.

To monitor the progress of the certification activities, a fortnightly status report against agreed key milestones will be used to monitor the R29 recertification progress.

The following status definitions are to be used:

| Symbol | Status |
| --- | --- |
|  | Completed |
| Green | Work to deliver milestone is on schedule with adequate contingency |
| Amber | Work to deliver milestone is on schedule but with inadequate contingency, a significant issue to be resolved, or behind schedule but will meet date using float time |
| Red | Work to deliver milestone or completion criteria cannot be met and will require re-planning |

The program of work has a go-live date of 30 July 2012, with a recertification work program operating from 1 April 2012 to 1 June 2012 inclusive.

# Process

## Initial reporting set up steps

## The set up stage gathers each organisation’s business contact, their target UAT completion dates and target recertification commencement date.

- GRCF reps are to complete Attachment A and email to AEMO (grcf@aemo.com.au) by Friday 23 March 2012.

- AEMO will populate the list of organisations that will be required to complete recertification and the relevant business report contact to provide reports as set out in Attachment B.

AEMO will consider requests from Participant in relation to certification beyond 1 June 2012 but these must be received by AEMO (emailed to grcf@aemo.com.au) before COB Tuesday 13 March 2012 stating the reasons why the Participant is seeking an extension to the prescribed timeline.

At this point in time, time extension beyond 1 July 2012 will not be accepted.

## Progress report steps

The reporting process kicks off on Monday 2 April 2012 (for week ending 30 March).

- Nominated business contacts to email AEMO (grcf@aemo.com.au) their report, as specified in Attachment C, by 10am (Melb Time) every second Monday.

- By noon each Tuesday, AEMO will collate the completed templates and prepare the progress report as set out in Attachment D and circulate.

Note: where there is a Melbourne-based public holiday, report requirements will move to Tuesday and Wednesday respectively.

This report highlights how each organisation is tracking in terms of completing UAT, commencing certification and whether certification is completed.

The following is a calendar showing the reporting activities:

## Attachment A

## Initial reporting set up template

This template is to be completed by each organisation and submitted to AEMO (grcf@aemo.com.au) by COB Friday 23 March 2012.

| ## Initial reporting set up template |  |
| --- | --- |
| ## Victorian Jurisdiction |  |
| ## Organisation | ## <insert company name> |
| ## Business Representatives to provide your organisation status report | ## <insert name> |
| ## Email address of business representative | ## <insert email address> |
| ## Target Milestones dates |  |
| ## UAT targeted completion date (Must be a date before recertification commencement date) | ## <insert date> |
| ## Certification targeted commencement date (As per the agreed testing scope must be between 1 Apr to 1 Jun and must be after UAT) | <insert date> |
| Queensland Jurisdiction |  |
| Organisation | <insert company name> |
| Business Representatives to provide your organisation status report | <insert name> |
| Email address of business representative | <insert email address> |
| Target Milestones dates |  |
| UAT targeted completion date (Must be a date before recertification commencement date) | <insert date> |
| Certification targeted commencement date (As per the agreed testing scope must be between 1 Apr to 1 Jun1 and must be after UAT) | <insert date> |
| South Australia Jurisdiction |  |
| Organisation | <insert company name> |
| Business Representatives to provide your organisation status report | <insert name> |
| Email address of business representative | <insert email address> |
| Target Milestones dates |  |
| UAT targeted completion date (Must be a date before recertification commencement date) | <insert date> |
| Certification targeted commencement date (As per the agreed testing scope must be between 1 Apr to 1 Jun1 and must be after UAT) | <insert date> |

## Attachment B

## Business Representatives

To provide progress reports the person or person assigned for that company is responsible for forwarding progress reports to AEMO (grcf@aemo.com.au).

The following are the list of organisations that will be required to complete recertification.

| Organisation | Jurisdiction | Contact person | Email Address | Title |
| --- | --- | --- | --- | --- |
| AEMO | Vic | Stef Monaco | stefanie.monaco@aemo.com.au | Senior Regulatory Analyst |
| AEMO | Qld | Stef Monaco | stefanie.monaco@aemo.com.au | Senior Regulatory Analyst |
| AEMO | SA | Stephen Smith | Stephen.smith@logica.com |  |
| Envestra | Vic | Rebecca Cregan | Rebecca.cregan@apa.com.au | Business Analyst |
| Envestra SA | SA | Rebecca Cregan | Rebecca.cregan@apa.com.au | Business Analyst |
| Envestra | Qld | Rebecca Cregan | Rebecca.cregan@apa.com.au | Business Analyst |
| APT Allgas | Qld | Rebecca Cregan | Rebecca.cregan@apa.com.au | Business Analyst |
| Multinet | Vic | Paul Sternberg Ferouza Saran | ## paul.sternberg@jemena.com.au ## ferouza.saran@jemena.com.au |  |
| SP AusNet | Vic | Thiru Nagalingam | Thiru.nagalingam@sp-ausnet.com.au | Senior Business Analyst |
| AGL | Vic | Allicia Volvricht | avolvricht@agl.com.au | Industry Advice Manager |
| AGL | Qld | Allicia Volvricht | avolvricht@agl.com.au | Industry Advice Manager |
| AGL | SA | Allicia Volvricht | avolvricht@agl.com.au | Industry Advice Manager |
| Origin Energy | Vic | ## Chantal Wright Kristy-Lee Richmond | ## chantal.wright@originenergy.com.au kristy-lee.richmond@originenergy.com.au |  |
| Origin Energy | Qld | ## Chantal Wright Kristy-Lee Richmond | ## chantal.wright@originenergy.com.au kristy-lee.richmond@originenergy.com.au |  |
| Origin Energy | SA | ## Chantal Wright Kristy-Lee Richmond | ## chantal.wright@originenergy.com.au kristy-lee.richmond@originenergy.com.au |  |
| Australian Power & Gas | Vic | Caroline McGeechan | cmcgeechan@auspg.com.au |  |
| Australian Power & Gas | Qld | Caroline McGeechan | cmcgeechan@auspg.com.au |  |
| TRUenergy | Vic | Hillary Nguyen | Hillary.Nguyen@truenergy.com.au | Industry Development Manager |
| TRUenergy 2 | Vic | Hillary Nguyen | Hillary.Nguyen@truenergy.com.au | Industry Development Manager |
| TRUenergy | SA | Hillary Nguyen | Hillary.Nguyen@truenergy.com.au | Industry Development Manager |
| Simply Energy | Vic | Marcus Mitford | Marcus.mitford@simplyenergy.com | Business Improvement Analyst |
| Simply Energy | SA | Marcus Mitford | Marcus.mitford@simplyenergy.com | Business Improvement Analyst |
| Lumo Energy | Vic | Alan Seiver | Alan.seiver@lumoenergy.com.au |  |
| Red Energy | Vic | Jade Wahapa | Jade.wahapa@redenergy.com.au | NECF Advisor |
| Aurora Energy | Vic | Giles Whitehouse | giles.whitehouse@auroraenergy.com.au | Regulatory & Compliance Manager |
| Alinta Energy | SA |  |  |  |
| Alinta Energy | Vic |  |  |  |

Attachment C

| Recertification Progress Report Report version <Draft/Final> |  |  |  |  |
| --- | --- | --- | --- | --- |
| Progress Report No : 1 |  |  | Week-ending: 30 March 2012 |  |
| Organisation: |  | Jurisdiction |  |  |
| This Report is to be completed and comments returned to AEMO by 10am each Monday |  |  |  |  |

| Symbol | Status |
| --- | --- |
|  | Completed |
| Green | Work to deliver milestone is on schedule with adequate contingency |
| Amber | Work to deliver milestone is on schedule but with inadequate contingency, a significant issue to be resolved, or behind schedule but will meet date using float time |
| Red | Work to deliver milestone or completion criteria cannot be met and will require re-planning |

| Key Milestone | Agreed completion date | Status Green / Amber / Red | Comments (if any) (Please advise if comments are confidential) |
| --- | --- | --- | --- |
| - Internal UAT completed | <As supplied – see Attachment A> |  |  |
| - Commenced certification | <As supplied – see Attachment A> |  |  |
| - Certification successfully completed |  |  |  |

## Attachment D

## GRCF certification report

| Organisation | Jurisdiction | Internal UAT completed milestone (as provided on 23rd March) | Progress against internal UAT milestone (Status Green / Amber / Red) | Commenced Certification Milestone (as provided on 23rd March) | Progress against Commenced Certification milestone (Status Green / Amber / Red) | R29 Certification Complete | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| AEMO | Vic | 25-May-12 |  | 28-May-12 |  |  |  |
| AEMO | Qld | 25-May-12 |  | 28-May-12 |  |  |  |
| AEMO | SA | 25-Apr-12 |  | 26-Apr-12 |  |  |  |
| Envestra | Vic | 20-Apr-12 |  | 16-May-12 |  |  |  |
| Envestra SA | SA | 22-Jun-12 |  | 25-Jun-12 |  |  |  |
| Envestra | Qld | 31-May-12 |  | 01-Jun-12 |  |  |  |
| APT Allgas | Qld | 15-Jun-12 |  | 18-Jun-12 |  |  |  |
| Multinet | Vic | 22-Jun-12 |  | 25-Jun-12 |  |  |  |
| SP AusNet | Vic | 01-Jun-12 |  | 04-Jun-12 |  |  |  |
| AGL | Vic | 22-Jun-12 |  | 25-Jun-12 |  |  |  |
| AGL | Qld | 22-Jun-12 |  | 25-Jun-12 |  |  |  |
| AGL | SA | 22-Jun-12 |  | 25-Jun-12 |  |  |  |
| Origin Energy | Vic | 15-Jun-12 |  | 18-Jun-12 |  |  |  |
| Origin Energy | Qld | 15-Jun-12 |  | 18-Jun-12 |  |  |  |
| Origin Energy | SA | 15-Jun-12 |  | 18-Jun-12 |  |  |  |
| Australian Power & Gas | Vic | 20-Apr-12 |  | 23-Apr-12 |  |  |  |
| Australian Power & Gas | Qld | 20-Apr-12 |  | 23-Apr-12 |  |  |  |
| TRUenergy | Vic | 07-May-12 |  | 25-Jun-12 |  |  |  |
| TRUenergy 2 | Vic | 25-May-12 |  | 28-May-12 |  |  |  |
| TRUenergy | SA | 07-May-12 |  | 25-Jun-12 |  |  |  |
| Simply Energy | Vic | 25-May-12 |  | 28-May-12 |  |  |  |
| Simply Energy | SA | 25-May-12 |  | 28-May-12 |  |  |  |
| Lumo Energy | Vic | 04-May-12 |  | 07-May-12 |  |  |  |
| Red Energy | Vic | 08-Jun-12 |  | 12-Jun-12 |  |  |  |
| Aurora Energy | Vic | 15-Jun-12 |  | 15-Jun-12 |  |  |  |
| Alinta Energy | SA | 15-Jun-12 |  | 15-Jun-12 |  |  |  |
| Alinta Energy | VIC | 15-Jun-12 |  | 15-Jun-12 |  |  |  |

Attachment E

Recertification timeline

AEMO will consider requests from Participant in relation to certification beyond 1 June 2012 but these must be received by AEMO (emailed to grcf@aemo.com.au) before COB Tuesday 13 March 2012 stating the reasons why the Participant is seeking an extension to the prescribed timeline. 
Time extension beyond 1 July 2012 will not be accepted at this point in time.

For SA AEMO IT systems are outsourced to Logica therefore the contact person is a Logica representative

Formally Energy Australia

One for each jurisdiction (Qld, SA and Vic)

For SA AEMO IT systems are outsourced to Logica therefore the contact person is a Logica representative

Formally Energy Australia