Release & cutover working group: Implementation Plan

PREPARED BY:	Gas Retail Market Development

DOCUMENT REF:	TBC

VERSION:	2.1

DATE:	27 July 2012

FINAL

Version Release History

| Version | Date | Author | Comments |
| --- | --- | --- | --- |
| 0.1 | 12 June 2012 | Justin Luu | Initial version |
| 0.2 | 26 June 2012 | Justin Luu | Updated |
| 0.3 | 6 July 2012 | Stefanie Macri | Update with feedback from 6 July meeting |
| 0.4 | 11 July 2012 | Justin Luu | Update with feedback from 11 July meeting |
| 2.0 | 19 July 2012 | Justin Luu | Final (approved by RCWG) |
| 2.1 | 27 July 2012 | Stefanie Macri | Update to Origin Energy and Multinet contact and APG contact number. |

Contents

1	Background	4

2	Implementation	4

3	Test of System Changes	4

4	Cutover Timetable and Responsibilities	5

5	Post-Schema Implementation Monitoring	7

6	Teleconferencing Details and Industry Contacts	8

7	Acceptance of Industry Implementation Plan	10

8	Reference Material	10

# Background

The Release & Cutover Working Group (RCWG) is being formed under the Gas Retail Consultative Forum (GRCF) to manage the lead up to the schema release on 30 July 2012.

The schema release will move the South Australian retail gas market from r13 to r29 and the Victorian and Queensland retail gas markets from r16 to r29. South Australian, Victorian and Queensland retail gas markets will implement enumerations file version 4.0 with schema r29.

This release includes a variety of changes, including:

- change to the Certificate of Compliance (IN016/10) and Plumbers Licence Number (IN007/11) to ensure Victorian systems are compliant with the safety requirements of Energy Safe Victoria; and

- introduction of Customer Classification (IN027/11) in order for all three retail gas markets to meet the obligations under the National Energy Retail Law.

This change also includes the NECF residual changes (IN011/12) which covers minor amendments to the documentation to ensure that the system build is consistent with the documentation.

It is expected that all participants will have completed internal UAT, certification and optional bi-lateral testing in the lead up to the schema release. This process is being managed and reported to the GRCF.

The FRC Hub will be in full operation during the cutover period to R29 in order to support the WA gas market.

# Implementation

Participants will need to plan the implementation of schema change for cutover on Sunday 29 July.

Participants will be responsible for developing their own release plan such that it is compatible with the overall Industry Implementation plan set out in section 4 of this document.

# Test of System Changes

In order to validate a successful implementation of the schema change a Production Verification Test will take place (see step 10 in Table below):

## AEMO to ebXML ping each participant

## Each Retailer will send each distributor a transaction

## Each Distributor will send each retailer a transaction

## AEMO will send each distributor and each retailer a transaction.

## All transactions will be acknowledged with BOTH an ebXML acknowledgement and an aseXML transaction acknowledgement.

Participants will pre-identify the transaction that will be provided to the Retailer / Distributor.

This will be sent to AEMO (grcf@aemo.com.au).

AEMO will collate this information and provide to the participants before 2pm.

During the PVT window (2PM – 4PM):

- AEMO will be available to assist where participants have issues that arise.

- All participants would be holding back all transactions other than those that are included in the test.

Note: Multinet’s gateway will not send transactions during PVT, their gateway will be available to ebXML acknowledge incoming transactions.

# Cutover Timetable and Responsibilities

| Item | Event | Market Time/EST | Responsible Party |
| --- | --- | --- | --- |
|  | - Cease generating new outbound transactions (i.e. R13, R16 aseXML) - Batch jobs completed before this time - Start using B2B Outage Protocol for all service order processing | Friday 27/07/12 3 PM AEST | All Participants |
|  | - Clear both incoming and outgoing failures from the gateway - All R13 and R16 aseXML processed | Friday 27/07/12 Before 6 PM AEST | All Participants |
|  | Via Teleconference: - Confirm all gateways are cleared of aseXML R13 and R16 - Confirm that gateways can be brought down at this time - Confirm readiness to commence implementation | Friday 27/07/12 6 PM AEST | All Participants |
|  | Via Teleconference: - Confirm readiness to commence implementation (for those who are implementing on Sunday). - Report implementation progress (for those implementing on Friday, Saturday or Sunday). | Sunday 29/07/12 9 AM AEST | All Participants |
|  | Implement schema change R29 (with version 4.0 of enumerations file) | Sunday 29/07/12 10 AM – 12 PM AEST | All Participants |
|  | Via Teleconference: - Participants to provide an update on implementation progress - Confirm readiness for 2PM PVT on track | Sunday 29/07/12 11:30 AM AEST | All Participants |
|  | Participants to provide AEMO (grcf@aemo.com.au) their transaction list to be sent. | Before 12 PM Sunday 29/07/12 AEST | All Participants |
| 8. | Send transaction list to participants detailing transactions they are expecting to receive | 12 PM – 1:30 PM Sunday 29/07/12 AEST | AEMO |
|  | - Internal troubleshooting period allowed to validate gateways are operational - Re-establish connectivity to FRC Hub | Sunday 29/07/12 12 PM – 2 PM AEST | All Participants |
|  | Via Teleconference: - Confirm starting Production Verification Testing | Sunday 29/07/12 2 PM AEST | All Participants |
|  | Conduct PVT as outlined in section 3 above. | Sunday 29/07/12 2 PM – 4PM AEST | All Participants |
|  | Participants to provide AEMO (grcf@aemo.com.au) their received transaction list. | Sunday 29/07/12 4PM - 4:30 PM AEST | All Participants |
|  | Via Teleconference: - Provide feedback on Production Verification Testing - Determine success of cutover | Sunday 29/07/12 4:30 PM AEST | All Participants |
|  | Systems into Production - All transactions sent with R29 schema - “trickle” feed transactions to each participants | Sunday 29/07/12 Post 4:30 PM AEST teleconference | All Participants |
|  | Participants to notify AEMO (grcf@aemo.com.au) once back-log has been cleared | Sunday 29/07/12 Post 4:30 PM AEST Before Monday 30/07/12 8:00AM AEST | All Participants |
|  | AEMO to provide email confirmation to RCWG representatives regarding back-log | Monday 30/07/12 Post 8:30 AM AEST | AEMO |
|  | Via Teleconference: - Determine the success of the implementation across industry - Determine if all backlog has been cleared per gateway | Monday 30/07/12 10:30 AM AEST | All Participants |
|  | Via Teleconference: - Determine the success of the implementation across industry | Monday 30/07/12 Post ITDF | All Participants (if required) |

# Post-Schema Implementation Monitoring

On Sunday 29 July 4:30PM AEST, to mitigate risk of the FRC Hub being flooded with transactions built up during the cutover period, all participants with the capability to, will limit the amount of transactions sent through their gateway to the FRC Hub.

On the morning of Monday 30 July, all participants will monitor their backend systems and gateways to ensure successful implementation.

A teleconference will be held at 10:30AM AEST to determine the success or otherwise of the implementation across the industry. Corrective action will be decided on issues and defects identified based upon their severity and market impact.

An additional teleconference will be held after the ITDF on Monday 30 July, if necessary. This will be determined at the 10:30AM teleconference.

# Teleconferencing Details and Industry Contacts

As detailed in this implementation plan, there will be a number of teleconferences to manage and monitor participant progress. The details of the teleconference are as follows:

Teleconference Chair: Stefanie Macri

VIC Participants dial: 07 3347 3030 or 02 8884 5050

QLD Participants dial: 07 3347 3030

SA Participants dial: 02 8884 5050

Passcode: 188916

This passcode will remain the same for all teleconferences held during the cutover period

| Name | Organisation | Email | Phone |
| --- | --- | --- | --- |
| Stefanie Macri | Chair Person | Stefanie.Macri@aemo.com.au | 03 9609 8419 0413 465 500 |
| Bert Naik (Primary) | AEMO FBS Admin | Bert.naik@aemo.com.au | 0409 165 146 |
| David Winship (Secondary) | AEMO FBS Admin | David.winship@aemo.com.au | 0403 895 398 |
| Ming Young (Secondary) | AEMO (VIC, QLD) | Ming.young@aemo.com.au | 0403 368 688 |
| Anne Waller (Primary) | AEMO (VIC, QLD) | Anne.waller@aemo.com.au | 0407 861 165 |
| Robert Gubbins | AEMO (SA) | robert.gubbins@logica.com | 02 8062 3030 |
| Minh Le | AEMO (SA) | Minh.le@logica.com | 0423 751 151 |
| Felicity Yates (Primary) | AGL (VIC, SA & QLD) | fyates@agl.com.au | 0403 604 720 |
| Chau Ly (Secondary) | AGL (VIC, SA & QLD) | cly@agl.com.au | 0408 950 194 |
| Howard Stoney | AGL (VIC, SA & QLD) | HStoney@agl.com.au | 03 8623 8454 |
| Priya Nellaiappan | AGL (VIC, SA & QLD) | PNellaia@agl.com.au | 03 8633 8320 |
| Tony Finch (Primary) | Alinta Energy Retail Sales (SA, VIC) | tfinch@serviceworks.com.au | 03 9862 8506 |
| Jennifer Bark (Secondary) | Alinta Energy Retail Sales (SA, VIC) | jbark@serviceworks.com.au | 03 9862 8509 |
| Kevin Boutchard | Aurora Energy(VIC) | Kevin.boutchard@auroraenergy.com.au | 0400 056 989 |
| Nick Gustafsson | Aurora Energy(VIC) | nick.gustafsson@utilisoft.com.au | 0434 424 049 |
| Martin Jenner | Australian Power & Gas (VIC) | mjenner@auspg.com.au | 02 8908 2784 |
| Mark Wass | Australian Power & Gas (QLD) | mwass@serviceworks.com.au | 03 9862 8507 0466 779 099 |
| Rebecca Cregan (Primary) | Envestra (SA, VIC, QLD)) APT Allgas (QLD) | rebecca.cregan@apa.com.au | 08 8113 9157 0415 729 503 |
| Maja Spuzic (Secondary) | Envestra (SA, VIC, QLD)) APT Allgas (QLD) | maja.spuzic@apa.com.au | 08 8113 9160 0423 180 036 |
| Alan Siever (Primary) | Lumo Energy (SA, VIC) | Alan.siever@lumoenergy.com.au | 0466 978 780 |
| Johan Santen (Secondary) | Lumo Energy (SA, VIC) | Johan.Santen@lumoenergy.com.au | 0407 447 614 |
| Paul Greenwood (Sunday) | Multinet (VIC) | Paul.Greenwood@jemena.com.au | 0404 046 613 |
| Matt Mullen (Friday) | Multinet (VIC) | matthew.mullen@jemena.com.au | 0400 342 438 |
| Malcolm Hempel (Primary) | Origin Energy (SA, VIC, QLD) | Malcolm.hempel@originenergy.com.au | 03 9652 5984 0407 719 554 |
| Kabeer Muhammed | Origin Energy (SA, VIC, QLD) | dlwiproitintmdhsupport@originenergy.com.au | 0413 606 014 |
| Maree Cockle (Primary) | Red Energy (VIC) | maree.cockle@redenergy.com.au | 0411 695 448 |
| Sanjesh Naidu (Secondary) | Red Energy (VIC) | sanjesh.naindu@redenergy.com.au | 0404 823 949 |
| Marcus Mitford (Primary) | Simply Energy (SA, VIC) | Marcus.Mitford@simplyenergy.com.au | 0418 370 620 |

| David Hains (Secondary) | Simply Energy | David.hains@simplyenergy.com.au | 0408 001 744 |
| --- | --- | --- | --- |
| Sarvesh Jerath (Secondary) | Simply Energy | Sarvesh.jerath@simplyenergy.com.au | 0402 162971 |
| Lynette Fernandes (Primary) | TRUenergy (SA, VIC) | lynettef@au1.ibm.com | 0437 430 471 |
| Adrian Sarris (Secondary) | TRUenergy (SA, VIC) | asarris@au1.ibm.com | 0423 776 760 |
| Holger Paffrath (Primary) | SP AusNet (VIC) | Holger.Paffrath@eb-Services.com.au | 0409 160 977 0418 611 345 03 9606 8833 |
| Siva Shivakumar (Secondary) | SP Ausnet (VIC) | Siva.shivakumar@eb-services.com.au | 0400 633 301 |
| Tarun Tummala | TRUenergy 2 (VIC) | TTummala@ausgrid.com.au | 02 8264 6312 |
| Rajesh Kumar | TRUenergy 2 (VIC) | rajesh.kumar@ausgrid.com.au | 02 8264 6432 |

# Acceptance of Industry Implementation Plan

RCWG representatives are the responsible persons to develop and approve the Industry Implementation Plan. Final review and acceptance will be minuted at the RCWG meeting.

# Reference Material

The following is a list of reference material for the RCWG:

| Document | Location |
| --- | --- |
| Retail Market Procedures (South Australia) Retail Market Procedures (Victoria) Retail Market Procedures (Queensland) | As published on 1 July 2012 on the AEMO website |
| Gas Interface Protocol Queensland Gas Interface Protocol (and associated Participant Build Packs) | As published (effective 30 July versions) on the industry only section of the AEMO website |
| Specification Pack (and associated technical protocols) | As published (effective 30 July versions) on the industry only section of the AEMO website |
| AEMO Decisions on: IN016/10, IN007/11, IN027/11 and IN011/12 | As published on the AEMO website |
| Guideline – Bulk Upload Process | Version 2 – as published on the industry only section of the AEMO website |
| r29 schema | As published on the AEMO website |
| FRC B2B Connectivity Testing and System Certification | Version 1.6 – as published on the AEMO website |