## Slide 1: 5MS & GS Executive Forum – Retail Go-Live Date Change
Thursday 11 February 2021
WebEx only: **Please disconnect from your workplace VPN for the WebEx call**
PLEASE NOTE THIS MEETING WILL BE RECORDED FOR THE PURPOSE OF PREPARING MINUTES

## Slide 2: AEMO Competition Law Meeting Protocol
AEMO is committed to complying with all applicable laws, including the Competition and Consumer Act 2010 (CCA). In any dealings with AEMO regarding proposed reforms or other initiatives, all participants agree to adhere to the CCA at all times and to comply with this Protocol.
Participants must arrange for their representatives to be briefed on competition law risks and obligations.
Participants in AEMO discussions must:
Ensure that discussions are limited to the matters contemplated by the agenda for the discussion
Make independent and unilateral decisions about their commercial positions and approach in relation to the matters under discussion with AEMO
Immediately and clearly raise an objection with AEMO or the Chair of the meeting if a matter is discussed that the participant is concerned may give rise to competition law risks or a breach of this Protocol.
Participants in AEMO meetings must not discuss or agree on the following topics:
Which customers they will supply or market to
The price or other terms at which Participants will supply
Bids or tenders, including the nature of a bid that a Participant intends to make or whether the Participant will participate in the bid
Which suppliers Participants will acquire from (or the price or other terms on which they acquire goods or services)
Refusing to supply a person or company access to any products, services or inputs they require.
Under no circumstances must Participants share Competitively Sensitive Information. Competitively Sensitive Information means confidential information relating to a Participant which if disclosed to a competitor could affect its current or future commercial strategies, such as pricing information, customer terms and conditions, supply terms and conditions, sales, marketing or procurement strategies, product development, margins, costs, capacity or production planning.

## Slide 3: Agenda
Welcome
Objectives
Retail Go-Live Feedback and Conclusions
March Checkpoint
Impact Assessment – Key Dates
5MS Rule Commencement Status Dashboard
Next Steps
Questions
Appendix 1: Further Information

## Slide 4: Objectives
This is a special purpose Executive Forum, to discuss the delays to AEMO’s Retail workstream
On 5 Jan, AEMO notified participants of delays in its Retail workstream
At the PCF on 28 Jan, provided a detailed update and proposed 2 delivery date options for industry feedback:
  Target Retail Go-Live for 31 May, with a checkpoint in early March
  Set 21 June as the Retail Go-Live, to provide increased date certainty
The purpose of this Executive Forum is to:
  Summarise industry feedback and advise option selected
  Provide 5MS Executives with the opportunity to understand the situation better

## Slide 5: Feedback and Conclusions
Industry feedback
  15 participants supported Option 1
  No participants supported Option 2
Additional points raised and noted
  Earlier date is preferred to provide for participants testing, Market Trial preparation, other readiness activities, incl. metering transition, and confidence in AEMO’s system stability
  Earliest possible deployment to pre-prod would be well received
  Fallback date – if required – should be as early as possible, not automatically locked in for 21 June
  Fallback date would require further replanning for participants – further clarity on approach to checkpoint and ongoing reporting is required
  Implications for costs, resource allocation and other regulatory change implementation (e.g. Customer Switching and WDR)
  More detailed feedback will be addressed through the relevant working groups
AEMO confirms the decision for Option 1:
  Retail go-live targeted for 31 May 2021
  Checkpoint in early March
  Fallback date (if needed) to be determined up to 21 June 2021.

## Slide 6: March Checkpoint
Week Commencing | Action
1 March | AEMO assess status against criteria and determine position for 31 May go-live
8 March | AEMO prepare PCF pack and publish to participants
18 March | Propose the PCF meeting for 18 March proceeds as scheduled If the PCF meeting were moved earlier, participants would have limited opportunity to review the pack prior to the meeting
Criteria
Enterprise Azure migration successfully completed
Build for critical defects completed
Target execution of test cases achieved, with no critical defects that cannot be remedied for 31 May go-live
Successful completion of Dress Rehearsal (DR2B)
Pre-Production environment established
Performance remediation for RM11 & RM16 completed, no new performance blockers
Schedule
Checkpoint
Criteria

## Slide 7: Initial Impact Assessment Key dates
Area | Original Date | New Date | Implication
5MS Rule Commencement | 1 Oct 21 | No change | No change to 5MS market start date Risk assessment requires review and re-rating to reflect revised schedule
UFE soft start | 1 Oct 21 | No change | Compresses available DNSP population time for some UFE Standing data activities and may result in re-scheduling of activities Leads to potentially less accurate UFE on 1 Oct 21 soft start
GS Rule Commencement | 1 May 22 | No change | No impact expected
5MS Market Trial | 5 July 21 | No change | No change to start date for 5MS market trial Acknowledge heightened risks around timely commencement
Dispatch IT Go-Live | 1 Apr 21 | No change | No impact expected
Settlements IT Go-Live | 15 Apr 21 | Mid-May | Will now go-live before Retail MDM Further testing required to allow for this Date currently being finalised, mid-May expected
Regulatory roadmap | Various | No change | No change currently anticipated to any dates: Customer Switching, WDR Regulatory roadmap session currently being arranged at which the overall view can be reviewed

## Slide 8: 5MS Rule Commencement Status
 | On track | On track for commencement date
 | Risk 1 – Risk to major milestones or deliveries | Remediation or contingency activation required to ensure on track delivery for Rule Commencement
 | Risk 2 – Risk to rule commencement | Cannot be addressed with available contingencies to be on track for commencement date
Activity | Status | Comments
AEMO Business Readiness for 5MS and GS (Part A) |  | Bidding Platform deployed for Industry test on Schedule. Retail Platform deployment being rescheduled with impact to dependent activities, Settlement platform go-live to mid-May. Rescheduling of platform deliveries is not expected to impact 5MS commencement or 5MS market trial.
Essential Industry Capabilities for 5MS commencement (Part A) |  | On track for 1 Oct 21 commencement, Metering Data Providers and MPs reporting on track. Generators reporting on-track delivery.
Other industry capabilities for 5MS and GS (Part B) |  | Non-essential activities across all participant types reported on track.
Summary: 5MS Rule Commencement |  | All components of 5MS Essential capability on track for Rule Commencement timeframe, replanning of AEMO Platform Deployments underway and heightened risk profile noted.
On track
On track
On track
On track
Risk 1
Risk 2
Risk 1
Dashboard commentary as at 28th January and will be updated with results from Readiness Survey #6, due 26th February. Represents overview of 5MS readiness and preparations for UFE soft start

## Slide 9: Next Steps: Communicating status on an ongoing basis
Next Executive Forum – 25-Mar-21
  Update on Retail workstream progress will be provided
  Further Executive Forums scheduled for 7 July and 2 Sept, aligned with Market Trial commencement and 5MS Market Start
A schedule will be presented to the PCF on 18-Feb outlining checkpoint dates and go/no-go decision dates with a view to integrate into the existing PCF timetable
All feedback received will be discussed with the relevant working / focus group

## Slide 10: Appendix 1: Further Information

## Slide 11
Migration to Enterprise Azure – Key Reason
  AEMO has completed its MDM build on what is called an “Interim” Cloud Platform. A corresponding project has run in parallel to 5MS to build an “Enterprise” Cloud Platform which contains significant improvements in stability, performance and security. 5MS found unforeseen technical complexities in moving to the Enterprise platform, which required remediation and a revised approach.
Challenges with Cutover Dress Rehearsal
  The program is completing multiple Dress Rehearsals for Cutover before deploying into Pre-Prod. A number of issues were identified and resolved through the rehearsal, this used up schedule and a further re-run is required before deploying.
Performance of Key RM Reports
  The RM11 and RM16 reports do not met performance targets, despite re-coding to address performance issues. The program team needs time to remediate to ensure performance targets meet industry expectations.
  For context, the functional delivery is accurate and the other RM Reports are ready for live deployment.
AEMO Response
  Identified resourcing dedicated to teams to address issues
  Put in place daily governance arrangements to allow for faster issues escalation and resolution
  Escalating the technical issues with its technology partners.
Key Drivers of Delay and AEMO Response
As reported to PCF on 28-Jan-21

## Slide 12: 5MS Program – IT Systems Status
Stream | Commentary
Retail | Core product build complete. Integration & User Acceptance Testing program is extensive. ~4500 test cases completed out of 5000. Parallel testing undertaken and defects in the process of being fixed Several rounds of performance testing undertaken and a number of improvements made Software is in Staging environment for participant interface testing since 3Q 2020 Key risk area of meter data ingestion is solid and performing to spec New issues encountered with Azure migration and cutover dress rehearsal Performance, end-to-end solution stability, final testing incomplete.
Dispatch | On schedule for 01-Apr-21 go-live
Settlements | Proposal to switch the order of Settlements and Retail deployment Additional testing of the new Settlements solution with the current MDM solution required accordingly. The Settlements solution pre-prod and go-live dates will be revised by approx 4 wks accordingly. Build complete and in User Acceptance Test. Overall no significant defects or issues, high level of confidence in product. Independent certification of settlements calculations – initial findings available, small number of material matters, now remedied. Date change is expected to impact AEMO internal only, no industry impact envisaged.
 | Go-live date impacted
 | At risk
 | On schedule
As reported to PCF on 28-Jan-21

## Slide 13: Actions to mitigate participant program impacts
Area | Mitigation | Participant Category | Implementation Status | Impact support
Bilateral Testing | Staging environment to support more extensive B2B and B2M bilateral testing | Retailer, DNSP, MDP | Under consideration, Updates being planned | Increased support of participant bilateral testing programs in advance of Retail pre-prod availability
5-minute Meter Data | Reduce period between retail platform go-live and acceptance of 5 minute granularity metering data | MDP | Under Consideration, Subject to participant input | Maximises transition window for the delivery of 5 minute metering data to AEMO prior to rule commencement
UFE | AEMO Support for bulk population of NCONUML | DNSP | Not currently Planned No TFG request as yet | Reduce impact of smaller transition window for the population of NCONUML NMIs, once approved
Industry Testing | Extend Industry Test period in advance of Retail Platform go-live | Retailer, DNSP, MDP | Only option 2 | Increase opportunity for participant process testing in upgraded environment prior to go-live
As reported to PCF on 28-Jan-21

## Slide 14: 5MS & GS Program Timeline: Level 1 Milestones
Current as at 08-02-2021

## Slide 15: External Milestones Impacted by Change
*Subject to Checkpoint with PCF 18-Mar-21 [Settlements dates under review]
ID | Milestone | Previous Date | Baselined Dates | Owner
L1-19 | AEMO Metering Solution - Go-Live | 9-Mar-21 | 31-May-21* | AEMO
L2-RE35 | Industry Go-Live Plan final - Release 3 - Retail MDM | 25-Jan-21 | 16-Apr-21 | AEMO
L2-M11 | Industry Test Preparation completed by Participants for MDM and B2M Go-Live | 1-Feb-21 | 19-Apr-21 | Participants
L2-M12 | Industry Test Preparation completed by AEMO for MDM and B2M Go-Live | 1-Feb-21 | 19-Apr-21 | AEMO
L2-RE29 | Retail MDM (incl. B2M) Invitation Industry Test Commences | 1-Feb-21 | 19-Apr-21 | AEMO
L2-RE30 | Retail MDM (incl. B2M) Invitation Industry Test Concludes | 3-Mar-21 | 21-May-21 | AEMO
L2-M24 | Retail MDM (incl. B2M) Go-Live | 9-Mar-21 | 31-May-21 | AEMO
L2-M10 | 5 minute files in MDFF format accepted by AEMO | 1-Apr-21 | 22-Jun-21 | AEMO
L1-22 | Settlements Platform Go-Live | 19-Apr-21 | [17-May-21] | AEMO
L2-S10 | Settlements Industry Test preparation completed by participants | 17-Feb-21 | [22-Mar-21] | Participants
L2-S11 | Settlements Industry Test preparation completed by AEMO | 17-Feb-21 | [22-Mar-21] | AEMO
L2-RE19 | Industry Go-Live Plan - Settlements finalised | 19-Mar-21 | [16-Apr-21] | AEMO
L2-RE32 | Settlements Industry Test Concludes | 14-Apr-21 | [13-May-21] | AEMO
Dates in square brackets subject to change