## Slide 1: Five-Minute Settlement Program: Program Consultative Forum 4
AEMO 5MS Program Team
THURSDAY 4 OCTOBER 2018
AEMO Offices:
Level 9, 99 Gawler Place, Adelaide
Level 10, 10 Eagle Street, Brisbane
Level 22, 530 Collins Street, Melbourne
LEVEL 2, 20 BOND STREET, SYDNEY
DIAL IN: 02 9087 3604 ACCESS CODE: 844-627-037

## Slide 2: Agenda
NO | Time | AGENDA ITEM | Responsible
Preliminary Matters |  |  | 
1 | 10:00am – 10:10am | Welcome, introduction and apologies | Chris Muffett (AEMO)
2 | 10:10am – 10:20am | Minutes and actions from previous meeting | Chris Muffett (AEMO)
Matters for Noting |  |  | 
3 | 10:20am – 10:40am | Program update | Graeme Windley (AEMO)
4 | 10:40am – 10:50am | Industry risks & issues | Graeme Windley (AEMO)
5 | 10:50am – 11:10am | Procedures workstream update | Emily Brodie (AEMO)
6 | 11:10am – 11:30am | Systems workstream update | Hamish McNeish (AEMO)
 | 11:30am – 11:40am | Break | 
Matters for Discussion |  |  | 
7 | 11:40am – 11:55am | Fact Sheets | Gary Eisner (AEMO)
8 | 11:55am – 12:15pm | Joint metering/systems focus group | Emily Brodie (AEMO)
9 | 12:15pm – 12:30pm | Non-mandatory components in 5MS | Chris Muffett (AEMO)
Other Business |  |  | 
10 | 12:30pm – 12:40pm | General questions | Chris Muffett (AEMO)
11 | 12:40pm – 12:45pm | Forward meeting plan | Chris Muffett (AEMO)

## Slide 3: Minutes and actions from previous meeting
Chris Muffett

## Slide 4: Program update
Graeme Windley

## Slide 5: High-level status
Procedures work is progressing well, with nearly all activities on track:
  Working groups and focus groups have been constructive
Systems work continues to ramp up:
  Architecture, Requirements and Design work underway
  Development work to commence in Q4 2018
Rule changes:
  Global settlement draft determination feedback due by 25 October
  DER rule has been made – potential impact to 5MS solution design; however go live of 1 December 2019 may have a resourcing impact for participants
Stakeholder engagement is proceeding:
  Next EF meeting scheduled for 13 November – AEMO view is to proceed and provide useful content
  1-on-1 discussions have been held and will continue on a rolling basis

## Slide 6: Industry risks & issues
Graeme Windley

## Slide 7: Summary
Latest risk/issue register included with meeting pack
Risk/issue register is published on 5MS PCF page: http://www.aemo.com.au/Electricity/National-Electricity-Market-NEM/Five-Minute-Settlement/Program-Management/Program-Consultative-Forum
AEMO welcomes any feedback from the PCF on the risks & issues

## Slide 8: Risk/issue updates
Risks updated:
  R01 updated: Plan for small participant engagement has been discussed with PCF, and AEMO is now executing plan. Propose risk remain open, and reviewed in mid-2019
  R10 added: Vendor contract negotiation timelines – raised by AGL, and AEMO agreed that it should be included
Issues updated:
  I01 closed: Need for MDP & MP reaccreditation – has been discussed with PWG and reported back at previous PCF

## Slide 9: Procedures workstream update
Emily Brodie

## Slide 10: Procedures workstream status

## Slide 11: Metering package 1
Timing has slipped by one month due to additional pre-consultation through the joint metering/systems focus group
Updated timing will be presented to the PWG for comment on 11th October

## Slide 12: Procedures workstream
Third PWG held Thursday 13th September
  Settlements – Prudentials
Next PWG is Thursday 11th October
  Settlements – Miscellaneous
  Dispatch – Spot Market
  Metering – debrief on joint metering/systems focus group
Joint procedures/IT system focus groups:
  Metering/Systems, held Friday 14th September 2018, Melbourne
  Metering/Systems, proposing to reconvene early November
  Dispatch/Systems, proposing to meet Monday 22nd October, Brisbane

## Slide 13: Consultations
Dispatch – Market suspension pricing methodology
The consultation considers potential improvements to how well the current market suspension pricing schedules reflect typical pricing outcomes. It aims to minimise unnecessary volatility or adverse incentives during periods of system stress.
Amendments to accommodate the change to 5MS are included and remove any need for further consultation because of that change.
Four submissions received on Issues Paper, varied opinions
Final stage of consultation underway: http://www.aemo.com.au/Stakeholder-Consultation/Consultations/Market-Suspension-Pricing-Consultation
Submissions due Monday 8 October
Final report will be published 16 November 2018

## Slide 14: Systems workstream update
Hamish McNeish

## Slide 15: Systems Workstream – Activities
Second SWG held on 24th August
  Focus on Bidding and Metering API interfaces
  Discussion on planned Focus Groups
  Summary of Transition joint focus group
Next SWG – 17th October
Joint procedures/IT system focus groups:
  Metering/Systems, held Friday 14th September 2018, Melbourne
  Metering/Systems, proposing to reconvene early November
  Dispatch/Systems, proposing to meet Monday 22nd October, Brisbane

## Slide 16: System Workstream – Dispatch
Planned dates are subject to PWG consultation progress
Early Release depends on PWG outcomes

## Slide 17: System Workstream – Metering
Planned dates are subject to PWG consultation progress
Early Release depends on PWG outcomes
* = Potential joint focus groups with PWG

## Slide 18: System Workstream – Settlement and Operations
Planned dates are subject to PWG consultation progress

## Slide 19: Fact Sheets
Gary Eisner

## Slide 20: Fact Sheets
AEMO will release several Fact Sheets over the coming months
3 are currently being drafted:
  High-level 5MS Fact Sheet – explaining what 5MS is, and summarising the impact across the industry
  High-level Global Settlement Fact Sheet – the objective of global settlement, and the impact of implementing (based on current AEMC draft determination)
  Outcomes of the 1-1 Discussions Fact Sheet
These will all be published in October on the AEMO website at: http://www.aemo.com.au/Electricity/National-Electricity-Market-NEM/Five-Minute-Settlement/Program-Information-and-Fact-Sheets

## Slide 21: Fact Sheets
The next round of fact sheets will start to delve into more detailed and specific areas, categorised by industry roles (e.g. metering businesses, networks, retailers, generators, large end-use consumers)
These role-specific fact sheets will also aim to address issues affecting a sub-class of industry participant (e.g. small renewable generators), and be helpful for new entrants and other interested parties
Any feedback or suggestions on this approach, or particular facts sheets to be developed is welcome

## Slide 22: Joint metering/systems focus group
Emily Brodie

## Slide 23: Joint metering/systems focus group: Friday 14th September, Melbourne
Good engagement and contributions
Discussion went for longer than expected so not all agenda items covered
Meeting notes and actions distributed to focus group, PWG and SWG on Thursday 20th September
Debrief of focus group meeting will be provided to the PWG at the next meeting on Thursday 11th October
Proposing to reconvene in early November soon after metering procedures package #1 is released for consultation, to workshop:
  Transition to 5 minute metering
  Discuss Metering Package #1 consultation topics
  Discuss and finalise relevant actions from the 14 Sept workshop

## Slide 24: Non-mandatory components in 5MS
Chris Muffett

## Slide 25: Background
Context:
  Implementation of 5MS by AEMO and the industry involves many key components that are explicitly set out in the amended rules – e.g. transition of physical metering, retrieval of 5-minute meter data, treatment of non-5-minute data, settlement calculations, granularity of bids/offers
  We also expect that Global Settlement will be implemented, which will involve additional explicit requirements – e.g. receipt of all meter data for settlement, calculation and apportionment of UFE
Opportunity:
  5MS and GS present an opportunity to consider other changes that are not explicitly required, e.g. to address long-standing arrangements where a case for change has previously not been sufficient.
AEMO has identified a number of non-mandatory components that are currently being considered through the PWG and SWG engagements

## Slide 26: Component summary
 | Component | Objective | Potential benefits
1 | Unify meter data delivery | Decommission (after transition period) the existing B2M meter data format, and use same format as B2B and CAD (i.e. MDFF) | Reduces system complexity, improves reconciliation, and reduces new entrant costs
2 | Register-level data streams for settlement | Allow import/export data to be provided for settlement activities (currently only net data is facilitated) | Avoid different meter data being used for retail/network billing and market settlement
3 | Non-energy data streams | Allow non-energy (e.g. kVA) data to be received by AEMO | Remove impediments for MDPs to provide identical data for retail/network billing and market settlement
4 | Overhaul dispatch interface | Uplift the interface that scheduled participants use to provide bid/offer and related information | Removes legacy technologies and better supports future changes
5 | Energy Storage System changes | Consider delivery of components of Energy Storage System work as part of 5MS | Avoids duplication of system work
6 | Decommission sample meters | Remove requirement for NSPs to install/maintain sample meters to support controlled load profiles | Addresses significant issue for NSPs post metering competition

## Slide 27: Feedback
AEMO seeks feedback from participants on the proposed non-mandatory components to be pursued
Feedback is welcome on additional components that could be included
  AEMO would need to demonstrate the changes have merit, and that inclusion does not have a material impact on risk of 5MS delivery

## Slide 28: General questions
Chris Muffett

## Slide 29: Further information
Global Settlement rule change:
  AEMC website: https://www.aemc.gov.au/rule-changes/global-settlement-and-market-reconciliation
AEMO 5MS Program contacts:
  Graeme Windley, 5MS Program Manager
  Chris Muffett, 5MS Business Lead
  Emily Brodie, 5MS Procedure Lead
  Hamish McNeish, 5MS Systems Lead
  Gary Eisner, 5MS Stakeholder Liaison
Contact details:
  5MS email: 5ms@aemo.com.au
  5MS webpage: http://www.aemo.com.au/Electricity/National-Electricity-Market-NEM/Five-Minute-Settlement

## Slide 30: Forward meeting plan
Chris Muffett

## Slide 31: Upcoming meetings
Program Consultative Forums:
  PCF #5: Monday 5 November
  PCF #6: Tuesday 4 December
Next Executive Forum:
  Tuesday 13 November
Next Procedure Working Group:
  Thursday 11 October
Next Systems Working Group:
  Wednesday 17 October
Meetings and forum dates: http://www.aemo.com.au/Electricity/National-Electricity-Market-NEM/Five-Minute-Settlement