## Slide 1: 5MS & GS Program Consultative Forum #26
Thursday, 1 October 2020
This meeting is recorded for the purpose of minute taking.

## Slide 2: AEMO Competition Law Meeting Protocol
AEMO is committed to complying with all applicable laws, including the Competition and Consumer Act 2010 (CCA). In any dealings with AEMO regarding proposed reforms or other initiatives, all participants agree to adhere to the CCA at all times and to comply with this Protocol. Participants must arrange for their representatives to be briefed on competition law risks and obligations.
Participants in AEMO discussions must:
Ensure that discussions are limited to the matters contemplated by the agenda for the discussion
Make independent and unilateral decisions about their commercial positions and approach in relation to the matters under discussion with AEMO
Immediately and clearly raise an objection with AEMO or the Chair of the meeting if a matter is discussed that the participant is concerned may give rise to competition law risks or a breach of this Protocol
Participants in AEMO meetings must not discuss or agree on the following topics:
Which customers they will supply or market to
The price or other terms at which Participants will supply
Bids or tenders, including the nature of a bid that a Participant intends to make or whether the Participant will participate in the bid
Which suppliers Participants will acquire from (or the price or other terms on which they acquire goods or services)
Refusing to supply a person or company access to any products, services or inputs they require
Under no circumstances must Participants share Competitively Sensitive Information. Competitively Sensitive Information means confidential information relating to a Participant which if disclosed to a competitor could affect its current or future commercial strategies, such as pricing information, customer terms and conditions, supply terms and conditions, sales, marketing or procurement strategies, product development, margins, costs, capacity or production planning.

## Slide 3: Agenda
# | Time | Topic | Presenter
1 | 10:00 – 10:05 | Welcome | Peter Carruthers
2 | 10:05 – 10:10 | Actions from previous meetings | Anne-Marie McCague
3 | 10:10 – 10:20 | Program Update | Rowena Leung
4 | 10:20 – 10:35 | Readiness Working Group Update | Greg Minney
7 | 10:35 – 10:40 | Forward Meeting Plan/Executive Forum Agenda | Anne-Marie McCague
8 | 10:40 – 10:50 | General Questions | Peter Carruthers
9 | 10:50 – 11:00 | Break | 
10 | 11:00 – 11:30 | Wholesale Demand Response (WDR) and Customer Switching Update | Various
11 | 11:30 | Meeting Close | Peter Carruthers

## Slide 4: Welcome
Peter Carruthers

## Slide 5: Actions from Previous Meetings
Anne-Marie McCague

## Slide 6: PCF Actions
No. | Status | Action | Comment
25.3.1 | Open | PCF to discuss proposed change in date to Settlements deployment with RWG members and provide AEMO feedback by 25 September 2020. | Feedback is required by 23 Oct.
25.5.1 | Closed | AEMO to update the Industry Risks and Issues Register to reflect the decisions from PCF#25. | Complete
25.6.1 | Closed | AEMO to issue invitations to the Transition Focus Group by 10 September 2020. | Invitation circulated to TFG mailing list 10/09/20.
25.6.2 | Open | AEMO to confirm the update of Readiness Strategy documents to reflect changes due to the revised rule commencement dates and associated milestone updates. | In progress.
25.9.1 | Closed | AEMO to consider adding risks and issues section to the Vendor Briefing Session. | A risks and issues section was added.

## Slide 7: Program Update
Rowena Leung

## Slide 8: 5MS Program Timeline Level 1 and External Level 2 Milestones 1/2
Current as at 18-09-2020

## Slide 9: 5MS Program Timeline Level 1 and External Level 2 Milestones 2/2
Current as at 18-09-2020

## Slide 10: Program update and current activities
AEMO program
Overall Program remains Green trending down. Delivery pressures remain with a very busy schedule.
The program remains in an intense period of delivery work focusing on:
  Non-critical build items
  Testing
  Dress Rehearsal
  Certifiation
Key focus is on the Testing program which is in full flight, there is concurrent testing phases across all 3 workstreams underway.
AEMO business readiness, change mgt and transition activities are in progress.
Systems
Testing and deployment work continues - no change to any upcoming Staging deployment, Pre-Production or Production dates.
3rd Retail drop in Staging completed, defect fixes and environment adjustments continue to be delivered.
AEMO internal SIT, Retail & Dispatch UAT continuing, Settlements UAT to begin early October.
Issue with performance testing – failure of running high volumes of >3 different report types at once. Remediation being worked through, resolution targeted by end of October.
Readiness
Results of Readiness Survey #3 reviewed with RWG. Essential Capability reporting considered and follow up activity identified
Consolidation of initial participant metering rollout plans for review at Transition Focus Group
Proposal for Settlement deployment date change and non 5MS data model changes
Proposal for simplification of RM reports for profile values

## Slide 11: AEMO Systems Deployment Cutover Risk - Update
Risk Description | Risk Assessment |  | 
The current Cutover approach has the 3 AEMO systems deployments in close succession. Retail Metering the largest, most technically complex and riskiest cutover going first on 9 March, then followed by both the Dispatch and Settlements systems deployments together 3 weeks later on 1 April. A go-live criteria for Settlements is a stable metering platform. The current timetable only allows one week for the Retail solution to be stabilised prior to commencing cutover activity for Settlements which is high-risk. | Inherent Likelihood | Inherent Consequence | Inherent Risk Rating
 | Possible | Major | Significant
 | Residual Likelihood | Residual Consequence | Residual Risk Rating
 | Unlikely | Moderate | Medium
AEMO has presented the proposal to change the deployment date for the Settlements solution to 19 April 2021 to the PCF and RWG.
To date there has been no feedback received.
AEMO has organised a Market Systems User Group (MSUG) for 14 October to review upcoming changes to the data model, including both 5MS and non-5MS changes (such as MT-PASA).
AEMO requests participant feedback on the proposed date change after the MSUG has taken place by 23 October 2020 to allow for discussion at the November PCF.
AEMO does not see a reason not to make this change, but will not confirm this until the MSUG session has concluded.

## Slide 12: Readiness Working Group Update
Greg Minney

## Slide 13: Level 2 Milestones – Readiness
Key Milestones (Program) |  |  |  |  | 
ID | Milestone | Target Date | Expected Date | Owner | Status
L2-RE11 | Metering Service Provider Accreditation Plan Finalised | 13-Mar-2020 | 18-Feb-2020 | AEMO | Complete
L2-S12 | Reallocations Go-Live | 01-Apr-2020 | 01-Apr-2020 | AEMO | Complete
L2-RE32 | Industry Test for Reallocations Concludes | 31-Mar-2020 | 31-Mar-2020 | AEMO | Complete
L2-RE22 | Industry Transition Plan – Dispatch​ final complete | 28-Aug-2020 | 28-Aug-2020 | AEMO | Complete
L2-M11 | Industry Test preparation completed by participants for MDM and B2M Go-Live | 01-Feb-2021 | 01-Feb-2021 | Participants | 
L2-M12 | Industry Test preparation completed by AEMO for MDM and B2M Go-Live | 01-Feb-2021 | 01-Feb-2021 | AEMO | 
L2-RE29 | Retail MDM (incl. B2M) Industry Test Commences | 01-Feb-2021 | 01-Feb-2021 | AEMO | 
L2-RE30 | Retail MDM (incl. B2M) Industry Test Concludes | 03-Mar-2021 | 03-Mar-2021 | AEMO | 
L2-RE18 | Industry Go-Live Plan Retail MDM finalised | 20-Nov-2020 | 20-Nov-2020 | AEMO | 
L2-M24 | B2M Go-Live | 09-Mar-2021 | 09-Mar-2021 | AEMO | 
L2-M10 | 5 minute files in MDFF accepted by AEMO | 01-Apr-2021 | 01-Apr-2021 | AEMO | 
L2-D7 | Dispatch Industry Test preparation completed by participants | 29-Nov-2020 | 29-Nov-2020 | Participants | 
L2-D8 | Dispatch Industry Test preparation completed by AEMO | 29-Nov-2020 | 29-Nov-2020 | AEMO | 
Milestone complete
Milestone on track
Milestone not achieved
Milestone at risk
Domain | Initiative | 2019 |  |  |  |  |  |  |  |  |  |  |  | 2020 |  |  |  |  |  |  |  |  |  |  |  | 2021 |  |  |  |  |  |  |  |  |  |  | 
 |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  | 
Readiness |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec
L2-RE11
L2-RE32
L2-S12
L2-RE22
L2-M11
L2-M12
L2-RE18
L2-M24
L2-M10
L2-D7
L2-D8
L2-RE29
L2-RE30
Current as at 18-09-2020

## Slide 14: Level 2 Milestones – Readiness
Key Milestones (Program) |  |  |  |  | 
ID | Milestone | Target Date | Expected Date | Owner | Status
L2-S10 | Settlements Industry Test preparation completed by participants | 17-Feb-2021 | 17-Feb-2021 | Participants | 
L2-S11 | Settlements Industry Test preparation completed by AEMO | 17-Feb-2021 | 17-Feb-2021 | AEMO | 
L2-RE28 | Dispatch Industry Test concludes | 15-Mar-2021 | 15-Mar-2021 | AEMO | 
L2-RE32 | Settlements Industry Test concludes | 15-Mar-2021 | 15-Mar-2021 | AEMO | 
L2-RE19 | Industry Go-Live Plan Settlements, Dispatch & Bidding finalised | 19-Mar-2021 | 19-Mar-2021 | AEMO | 
L2-RE23 | 5MS Capability Market Trial preparation completed by participants | 05-Jul-2021 | 05-Jul-2021 | Participants | 
L2-RE24 | 5MS Capability Market Trial preparation completed by AEMO | 05-Jul-2021 | 05-Jul-2021 | AEMO | 
L2-RE31 | 5MS Capability Market Trial commences | 05-Jul-2021 | 05-Jul-2021 | AEMO | 
L2-RE20 | Industry Go-Live Plan – 5MS Capability final complete | 01-Aug-2021 | 01-Aug-2021 | AEMO | 
L2-D10 | 5MS Capability Market Trial concludes | 27-Aug-2021 | 27-Aug-2021 | AEMO | 
L2-D11 | 30-min Bidding no longer accepted by AEMO | 01-Oct-2021 | 01-Oct-2021 | AEMO | 
L2-RE25 | MDMT format no longer accepted by AEMO for interval meters | 01-Oct-2021 | 01-Oct-2021 | AEMO | 
L2-RE26 | GS Market Trial preparation completed by participants | 01-Feb-2022 | 01-Feb-2022 | Participants | 
L2-RE27 | GS Market Trial preparation completed by AEMO | 01-Feb-2022 | 01-Feb-2022 | AEMO | 
L2-RE21 | Industry Go-Live Plan – GS Capability final complete | 21-Dec-2021 | 21-Dec-2021 | AEMO | 
Domain | Initiative | 2019 |  |  |  |  |  |  |  |  |  |  |  | 2020 |  |  |  |  |  |  |  |  |  |  |  | 2021 |  |  |  |  |  |  |  |  |  |  | 
 |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  | 
Readiness |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec
L2-S10
L2-S11
L2-RE32
L2-RE23
L2-RE24
L2-RE20
L2-D10
L2-D11
L2-RE25
L2-RE21
L2-RE31
L2-RE328
Current as at 18-09-2020
Milestone complete
Milestone on track
Milestone not achieved
Milestone at risk
Milestone deferred
L2-RE19

## Slide 15: Readiness Working Group Update
Working Group update:
Readiness reporting participant follow up and consideration of essential industry capability reporting
Participant approaches to 5 minute data delivery
RM20 PPS Report Simplification
Systems Stream updates also included, no additional callouts for the industry
Go-Live Plans
Upcoming activity
  TFG – review of consolidated rollout plans, commence consideration of CATS volume implications
  Planning for Retail Invitation Industry Test
  Initial review Retail Industry go-live plan
  Dispatch and Bidding Industry Test Support

## Slide 16: Platform Go-Live Plans
Approach:
Go-live plan developed for each AEMO platform go-live.
Identify and schedule participant activity during cutover window to facilitate the deployment of AEMO market systems
In scope
Cutover approach overview
Industry responsibilities and expectations, including Production Verification Monitoring, as part of the restarting of production systems
AEMO Platform Go/no-go decision approach and timeframes
Industry Cutover Schedule
Communication and notification approach
  Approach and formats for communication of schedule updates and key decision points
Contingency and restart process and notification
Out of scope
Participant deployment plans and schedules
Participant roll-back plans

## Slide 17: 5MS / GS platform go-lives engagement timeframes
Release | Industry Engagement | Plan Finalisation | Go-Live
Retail/ MDM | October 20 | December 20# | 9th March
Settlements | November 20 | February 21 | 1 April*
Bidding/ Dispatch | November 20 | February 21 | 1 April
# Updates to detail schedule timings if required post Dress Rehearsals
* Go-live date proposed to move to 19th April 2021

## Slide 18: Overall systems delivery status
Dispatch
Retail
Settlements
Reallocations (P1) 01-Apr-20
Settlements Platform (P2&3) - 01-Apr-21
Reallocations (P1) – 26-Feb-20
Settlements Platform (P2&3) – 17-Feb-21
5-min Bidding (all packages) – 29-Nov-20
P1 – Bidding FTP & API –
29-Nov-19
P2 – Bidding Web UI – 29-Nov-19
P3 – Dispatch, Pre-dispatch and PASA - 29-Nov-19
P4 – Pricing & Miscellaneous – 15-May-20
P1: Reallocations – 01-Nov-19
P2: Settlements & Billing –
16-Mar-20
P3: Prudentials & Estimation – 15-May-20
P1: MTRD FTP Metering Data Ingestion – 01-Dec-19
P2: B2M via API (API Push) & All Meter Data Ingestion scenarios – 15-Jun-20
P3: B2M via API (API Pull) & MSATS Reports, 30-min transition state w 30-min reporting – 31-Aug-20
P4: Environment set to 5-min, 5-min reporting enabled – 31-Oct-20
MDM solution (all packages) – 01-Feb-21
5-min Bidding (all packages) – 01-Apr-21
MDM solution (all packages) – 09-Mar-21
Overall Program Status
On track | 
At risk | 
Delayed | 
Complete | 
Staging Environment
Pre-Production
Production Go-Live
Overall systems delivery status
On track | 
At risk | 
Delayed | 
Complete | 

## Slide 19: Retail – Functionality in Staging Release 3
Assumptions/Constraints
  Standing Data updates will not be flow through to Meter Data validations.
  Connectivity is only via AEMO’s MarketNet.

## Slide 20: Retail – Functionality in Staging Release 3

## Slide 21: 5MS Staging Environment – Retail Release
Issue ID​ | Description​ | Status​ | Action​
​ | Missing files from 28 Aug FOR tradingprice or averageprice30 ​ | Closed​ | Fixed and regeneration of missing files inprogress​
1992​ | Screen display issue only - An extra TNI2 field is getting displayed under AddressInformation section in NMI Master, Point in Time NMI Master Summary and NMI Discovery Type 1 and Type 2 search page.​ | InProgress​ | It is a display issue only no functionality affected​
2193​ | Market Portal does not contain MSATS screens​ | Closed | Unable to access MSATS via the market portal menu​
2185​ | Unable to login to MSATS with newly created and updated user id and password​ | In Progress​ | Once created/updated in MSATS users can reset password by logging onto the market portal​
2349​ | ​ Incorrect rejection of CATS requests via FTP because of file name validation. ​ | Closed​ | Work around – use the naming convention ​ catsm_participant ID_nnnnnnnn... if submitting via FTP​
 | A performance issue affecting the generation and publication of reports for wholesale has been identified and is currently being remediated to allow dispatch and bidding reports to run faster | In Progress | Current reviewing logs to identify possible issues.

## Slide 22: Forward Meeting Plan
Anne-Marie McCague

## Slide 23: Forward Meeting Plan
Next PCF: 05-Nov-20
Agenda topics:
  Update on Dispatch release into pre-prod environment
  High-level summary of Readiness Reporting Round 4
  Update on date for Settlements Go-Live

## Slide 24: Upcoming meetings
Current as at 25/09/2020
https://aemo.com.au/initiatives/major-programs/nem-five-minute-settlement-program-and-global-settlement

## Slide 25: General Questions
Peter Carruthers

## Slide 26: Wholesale Demand Response (WDR) Update
Various

## Slide 27: Session
Context
WDR impacts to market systems
Proposed WDR implementation timeline
Next steps

## Slide 28: Context
Emily Brodie, WDR Stakeholder Engagement Lead

## Slide 29: Regulatory implementation roadmap
For full details see: https://www.aemo.com.au/initiatives/major-programs/regulatory-implementation-roadmap
April 20
Market bodies begin prioritising regulatory program due to:
21 April 20
First draft of roadmap
10 August 20
Roadmap updated to reflect:
Stakeholder forum
new rules
stakeholder feedback
impacts of COVID-19
Recognised regulatory burden
31 August 20
Stakeholder forum and consultation following release of AEMC decisions on 5MS date and WDR

## Slide 30: Key roadmap dates
1 October 2021: New commencement date for 5MS and GS soft start
1 October 2021: Customer switching go-live
24 October 2021: Confirmed WDR commencement date
November 2021: Electricity and gas B2B changes
30 March 2022: Metering Coordinator Planned Interruptions and MSATS Standing Data Review (v1) go-lives

## Slide 31: Partial snapshot of regulatory implementation roadmap
For full details see: https://www.aemo.com.au/initiatives/major-programs/regulatory-implementation-roadmap

## Slide 32: Planned retail schema changes
For full details see: https://www.aemo.com.au/initiatives/major-programs/regulatory-implementation-roadmap

## Slide 33: WDR system impacts
Ruth Guest, WDR Business Lead

## Slide 34: NEM Wholesale Systems: 5MS change heatmap
DISPATCH
SETTLEMENT
POWER SYSTEM
Bids/Offers
Dispatch
Predispatch (P5/P30s)
ST PASA
Settlement 5MS Calc.
Settlement GS Calc.
Causer Pays Factors
Data Model
SRA
MT PASA / EAAP
Demand Forecasting
Data Model
Generator Recall
Data Model
RERT
Administered Pricing
Suspension Pricing
Negative Residue Management
Wind/Solar Availability
Reallocations
Estimation and Prudentials
VAR/MW Dispatch
Constraints
Spot Price
Registration
IRSR Calc.

## Slide 35: NEM Wholesale Systems: Combined 5MS + WDR change heatmap
There is no impact from Customer Switching on NEM wholesale systems
DISPATCH
SETTLEMENT
POWER SYSTEM
Bids/Offers
Dispatch
Predispatch (P5/P30s)
ST PASA
Settlement 5MS Calc.
Settlement GS Calc.
Causer Pays Factors
Data Model
SRA
MT PASA / EAAP
Demand Forecasting
Data Model
Generator Recall
Data Model
RERT
Administered Pricing
Suspension Pricing
Negative Residue Management
Wind/Solar Availability
Reallocations
Estimation and Prudentials
VAR/MW Dispatch
Constraints
Spot Price
Registration
IRSR Calc.
NEW WDR SYSTEMS
Portfolio management
Baselines
*
*
* 5MS settlement calculations are not impacted. WDR will provide additional settlement functionality.
5MS major impact
5MS moderate impact
5MS some impact
5MS no impact
WDR major impact
WDR moderate impact
WDR some impact - adding DRSP participant type & related attributes

## Slide 36: NEM Retail Systems: 5MS change heatmap
B2M / B2B Interfaces
CATS / MDM Processes
MSATS Browser / Reports
MDMT
CATS Standing Data
B2M aseXML schema
NMID
CATS
B2B Transactions
B2B aseXML schema
Meter Data screens
RM21/27
CR Processing
RM11,12,13,14,16
RM17,18,19,20,22
VIC TUoS
Profiling
Energy Allocation
Estimation / Substitution
Meter Data Validation
RM28,30,31,32
RM33
RM7,8,9,10
RM15,29
C2,3,6,7,9,10
C11,12,13
SDR
C1,4
MSATS B2M APIs

## Slide 37: NEM Retail Systems: Combined 5MS + CS + WDR change heatmap
B2M / B2B Interfaces
CATS / MDM Processes
MSATS Browser / Reports
MDMT
CATS Standing Data
B2M aseXML schema
NMID
CATS
B2B Transactions
B2B aseXML schema
Meter Data screens
RM21/27
CR Processing
RM11,12,13,14,16
RM17,18,19,20,22
VIC TUoS
Profiling
Energy Allocation
Estimation / Substitution
Meter Data Validation
RM28,30,31,32
RM33
RM7,8,9,10
RM15,29
C2,3,6,7,9,10
C11,12,13
SDR
C1,4
MSATS B2M APIs
NMID
5MS major impact
5MS moderate impact
5MS some impact
5MS no impact
WDR major impact
WDR moderate impact
WDR some impact - adding DRSP participant type & related attributes
CS major impact
CS moderate impact
CS some impact

## Slide 38: WDR participant readiness considerations
WDR approach (as determined in the WDR Rule) is to minimise system impacts to AEMO and participants
Data model changes will be rolled out to all participants
DRSP will need to:
  Develop dispatch and settlement capability (standard for participants)
  Access portfolio management system to classify NMIs as WDR units.
Retailers can choose whether or not to make any customised changes in their wholesale systems e.g. automated reconciliation processes
Changes may be required in B2B systems to accommodate the new DRSP role depending on participants’ systems configurability

## Slide 39: Proposed WDR implementation timeline
Neil Batie, WDR Senior Project Manager
Ruth Guest, WDR Business Lead

## Slide 40: WDR timeline options considered
AEMO assessed options for combining 5MS and WDR development and test activities. Considerations were that:
Regulatory commencement dates must be met
  5MS: 01 Oct 2021 (go-live)
  WDR: 24 Jun 2021 (open for registration)
  WDR: 24 Oct 2021 (go-live)
AEMO and participant implementations should be as efficient as possible
5MS systems builds are well progressed, WDR is in system design phase
5MS is a mandatory reform, impacting multiple participant types
Customer Switching is to be implemented at the same time as 5MS (agreed through Regulatory Implementation Roadmap process)
WDR has a limited impact:
  DRSPs that choose to participate (either from the commencement date or a later time)
  Retailers (FRMPs) that are required to fund WDR at their NMIs, noting that WDR only applies to large electricity customers

## Slide 41: WDR timeline options considered
Option | Pros | Cons | Recommendation
Combine 5MS and WDR releases into production | Potentially more efficient implementation for participants by combining WDR & 5MS development & testing activities | Would not meet WDR regulatory dates Not feasible for WDR to meet these timeframes Adds risk to 5MS delivery (environment and code management) | Not recommended
Release WDR before 5MS market trial | Meets regulatory dates Potentially more efficient implementation for participants by combining WDR & 5MS development & testing activities | WDR is dependent on 5MS foundation Not feasible for WDR to meet these timeframes | Not recommended
Two releases: 24 Jun 21: RMC, MDM, PAE, PoL baseline, Portfolio Management 24 Oct 21: Dispatch, Settlements, Settlements baseline | Meets regulatory dates Good level of confidence that these dates can be met Better able to manage 5MS and WDR delivery risks and defect management Participant testing can commence early for some functionality | Participants will need to complete WDR Testing after 5MS Market Trial Wholesale functions cannot be tested until October | Recommended
After 5MS market trial | Good level of confidence that these dates can be met Manageable risk of impact to 5MS implementation | Would not meet WDR regulatory dates Participants will need to complete WDR testing after 5MS market trial | Not recommended

## Slide 42: Timelines: 5MS + CS + indicative WDR

## Slide 43: Discussion
Given the delivery timelines that AEMO has outlined are there:​
  Any further implications of the WDR timeline for 5MS/CS implementation?​
  Any opportunities to assist with participants' delivery that you believe AEMO should consider?

## Slide 44: Next steps
Please provide feedback by Fri 9 Oct to either:
  5MS@aemo.com.au
  WDR@aemo.com.au
Debrief to the WDR Consultative Group: Tue 20 Oct
Debrief to the PCF: Thu 05 Nov
If there is an identified need, can hold further joint information sessions or joint focus groups

## Slide 45: WDR contact and information
Mailbox
wdr@aemo.com.au
WDR program information
https://aemo.com.au/initiatives/trials-and-initiatives/wholesale-demand-response-mechanism
WDR stakeholder engagement options
https://aemo.com.au/consultations/industry-forums-and-working-groups/list-of-industry-forums-and-working-groups/wdr

## Slide 46: Meeting Close
Peter Carruthers