## Slide 1: 5MS & GS Program Consultative Forum #28
Tuesday, 1 December 2020
This meeting is recorded for the purpose of minute taking.

## Slide 2: AEMO Competition Law Meeting Protocol
AEMO is committed to complying with all applicable laws, including the Competition and Consumer Act 2010 (CCA). In any dealings with AEMO regarding proposed reforms or other initiatives, all participants agree to adhere to the CCA at all times and to comply with this Protocol. Participants must arrange for their representatives to be briefed on competition law risks and obligations.
Participants in AEMO discussions must:
Ensure that discussions are limited to the matters contemplated by the agenda for the discussion
Make independent and unilateral decisions about their commercial positions and approach in relation to the matters under discussion with AEMO
Immediately and clearly raise an objection with AEMO or the Chair of the meeting if a matter is discussed that the participant is concerned may give rise to competition law risks or a breach of this Protocol
Participants in AEMO meetings must not discuss or agree on the following topics:
Which customers they will supply or market to
The price or other terms at which Participants will supply
Bids or tenders, including the nature of a bid that a Participant intends to make or whether the Participant will participate in the bid
Which suppliers Participants will acquire from (or the price or other terms on which they acquire goods or services)
Refusing to supply a person or company access to any products, services or inputs they require
Under no circumstances must Participants share Competitively Sensitive Information. Competitively Sensitive Information means confidential information relating to a Participant which if disclosed to a competitor could affect its current or future commercial strategies, such as pricing information, customer terms and conditions, supply terms and conditions, sales, marketing or procurement strategies, product development, margins, costs, capacity or production planning.

## Slide 3: Agenda
# | Time | Topic | Presenter
1 | 10:00 – 10:05 | Welcome | Peter Carruthers
2 | 10:05 – 10:10 | Actions from previous meetings | Anne-Marie McCague
3 | 10:10 – 10:20 | Program Update | Rowena Leung
4 | 10:20 – 10:30 | Readiness Working Group Update | Greg Minney
5 | 10:30 – 10:45 | Industry Risks and Issues | Anne-Marie McCague
6 | 10:45 – 10:55 | Forward meeting plan | Anne-Marie McCague
7 | 10:55 – 11:05 | General Questions | Peter Carruthers
8 | 11:05 | Meeting Close | Peter Carruthers

## Slide 4: Welcome
Peter Carruthers

## Slide 5: Actions from Previous Meetings
Anne-Marie McCague

## Slide 6: PCF Actions
No. | Status | Action | Comment
27.5.1 | Closed | AEMO to confirm when the Cross Boundary Supply Guideline will be released. | Update provided during meeting – Document in in AEMO review process and is expected to be published by the end of the week.
27.6.1 | Closed | Customers Switching to update integrated Customer Switching, 5MS and WDR timeline slide with revised industry test dates. | This is complete and the updated timeline is at the end of this pack. This will be maintained in the WDR webpage.
N/A | Closed | AEMO to provide update on Readiness Reporting for Customer Switching and WDR | WDR: Approach to Readiness Reporting will be discussed at WDR CG on 15-Dec Cust. Switch.: Readiness reporting will not be used for CS. All relevant market participants must be compliant with the rule by 01-Oct-21. The impact of a participant not being ready is on participant and the customer requesting the change and would be a compliance matter for AER.

## Slide 7: Program Update
Rowena Leung

## Slide 8: 5MS Program Timeline Level 1 and External Level 2 Milestones 1/2
Current as at 20-11-2020
Callouts:
Industry Test period extended to 14/04/21
Industry Go-Live Plan – Retail MDM: Interim version available 11/12/20 and Final version 25/01/21

## Slide 9: 5MS Program Timeline Level 1 and External Level 2 Milestones 2/2
Current as at 20-11-2020

## Slide 10: Program update and current activities
AEMO program
Overall Program remains Green trending down. Delivery pressures remain particularly with the Retail workstream.
L2 Internal milestones have been re-baselined with no impact to external milestones.
Build is complete for all 5MS and GS functionality across all 3 releases, however development for non-critical items continue for the Retail release.
Full focus of the program will be on completing the Testing program for quality, function and performance.
AEMO internal readiness preparation activities for go-live continue.
Systems
Testing and deployment work continues across all streams - no change to any upcoming Staging deployment, Pre-Production or Production deliveries.
Dispatch Pre-Prod deployment on schedule, to complete by 30-Nov-2020.
Issues with performance testing of running >3 high-frequency RM reports now resolved. Some performance issues continue with some RM reports (in Databricks), the program continues to work through options.
UAT for Retail Day 1 due to complete early January, PCF to be informed via mail if significant issues are outstanding post-Christmas.
Readiness
Readiness Survey #5 issued 17th Nov, with surveys due 26th. Survey #4 trend indicates essential capability on Track
Metering Transition tasks reported on track, upcoming activity includes assessment of NCOUML profiles
Drafting of Industry Go-live plan for retail, with reissue of plan following confirmation of detailed timings in AEMO Dress Rehearsal

## Slide 11: AEMO IT Platform Deployment Status
Stream | Build | AEMO Testing | Pre-prod | Cutover | Commentary
Retail | Non-critical build items in progress | SIT completed for Day 1 Go Live UAT for metering data ingestion completed UAT for profiling & Reporting in progress, target completion early January 2021. Good Performance Testing results from initial re-writes, some poor performance from a few Databricks continues, considering options. | On track for industry testing commencing 01-Feb-21 Invitation test planning underway | Dress Rehearsal 1 learnings Planning Dress Rehearsal 2 | Pressure remains on Retail delivery Major issues encountered during perf testing amended, UAT & Performance testing is now continuing Still, no timeline contingency remains for Retail stream If contingency is needed AEMO will deprioritise non-critical items and introduce a secondary drop in advance of Market Trials. This will maintain 09-Mar-21 Go-Live and 01-Oct-21 5-min market start
Dispatch | Complete | SIT completed for Day 1 Go Live UAT in progress | On track for industry testing commencing 30-Nov-20 | Cutover Planning in progress | Tracking towards deployment dates AEMO to conduct performance testing in Pre-Prod over summer period
Settlements | Complete | SIT completed for Day 1 Go Live UAT in progress | On track for industry testing commencing 17-Feb-21 | Cutover Planning in progress | Tracking towards deployment dates AEMO to conduct performance testing & parallel run in Pre-Prod over summer period (not noticeable to industry, date of 17-Feb-21 remains for Pre-Prod deployment).
 | Go-Live date will be impacted
 | At risk
 | On schedule

## Slide 12: Readiness Working Group Update
Greg Minney

## Slide 13: Level 2 Milestones – Readiness
Key Milestones (Program) |  |  |  |  | 
ID | Milestone | Target Date | Expected Date | Owner | Status
L2-RE11 | Metering Service Provider Accreditation Plan Finalised | 13-Mar-2020 | 18-Feb-2020 | AEMO | Complete
L2-S12 | Reallocations Go-Live | 01-Apr-2020 | 01-Apr-2020 | AEMO | Complete
L2-RE32 | Industry Test for Reallocations Concludes | 31-Mar-2020 | 31-Mar-2020 | AEMO | Complete
L2-RE22 | Industry Transition Plan – Dispatch​ final complete | 28-Aug-2020 | 28-Aug-2020 | AEMO | Complete
L2-M11 | Industry Test preparation completed by participants for MDM and B2M Go-Live | 01-Feb-2021 | 01-Feb-2021 | Participants | 
L2-M12 | Industry Test preparation completed by AEMO for MDM and B2M Go-Live | 01-Feb-2021 | 01-Feb-2021 | AEMO | 
L2-RE29 | Retail MDM (incl. B2M) Industry Test Commences | 01-Feb-2021 | 01-Feb-2021 | AEMO | 
L2-RE30 | Retail MDM (incl. B2M) Industry Test Concludes | 03-Mar-2021 | 03-Mar-2021 | AEMO | 
L2-RE18 | Industry Go-Live Plan Retail MDM finalised | 20-Nov-2020 | 20-Nov-2020 | AEMO | 
L2-M24 | B2M Go-Live | 09-Mar-2021 | 09-Mar-2021 | AEMO | 
L2-M10 | 5 minute files in MDFF accepted by AEMO | 01-Apr-2021 | 01-Apr-2021 | AEMO | 
L2-D7 | Dispatch Industry Test preparation completed by participants | 29-Nov-2020 | 29-Nov-2020 | Participants | 
L2-D8 | Dispatch Industry Test preparation completed by AEMO | 29-Nov-2020 | 29-Nov-2020 | AEMO | 
Milestone complete
Milestone on track
Milestone not achieved
Milestone at risk
Domain | Initiative | 2019 |  |  |  |  |  |  |  |  |  |  |  | 2020 |  |  |  |  |  |  |  |  |  |  |  | 2021 |  |  |  |  |  |  |  |  |  |  | 
 |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  | 
Readiness |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec
L2-RE11
L2-RE32
L2-S12
L2-RE22
L2-M11
L2-M12
L2-RE18
L2-M24
L2-M10
L2-D7
L2-D8
L2-RE29
L2-RE30
Current as at 20-11-2020

## Slide 14: Level 2 Milestones – Readiness
Key Milestones (Program) |  |  |  |  | 
ID | Milestone | Target Date | Expected Date | Owner | Status
L2-S10 | Settlements Industry Test preparation completed by participants | 17-Feb-2021 | 17-Feb-2021 | Participants | 
L2-S11 | Settlements Industry Test preparation completed by AEMO | 17-Feb-2021 | 17-Feb-2021 | AEMO | 
L2-RE28 | Dispatch Industry Test concludes | 15-Mar-2021 | 15-Mar-2021 | AEMO | 
L2-RE32 | Settlements Industry Test concludes | 14-Apr-2021 | 14-Apr-2021 | AEMO | 
L2-RE19 | Industry Go-Live Plan Settlements, Dispatch & Bidding finalised | 19-Mar-2021 | 19-Mar-2021 | AEMO | 
L2-RE23 | 5MS Capability Market Trial preparation completed by participants | 05-Jul-2021 | 05-Jul-2021 | Participants | 
L2-RE24 | 5MS Capability Market Trial preparation completed by AEMO | 05-Jul-2021 | 05-Jul-2021 | AEMO | 
L2-RE31 | 5MS Capability Market Trial commences | 05-Jul-2021 | 05-Jul-2021 | AEMO | 
L2-RE20 | Industry Go-Live Plan – 5MS Capability final complete | 01-Aug-2021 | 01-Aug-2021 | AEMO | 
L2-D10 | 5MS Capability Market Trial concludes | 27-Aug-2021 | 27-Aug-2021 | AEMO | 
L2-D11 | 30-min Bidding no longer accepted by AEMO | 01-Oct-2021 | 01-Oct-2021 | AEMO | 
L2-RE25 | MDMT format no longer accepted by AEMO for interval meters | 01-Oct-2021 | 01-Oct-2021 | AEMO | 
L2-RE26 | GS Market Trial preparation completed by participants | 01-Feb-2022 | 01-Feb-2022 | Participants | 
L2-RE27 | GS Market Trial preparation completed by AEMO | 01-Feb-2022 | 01-Feb-2022 | AEMO | 
L2-RE21 | Industry Go-Live Plan – GS Capability final complete | 21-Dec-2021 | 21-Dec-2021 | AEMO | 
Domain | Initiative | 2019 |  |  |  |  |  |  |  |  |  |  |  | 2020 |  |  |  |  |  |  |  |  |  |  |  | 2021 |  |  |  |  |  |  |  |  |  |  | 
 |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  | 
Readiness |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec
L2-S10
L2-S11
L2-RE32
L2-RE23
L2-RE24
L2-RE20
L2-D10
L2-D11
L2-RE25
L2-RE21
L2-RE31
L2-RE328
Current as at 20-11-2020
Milestone complete
Milestone on track
Milestone not achieved
Milestone at risk
Milestone deferred
L2-RE19

## Slide 15: Readiness Working Group Update
Retail Go-Live Plan:
Updated draft of Retail Go-live plan issued 20 November to incorporate Industry Feedback
Further Feedback due 27 November
Confirmation of process timing and technical approach to rollback plans, holding of B2B and B2M transactions and PVM detailed approach is dependent on outcomes of AEMO Dress Rehearsal
An updated plan will be issued on 22 January to confirm timings and PVM approach.
Transition Focus Group
Transition Focus group held on 26 November with a focus on:
  Implementation guidelines for Cross-Boundary meters
  Volume implications and management related to the 5MS metering rollout
  Clarification of responsibilities for the agreement of NCOUML profiles
Invitation Industry Test planning - Retail
  Scenarios distributed for consideration by participants
  Planned data refresh of pre-prod as at 14th December
  Planning for conduct will take place in ITWG

## Slide 16: Readiness Working Group Update
Staging Environment
Retail environment has had a 5-min PAE run completed (100 days used for any read that needed estimation)
Some interruption to the Retail environment around 19 – 23 November 2020 due to an environment change.
Current MSATS defects will be fixed with r39 P1 deployment, targeting 11 December 2020.
Dispatch Industry Test
Following pre-prod deployment available for Industry test – 13:00 AEST 30-Nov
Q&A sessions have been scheduled 01-Dec to 04-Dec, may be extended if needed
Upcoming activity
RWG:
  Consideration of readiness report #5
  Initial engagement for Settlement and Dispatch industry Go-Live Plans
  Updates Retail Industry go-live plan and response to industry feedback
ITWG
  Planning for Invitation Industry Test – Retail
  Data availability for Settlements Industry Test

## Slide 17: Readiness Reporting #5
Initial results for Readiness Survey # 5 will be provided at the PCF meeting
Survey responses expected by 26 November
Summary and key items consistent with PCF summary to be presented at Executive Forum.

## Slide 18: Readiness Report #5 – Preliminary results
Chart: Total participant types
| Round 1 | Round 2 | Round 3 | Round 4 | Round 5
Generator | 8 | 12 | 14 | 17 | 17
Retailer | 10 | 15 | 16 | 19 | 18
MP | 13 | 18 | 17 | 17 | 16
MDP | 12 | 17 | 14 | 16 | 15
MC | 0 | 17 | 14 | 19 | 16
DNSP | 9 | 10 | 10 | 10 | 9
TNSP | 3 | 7 | 7 | 7 | 8
Organisations | 26 | 40 | 42 | 44 | 43
Preliminary Analysis based on current survey responses, with noted responses outstanding
42/ 43 overall reported programs on track
“late” response not critical to market share and same participant as previous survey
94% of respondents to participant in Market Trial
3 at Risk/Late, 5 not relevant
No further adverse impact to programs due to Covid-19 response noted
No new systemic risk escalations reported, single participant reported risks will be verified against broader participant category

## Slide 19: Essential Criteria – Leading Indicators
MP response for outstanding MP to be updated in final report-
MC/ MP response coverage for all essential meters
Expect critical generator coverage to be met in all regions – subject to delayed response
AEMO criteria – on track for rule commencement criteria
No further escalation currently required

## Slide 20: Industry Risks and Issues
Anne-Marie McCague

## Slide 21: Purpose of this session
Identify the existing risks and issues that should be presented at the Executive Forum on 10-Dec
Identify any new risks or issues that should be included in the Industry Risks and Issues Register and determine whether they should be escalated to the Executive Forum.
Other Notes:
The Industry Risks and Issues Register will be updated on the website after the Exec Forum.
The slides for the Executive Forum will be circulated by Friday 4 December.
The current version of the Industry Risks and Issues Register is the September update available on the 5MS website.

## Slide 22: Overview
At the last Executive Forum (30-Jul) we identified three overarching risks and the associated risks from the register:
  The proposed deferral of the 5MS and GS go-live dates
  The impacts of moving the Metering Solution release to 09-Mar-21
  The impacts of Covid-19.
AEMO is proposing that the three key risks for discussion at the next Executive Forum (10-Dec) be:
  No remaining contingency for Retail Solution deployment
  Volume of regulatory change
  Participant and AEMO readiness

## Slide 23: No Remaining Contingency for Retail Solution Deployment
Risk ID | Description | Inherent Risk Rating |  | Residual Risk Rating | 
NEW | No Remaining Contingency for Retail Deployment There is a risk that an issue may be identified through the remaining scheduled testing of the Retail IT Solution which could result in a delay to the release as there is no remaining contingency. | Inherent Likelihood | Possible | Residual Likelihood | Possible
 |  | Inherent Consequence | Major | Residual Consequence | Minor
 |  | Inherent Rating | Significant | Residual Rating | Medium
Mitigation Actions:
AEMO has identified the functionality of the Retail IT Solution that is not participant facing. To ensure that the necessary functionality is available to participants on 09-Mar-21, AEMO is prioritising testing of participant facing functionality.
Currently the schedule allows for all functionality to be deployed, however, should this risk materialise, AEMO will deploy the participant facing functionality by 09-Mar-21 and will deploy the remaining aspects in a post go-live drop prior to market trial. This would not impact participants.
​ | Improving​ ​ No Change /Stable​ ​ Worsened ​

## Slide 24: Volume of Regulatory Change
Risk ID | Description | Residual Rating (Current) | Comments
R06 | Interaction with other industry changes that have already been adopted through rule changes | Significant | This risk focuses on the demand on industry resources as a result of change programs such as WDR and Customer Switching. This risk is still present in working group discussions and further work is progressing on finalising details of the joint timeline.
R09 | Impact to 5MS from other rule changes that are being considered | Critical | Currently there are no further rule changes being considered that would impact 5MS. Given there are 10 mths until 5MS rule commencement, AEMO is proposing to reduce the likelihood of this risk from “likely” to “possible” and to keep the trend as improving. This results in a residual risk rating of “Significant”
R30 | Risk that new 5MS and GS Go-Live dates could impact other industry change programs | Significant | Similar risk to R06 with the inclusion of risk to system stability. AEMO will continue to review this risk internally to identify the risks involved within the interactions between 5MS, WDR and Customer Switching. Proposing no change to the risk rating and to change trend to “neutral”.
AEMO has continued to work with industry to understand the impacts of other market changes on participants’ 5MS Programs
AEMO understands that while this risk is still present it is more understood as a result of the Regulatory Change Roadmap, the joint 5MS, WDR and Customer Switching program timelines and the establishment of the WDR stakeholder engagement framework.
AEMO considers that the appropriate mitigation measures are in place and that this risk and its associated risks should continue to be monitored.
​ | Improving​ ​ No Change /Stable​ ​ Worsened ​

## Slide 25: Participant and AEMO Readiness
Risk ID | Description | Residual Rating (Current) | 
R11 | The AEMO internal project is not ready for 5MS Go Live | Medium | Proposing to change trend to “neutral”
R16 | Potential impacts from MSP accreditation resource and timing constraints | Medium | No change proposed.
R19 | Risk of a critical capability of participants not being ready at identified critical path milestones | Medium | No change proposed.
R26 | Impact of Covid-19 resulting in participants and / or AEMO being unable to meet 5MS Program timelines | Medium | Proposing to change trend to “neutral”
Overall, the risk that participants or AEMO would not be ready for 5MS Rule commencement is considered Medium. This risk is managed through Readiness Reporting. Essential capability indicators are reflecting on track delivery, all major participant groups have majority of programs on schedule, 95% of survey respondents indicate intention to participate in Market Trials.
Participants are not indicating any further impact on program readiness as a result of Covid-19 responses, although remains on risk list for a number of participants
AEMO is proposing that the risks as set in the register represent the current state and that these risks should be continued to be monitored through the existing mechanisms
​ | Improving​ ​ No Change /Stable​ ​ Worsened ​

## Slide 26: Forward Meeting Plan
Anne-Marie McCague

## Slide 27: Indicative PCF Plan for 2021
Month | Topics | Month | Topics
January | AEMO go-live decision making process Risk Review | June | Market Trial prep status
February | Retail Cutover Status Exec Forum Agenda | July | Market Trial progress Readiness Reporting #8
March | Debrief of Retail Go-Live Dispatch and Settlements Cutovers Preparation Status Readiness Reporting #6 5MS Rule Commencement check point | August | Market Trial progress Risk Review – focus on rule commencement Exec Forum Agenda
April | Debrief on Dispatch & Settlements go-live Risk Review | September | Results of Market Trial Preparing for 1 Oct – Ind Go-Live Plan review Readiness Reporting #9
May | Readiness Reporting #7 Exec Forum Agenda Approach to Global Settlements engagement | October | Debrief and reconfirmation of approach for Global Settlements
This table provides a list of key topics. The normal updates will also be provided at each PCF. This table will evolve as the year progresses.

## Slide 28: Indicative Executive Forum Plan for 2021
Month | Topics
25 March | Rule commencement decision making process Retail go-live debrief Settlements and Dispatch Go-Live update Readiness Reporting # 6
24 June TBC | Readiness Reporting #7 Market Trial Preparation Update against Rule Commencement criteria
02 September | Rule Commencement review Market Trial Results Summary Preparing for 1 Oct - Industry Go-Live Plan

## Slide 29: Forward Meeting Plan
Next PCF: 20-Jan-21
Agenda topics:
  Go-live and rule commencement decision making timeline
  Risk Review with a focus on system deployment
Note: General Information Session on 21-Jan-20
  Please forward invite to anyone in your organisation that may be interested
  Agenda to be circulated by 18-Dec-20

## Slide 30: Proposed Executive Forum Agenda
Scheduled 10-Dec-20
Propose Agenda:
  Readiness Reporting Round 4
  AEMO Readiness including systems go-live updates
  Review of Critical Risks and Issues
  Regulatory Roadmap Update
  Exec Forum schedule for 2021

## Slide 31: Upcoming meetings with draft 2021 dates
Current as at 24/11/2020
https://aemo.com.au/initiatives/major-programs/nem-five-minute-settlement-program-and-global-settlement
Gen Info Session may move from 22-Jan to 21-Jan to avoid clash with ERCF. Will confirm at PCF.

## Slide 32: General Questions
Peter Carruthers

## Slide 33: Meeting Close
Peter Carruthers

## Slide 35: Wholesale Demand Response: Industry View
REGULATORY & GO-LIVE
Retail
Industry Test
3/3
1/2
9/3 AEMO Metering
Solution Go-Live
5MS Market Trial
27/8
5/7
24/6 Open for
Registration
24/10 WDR Rule
Commencement
1/10 5MS Rule Commencement
& UFE soft start
Informal CS
Industry Test
1/10 Customer Switching
Go-Live
Industry Test
Draft WDR Guidelines
and Procedures
Publish WDR Guidelines
and Procedures
29/11
Dispatch Industry Test
15/3
Settlement
Industry Test
15/3
17/2
CS Procedures published
with Effective Date
1/4 DSP
Portal Open
1/4 5-min Bidding Phase Go-Live begins
19/4 Settlements
Platform Go-Live
10/11 B2B Prod Release
B2B Pre-Prod
Release
WDR SYSTEMS DEVELOPMENT AND TEST
RELEASE 1 Requirements, Design, Development & Test [RMC, MDM, PAE, PoL Baseline, Portfolio Management]
RELEASE 2 Requirements, Design, Development & Test [Dispatch, Settlements, Settlement Baseline]
INDUSTRY TESTING (PRE-PROD ENVIRONMENT)
WDR (Indicative)
WDR (Confirmed)
5MS
Customer Switching
Electricity Retail B2B
LEGEND
Current as of 16 Nov 20
TODAY
Draft WDR Test Strategy
Final WDR Test Strategy
Draft WDR Test Plan
Final WDR Test Plan
ENGAGEMENT ON WDR SYSTEM DOCUMENTATION CHANGES
Registration Workshop
Portfolio Mgmt Workshop
Draft CS Tech Spec & workshop
Final MSATS 46.99 Tech Spec (indicative)