## Slide 1: 5MS & GS Program Consultative Forum #18
Tuesday, 4 February 2020
This meeting is recorded for the purpose of minute taking.

## Slide 2: Agenda
No | Time (AEST) | Agenda item | Presenter
1 | 10:00 – 10:05 | Welcome and Apologies | Peter Carruthers
2 | 10:05 – 10:20 | Meeting Notes and Actions | Peter Carruthers
3 | 10:20 – 10:30 | Program Update | Graeme Windley
4 | 10:30 – 10:45 | Milestones Realignment | Greg Minney
5 | 10:45 – 11:00 | Systems Workstream Update | Graeme Windley
6 | 11.00 – 11:10 | Readiness Workstream Update | Greg Minney
7 | 11:10 – 11:15 | Change Request Update | Anne-Marie McCague
Break 11:15 – 11:30am |  |  | 
8 | 11:30 – 11:45 | Readiness Strategies Update | Greg Minney
9 | 11:45 – 11:50 | Cost Recovery Consultation Update | Peter Carruthers
10 | 11:50 – 12.20 | Industry Risks and Issues Register – Review | Anne-Marie McCague
11 | 12.20 – 12:30 | General Questions | Peter Carruthers
12 | 12:30 – 12:40 | Forward Meeting Plan | Anne-Marie McCague
13 | 12:40 | Meeting Close | Peter Carruthers

## Slide 3: Welcome and apologies
Peter Carruthers

## Slide 4: Meeting Notes and Actions
Peter Carruthers

## Slide 5: Actions
Item | Topic | Action required | Owner | Update
17.3.1 | Program Update | All participants to inform AEMO if a delay to L2-M14 – B2M via API Go Live would cause an impact to participant programs. | Participant | Discussions determined that this functionality was not required and that a delay did not impact participants. - Close
17.3.2 | Program Update | AEMO to present potential delay to L2-M14 - B2M via API Go Live to the RWG and SWG | AEMO | Completed at SWG#17, SWG #18 and will be communicated to RWG#8 - Close
17.4.1 | Systems Workstream Update | AEMO to consider whether the addition of the TNI2 field in MSATS will require a procedural change and provide conclusion to the PCF | AEMO | This will require a procedural change. This will be communicated to the SWG and RWG. - Close
17.4.2 | Systems Workstream Update | AEMO to review the request for sample files for the XML schema changes to be made available to participants | AEMO | Sample files will be made available. This will be communicated through the SWG. - Close
17.5.1 | Readiness Workstream Update | AEMO to circulate the output of the Contingency Planning Workshop to the RWG | AEMO | Complete - circulate 20 December 2020 –Close
17.7.1 | Managing Emerging Procedures Issues | AEMO to consider creating a log that tracks all procedure and system changes across the program and making it available to stakeholders. | AEMO | New log will be established and published on 5MS website in February 2020 - Close
17.9.1 | Cost Recovery | AEMO to provide an update on the timelines for the next steps for the development of the cost recovery process for the 5MS Program. | AEMO | Update to be provided in next EF – Close
17.11.1 | Forward Meeting Plan | AEMO to consider the status of media in relation to 5MS. | AEMO | AEMO not engaging with Media at this time but will review interaction in Q3 2020 – Close

## Slide 6: Program Update
Graeme Windley

## Slide 7: Program update and current activities
AEMO program
Overall green. As reported B2M API Go-Live delayed.
Realignment of key milestones post-Readiness work to be reviewed with PCF.
New Program Director joins the program from 10-Feb-20; replacing Sonja Nigmann.
Industry information session held 23-Jan-20, over 80 participants attending via the Webex.
Systems
5MS Staging Environment live with updates from all streams. Participant usage has increased since December
The Settlements & Billing Tech Spec has been released to participants (20-Jan-20) and the Prudentials and Estimations Tech Spec is to be released to participants (31-Jan-20).
Internal retail, dispatch and settlements workstreams systems development on track to meet 30-Jun-20 development completion date.
Readiness
Transition and Go-Live and Industry Testing and Market Trial strategies finalised
Metering Transition Plan (7 Feb) and MSP Accreditation Update Plan (13/3 to be finalised incorporating Industry feedback.
Draft Industry Contingency plan issued for Review
Initial Readiness Reporting survey to be issued 5 Feb.

## Slide 8: Level 2 Milestones Exceptions (External)
Impact Assessment Required: Participants to provide feedback by Friday 21 February of internal program impacts
Current as at 30-01-2020
ID | Stream | Milestone | Planned Date | Expected Date | % | Comments
New L2-M14 | Metering | B2M via API Go Live | 17-Mar-20 | 07-Dec-20 | 70% | AEMO has experienced delays establishing the MarketNet link to AEMOs new API Gateway in conjunction with the legacy SMP e-Hub API Gateway. AEMO proposes a new go-live date of 07-Dec-2020 which will align with the Milestone of the 30-min Metering solution go-live. This will allow time saving on additional testing, deployment and cutover activities required with two separate go-lives. Initially AEMO targeted a phased deployment from this activity, but due to the delay, advantages gained by this approach are minimal. Feedback received so far from market participants is that there is minimal advantage deploying this early (due to the low number of participants using the software).

## Slide 9: Milestone Realignment
Greg Minney

## Slide 10: Milestone Alignment Exercise
Milestones have been reported as TBC (square brackets) awaiting the final Transition Strategy
Readiness Team has aligned Milestones to reflect the agreed Transition Strategy
As the focus of the 5MS Program shifts to Readiness, we have refocused the Milestones to deliver implementation as opposed to development
This will allow us to align Participant Milestones with Readiness Reporting
Participant feedback on any impacts of changes requested to 5MS@AEMO.com.au within two weeks

## Slide 11: Level 1 Milestone Alignment
ID | Task Name | Current Date | Proposed Date | Change
L1-14 | Market Participants Ready for 5MS Capability Market Trials | 30/11/2020 | 6/04/2021 | Description updated and date aligned to commencement of 5MS Capability Market Trial
L1-8 | 5MS Capability Participant Market Trials commence | 1/12/2020 | 6/04/2021 | Date aligned to commencement of 5MS Capability Market Trial

## Slide 12: Retail Milestones Alignment
ID | Task Name | Current Date | Proposed Date | Change
L2-M6 | Agreement on Accreditation Requirements | 31/03/2020 | - | Remove this milestone, as it is a duplicate of L2-RE11
L2-M14 | B2M go-live | 17/03/2020 | 7/12/2020 | Date change to align with updated delivery schedule, and move to Readiness
L2-M9 | AEMO Metering solution – Go Live complete | 31/10/2020 | 7/12/2020 | Description change, update date to align with Transition Strategy, move to Readiness section
L2-M10 | New MDFF format accepted by AEMO | 1/10/2020 | 1/02/2021 | Date change to align with Transition Strategy , move to Readiness section
New | MDMT format no longer accepted by AEMO for interval meters | - | 1/07/2021 | New Milestone to align with procedures, include in readiness section
L2-M11 | Industry Test preparation completed by participants for MDM and B2M go-live | 30/11/2020 | 22/10/2020 | Description update and date change to align with Transition Strategy, move to Readiness section
L2-M12 | Industry Test preparation completed by AEMO for MDM and B2M go-live | 30/11/2020 | 22/10/2020 | Description update and date change to align with Transition Strategy, move to Readiness section
L2-M13 | Market Trials conclude | 31/05/2021 | - | Move to Readiness section and consolidate into a single milestone

## Slide 13: Dispatch Milestones Alignment
ID | Task Name | Current Date | Proposed Date | Change
L2-D7 | Dispatch Market Trial Preparation completed by participants | 30/11/2020 | 17/02/2021 | Description update and date change to align with Transition Strategy, move to Readiness section
L2-D8 | Dispatch Market Trial Preparation completed by AEMO | 30/11/2020 | 17/02/2021 | Description update and date change to align with Transition Strategy, move to Readiness section
L2-D9 | 5-min Bidding Phased Go-Live Begins | 1/04/2021 | - | Move to Readiness section
L2-D10 | 5 MS Market Trial concludes | 31/05/2021 | - | Move to Readiness Section and consolidated into single milestone
L2-D11 | 30-min Bidding no longer accepted by AEMO | 1/07/2021 | - | Move to Readiness section

## Slide 14: Settlements Milestones Alignment
ID | Task Name | Current Date | Proposed Date | Change
L2-S8 | Industry Test for Reallocations | 13/03/2020 | 1/03/2020 | Date change to reflect commencement of Industry Test
L2-S12 | Reallocations Go-Live | 1/04/2020 | - | Move to Readiness
L2-S10 | Settlements Market Trial preparation completed by participants | 30/11/2020 | 17/02/2021 | Description updated and date changed to reflect Transition Strategy
L2-S11 | Settlements Market Trial preparation completed by AEMO | 30/11/2020 | 17/02/2021 | Description updated and date changed to reflect Transition Strategy
L2-S13 | Market Trials conclude | 31/05/2021 | - | Move to Readiness and consolidated into a single milestone
New | Settlements Platform Go-Live | - | 01/04/2021 | New milestone added, included in Readiness

## Slide 15: Readiness Milestones Alignment
ID | Task Name | Current Date | Proposed Date | Change
L2-RE18 | Industry go live plan Retail MDM finalised | - | 20/11/2020 | New External Milestone, description updated
L2-RE19 | Industry Go-Live Plan Settlements, Dispatch & Bidding finalised | - | 19/03/2021 | New External Milestone, description updated
L2-RE20 | Industry go-Live Plan - 5MS Capability final complete | - | 7/05/2021 | New External Milestone, description updated
L2-RE21 | Industry Go-Live Plan - GS Capability finalised | - | 21/12/2021 | New External Milestone, description updated
L2-RE22 | Industry Transition Plan - Dispatch finalised | - | 28/08/2020 | New External Milestone, description updated
New | 5MS Capability Market Trial preparation completed by Participants | - | 6/04/2021 | New External Milestone to reflect transition strategy
New | 5MS Capability Market trial preparation completed by AEMO | - | 6/04/2021 | New External Milestone to reflect transition strategy
New | GS Market Trial preparation completed by participants | - | 15/09/2021 | New External Milestone to reflect transition strategy
New | GS Market Trial preparation completed by AEMO | - | 15/09/2021 | New External Milestone to reflect transition strategy
New | GS Market Trial concludes | - | 1/12/2021 | New External Milestone to reflect transition strategy

## Slide 16: 5MS & GS Program Timeline
Current as at 26-01-2020
The 5MS Program is currently incorporating feedback received during PCF#18. This slide does not represent the current Milestone status.

## Slide 17: 5MS Program Timeline (Jan ‘20 to Jul ‘21) Level 1 and External Level 2 Milestones
Current as at 26-01-2020
The 5MS Program is currently incorporating feedback received during PCF#18. This slide does not represent the current Milestone status.

## Slide 18: Level 1 Milestones - Status Report
Key Milestones (Program) |  |  |  | 
ID | Milestone | Target Date | Expected Date | Status
L1-1 | 5MS Drafting Amendments submitted to AEMC | 20-Mar-2019 | 15-Mar-2019 | Complete
L1-11 | All AEMO workstream development commenced | 23-May-2019 | 23-May-2019 | Complete
L1-2 | IEC Approves B2B Procedures | 01-Jul-2019 | 01-Jul-2019 | Complete
L1-15 | 5MS Drafting Amendments determined by AEMC | 31-Aug-2019 | 08-Aug-2019 | Complete
L1-12 | 5MS Staging Environment live | 01-Dec-2019 | 01-Dec-2019 | Complete
L1-3 | AEMO publishes NEM Procedures | 01-Dec-2019 | 01-Dec-2019 | Complete
L1-7 | Market Readiness Strategy published by AEMO | 20-Jan-2020 | 29-Oct-2019 | Complete
L1-13 | AEMO internal development complete | 30-Jun-2020 | 30-Jun-2020 | 
L1-14 | Market participants ready for 5MS Capability Market Trials | 06-Apr-2021 | 06-Apr-2021 | 
L1-16 | 5MS Cost Recovery Approach finalised | 30-Sep-2020 | [30-Sep-2020] | 
L1-8 | 5MS Capability Participant Market Trials commence | 06-Apr-2021 | 06-Apr-2021 | 
L1-9 | Participant Market Trials conclude | 31-May-2021 | 31-May-2021 | 
L1-10 | Metering Accreditation complete | 31-May-2021 | 31-May-2021 | 
L1-4 | 5MS & UFE Market go Live | 01-Jul-2021 | 01-Jul-2021 | 
L1-5 | GS Market go live | 06-Feb-2022 | 06-Feb-2022 | 
L1-6 | Mandatory 5MS meter data delivery | 01-Dec-2022 | 01-Dec-2022 | 
Domain | Initiative | 2019 |  |  |  |  |  |  |  |  |  |  |  | 2020 |  |  |  |  |  |  |  |  |  |  |  | 2021 |  |  |  |  |  |  |  |  |  |  | 
 |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  | 
Program |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec
Milestone complete
Milestone on track
Milestone not achieved
Milestone at risk
L1-1
L1-11
L1-2
L1-12
L1-3
L1-7
L1-13
L1-14
L1-8
L1-9
L1-10
L1-4
L1-15
L1-16
Current as at 30-01-2020
The 5MS Program is currently incorporating feedback received during PCF#18. This slide does not represent the current Milestone status.

## Slide 19: Level 2 Milestones – Readiness
Domain | Initiative | 2019 |  |  |  |  |  |  |  |  |  |  |  | 2020 |  |  |  |  |  |  |  |  |  |  |  | 2021 |  |  |  |  |  |  |  |  |  |  | 
 |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  | 
Readiness |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec
Key Milestones (Program) |  |  |  | 
ID | Milestone | Target Date | Expected Date | Status
L2-RE01 | Industry Working Group Established | 15-Jul-2019 | 15-Jul-2019 | Complete
L2-RE02 | Market Readiness Strategy Industry Draft | 30-Aug-2019 | 30-Aug-2019 | Complete
L2-RE03 | Market Readiness Strategy Finalised | 29-Nov-2019 | 30-Oct-2019 | Complete
L2-RE04 | Industry Test Strategy Industry Draft Released | 30-Sep-2019 | 30-Sep-2019 | Complete
L2-RE05 | Industry Test Strategy Finalised | 29-Nov-2019 | 29-Nov-2019 | Complete
L2-RE06 | Transition and Go Live Strategy Industry Draft Released | 30-Sep-2019 | 30-Sep-2019 | Complete
L2-RE07 | Transition and Go Live Strategy Finalised | 29-Nov-2019 | 29-Nov-2019 | Complete
L2-RE08 | Market Trial Strategy Industry Draft | 30-Sep-2019 | 30-Sep-2019 | Complete
L2-RE09 | Market Trial Strategy Finalised | 29-Nov-2019 | 29-Nov-2019 | Complete
L2-RE10 | Metering Service Provider Accreditation Update Plan Industry Draft | 29-Nov-2019 | 29-Nov-2019 | Complete
L2-RE12 | Industry Readiness Reporting Plan Industry Draft | 31-Oct-2019 | 31-Oct-2019 | Complete
L2-RE13 | Industry Readiness Reporting Plan Finalised | 13-Dec-2019 | 13-Dec-2019 | Complete
L2-RE15 | Industry Transition Plan – Metering final complete | 07-Feb-2020 | 07-Feb-2020 | 
L2-RE14 | 5MS / GS Industry Readiness Reporting Implemented | 28-Feb-2020 | 28-Feb-2020 | 
L2-S8 | Industry Test start for Reallocations | 01-Mar-2020 | 01-Mar-2020 | 
Milestone complete
Milestone on track
Milestone not achieved
Milestone at risk
L2-RE13
L2-RE01
L2-RE02
L2-RE03
L2-RE04
L2-RE09
L2-RE06
L2-RE08
L2-RE05
L2-RE07
L2-RE10
L2-RE12
L2-RE14
Current as at 30-01-2020
L2-RE15
L2-S8
L2-RE11
L2-M6
L2-S12
L2-RE22
L2-M11
L2-M12
L2-RE18
L2-M9
L2-M24
L2-M10
L2-D7/8
L2-S10/11
L2-RE19
L2-D9
L2-RE23
L2-RE24
L2-RE20
L2-D10
L2-D11
L2-RE25
L2-RE26
L2-RE27
L2-RE28
L2-RE21
The 5MS Program is currently incorporating feedback received during PCF#18. This slide does not represent the current Milestone status.

## Slide 20: Level 2 Milestones - Readiness
Key Milestones (Program) |  |  |  | 
ID | Milestone | Target Date | Expected Date | Status
L2-RE11 | Metering Service Provider Accreditation Plan Finalised | 31-Mar-2020 | 31-Mar-2020 | 
L2-S12 | Reallocations Go-Live | 01-Apr-2020 | 01-Apr-2020 | 
L2-RE22 | Industry Transition Plan – Dispatch​ final complete | 28-Aug-2020 | 28-Aug-2020 | 
L2-M11 | Industry test preparation completed by participants for MDM and B2M Go-Live | 22-Oct-2020 | 22-Oct-2020 | 
L2-M12 | Industry test preparation completed by AEMO for MDM and B2M Go-Live | 22-Oct-2020 | 22-Oct-2020 | 
L2-RE18 | Industry Go-Live Plan Retail MDM finalised | 20-Nov-2020 | 20-Nov-2020 | 
L2-M24 | B2M Go-Live | 17-Mar-2020 | 07-Dec-2020 | 
L2-M9 | AEMO Metering Solution – Go-Live complete | 07-Dec-2020 | 07-Dec-2020 | 
L2-M10 | New MDFF format accepted by AEMO | 01-Feb-2021 | 01-Feb-2021 | 
L2-D7 | Dispatch Market Trial preparation completed by participants | 17-Feb-2021 | 17-Feb-2021 | 
L2-D8 | Dispatch Market preparation completed by AEMO | 17-Feb-2021 | 17-Feb-2021 | 
Milestone complete
Milestone on track
Milestone not achieved
Milestone at risk
Current as at 30-01-2020
Domain | Initiative | 2019 |  |  |  |  |  |  |  |  |  |  |  | 2020 |  |  |  |  |  |  |  |  |  |  |  | 2021 |  |  |  |  |  |  |  |  |  |  | 
 |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  | 
Readiness |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec
L2-RE11
L2-M6
L2-S12
L2-RE22
L2-M11
L2-M12
L2-RE18
L2-M9
L2-M24
L2-M10
L2-D7
L2-D8
The 5MS Program is currently incorporating feedback received during PCF#18. This slide does not represent the current Milestone status.

## Slide 21: Level 2 Milestones - Readiness
Key Milestones (Program) |  |  |  | 
ID | Milestone | Target Date | Expected Date | Status
L2-S10 | Settlements Market Trial preparation completed by participants | 17-Feb-2021 | 17-Feb-2021 | 
L2-S11 | Settlements Market Trial preparation completed by AEMO | 17-Feb-2021 | 17-Feb-2021 | 
L2-RE19 | Industry Go-Live Plan Settlements, Dispatch & Bidding finalised | 19-Mar-2021 | 19-Mar-2021 | 
L2-D9 | 5-min Bidding Phased Go-Live begins | 01-Apr-2021 | 01-Apr-2021 | 
XX-XX | Settlement Platform Go- Live | 01-Apr-2021 | 01-Apr-2021 | 
L2-RE23 | 5MS Capability Market Trial preparation completed by participants | 06-Apr-2021 | 06-Apr-2021 | 
L2-RE24 | 5MS Capability Market Trial preparation completed by AEMO | 06-Apr-2021 | 06-Apr-2021 | 
L2-RE20 | Industry Go-Live Plan – 5MS Capability final complete | 07-May-2021 | 07-May-2021 | 
L2-D10 | 5MS Capability Market Trials conclude | 31-May-2021 | 31-May-2021 | 
L2-D11 | 30-min Bidding no longer accepted by AEMO | 01-Jul-2021 | 01-Jul-2021 | 
L2-RE25 | MDMT format no longer accepted by AEMO for interval meters | 01-Jul-2021 | 01-Jul-2021 | 
L2-RE26 | GS Market Trial preparation completed by participants | 15-Sep-2021 | 15-Sep-2021 | 
L2-RE27 | GS Market Trial preparation completed by AEMO | 15-Sep-2021 | 15-Sep-2021 | 
L2-RE28 | GS Market Trial concludes | 01-Dec-2021 | 01-Dec-2021 | 
L2-RE21 | Industry Go-Live Plan – GS Capability final complete | 21-Dec-2021 | 21-Dec-2021 | 
Milestone complete
Milestone on track
Milestone not achieved
Milestone at risk
Current as at 30-01-2020
Domain | Initiative | 2019 |  |  |  |  |  |  |  |  |  |  |  | 2020 |  |  |  |  |  |  |  |  |  |  |  | 2021 |  |  |  |  |  |  |  |  |  |  | 
 |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  | 
Readiness |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec
L2-S10
L2-S11
L2-RE19
L2-D9
L2-RE23
L2-RE24
L2-RE20
L2-D10
L2-D11
L2-RE25
L2-RE26
L2-RE27
L2-RE28
L2-RE21
The 5MS Program is currently incorporating feedback received during PCF#18. This slide does not represent the current Milestone status.

## Slide 22: Systems Workstream Update
Graeme Windley

## Slide 23: 5MS Release 1: Reallocations
Staging
Training
AEMO UAT
Go Live
BAU
From 01 Nov 2019
Software published and available for participants to interact with.
Industry-discovered defects submitted via Support Hub.
01 Nov 2020
Tech Spec published and available for participants
User Guide published and available for participants
Jan 2020
Internal AEMO testing, only a few P4s (cosmetic) defects remaining.
AEMO business has accepted the results of testing.
26 Feb 2020
Deployment in pre-PROD with software available for participants to test (note, there is no co-ordinated Market Trial of the software).
1 Apr 2020
Deployment in PROD environment. There is no participant impact as part of the cutover.
From 01 Apr 2020
Market Participants can submit reallocations with a 5-min cadence for the time period from 00:00:00 01-Jul-2021
Industry Test

## Slide 24: SWG #18 Update
24
aseXML schema changes
  Slides presented, including new RM reports, update to the “Last Sequence Number” field, and additions of second TNI field, X and Y messages and additional details where NMI data streams have multiple uses.
  The slide pack is available here. Minutes are to be published shortly.
  Release schedule TBC (Customer Switching timing TBD, provided by March PCF)
Dispatch Stream updates
  Tech Spec – a number corrections presented and discussed within a reissue.
  Dispatch Data Model v5.0 – changes to bid transition from 30-min to 5-min highlighted.
  Details available at slides within above link.
Risk Review
  Discussion held on the risks relevant to the Systems aspects of the delivery. No significant adjustments requested from participants.
SWG#17 Minutes - Delay
  The minutes of the previous SWG have not yet been finalised. AEMO apologises for the delay and will issue the minutes to the SWG for their review prior to publishing on 5MS website.
Future Topics
  None received from participants.

## Slide 25: 5MS Staging Environment Update
Dispatch | Settlements | Metering
DROP ONE – 29 November 2019 Submit 5-Min Bids, via new web interface, API and/or FTP Bidding Data Model changes as per technical specifications released July 2019 Case Loaders for PASA, Dispatch, 5-minute Pre-Dispatch & 30-minute Pre-Dispatch data | DROP ONE – 1 November 2019 Reallocations: available at both 30 and 5-min intervals New Web UI Calendar selection Alerts | DROP ONE – 1 December 2019 Test connection to Staging Test MDFF validations Validate data exchange
Status: Live Participant interaction: at least 6 participants accessing in January Issues: issues related to the tech specs, now addressed. API connectivity issues for some participants. | Status: Live Participant interaction: at least 6 participants accessing in January Issues: incorrect setup by participants of their user roles. | Status: Live Participant interaction: 2 participants accessing in January Issues: None identified
DROP TWO – 15 May 2020 | DROP TWO – 31 Jan 2020 | DROP TWO – 31 July 2020
Status: On track | Status: Data Model finalisation delayed to 20-Feb; UFE tables delivered with DROP THREE (SQL Server v Oracle environment delivery) | Status: On track
 | DROP THREE – 16 March 2020 | 
 | Status: On Track | 

## Slide 26: Settlements & Billing Data Model Changes
26
The below Data Model changes are to be made:
  Adds SETTLEMENTINTERVALLENGTH column to the DAYTRACK table for SETTLEMENT_DATA package
  Adds AGE column, removes UFEADOLLARVALUE column for BILLINGCPDATA table in the BILLING_RUN package
  Adds new tables: BILLRESERVETRADERPAYMENT, BILLRESERVETRADERRECOVERY for RERT calculations
  Discontinues BILLING_RES_TRADER_PAYMENT, BILLING_RES_TRADER_RECOVERY tables
The retention policy for correspondence on Settlements Direct is increased to 3 years
The changes will be reflected in a republishing of the Settlements & Billing Tech Spec on 14-Feb-20.

## Slide 27: Systems Workstream – Dispatch & Operations
5 MINUTE SETTLEMENT SYSTEMS TRACKING | TIMING |  |  |  |  |  |  |  |  | 
 | Internal HLIA | Focus/Group | SWG Engagement | External HLIA | Draft Tech Spec | Final Tech Spec | User Guides | 5MS Staging | Preprod | Production
DISPATCH and OPERATIONS |  |  |  |  |  |  |  |  |  | 
PACKAGE 1 - Bidding FTP and API |  |  |  |  |  |  |  |  |  | 
Transition | Aug-18 | Oct-18 | Aug-18 | Nov-18 | Dec-18 | 2-Apr-19 | 31-Oct-19 | 29-Nov-19 | Nov-20 | Mar-21
Bidding Data Model | Aug-18 | - | Sep-18 | Mar-19 | Dec-18 | 2-Apr-19 | 31-Oct-19 | 29-Nov-19 | Nov-20 | Mar-21
Bidding Format | Aug-18 | - | Sep-18 | Nov-18 | Dec-18 | 2-Apr-19 | 31-Oct-19 | 29-Nov-19 | Nov-20 | Mar-21
PACKAGE 2 - Bidding Web UI |  |  |  |  |  |  |  |  |  | 
Bidding Web UI and APIs | Aug-18 | Nov-18 | Dec-18 | Jan-19 | Mar-19 | 31-Jul-19 | 16-Dec-19 | 29-Nov-19 | Nov-20 | Mar-21
PACKAGE 3 - Dispatch, Pre-dispatch and PASA |  |  |  |  |  |  |  |  |  | 
Dispatch | Aug-18 | - | Oct-18 | Nov-18 | Oct-18 | 2-Apr-19 | - | 29-Nov-19 | Nov-20 | Mar-21
Predispatch P30/7DAY | Aug-18 | - | Oct-18 | Nov-18 | Oct-18 | 2-Apr-19 | - | 29-Nov-19 | Nov-20 | Mar-21
Predispatch P5 | Nov-18 | Oct-18 | Nov-18 | TBC | TBC | TBC | - | TBC | Nov-20 | May-21
ST and PD PASA | Aug-18 | - | Oct-18 | Nov-18 | Oct-18 | 2-Apr-19 | 31-Oct-19 | 29-Nov-19 | Nov-20 | Mar-21
PACKAGE 4 - Pricing and Miscellaneous |  |  |  |  |  |  |  |  |  | 
Trading Price / Price Revision | Aug-18 | - | Feb-19 | Nov-18 | Mar-19 | 31-Jul-19 | - | 15-May-20 | Nov-20 | May-21
Administered Pricing and CPT | Aug-18 | - | Feb-19 | Dec-18 | Mar-19 | 31-Jul-19 | - | 15-May-20 | Nov-20 | May-21
Suspension Pricing | Sep-18 | - | Feb-19 | Dec-18 | Mar-19 | 31-Jul-19 | - | 15-May-20 | Nov-20 | May-21
Negative Residue Management | Sep-18 | - | Feb-19 | Dec-18 | Jun-19 | 31-Jul-19 | - | 15-May-20 | Nov-20 | May-21
RERT | Oct-18 | - | - | - | - | - | - | - | - | -
PACKAGE 5 - Full Data Model |  |  |  |  |  |  |  |  |  | 
Full Data Model | Sep-18 | Ongoing | Ongoing | Apr-19 | Ongoing | 31-Jan-20 | 16 Mar 20 | 29-Nov-19 | Nov-20 | May-21
Current as at 13 Jan 2020

## Slide 28: Systems Workstream - Metering
Current as at 13 Jan 2020
5 MINUTE SETTLEMENT SYSTEMS TRACKING | TIMING |  |  |  |  |  |  |  |  | 
 | Internal HLIA | Focus/Group | SWG Engagement | External HLIA | Draft Tech Spec | Final Tech Spec | User Guides | 5MS Staging | Preprod | Production
METERING |  |  |  |  |  |  |  |  |  | 
PACKAGE 1 - Metering Data & Metrology |  |  |  |  |  |  |  |  |  | 
MDFF • MDFF Specification NEM12 NEM13 v20 | Aug-18 | Oct-18 | Oct-18 | Nov-18 | Jan-19 | Apr-19 | - | 1 Dec 19 | Sep-20 | Nov-20
PACKAGE 2 - MSATS & SLPs |  |  |  |  |  |  |  |  |  | 
Transition • MSATS Technical Specification | Aug-18 | Sep-18 | Aug-18 | Nov-18 | 31-May-19 | 30-Sep-19 | - | - | - | -
Meter Data - MDFF and MDMF • MDM File Format and Load Process (User Guide) • MSATS Technical Specification | Aug-18 | Oct-18 | Sep-18 | Nov-18 | 31-May-19 | 30-Sep-19 | - | 1 Dec 19 | Sep-20 | Nov-20
PACKAGE 3 - Miscellaneous |  |  |  |  |  |  |  |  |  | 
B2M via API • MSATS Release Schedule & Technical Specification | Oct-18 | - | Apr-19 | 9-May-19 | 31-May-19 | 30-Sep-19 | TBC | N/A | 07-Dec-20 | 07-Dec-20
MSATS Browser (LVI) changes • MSATS Technical Specification | Aug-18 | - | May-19 | 9-May-19 | 28-Jun-19 | 30-Sep-19 | 31-Jul-20 | 31-Jul-20 | Sep-20 | Nov-20
MSATS Report changes • MSATS Procedures MDM Procedure • MDM File Format and Load Process (User Guide) • MSATS Technical Specification General Process & Document Clean-up | Oct-18 | - | Apr-19 | Apr-19 | 28-Jun-19 | 30-Sep-19 | - | 31-Jul-20 | Sep-20 | Nov-20
Date to be revisited with new B2M timeline

## Slide 29: Systems Workstream - Settlements
Current as at 13 Jan 2020
The Tech Spec for Prudentials and Estimations are due out 31-Jan-20
A data model change to be introduced short

## Slide 30: Level 2 Milestones - Dispatch
Domain | Initiative | 2019 |  |  |  |  |  |  |  |  |  |  |  | 2020 |  |  |  |  |  |  |  |  |  |  |  | 2021 |  |  |  |  |  |  |  |  |  |  | 
 |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  | 
Dispatch |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec
Key Milestones (Program) |  |  |  | 
ID | Milestone | Target Date | Expected Date | Status
L2-D1 | Final technical specifications for Package 1 published by AEMO | 2-Apr-2019 | 2-Apr-2019 | Complete
L2-D2 | Final technical specifications for Package 2 published by AEMO | 31-Jul-2019 | 31-Jul-2019 | Complete
L2D12 | Final technical specifications for Package 4 published by AEMO | 31-Jul-2019 | 31-Jul-2019 | Complete
L2-D3 | Software drop for Packages 1,2 & 3 in 5MS Staging Environment | 29-Nov-2019 | 29-Nov-2019 | Complete
L2-D13 | Final technical specifications for Package 5 published by AEMO | 31-Jan-2020 | 31-Jan-2020* | On track
L2-D5 | Software drop for Package 4 in 5MS Staging Environment | 15-May-2020 | 15-May-2020 | 
L2-D4 | Development completed (internal) | 31-May-2020 | 31-May-2020 | 
Milestone complete
Milestone on track
Milestone not achieved
Milestone at risk
L2-D1
L2-D2
L2-D3
L2-D5
L2-D4
L2-D12
L2-D13
* Data available in Tech Specs now and in 5MS Staging from 29-Nov-2019
Current as at 30-01-2020

## Slide 31: Level 2 Milestones – Metering
Domain | Initiative | 2019 |  |  |  |  |  |  |  |  |  |  |  | 2020 |  |  |  |  |  |  |  |  |  |  |  | 2021 |  |  |  |  |  |  |  |  |  |  | 
 |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  | 
Metering |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec
Key Milestones (Program) |  |  |  | 
ID | Milestone | Target Date | Expected Date | Status
L2-M1 | AEMO internal metering solution – solution design complete (internal) | 31-May-2019 | 17-Jun-2019 | Complete
L2-M2 | Final technical specifications for Package 1 published by AEMO | 30-Jun-2019 | 30-Apr-2019 | Complete
L2-M3 | Final technical specifications for Package 2 published by AEMO | 30-Sep-2019 | 30-Sep-2019 | Complete
L2-M4 | Final technical specifications for Package 3 published by AEMO | 30-Sep-2019 | 30-Sep-2019 | Complete
L2-M5 | Software drop for Packages 1 & 2 in 5MS Staging Environment | 01-Dec-2019 | 01-Dec-2019 | Complete
L2-M7 | AEMO internal metering solution – build complete (internal) | 30-Jun-2020 | 30-Jun-2020 | 
L2-M8 | Software drop for Package 3 in 5MS Staging Environment | 31-Jul-2020 | 31-Jul-2020 | 
Milestone complete
Milestone on track
Milestone not achieved
Milestone at risk
L2-M1
L2-M2
L2-M4
L2-M5
L2-M7
L2-M8
L2-M3
Current as at 30-01-2020

## Slide 32: Level 2 Milestones – Settlements
Domain | Initiative | 2019 |  |  |  |  |  |  |  |  |  |  |  | 2020 |  |  |  |  |  |  |  |  |  |  |  | 2021 |  |  |  |  |  |  |  |  |  |  | 
 |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  | 
Settlements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec
Key Milestones (Program) |  |  |  | 
ID | Milestone | Target Date | Expected Date | Status
L2-S1 | Final technical specifications for Package 1 published by AEMO | 15-Oct-2019 | 15-Oct-2019 | Complete
L2-S2 | Software drop for Package 1 | 01-Nov-2019 | 01-Nov-2019 | Complete
L2-S3 | Final technical specifications for Package 2 published by AEMO | 15-Dec-2019 | 16-Dec-2019 | Complete
L2-S4 | Final technical specifications for Package 3 published by AEMO | 31-Jan-2020 | 31-Jan-2020 | On track
L2-S6 | Software drop for Package 2 in 5MS Staging Environment | 16-Mar-2020 | 16-Mar-2020 | 
L2-S7 | Software drop for Package 3 in 5MS Staging Environment | 15-May-2020 | 15-May-2020 | 
L2-S5 | Development completed (internal) | 31-May-2020 | 31-May-2020 | 
Milestone complete
Milestone on track
Milestone not achieved
Milestone at risk
L2-S1
L2-S2
L2-S3
L2-S4
L2-S5
L2-S6
L2-S7
Current as at 30-01-2020

## Slide 33: Readiness Workstream Update
Greg Minney

## Slide 34: Readiness papers - timelines
Item | RWG/ITWG/FG engagement | Draft paper | Consultation | Comments due | Final paper
Industry test and market trial strategy | Jul-19 | 30-Sep | 4 weeks | 28-Oct | 29-Nov
Transition and go-live strategy | Jul-19 | 30-Sep | 4 weeks | 28-Oct | 29-Nov
Metering transition plan | Aug-19 onwards | 29-Nov | 3 weeks | 20-Dec | 7-Feb-20
Industry contingency plan | Nov-19 | 20-Dec | 6 weeks | 31-Jan-20 | 13-Mar-20
Industry readiness reporting plan | Sep-19 | 31-Oct | 3 weeks | 21-Nov | 13-Dec
MSP accreditation update plan | Oct-19 | 29-Nov | 11 weeks | 31-Jan-20 | 21-Feb-20
Major strategy positions established, workstream focus now on implementation of those strategies

## Slide 35: Workstream engagement
Contingency Planning
  Draft plan issued on 20th Dec
  Consultation in progress with feedback due 31st Jan
  Contingency approaches have been aligned with identified Industry Risks
  Utilisation of existing Market exception processes, including across rule commencement dates
Readiness Reporting
  Initial (full) readiness survey to be distributed 5th Feb
  Will be distributed to RWG reps for submission
  Readiness Report available 28th Feb for review with RWG/PCF
  Reporting criteria differentiated by Participant type
Metering Transition Plan
  Consultation completed 20th December
  Feedback from 7 Participants (MSP,LNSP, Retailer)

## Slide 36: Workstream engagement
ITWG
  Working group established
  Current focus on Test planning for B2M via API release
  Developing position for timing of GS Testing
Metering Accreditation Update Plan
  Feedback on Draft plan due 31st Jan
  Establishing level of change, timing requirements for accreditation updates
  Guidance questions issued to assist assessment of scale of change, and to assist in queue management and timing

## Slide 37: Change Request Update
5MS Team Members

## Slide 38: Change Requests Under Consideration
CR# | Title | Objective | Status
CR19 | Continuation of 30-minute RM and settlement reports | Reconciliation workshop #2: Consider continued delivery of reports in simulated 30-minute format to reduce transition impact to participant reconciliation | CR is cancelled due to no requirement from participants and business
CR32 | 5MPD Price Sensitivities | Consider publishing 5-minute price sensitivities as part of 5-minute Predispatch (5MPD) | Steering Committee requested further information. Returning to CAB 31 Jan – update will be provided during PCF#18

## Slide 39: Industry Readiness Strategies Update
Greg Minney

## Slide 40: Metering Transition - Draft

## Slide 41: Metering Transition Plan
Responsibilities and expected timeframes for metering activities to support transition to 5MS and GS
Covers requirements for:
  5MS rule commencement
  GS updates to support UFE calculation and rule commencement
  New & replacement rollout completion
Alignment with participant capability and obligation to consume 5 minute metering data
Providing transition start and end dates for key activities
Basis for metering business to provide readiness updates against planned activities
Recognises agreements and alignment necessary to manage transition and rule commencement risks

## Slide 42: Cost Recovery Consultation Update
Peter Carruthers

## Slide 43: Industry Risks and Issues Register
Anne-Marie McCague

## Slide 44: Background
The Industry Risks and Issues Register is reviewed by the PCF on a quarterly basis
In advance, the RWG and SWG have reviewed their relevant risks
The 5MS Program Team has reviewed the register and provided their view of the trend of each risk
The review today will focus on changes: new risks added by the working group and changes to risks with a critical or significant residual risk
The Industry Risks and Issues Register will be published on the 5MS Program website after any updates have been incorporated
The next review will take place at the PCF in May 2020
New risks and risks that trend downwards will be reported on in the PCFs between the review cycle

## Slide 45: New Risks
Risk No. | Title | Trend | Risk Owner | Residual Likelihood | Residual Consequence | Residual Risk Rating
R20 | Risk of AEMO cutover failure | No Trend | Readiness Working Group | Unlikely | Major | Medium
R21 | Risk of degraded operational performance at go-live | No Trend | Systems / Readiness Workstream | Unlikely | Major | Medium
R22 | Introduction of 5MS capability and architecture increases risk of system unavailability post cutover | No Trend | Systems / Readiness Workstream | Unlikely | Major | Medium
R23 | Major event occurs at cutover | No Trend | Readiness Working Group | Unlikely | Major | Medium
R24 | Not enough participants for Market Trials | No Trend | Readiness Working Group | Unlikely | Major | Medium
 | Improving
 | Stable
 | Worsened

## Slide 46: Critical Risks
Risk No. | Title | Trend | Risk Owner | Residual Likelihood | Residual Consequence | Residual Risk Rating
R06 | Interaction with other industry changes that have already been adopted through rule changes |  | Business Advocate / Program Workstream | Likely | Major | Critical
 | Improving
 | Stable
 | Worsened

## Slide 47: Significant Risks
Risk No. | Title | Trend | Risk Owner | Residual Likelihood | Residual Consequence | Residual Risk Rating
R02 | Risk that there is one or more participants that aren’t ‘ready’ at go-live |  | Systems / Readiness Workstream | Possible | Major | Significant
R03b | Resource constraints over summer periods |  | Systems / Readiness Manager | Possible | Moderate | Significant
R09 | Impact to 5MS from other rule changes that are being considered |  | Business Advocate / Executive Forum | Possible | Major | Significant
R17 | Industry 'big bang' approach |  | Readiness Working Group | Possible | Major | Significant
 | Improving
 | Stable
 | Worsened

## Slide 48: Issues
ID# | Title | Rating | Trend | Actions | Target Resolution Date
I05 | Visibility of 5MS implementation costs | Medium | ↔ | • AEMO has commenced consultation for 5MS and GS are a declared NEM project, under a two stage consultation process. • AEMO has completed the first stage of consultation for 5MS and GS. The result of this consultation is that the 5MS and GS Program meets the criteria to be a declared NEM project. • The second stage of the process will address the actual fee structure for recovery of the costs of the project including the Registered Participants that will be charged the fees. | TBC
I06 | Support for metering transition activities throughout 2022 | Medium | ↔ | • This matter has been moved to the Readiness Workstream. • Initial conversations were held at the Transition Focus Group 30 August 2019. • AEMO is seeking views from MDPs and MPs regarding the activities and levels of activities that may require to support the retail metering transition • AEMO has completed the consultation period for the Metering Transition Plan and has reviewed all feedback received. The final Metering Transition Plan will be published on 7 Feb 2020 | 07-Feb-20
I07 | Support for Global Settlement go live | Medium | ↔ | • This matter has been moved to the Readiness Workstream. • AEMO will develop a proposal to align market trials with go live date in the Transition and Go-Live Strategy and Market Trial Strategy. • Testing of UFE and GS invoicing has been incorporated into the test strategies. | 29-Apr-20

## Slide 49: General Questions
Peter Carruthers

## Slide 50: Forward Meeting Plan
Anne-Marie McCague

## Slide 51: Executive Forum – Change of Dates
We are proposing to change the Executive Forum dates so that they align with the Readiness Reporting Schedule
This will allow for reporting to be discussed at the RWG and PCF in advance of the Exec Forum
Proposed Executive Forum dates for 2020:
Readiness reporting | Survey released | Survey responses due | Distribute results | Discuss at RWG | Discuss at PCF | Discuss at EF
Round #1 | 05-Feb-20 | 14-Feb-20 | 28-Feb-20 | 11-Mar-20 | 05-Mar-20 | 12-Mar-20
Round #2 | 14-Apr-20 | 23-Apr-20 | 07-May-20 | 14-May-20 | 02-Jun-20 | 11-Jun-20
Round #3 | 07-Jul-20 | 16-Jul-20 | 30-Jul-20 | 13-Aug-20 | 03-Sep-20 | 7-Sep-20
Round #4 | 01-Sep-20 | 10-Sep-20 | 24-Sep-20 | 08-Oct-20 | 05-Nov-20 | 19-Nov-20
Round #5 | 03-Nov-20 | 12-Nov-20 | 26-Nov-20 | 09-Dec-20 | tbc | tbc
Original date | Proposed new date
25 Feb | 12 Mar
21 May | 11 June
20 Aug | 7 Sep
19 Nov | No change

## Slide 52: Initial Survey Results
Survey Results
Survey closed 10 Jan
Low response rate – 9 responses
Key areas to consider
  Frequency and duration of meetings / Working Groups
  Consistency and clarity of information across the program
Report to be issued by 12 Feb
  Suggested topics for agenda:
Staging experience
Participant Testing incl. Market Trials
Metering
Risks, issues & contingency
Key Program considerations
Milestone Status updates
Working Group updates
Costs of the change

## Slide 53: Forward Meeting Agenda
March Agenda
Round #1 Readiness Reporting
Next meeting: 5 March 2020
To add items to the agenda, please contact us at 5MS@aemo.com.au

## Slide 54: Upcoming meetings
Current as at 29/01/2020
https://aemo.com.au/initiatives/major-programs/nem-five-minute-settlement-program-and-global-settlement

## Slide 55: Meeting Close
Peter Carruthers