## Slide 1: 5MS & GS Program Consultative Forum #30
Thursday, 18 February 2021
This meeting is recorded for the purpose of minute taking.

## Slide 2: AEMO Competition Law Meeting Protocol
AEMO is committed to complying with all applicable laws, including the Competition and Consumer Act 2010 (CCA). In any dealings with AEMO regarding proposed reforms or other initiatives, all participants agree to adhere to the CCA at all times and to comply with this Protocol. Participants must arrange for their representatives to be briefed on competition law risks and obligations.
Participants in AEMO discussions must:
Ensure that discussions are limited to the matters contemplated by the agenda for the discussion
Make independent and unilateral decisions about their commercial positions and approach in relation to the matters under discussion with AEMO
Immediately and clearly raise an objection with AEMO or the Chair of the meeting if a matter is discussed that the participant is concerned may give rise to competition law risks or a breach of this Protocol
Participants in AEMO meetings must not discuss or agree on the following topics:
Which customers they will supply or market to
The price or other terms at which Participants will supply
Bids or tenders, including the nature of a bid that a Participant intends to make or whether the Participant will participate in the bid
Which suppliers Participants will acquire from (or the price or other terms on which they acquire goods or services)
Refusing to supply a person or company access to any products, services or inputs they require
Under no circumstances must Participants share Competitively Sensitive Information. Competitively Sensitive Information means confidential information relating to a Participant which if disclosed to a competitor could affect its current or future commercial strategies, such as pricing information, customer terms and conditions, supply terms and conditions, sales, marketing or procurement strategies, product development, margins, costs, capacity or production planning.

## Slide 3: Agenda
# | Time | Topic | Presenter
1​ | 10:00 – 10:05​ | Welcome​ | Peter Carruthers​
2​ | 10:05 – 10:10 | Actions from Previous Meetings​ | Anne-Marie McCague​
3​ | 10:10 – 10:30 | Program Update​ | ​Rowena Leung & Graeme Windley
4​ | 10:30 – 11:00 | Retail Reporting Approach | Multiple
6​ | 11:00 – 11:15 | Readiness Working Group Update​ | Greg Minney​
7​ | 11:15 – 11:20 | Forward Meeting Plan | Anne-Marie McCague​
8​ | 11:20 – 11:30 | General Questions​ | Peter Carruthers​
9​ | 11:30 ​ | Meeting Close​ | Peter Carruthers​

## Slide 4: Welcome
Peter Carruthers

## Slide 5: Actions from Previous Meetings
Anne-Marie McCague

## Slide 6: PCF Actions
No. | Status | Action | Comment
29.3.1 | Closed | AEMO to provide clarity on the long-term plans for sunsetting FTP. | Back in 2018, AEMO provided an approximate date of sunsetting FTP of 2025. The current position is this is a long-term goal from AEMO to do, but there is no current plan or timetable on this. It won’t be delivered within or communicated by the 5MS program. For clarification, the migration to the new Enterprise Azure environment for AEMO’s Retail solution is not related to FTP as a route into market.
29.3.2 | Closed | AEMO to issue invitations for an Executive Forum on 11-Feb-21. | Complete
29.3.3 | Closed | AEMO to confirm the date for the March checkpoint meeting and the checkpoint criteria. | Approach described in section 4 of this pack
29.3.4 | Closed | AEMO to provide a date for release of the Settlements Certification report | Certifier will provide presentation at PCF in March (TBC)

## Slide 7: Program Update
Rowena Leung & Graeme Windley

## Slide 8: 5MS Program Timeline A Level 1 and External Level 2 Milestones 1/2
Current as at 12-02-2021
On track
Dispatch SIT and UAT – Complete
Performance testing is in progress
Settlements SIT & UAT in progress. Performance testing to commence late Feb
Retail SIT & UAT in progress. Performance testing to recommence early March
Milestones in blue changed due to Retail replan

## Slide 9: 5MS Program Timeline Level 1 and External Level 2 Milestones 2/2
Current as at 12-02-2021
No changes

## Slide 10: List of L1 and L2 Milestones impacted by change
ID | Milestone | Previous Date | Baselined Dates | Owner
L1-19 | AEMO (Retail) Metering Solution - Go-Live | 9-Mar-21 | 31-May-21* | AEMO
L2-RE35 | Industry Go-Live Plan final - Release 3 - Retail MDM | 25-Jan-21 | 16-Apr-21 | AEMO
L2-M11 | Industry Test Preparation completed by Participants for MDM and B2M Go-Live | 1-Feb-21 | 19-Apr-21 | Participants
L2-M12 | Industry Test Preparation completed by AEMO for MDM and B2M Go-Live | 1-Feb-21 | 19-Apr-21 | AEMO
L2-RE29 | Retail MDM (incl. B2M) Invitation Industry Test Commences | 1-Feb-21 | 19-Apr-21 | AEMO
L2-RE30 | Retail MDM (incl. B2M) Invitation Industry Test Concludes | 3-Mar-21 | 21-May-21 | AEMO
L2-M24 | Retail MDM (incl. B2M) Go-Live | 9-Mar-21 | 31-May-21 | AEMO
L2-M10 | 5 minute files in MDFF format accepted by AEMO | 1-Apr-21 | 22-Jun-21 | AEMO
L1-22 | Settlements Platform Go-Live | 19-Apr-21 | 17-May-21 | AEMO
L2-S10 | Settlements Industry Test preparation completed by participants | 17-Feb-21 | 22-Mar-21 | Participants
L2-S11 | Settlements Industry Test preparation completed by AEMO | 17-Feb-21 | 22-Mar-21 | AEMO
L2-RE19 | Industry Go-Live Plan - Settlements finalised | 19-Mar-21 | 16-Apr-21 | AEMO
L2-RE32 | Settlements Industry Test Concludes | 14-Apr-21 | 13-May-21 | AEMO
* Confirmation of date is dependent upon status at the March Checkpoint

## Slide 11: 5MS Rule Commencement Status
 | On track | On track for commencement date
 | Risk 1 – Risk to major milestones or deliveries | Remediation or contingency activation required to ensure on track delivery for Rule Commencement
 | Risk 2 – Risk to rule commencement | Cannot be addressed with available contingencies to be on track for commencement date
Activity | Status | Comments
AEMO Business Readiness for 5MS and GS (Part A) |  | Bidding Platform deployed for Industry test on Schedule. Retail Platform deployment rescheduled with impact to dependent activities. Settlement platform go-live rescheduled to mid-May. Rescheduling of platform deliveries is not expected to impact 5MS commencement or 5MS market trial but heightened risk profile noted.
Essential Industry Capabilities for 5MS commencement (Part A) |  | On track for 1 Oct 21 commencement, Metering Data Providers and MPs reporting on track. Generators reporting on-track delivery.
Other industry capabilities for 5MS and GS (Part B) |  | Non-essential activities across all participant types reported on track.
Summary: 5MS Rule Commencement |  | All components of 5MS Essential capability on track for Rule Commencement timeframe, replanning of AEMO Platform Deployments underway and heightened risk profile noted.
On track
On track
On track
On track
Risk 1
Risk 2
Risk 1
Dashboard commentary for Industry Readiness as at 28th January and will be updated with results from Readiness Survey #6, due 26th February. Represents overview of 5MS readiness and preparations for UFE soft start

## Slide 12: 5MS Program – IT Systems Status
Stream | Commentary
Retail | Core product build complete. More detailed status provided on slide 17 - Checkpoint Criteria – Interim Status
Dispatch | On schedule for 01-Apr-21 go-live
Settlements | The order of Settlements and Retail deployments now switched. Additional testing of the new Settlements solution with the current MDM solution required and progressing. The Settlements solution pre-prod and go-live dates will be revised by four weeks. Build complete and in User Acceptance Test. Overall no significant defects or issues, high level of confidence in product. Independent certification of settlements calculations – initial findings available, small number of material matters, now remedied. Date change is expected to impact AEMO internal only, no industry impact envisaged.
 | Go-live date impacted
 | At risk
 | On schedule

## Slide 13: Retail Reporting Approach
Multiple

## Slide 14: Approach to Retail Status Updates
18-Feb PCF
Forward Planning for Retail
Update on Interim Checkpoint Criteria Status
Week beginning 5-Apr
18-Mar PCF
March Checkpoint Criteria – assessment and outcomes
Pre-prod – status and go/no-go date
Production go-live – checkpoint date and criteria, go/no-go date
Pre-Prod Go/No-Go email
19-Apr
Retail Industry Testing Commences
12-May [TBC]
Retail Go/No-Go Communicated to PCF via email
23-Apr PCF
April Checkpoint Criteria - assessment and outcomes
Go/No-Go – confirm date
19-May PCF
Confirming Go/No-Go
Issue management
Replanning (if necessary)
31-May
5MS Retail / Metering Solution Go-Live
Key milestones
Communication timeline

## Slide 15: Summary of feedback received
Feedback received from 15 participants all in favour of May 31 go-live with March checkpoint
The earlier date was flagged as preferred to provide additional time for participant testing and other readiness activities. However it was noted that a date beyond end of June would be a critical risk for 5MS rule commencement on 01-Oct-21
Earliest possible deployment to pre-prod would be well received
  Noted, current industry testing date (19-Apr) has taken this into account
Some Participants have requested that in the case where 31-May-21 becomes unfeasible, AEMO will consider going live as soon after the 31-May-21 as possible rather than reverting directly to Option 2 (21-Jun-21)
  If a delay does occur, AEMO will go-live with the Retail platform as soon as possible after 31-May-21
MTP impacts understood, participants assessing changes to their programs and transition timings
  Updated version of MTP to be circulated to TFG
Clarity on checkpoint approach, criteria and timings to be provided to industry
  To be provided during PCF #30
Participant concerns on impact to delivery and timing to other regulatory reforms
  Regulatory Implementation Roadmap – Industry Session scheduled for 24-Feb at 13:00 email: StakeholderRelations@aemo.com.au
Participant changes may be required to update transition plans (timing and approach) to mitigate capacity concerns
Approaches and environment support to conduct bi-lateral testing being evaluated by participants to support their planned timelines

## Slide 16: Approach to Checkpoint Criteria
Assessment Approach
Criteria represent activities that are due for completion by the end of February
Objective is for criteria to be fully met
  Reflects on-time completion of scheduled activities
If one (or more) criteria not fully achieved, then implications and remedies are assessed before broader conclusions are made
5MS Program objective is to maintain 31-May go-live and will work to find remedies if not all criteria are met
31-May target go-live will be deferred if criteria are not met and remedies are judged as insufficient
Criteria for April checkpoint will adopt a similar approach

## Slide 17: Checkpoint Criteria – Interim Status
Criteria | Interim Status
Enterprise Azure migration successfully completed | Migration completed in all five environments. Testing and defect fixing has recommenced. Staging is now available for participants. Some teething issues but B2B is working for participant testing. Verbal update to be provided in meeting.
Build for critical defects completed | In progress and currently on track.
Target execution of test cases achieved, with no critical defects that cannot be remedied for 31 May go-live | In progress but behind schedule, slowed by 2 x technical issues (one now resolved and one with a workaround being built). Will be a key item for assessment at the March checkpoint. Test metrics (dashboard) to be made available to PCF
Successful completion of Dress Rehearsal (DR2B) | Scheduled for the end of February. No current issues impeding on-time commencement before March.
Pre-Production environment established | In progress and on track for completion by end of February.
Performance remediation for RM11 & RM16 completed, no new performance blockers | Remediation of RM11 & RM16 satisfactory for go-live completed, planning underway for “day in the life” performance test mid-March.

## Slide 18: Retail Testing Progress
Observations:
System test fully complete
System integration testing completing its final cases related to the final security changes
User Acceptance testing is focus
  Pass rate for executed tests is sound
  Priority is to clear blocking issues to increase test case execution
 | % Executed | % Executed Passed | % Total Pass
System Test | 100 | 100 | 100
System Integration Test | 94 | 97 | 91
User Acceptance Test | 77 | 85 | 65
Retail test metrics for 31 May go-live are provided for additional level of transparency and will help participants understand AEMO’s Retail platform progress towards 31 May

## Slide 19: Readiness Working Group Update
Greg Minney

## Slide 20
Chart: Proportion of respondents
| R1 | R2 | R3 | R4 | R5 | R6
0% | 0 | 0 | 0.02381 | 0 | 0 | 0
1 - 24% | 0.92308 | 0.7 | 0.40476 | 0.34091 | 0.30435 | 0.18182
25 - 49% | 0.076923 | 0.2 | 0.38095 | 0.45455 | 0.3913 | 0.25
50 - 74% | 0 | 0.05 | 0.16667 | 0.18182 | 0.26087 | 0.5
75 - 99% | 0 | 0.025 | 0.02381 | 0.022727 | 0.043478 | 0.068182
100% | 0 | 0 | 0 | 0 | 0 | 0
Not relevant | 0 | 0.025 | 0 | 0 | 0 | 0
Chart: Total participant types
| R1 | R2 | R3 | R4 | R5 | R6
Generator | 8 | 12 | 14 | 17 | 18 | 17
Retailer | 10 | 15 | 16 | 19 | 19 | 18
MP | 13 | 18 | 17 | 17 | 18 | 18
MDP | 12 | 17 | 14 | 16 | 17 | 16
MC | 0 | 17 | 14 | 19 | 18 | 16
DNSP | 9 | 10 | 10 | 10 | 10 | 10
TNSP | 3 | 7 | 7 | 7 | 7 | 7
Organisations | 26 | 40 | 42 | 44 | 46 | 44
Readiness Survey # 6 Initial Observations
Survey participation
Participants’ 5MS & GS program overall progress and status
Readiness Area | Initial Observations
Overall Participant Program Status | 41/44 organisations reporting “On Track” 1 generator (non critical) reporting “late” 1 MC/TNSP “at risk” , 1 MDP "at risk"
Program Risks | No new major program risks raised this survey COVID-19 risk status notes interstate restrictions having some impact for 1 participant
Impact of retail delay | No red flag on participant programs due to retail platform delay, risk raised for participant program if Option 1 not achieved and Retail Platform go-live moves post June 21
Essential Capability | 16 / 17 Generators report on track, 1 TNSP /MP meter installation program reported “late”, mitigation tbd Readiness Survey yet to be received for 1 key MDP 1 TNSP/MC has reported “at risk” with planned mitigation 1 MP has reported “complete” for metering installation and configuration
Other Participant Capability | All retailer programs reported on track, with spread of overall delivery % GS standing data updates and metering data delivery reported on track with minor exception for 1 DNSP 1 MDP “at risk” – 2 week delay, no essential meters

## Slide 21: Readiness Working Group Update
Platform Go-Live Plans:
Bidding Industry Go-Live Plan was circulated for comment
  Feedback due 22nd Feb
  Finalisation 8th March
Finalisation of retail industry go-live plan will be provided to incorporate:
    updates to timings
    PVM approach, and
Settlement Draft industry Go-live plan to be circulated for comment
Transition Focus Group
MTP Updated to reflect Retail Platform deployment 31 May, Key Impacts
  Commencement of 5 minute settlement data delivery
  Timeframe population of NONCONUML NMIs
Updated and extended meter rollout plans to be provided 1 March
  Consolidate rollout, and where available individual rollout plans to be distributed to impacted participants
Consolidated transaction volume assumptions to be provided as input to MSDR workgroup
  Invitation Industry Test planning - Retail
  Scenarios distributed for consideration by participants, participants to reconsider availability for testing
  Planning for conduct will take place in ITWG and with focused sessions for participating organisations

## Slide 22: Readiness Working Group Update
Readiness Risk Review
Review of readiness risks conducted
New and revised readiness risks reflecting Retail Platform Date change incorporated
No major change in overall readiness risk trend
Will be reassessed at next RWG in light of changes to AEMO platform delivery timeframes
Upcoming activity
RWG:
  Readiness Reporting Round #6
  Bidding go-live impacts and plan review
  Review of draft Settlements Industry Go Live Plan
ITWG
  Planning for Invitation Industry Test – Retail
  Data availability for Settlements Industry Test

## Slide 23: Readiness Working Group Update
Staging Environment
Outage migrate across to end state solution 8-12th Feb – MSATS/ Retail only impacted
  Environment available from 16 /2 for resumption of industry use
Full functionality for B2B testing is supported in the staging environment for participants wanting to perform bilateral testing including 30-minute and 5-minute reads.
Participants can refer to the Functional Deployment Matrix for more details of capability, reissued 12th Feb
Dispatch Industry Test
Continued industry activity noted to date for Bidding platform – No significant defects identified
  Update release to remediate defects identified in AEMO UAT

## Slide 24: Forward Meeting Plan
Anne-Marie McCague

## Slide 25: High-Level Plan for 2021
Month | Topics | Month | Topics
January | AEMO go-live decision making process Risk Review Readiness and go-live dashboard | June | Market Trial prep status Debrief on Retail Go-Live*
18 February | Retail Solution Status Exec Forum Agenda | July | Market Trial progress Readiness Reporting #8
18 March | Dispatch Cutover Preparation Status Readiness Reporting #6 Retail Checkpoint Criteria – assessment and outcomes Retail Pre-prod – status and go/no-go date Retail Production go-live – checkpoint date and criteria Settlements Certification Process Conclusions - TBC | August | Market Trial progress Risk Review – focus on rule commencement Exec Forum Agenda
23 April | Debrief on Dispatch go-live Settlements Cutover Preparation Status Risk Review Retail Checkpoint Criteria – assessment and outcomes* Retail Production go-live – confirmation of go/no-go date* | September | Results of Market Trial Preparing for 1 Oct – Ind Go-Live Plan review Readiness Reporting #9
19 May | Readiness Reporting #7 Exec Forum Agenda Approach to Global Settlements engagement Retail Production: Confirming go/no-go Retail Cutover Preparation Status* | October | Debrief and reconfirmation of approach for Global Settlements
This table provides a list of key topics. The normal updates will also be provided at each PCF. This table will evolve as the year progresses.
*Dates depend on March Checkpoint outcomes

## Slide 26
Pack to be circulated 19-Mar after PCF on 18-Mar
Proposed agenda:
  Readiness Dashboard – AEMO and Industry status, key issues or risks
  Retail status update
  Confirmation of Bidding go-live (01-Apr-21) and Settlements pre-prod release (19-Apr-21)
Executive Forum Agenda – 25-March

## Slide 27: Upcoming meetings
Current as at 12/02/2021
https://aemo.com.au/initiatives/major-programs/nem-five-minute-settlement-program-and-global-settlement

## Slide 28: General Questions
Peter Carruthers

## Slide 29: Meeting Close
Peter Carruthers

## Slide 30: Appendix

## Slide 31: Readiness Dashboard Part A - Essential Capability Status supporting evidence – Draft
Criteria | Capabilities | March | May | July | Sept
AEMO Capability | Metering: | Deployment of Metering Platform schedule | Metering Platform deployed for 30 Minute operation | Business Operations Stable | Market Trial Conducted successfully
 | Receive and Process 5 minute metering data | Metering Platform Industry testing Conducted | Business operations stable | 5MS Capability in place for Market Trial | 
 | Support 5 Minute Profiling |  |  | Market Trial Planned | 
 | Settlements: | Platform Industry testing underway | Platform deployed for 30 Minute operation | Business Operations Stable | Market Trial Conducted successfully
 | Support 5 minute Settlement processes | Platform deployment on track for scheduled date | Business operations stable | Capability in place for Market Trial | 
 |  |  |  | Market Trial Planned | 
 | Dispatch (Bidding): | Platform Industry testing underway | Platform deployed for Transition mode operation | Platform Stable | Market Trial Conducted successfully
 | Support 5 Minute bidding services | Platform deployment on track for scheduled date | Business operations stable | Capability in place for Market Trial | Bidding table updates in place
 | Provide 5 Minute web bidding interface | Bidding table updates in place | Bidding table updates in place | Market Trial Planned | 
 |  |  |  | Bidding table updates in place | 
Essential Bidding | Generators: | Testing of upgrades commenced | Testing of upgrades | Deployments of 5 Minute Capability (Transition mode) | Deployments of 5 Minute Capability (Transition mode)
 | generators representing at least 80% of load in each region are capable of providing 5 minute bids |  | Initial deployments of 5 Minute Capability (Transition mode) | Market Trial Participation Planned | Market Trial Participation Planned
Essential Metering | MP's upgraded ensured that essential meters are capable of providing 5 minute metering data | Metering rollout plans with reported progress versus MTP | Metering rollout plans with reported progress on track | Metering rollout plans with reported progress on track | Metering rollout plans Completed
 | MDPs are able to provide 5 minute metering data for essential meters for settlement | Metering rollout plans available Accreditation initial meetings held Program Progress being Reported on track | Accreditation Updates planned / Underway | Market Trial Participation | Market Trial Participation
 |  |  | Initial Delivery of 5 minute data for Settlement | Accreditation updates Achieved / Underway | Accreditation updates Achieved
 |  |  |  | Initial Delivery of 5 minute data for Settlement | Initial Delivery of 5 minute data for Settlement

## Slide 32: Readiness Dashboard Part B - Participant Readiness Status supporting evidence - Draft
Participant | Capabilities | March | May | July | Sept
Retailers | Receive and process 5 minute metering data |  | Planned participation in Market Trials | Participation in Market Trial | Market Trial successful participation
 | Receive and process 5 minute Settlement statements |  | Level of bi-lateral testing of B2B processes | Level of bi-lateral testing of B2B processes | 
DNSPs/ TNSPs | Receive and process 5 minute metering data | Published plans for Standing data and Metering upgrades | On track delivery against Standing Data and Metering Upgrades | On track delivery against Standing Data and Metering Upgrades | On track delivery against Standing Data and Metering Upgrades
 | Provide GS Metering and Standing Data updates (inc. NCONUML) |  |  | Market Trial Participation | Market Trial successful participation
MDPs | Provide 5 minute Data T1-3 Distribution connected metering data | Published plans for T1 Basic Meter Delivery, Accreditation Updates planned Rollout Plans for T1-3 4*, 7 - distribution connected | On track delivery for T1 Basic Meter Delivery | On track delivery for T1 Basic Meter Delivery | T1-3, Type 7 distribution connected meters providing 5 minute metering data for Settlement T1 Basic Meter Data completed
 | Provide T1 Basic Metering Data |  | Level of bi-lateral testing of B2B processes | Level of bi-lateral testing of B2B processes | 
 | Provide MDFF Interval Data / Inc |  | Ontrack for T1-3, 7 distribution connected metering data delivery | Ontrack for T1-3, 7 distribution connected metering data delivery | 
MDPs | Provide 5 Minute metering Data (4, 4A, VicAMI) | Rollout Plans Provided | Rollout Plans Provided | Market Trial Participation | All Interval Metering Data delivered via MDFF
MPs | T1-3 distribution connected metres capable of producing 5 Minute Data | Metering rollout plans with reported progress versus MTP | Metering rollout plans with reported progress on track | Metering rollout plans with reported progress on track | Metering Rollout Completed