## Slide 1: 5MS Program Consultative Forum #32
Friday, 23 April 2021
This meeting is recorded for the purpose of minute taking.

## Slide 2: AEMO Competition Law Meeting Protocol
Under no circumstances must Participants share Competitively Sensitive Information. Competitively Sensitive Information means confidential information relating to a Participant which if disclosed to a competitor could affect its current or future commercial strategies, such as pricing information, customer terms and conditions, supply terms and conditions, sales, marketing or procurement strategies, product development, margins, costs, capacity or production planning.
AEMO is committed to complying with all applicable laws, including the Competition and Consumer Act 2010 (CCA). In any dealings with AEMO regarding proposed reforms or other initiatives, all participants agree to adhere to the CCA at all times and to comply with this Protocol. Participants must arrange for their representatives to be briefed on competition law risks and obligations.
Participants in AEMO discussions must:
Ensure that discussions are limited to the matters contemplated by the agenda for the discussion
Make independent and unilateral decisions about their commercial positions and approach in relation to the matters under discussion with AEMO
Immediately and clearly raise an objection with AEMO or the Chair of the meeting if a matter is discussed that the participant is concerned may give rise to competition law risks or a breach of this Protocol
Participants in AEMO meetings must not discuss or agree on the following topics:
Which customers they will supply or market to
The price or other terms at which Participants will supply
Bids or tenders, including the nature of a bid that a Participant intends to make or whether the Participant will participate in the bid
Which suppliers Participants will acquire from (or the price or other terms on which they acquire goods or services)
Refusing to supply a person or company access to any products, services or inputs they require

## Slide 3: Agenda
# | Time | Topic | Presenter
1​ | 10:00 – 10:05​ | Welcome​ | Peter Carruthers​
2​ | 10:05 -10:10 | Actions from Previous Meetings​ | Anne-Marie McCague​
3​ | 10:10 – 10:20 | Program Update​ | ​Rowena Leung & Graeme Windley
4 | 10:20 – 10:40 | Retail Reporting | Graeme Windley
5​ | 10:40 – 10:50 | Readiness Working Group Update​ | Greg Minney​
6 | 10:50 – 11:05 | Industry Risks and Issues | Anne-Marie McCague
7​ | 11:05 – 11:35 | Contingency Planning | Anne-Marie McCague, Greg Minney, Peter Carruthers
8​ | 11:35 – 11:40 | Forward Meeting Plan | Anne-Marie McCague​
9​ | 11:40 ​- 11:50 | General Questions​ | Peter Carruthers​
10 | 11:50​ | Meeting Close​ | Peter Carruthers​

## Slide 4: Welcome
Peter Carruthers

## Slide 5: Actions from Previous Meetings
Anne-Marie McCague

## Slide 6: PCF Actions
No. | Status | Action | Comment
 |  | No actions recorded from previous PCF and no open actions on log | 

## Slide 7: Executive Forum Actions
No. | Status | Action | Comment
12.4.1 | Open | AEMO to consider seeking information on whether Retailers are deploying the code for Customer Switching at the same time as 5MS Retail through readiness reporting survey or direct poll. | AEMO will issue a survey to RWG members.
12.6.1 | Open | AEMO to include an agenda item on contingency planning at the next Executive Forum | Contingency planning will be discussed at PCF and RWG in preparation of next Executive Forum.
12.7.1 | Closed | AEMO to consider the positioning of the Regulatory Implementation Roadmap webpage within the AEMO website. | This feedback has been provided to the Corporate Affairs team.
12.8.1 | Closed | AEMO to issue invitation for an Executive Forum in May or June. | AEMO has issued an invitation to a Special Executive Forum for 01-June that will be held if the Retail go-live date of 31-May is missed.

## Slide 8: Program Update
Rowena Leung & Graeme Windley

## Slide 9: 5MS Program Timeline Readiness and Go-Live
As at 09th April 2021
5-min Bidding Phased Go-Live achieved on 01-Apr-21
Retail solution available for participant testing from 16-Apr-21
Settlements Industry Test Period ongoing
User Acceptance Testing is in progress for both Retail and Settlements
Performance Testing is complete for Settlements and in-progress with Day in the Life testing for Retail

## Slide 10: 5MS Program – IT Systems Status
Stream | Status | Commentary
Retail |  | More detailed status provided in next section Run-through for cutover will take place at the RWG in mid-May post the Go/No-Go decision.
Dispatch |  | 5MS Bidding Service went live on 1 April 2021. Participants may choose to submit 5-min bids (must be equal for a 30-min period). Pre-dispatch P5 – Fast Start Inflexibility Profile (FSIP) was deployed into pre-prod on 01-Apr-21 and is on track for production on 03-May-21 5MPD Price Sensitivity – deployment dates TBC with RWG. Estimating August for pre-prod and September for production
Settlements |  | Overall, no significant defects or issues, high level of confidence in product for 30-minute functionality - progressive testing on 5-minute functionality continuing No blockers ahead of 17 May 2021 Platform Go Live, Go/No-Go email will be issued 10-May-21 Additional testing of the new Settlements solution with the current MDM solution progressing (RM40 5-min solution required remediation) Settlement Industry Testing commenced as scheduled on 22-March-21 Three settlement runs have been executed, Q&A session took place on 31-Mar Weekly defect email providing status update on known issues is being issued to RWG, SWG and ITWG (includes Staging) Run-through for cutover will take place at RWG on 04-May-21 Go/No-Go email will be issued 10-May-21
Overall AEMO Status |  | Overall, the AEMO 5MS program remains Amber. Although good progress has been made across all workstreams and we are tracking to the re-baselined schedule, the Retail workstream remains Amber.
 | Go-live date impacted
 | At risk
 | On schedule

## Slide 11: Retail Reporting
Graeme Windley

## Slide 12: Approach to Retail Status Updates
18-Feb PCF
Forward Planning for Retail
Update on Interim Checkpoint Criteria Status
18-Mar PCF
March Checkpoint Criteria – assessment and outcomes
Pre-prod – status and go/no-go date
Production go-live – checkpoint date and criteria, go/no-go date
08-Apr
Pre-Prod Go/No-Go email
19-Apr
Retail Industry Testing Commences
14-May
Retail Go/No-Go Communicated to PCF via email
23-Apr PCF
April Checkpoint Criteria - assessment and outcomes
Go/No-Go – confirm date
19-May PCF
Confirming Go/No-Go
Issue management
Replanning (if necessary)
31-May
5MS Retail/ Metering Solution Go-Live
Key milestones
Communication timeline
07-May
PCF Update Session

## Slide 13: April Retail Checkpoint Criteria as at 16-Apr
Criteria​ | Description | Status | Commentary
Testing | All UAT test cases executed with no critical defects that cannot be remedied for 31 May go-live. | In Progress | Data-related defects have caused the UAT target completion date to push out to 30-Apr. There will be defect resolutions that will need to go into May. The program needs to see UAT complete before it can commit that all critical defects can be remedied in time for 31 May go-live.
Solution Stability | End-to-end solution operating stably in Test with no process blockers or unexplainable pauses/interruptions to processing. |  | Stability has improved, and enabled testing execution to progress. Improvements (i.e. defensive programming) introduced have been successful.
Remediation | Known remediation work (internal reports performance, business activity monitoring) completed and remediation for any new defects scheduled. | In Progress | Internal work on Operational Reporting and Business Activity Monitoring has progressed well. However there remains work to do to ensure key Operational Reports are ready for go live as per AEMO business team expectations.
Performance | “Day in the Life Testing” completed with no performance issues identified that cannot be remedied for 31 May go-live. | In Progress | Some delays starting, now in progress and initial results from 2 / 5 runs are positive.
Pre-Production | Data migration on track and no blockers to meeting criteria/schedule for pre-production deployment. |  | Pre-production deployment complete. Reviewing timeline for go-live cutover from lessons learnt.
Industry Test | On track to commence Retail Industry Test on 19 April. |  | Industry testing available from 15-Apr Retail industry invitation testing to commence on 19-Apr as scheduled.
Overall |  |  | Overall, the Retail workstream remains amber for 31 May go-live. There are currently no blockers to achieving 31 May go-live, and the project remains committed to meeting this date. However, as per the above, there are still a number of outstanding items that is putting pressure on meeting the timeframe.

## Slide 14: Retail Testing Progress
Observations:
UAT progress has been made in both test case execution and pass levels, now only 5% execution remaining
Test execution productivity is improved, close to completion.
Current target is for all test cases to be executed by end-April. Complexities in setting up E2E PAE test cases within the test environments now almost concluded (PAE test cases at 97%).
AEMO will run Settlement runs in the MDM Pre-Production environment on conclusion of the PAE UAT execution and defect resolution, likely early May.
 | As at 18-Feb |  |  | As at 12-Mar |  |  | As at 16-Apr |  | 
 | % Executed | % Executed Passed | % Total Pass | % Executed | % Executed Passed | % Total Pass | % Executed | % Executed Passed | % Total Pass
System Test | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
System Integration Test | 94 | 97 | 91 | 96 | 98 | 93 | 96 | 99 | 95
User Acceptance Test | 77 | 85 | 65 | 89 | 90 | 81 | 95 | 96 | 91
Retail test metrics for 31 May go-live are provided for additional level of transparency and will help participants understand AEMO’s Retail platform progress towards 31 May (see next slide).

## Slide 15: Criteria for a “go” on 14-May
Criteria​ | Description
Testing | All UAT test cases executed with no Sev1 or Sev2 defects outstanding. All Sev3 defects have sufficient workarounds / are acceptable for go live.
Solution Stability | End-to-end solution operating stably in Test and Pre-Production with no process blockers or unexplainable pauses/interruptions to processing.
Remediation | All AEMO significant defect remediation and internal build work has completed, and the AEMO business and IT teams have approved the Go Live.
Performance | “Day in the Life Testing” completed, with results matching what is required for market stability and no outstanding go-live issues to be resolved.
Pre-Production | Successful and timely deployment and Cutover delivered into the Pre-Production environment.
Industry Test | Retail Industry Testing completes successfully, with raised participant issues dealt with in accordance to defect priority.
Overall | 
The below is the Criteria that AEMO will use to evaluate the Retail solution with the PCF on 14 May 2021 (via email). Results where a “not ready” or “conditional approval” are received will result in a broader discussion:

## Slide 16: Next Steps
AEMO is progressing activities for a go-live on 31-May-21 with the Go/No-Go decision on 14-May-21
AEMO will provide an update on the checkpoint criteria to the RWG on 04-May-21
AEMO proposes a 30-minute update session for PCF on 07-May-21

## Slide 17: Readiness Working Group Update
Greg Minney

## Slide 18: Market Trial Planning
Market Trial Focus Group established to develop initial view of industry scenarios to agree scope of 5MS market trial
Initial MTFG Session (29th March) identified suggested priority scenarios
ITWG to consider scenarios (27th April) and provide further input
Scenarios identified to date include:
30-5 minute settlement week (5 days 30 / 2 days 5 minute)
Daily / weekly operation of 5 minute settlement operations
Bidding scenarios incorporating price sensitivities, rolling sum pricing, intervention data
Metering scenarios in general to support settlement testing scenarios
UFE reports run on the basis of available test data , so can be tested for functionality not data outcomes
Consideration to be given to incorporating scenarios where execution enables some level of customer switching support
Issues and exceptions arising will not be addressed by 5MS program
Enables some co-ordination of activity between participant groups
Once scenarios agreed, industry participation and pairing will be established.

## Slide 19: Industry Test Progress
Settlements Industry Testing
Industry Test period commenced 22nd March
3 settlement runs provided for industry consumption from current MSATS platform:
  Runs can be compared to production run at same point in time
  Forms basis of settlement platform operation at platform go-live (17th May)
Further 3 Settlement runs to be provided for industry consumption from new Retail Platform
  Runs will also provide opportunity to compare against equivalent production settlement runs
  Forms basis of settlement operation against retail platform from 31st May
All settlements industry testing performed @ 30 minute as this is basis of platform go-live
Retail Invitation Industry testing:
Scheduled commence 19th April with participant shakeout
Scenarios and participant pairings agreed
Daily meetings to review progress and issue resolution – open to all participants
Daily testing progress report and defect report will be issued to RWG, SWG & ITWG​

## Slide 20: Readiness Survey #7
Closure date for responses to Industry Readiness Survey #7 was 15th April
Readiness report will be issued on the 29th April for review at RWG on 4th May
An initial summary of results will be provided in an update at the PCF meeting on the 23rd April

## Slide 21
Readiness Survey # 7 Initial Observations –
Coverage and Essential Capability
Coverage:
45 organisations have responded to the seventh round of readiness reporting, as of 20 April, with increase of 6 in role responses
Retailer coverage lower than expected (83.7%) due to one key Retailer not submitting a survey response, follow up in progress
40/45 participants intend to participate in Market trials
Essential Capability
Generation essential capability criteria met -16/17 generators intend to utilise bidding transition period
Previous “late” status recovered by MP
MSP is reporting on track against compliance obligations but amber against AEMO MTP readiness criteria due to minimal schedule contingency. AEMO discussing contingency approach with the MSP.
AEMO criteria re deployment of MDM remains at Amber Status: ahead of planned 31 May
Settlements platform on track for 17 May deployment
AEMO Bidding platform deployed 1 April
Other Participant Criteria
DNSPs in Victorian Jurisdiction reporting at risk or late for some GS installation and data population activities, impact assessments being sought
All retailer participants report “on track” for rule commencement, with increase in level of retail bi-lateral testing planned with a Q1/2 commencement

## Slide 22: RWG/TFG/ITWG Update
Upcoming MTP activity
RWG Agenda:
  Program progress toward May 31 go-live
  Readiness Report analysis
  Settlements go-live plan briefing
  Retail go-live plan implications
  Contingency plans
ITWG:
  Market Trial Scenarios
  Invitation Industry test progress
TFG
  CATS volume and meter rollout analysis
  GLOPOOL plans
  Rollout plan updates

## Slide 23: Industry Risks and Issues
Anne-Marie McCague

## Slide 24: Purpose of this Risk Review
Review the three key areas of risk:
  Retail delay
  AEMO and industry readiness
  Volume of regulatory change
Provide an overview of the status of other PCF risks
Discuss any other risks or issues that should be added to the register

## Slide 25: Retail Risk
Risk ID | Description | Residual Rating | Comments
R33 | Further delays to AEMO Retail Systems impact 5MS rule commencement critical path There is a risk that further delays beyond those identified put the critical path through market trial to 5MS rule commencement (01-Oct-21) at risk | Significant | Risk was discussed at RWG 06-Apr. This risk remains a “significant” risk and is being monitored through checkpoints with the PCF. Trend remains at stable. No issue has been identified that would impact critical path. Residual Likelihood: Unlikely Residual Consequence: Extreme Actions: Develop contingency plan with PCF and RWG (discussed in next section)
​ | Improving​ ​ No Change /Stable​ ​ Worsened ​
Issue ID | Description | Rating | Mitigations
I12 | No Remaining Contingency for Retail Deployment Issues identified during Dress Rehearsal 2 and Azure migration coupled with existing Retail timeline challenges mean that delays have occurred within the 5MS Retail workstream. There is no schedule contingency within this workstream to compensate for the time needed to remediate these issues therefore the scheduled go-live of 09-Mar-21 will not be met. | High | The Retail systems program has been reviewed and the timeline has been revised to provide sufficient time to remediate the identified issues Established a reporting process with PCF through checkpoint criteria R33 has been opened to represent the risk of further delays impacting the critical path

## Slide 26: AEMO & Industry Readiness
Risk ID | Description | Residual Rating | Comments
R34 | Delay to AEMO 5MS Retail impacts participants readiness There is a risk that the delayed availability of the 5MS Retail solution impacts participants readiness programs resulting in delays in some participants programs. | Significant | Readiness Reporting Round 6 showed majority of participant were on track. None of the respondents noted that the Retail replan had caused a change in their readiness status. While dependencies had been identified e.g. NCONUML, none of the respondents noted their critical capability at risk as a result of the replan. The key impact reported was a decrease in the time available for testing RWG 06-Apr agreed that Residual Likelihood be set as “Unlikely”, Residual Consequence to remain as “Major”. This provides an overall Residual Rating of “Significant”. Actions: Continue to monitor through Readiness Reporting
R11 | The AEMO business and operations are not ready for 5MS Rule Commencement on 1 Oct 21 The AEMO business may not be ready to deliver the full extent of the 5MS deliverables by 5MS and GS rule commencement including business processes and resource training, results in failure of Go Live for 5MS and GS Program | Significant | Reviewed at RWG 06-Apr. As reported through AEMO’s Readiness Report, the Retail workstream within the 5MS Program is amber which is impacting AEMO’s overall Readiness. Progress on the Retail Go-Live is being monitored through monthly checkpoints with the PCF. Currently, AEMO remains on track for Retail Go-Live on 31-May. Actions: Proposing that trend be set as stable as status through readiness reporting has not changed Continue to monitor through Readiness Reporting
R19 | Risk of a critical mass of participants not being ready at identified critical path milestones Critical capability of participants fail to meet expected industry Readiness critical path milestones, resulting in failure to be ready for go-live and impacting the proper functioning of the market. | Medium | Results of Readiness Reporting Round 6 shows that critical capability of respondents is green, on track and stable. RWG 06-Apr agreed that trend remains stable and rating remains Medium Actions: Continue to monitor through Readiness Reporting
​ | Improving​ ​ No Change /Stable​ ​ Worsened ​

## Slide 27: Volume of Regulatory Change
Risk ID | Description | Residual Rating (Current) | Comments
R37 | New 5MS Retail Solution Go-Live Dates impact other regulatory change programs There is a risk that the changes to the 5MS retail timeline may have impacts on other AEMO change programs (e.g. Customer Switching or WDR) which may result in a need for those programs to replan having knock-on effects to the industry. | Medium | Regulatory Implementation Roadmap has been updated with new Retail dates Actions: AEMO proposes to close this risk, noting that the risk of any further changes to the Retail timeline are covered through R33
R06 | Interaction with other industry changes that have already been adopted through rule changes Significant regulatory changes across the energy sector will stretch resources allocated to market change programs, resulting in potential impacts to participants resourcing and program delivery. | Significant | Regulatory Implementation Roadmap has been updated Detailed Implementation Scheduled has been developed and shared with industry Actions: AEMO proposes that this risk remains as “significant” but that the trend changes to stable
R09 | Impact to 5MS from other rule changes that are being considered Future rule changes could affect the implementation of 5MS, resulting in impacts to industry program implementation timelines | Significant | Current Residual Likelihood: Possible Current Residual Consequence: Major There are currently no rules in the AEMC process that would impact 5MS. Given the standard AEMC process is a minimum of 6 months, the risk of a new rule being passed before 01-Oct-21 that would impact 5MS is reduced. Actions: AEMO proposes to reduce the Residual Likelihood to “unlikely”, giving an overall rating of Medium. Trend remains improving as time progresses.
R30 | Risk that new 5MS and GS Go-Live dates could impact other industry change programs The new commencement dates are closer to some other industry change programs. There is a risk that industry and AEMO resources and systems may be constrained during a period of multiple major go-lives which may lead to difficulties with timelines and system stability. | Significant | Pressures remain within industry and AEMO as a result of a constrained period of multiple major go-lives. Therefore, AEMO does not proposed to change the rating. Trend remains as stable. Actions: Continue to monitor through Readiness Reporting
​ | Improving​ ​ No Change /Stable​ ​ Worsened ​

## Slide 28: Other PCF Risks
ID# | Title | Residual Rating | Comment
R01 | Small participant Engagement | Medium | AEMO has sent an email providing information about the 5MS website and working groups to the following registered market participant groups that are not already on 5MS mailing list: SGAs, Large End-Users, Retailers. Currently progressing with Generators. The Clean Energy Council issued an email to all their members on behalf of AEMO and included a note in their newsletter.
R02 | Risk that there is one or more participants that aren’t ‘ready’ at go-live | Significant | RWG are considering closing this risk as it was opened before the critical capability was defined. R02 is a likely risk but would only have an impact on the market if the participant that was not ready contributed to the critical capability. This risk is covered by R19.
R04 | AEMO Big Bang Approach | Medium | RWG to consider closing this risk post Settlements go-live
R05 | Unintended consequences of Rule as drafted | Low | No change
R07 | Potential implications for financial markets | Medium | ASX 5-min contracts are now live.
R08 | Procedure changes arising from program implementation and testing activities | Low | No change
R10 | Vendor contract negotiation timelines | Low | No risks currently being raised via readiness reporting
R18 | Potential for implementation approach to materially increase Program costs | Medium | AEMO presented approach to consulting on cost recovery and fees at Executive Forum
R26 | Impact of Covid-19 resulting in participants and / or AEMO being unable to meet 5MS Program timelines | Medium | Impact varies by participant. No impacts to participant program status have been raised through Readiness Reporting.
R29 | Risk that participants that paused their programs will not be ready | Low | No change to rating. Participants that reported they had paused their program due to the rule deferral in 2020 are not reporting delays to their program due to their shutdown
R35 | Compression of window for transition 5-min metering data delivery | Medium | Reviewed by RWG and TFG. Adjustment to participant programs reflected in MTP. No change to rating.
R36 | Compressed MTP transition windows for the population of NCONUML NMIs impacts the accuracy of UFE Reporting | Medium | Reviewed by RWG and TFG. Adjustment to participant programs reflected in MTP. No change to rating.

## Slide 29: Other PCF Risks – Proposing to Close
Risk ID | Description | Residual Rating | Comments
R28 | AEMO Systems Deployment Cutover Risk The current approach to the AEMO systems deployments elements of the cutover has the Retail stream (the most complex and riskiest) going first on 9 March, then both the Dispatch and Settlements systems deployments together 3 weeks later on 1 April. There is a risk that the Retail deployment could lead to push back on the following deliveries from the 5MS program, the AEMO business and/or market participants. | Medium | AEMO proposing to close this action. Through the Retail replan, the link between the Settlements solution and the Retail systems has been separated. Settlements will now go live on 17-May-21 independently of Retail. A risk remains that the Retail deployment may be delayed and have knock-on consequences for Market Trial and Market commencement. This risk is covered through R33.

## Slide 30
Are there any new risks or issues to be raised?

## Slide 31: Contingency Planning
Multiple

## Slide 32: Purpose of this section
Provide an overview of 5MS Contingency Planning
Discuss the addition of the Retail delay risk to the 5MS Contingency Plan and the approach to developing the contingency
Review the risk and proposed contingency options
Review the Regulatory tools that may be used to achieve the contingency response
Discuss initial thoughts from PCF
Agree the timing to develop the contingency response and next steps

## Slide 33: Overview of Industry Contingency Planning to date
Industry Contingency plan developed by RWG in April 2020
26 contingency scenarios identified, with associated monitoring , responses and trigger points
Scenarios coverage includes:
  AEMO “Not Ready” to operate for 5MS Rule commencement
  Minimum / Essential criteria not met for 5MS Rule Commencement
  Essential Meters not fully compliant at 5MS rule Commencement
  Essential Meter(s) metering data delivery issues
  Delays to platform deployments
  Platform Deployment failures
  Post go-live inaccuracies and issues
Where applicable contingency responses utilise existing NEM operating processes
Monitoring Mechanism a number of scenarios include monitoring of participant and AEMO progress via readiness reporting and completion of planned milestones
As component of RWG readiness reporting assessment will be made against identified contingency scenarios for contingency implementation

## Slide 34: Contingency Plan Extract
5MS GS INDUSTRY READINESS CONTINGENCY PLAN |  |  |  |  |  |  | 5-Jun-20 |  |  | 
Contingency Scenario Ref | Industry Risk Ref | Contingency Scenario | Scenario Description | Scenario Category | Priority (H/M/L) | Likelihood (H/M/L) | Impacted Stakeholders | Triggers | Monitoring Mechanism | Response
C1 | R14, R15, R16, R17 | Minimum criteria not met for 5MS/GS commencements | Minimum criteria (defined in Industry readiness contingency plan word document) not met for 5MS/GS commencements resulting in critical impact to NEM operations and/or material risk of market or power system failure | Readiness | H | L | AEMO, Impacted Participants | The following triggers may indicate that minimum criteria for 5MS/GS commencements may not be met: - Readiness reporting results, 7-8 months in advance of the commencement dates - Insufficient participants in industry testing/market trials - Unfavourable industry testing/market trial results | Industry Readiness Reporting, Industry testing and Market trials | - Perform impact assessment, confirming risk of fundamental market failure and recommend preferred contingency response based on the physical and commercial market requirements - Where necessary, escalate issue and recommend actions to the PCF or EF - Submit rule change to AEMC (6 month process) where no other alternative approach exists
C25 | R11 | AEMO 'not ready' to operate | AEMO 'not ready' to operate within market conditions at rule commencement resulting in fundamental impact to ongoing NEM operations | Readiness | H | L | AEMO, Impacted Participants | Critical AEMO Milestones missed and not considered recoverable prior to rule commencement when assessed major checkpoint | Program Milestones and Industry Readiness Reporting | Establishment of extent of delay and industry consultation on appropriate response. Confirmation that impact of delay will result in fundamental market failure Development of Rule Change Proposal for AEMC consideration (AEMO).

## Slide 35: Risk Assessment
AEMO is proposing to add this risk to the contingency planning, linked to C25. It is considered that this is the most likely risk scenario related to the Retail workstream.
The following slides explore the contingency options in more detail
The contingency options would be executed through a regulatory tool. Possible regulatory tools include:
  Letter of no action from AER
  Rule change by AEMC
Which regulatory tool should be selected depends on the timeline for decision making, the impact of the contingency options on industry, NER and other regulatory initiatives.
Whether GS commencement date would be proportionately deferred may depend on the severity of the delay
AEMO’s new MDM solution is deployed and operating successfully in 30-min mode, but not ready to properly process 5-min metering data by 1 October due to further workstream slippages
AEMO would be able to receive 5-min meter reads, it would not be possible to process the data for the purposes of Settlements and calculation of UFE
Risk
Impact
  Move the commencement date for all aspects of 5MS rule
  Move the start date for a subset of the 5MS rule (i.e. for AEMO settlement only)
  Resettle the market at 5-min
Contingency options

## Slide 36: Option 1 & 2: Move the commencement date
 | For all aspects of 5MS Rule | Only for AEMO’s 5MS Settlement
Description | Postpone all elements of 5MS Rule for AEMO and participants. | Allow the rules relating to bidding, dispatch and meter data provision to commence. Defer the obligation on AEMO to settle at 5-mins.
Impact to GS | Not moving GS proportionately reduces the time between UFE soft-start and when participants become financially responsible for UFE. Feedback is requested from industry on the maximum period of delay to GS soft start that would be acceptable without a deferral to GS commencement. | 
Pros | Simple approach and well understood process | Less impact to participant readiness timelines – feedback requested Contract market may use 5-min spot price
Cons | Impacts other initiatives – WDR must commence in a 5-min market, CS code is linked to 5MS Retail solution Increases participant readiness program timelines which may increase costs | Customer Switching and WDR are impacted There will be winners and losers compared to a market that would have been settled at 5-mins

## Slide 37: Option 3: Resettle the Market at 5-min
Under this approach, AEMO would continue settling the market at 30-mins. Once the 5-min Retail solution went live, AEMO would resettle at 5-mins.
Pros:
  Since participants would be resettled, it could allow the benefits of 5MS to be realised from 01-Oct-21
  It may be beneficial for a short delay (<3.5 weeks) as it would have minimal impact on industry
Cons:
  Cashflow implications for participants if delay is beyond Final Statement
  May have implications to prudentials
  More complicated approach
Billing week 40: 26-Sep-21 to 02-Oct-21
Payment Due 29-Oct-21 (4wks)
20-wk Revised Statement
15-Feb-22
Preliminary Statement
08-Oct-21 (1 wk)
Final Statement 27-Oct (3.5 wks)
30-wk Revised Statement
28-Apr-22
Delay <3.5 wks would mean that the final statement would be in 5-mins
Delay >3.5 wks would mean that the final statement would be in 30-mins and a revision would take place in 5-mins through either the 20 or 30 wk statement

## Slide 38: Leadtime to Implement
14-May Go/
No-Go Decision
Go
05-Jul Market Trial Commences
21-Jun back-up date
Contingency trigger assessment
01-Oct-21 5MS Rule Commences
Dates are indicative only and assume an expedited rule change process is followed
Rule change
07-Jul AEMC Consultation commence for
4 weeks
04-Aug AEMC Consultation close
01-Sep AEMC Final Determination
New date 5MS Rule Commences
Planned timeline
8 weeks
4 weeks notice TBD
31-May –
Retail Go-Live
Mid-June assessment
Mid-June
AEMO submission to AEMC

## Slide 39: Considerations to assess options – feedback requested by 11-May
What level of impact would each of the contingency options have on your organisation's implementation program?
What commercial impacts would each of the contingency options have on your organisation?
What is the maximum deferral of the GS soft-start that is acceptable without deferring the GS rule commencement?
The delay of 5MS commencement would impact WDR and Customer Switching as both are dependent on a 5-min market
  What impact would each of the contingency options have on your organisation’s other regulatory delivery programs?
The earlier in the timeline that AEMO needs to determine a new commencement date, the more likely it is that assumptions will be taken to determine that new date, increasing the risk of a longer delay than necessary. AEMO is seeking feedback on the required notice period for a new commencement dates, should this scenario arise.
  What is the minimum notice period required for a change to the 5MS commencement date?
  Which should AEMO consider more important when assessing the contingency options: certainty of go-live date or ability to reduce overall delay period?
Does your organisation have a preferred contingency option?

## Slide 40: Next Steps
AEMO requests that PCF Members discuss the options presented with their RWG reps to prepare for a detailed discussion at next RWG on 4 May (see previous slide)
Discussion during RWG will be captured and AEMO encourages written submissions by 11 May
Summary of feedback and next steps will be discussed at 19-May PCF

## Slide 41: Forward Meeting Plan
Anne-Marie McCague

## Slide 42: High-Level Plan for 2021
Month | Topics | Month | Topics
January | AEMO go-live decision making process Risk Review Readiness and go-live dashboard | June | Market Trial prep status Debrief on Retail Go-Live*
18 February | Retail Solution Status Exec Forum Agenda | July | Market Trial progress Readiness Reporting #8
18 March | Dispatch Cutover Preparation Status Readiness Reporting #6 Retail Checkpoint Criteria – assessment and outcomes Retail Pre-prod – status and go/no-go date Retail Production go-live – checkpoint date and criteria Settlements Certification Process Conclusions | August | Market Trial progress Risk Review – focus on rule commencement Exec Forum Agenda
23 April | Debrief on Dispatch go-live Settlements Cutover Preparation Status Risk Review Retail Checkpoint Criteria – assessment and outcomes Retail Production go-live – confirmation of go/no-go date | September | Results of Market Trial Preparing for 1 Oct – Ind Go-Live Plan review Readiness Reporting #9
19 May | Readiness Reporting #7 Exec Forum Agenda Approach to Global Settlements engagement Retail Production: Confirming go/no-go Retail Cutover Preparation Status* | October | Debrief and reconfirmation of approach for Global Settlements
This table provides a list of key topics. The normal updates will also be provided at each PCF. This table will evolve as the year progresses.
*Dates depend on GO/No-Go notice

## Slide 43: Upcoming Meetings AEMO | Program Calendar and Timelines
Current as at 09/04/2021

## Slide 44: General Questions
Peter Carruthers

## Slide 45: Meeting Close
Peter Carruthers