## Slide 1: 5MS & GS Program Consultative Forum #33
Wednesday, 19 May 2021
This meeting is recorded for the purpose of minute taking.
Please disconnect from your workplace VPN for the WebEx call​

## Slide 2: AEMO Competition Law Meeting Protocol
Under no circumstances must Participants share Competitively Sensitive Information. Competitively Sensitive Information means confidential information relating to a Participant which if disclosed to a competitor could affect its current or future commercial strategies, such as pricing information, customer terms and conditions, supply terms and conditions, sales, marketing or procurement strategies, product development, margins, costs, capacity or production planning.
AEMO is committed to complying with all applicable laws, including the Competition and Consumer Act 2010 (CCA). In any dealings with AEMO regarding proposed reforms or other initiatives, all participants agree to adhere to the CCA at all times and to comply with this Protocol. Participants must arrange for their representatives to be briefed on competition law risks and obligations.
Participants in AEMO discussions must:
Ensure that discussions are limited to the matters contemplated by the agenda for the discussion
Make independent and unilateral decisions about their commercial positions and approach in relation to the matters under discussion with AEMO
Immediately and clearly raise an objection with AEMO or the Chair of the meeting if a matter is discussed that the participant is concerned may give rise to competition law risks or a breach of this Protocol
Participants in AEMO meetings must not discuss or agree on the following topics:
Which customers they will supply or market to
The price or other terms at which Participants will supply
Bids or tenders, including the nature of a bid that a Participant intends to make or whether the Participant will participate in the bid
Which suppliers Participants will acquire from (or the price or other terms on which they acquire goods or services)
Refusing to supply a person or company access to any products, services or inputs they require

## Slide 3: Agenda
# | Time | Topic | Presenter
1​ | 10:00 – 10:05​ | Welcome​ | Peter Carruthers​
2​ | 10:05 -10:10 | Actions from Previous Meetings​ | Anne-Marie McCague​
3​ | 10:10 – 10:25 | Program Update | ​Rowena Leung
4 | 10:25 – 10:45 | Retail Go-Live Status | Graeme Windley
5​ | 10:45 – 11:00 | Readiness Implications | Greg Minney​
6 | 11:00 – 11:10 | Readiness Working Group Update​ | Greg Minney​
7​ | 11:10 – 11:25 | Contingency Planning - Summary of Feedback Received and Next Steps | Anne-Marie McCague
8 | 11:25 – 11:35 | Industry Risks and Issues – Impact of Retail Go-Live Date Change | Anne-Marie McCague
9 | 11:35 ​- 11:40 | Forward Meeting Plan | Anne-Marie McCague​
10 | 11:40​ - 12:00 | General Questions​ | Peter Carruthers​
11 | 12:00 | Meeting Close​ | Peter Carruthers​

## Slide 4: Welcome
Peter Carruthers

## Slide 5: Actions from Previous Meetings
Anne-Marie McCague

## Slide 6: PCF Actions
No. | Status | Action | Comment
32.4.1 | Closed | AEMO to incorporate likely 5MS CATS transaction volumes into scope for planned post day 1 performance testing | CATS transaction volumes from 5 MS rollout will be used as component of next round of 5MS volume testing
32.6.1 | Closed | AEMO to update Industry Risks and Issues Register in line with discussions at RWG and PCF. | 
32.7.1 | Open | AEMO to consider how the timeline could be compressed if an unknown issue arises that could impact 01-Oct-21 rule commencement. | Will be incorporated into program contingency planning.
32.7.2 | Closed | AEMO to confirm the impact of a change to the 5MS commencement date on other regulatory implementation programs. | Included in contingency impact assessments

## Slide 7: Program Update
Rowena Leung

## Slide 8: 5MS Program – IT Systems Status
Stream | Status | Commentary
Retail |  | Retail go-live milestone of 31-May-21 will not be met. Go-Live has been deferred until back-up date of 21-June-21 Further detail provided in next section.
Dispatch |  | 5MS Bidding Service went live on 1 April 2021. Participants may choose to submit 5-min bids (must be equal for a 30-min period). Pre-dispatch P5 – Fast Start Inflexibility Profile (FSIP) production go-live was scheduled for 03-May but has been delayed due to testing requirements by software certifiers. New go-live date is 07-July-21. 5MPD Price Sensitivity – deployment dates TBC with RWG. Planning to align with FSIP release date.
Settlements |  | Settlements systems was successfully deployed in the production environment on 16-May-21. Remains in 30-min mode until 01-Oct-21. Release included web changes, new APIs, dashboard for settlements direct and prudentials, and new look for invoices and statements.
Overall AEMO Status |  | Overall, the AEMO 5MS program remains Amber due to Retail platform delay.
 | Go-live date impacted
 | At risk
 | On schedule

## Slide 9: 5MS Program Timeline Readiness and Go-Live
As at 17 May 2021
Retail Go-Live on 31-May will be missed. Rescheduled for 21-June (see next slide)
Settlements Go-Live successfully completed on 16-May
User Acceptance Testing is in progress for Retail – update in next section
Day in the Life testing for Retail is complete
Retail Invitation Industry Testing progressing. Issues identified are being discussed with ITWG at calls x3 week. End-date to be extended as a result of Retail Go-Live delay.
Market Trial period Amber due to Retail Go-Live delay

## Slide 10: Proposed Updated 5MS Program Timeline
Retail Go-Live moved from 31-May to 21-June
Rule Commencement remains green but with heightened risk profile and subject to achievement of Retail go-live backup date
Retail Industry Test period extended from 21-May to 14-June
Market Trial period moved from 05-Jul – 28-Aug to 19-Jul – 10-Sep (TBC with RWG)
Market Trial prep milestone moved from 05-Jul to 12-Jul
Retail Industry Go-Live Plan will be reissued by 28-May. Cutover walk-through session will be rescheduled with RWG.

## Slide 11: Proposed Date Change to Milestones Impacted by Retail Go-Live to be discussed with RWG
ID | Description | Previous Date | New Date | Owner
L1-19 | AEMO Metering Solution – Go-Live | 31-May-21 | 21-Jun-21 | AEMO
L1-17 | 5MS Market Trial Commences | 05-July-2021 | [19-July-21] | AEMO
L1-9 | 5MS Market Trial Successfully completed | 27-Aug-2021 | [10-Sept-21] | AEMO
L2-RE30 | Retail MDM (incl. B2M) Industry Test Concludes | 21-May-2021 | 14-Jun-21 | AEMO
L2-RE35 | Industry Go-Live Plan Retail MDM final (reissue) | 10-May-21 | 28-May-21 | AEMO
L2-M24 | Retail MDM (incl. B2M) Go-Live | 31-May-2021 | 21-Jun-21 | AEMO
L2-M10 | 5 minute files in MDFF accepted by AEMO | 22-Jun-2021 | 22-Jun-21 | AEMO
L2-RE23 | 5MS Capability Market Trial preparation completed by participants | 05-Jul-2021 | 12-Jul-21 | Participants
L2-RE24 | 5MS Capability Market Trial preparation completed by AEMO | 05-Jul-2021 | 12-Jul-21 | AEMO
L2-RE31 | 5MS Capability Market Trial commences | 05-Jul-2021 | [19-Jul-21] | AEMO
L2-D10 | 5MS Capability Market Trial concludes | 27-Aug-2021 | [10-Sept-21] | AEMO

## Slide 12: Retail Go-Live Status
Graeme Windley

## Slide 13: Approach to Retail Status Updates
14-May
Retail No-Go Communicated to PCF via email
19-May PCF
Timeline replanning
Impacts of replan
Retail Checkpoint update
21-June
5MS Retail/ Metering Solution Go-Live
Key milestones
Communication timeline
07-May
PCF Update Session
01-June Exec Forum
Retail Checkpoint Update
Impacts of replan
14-June
Retail Go/No-Go Communicated to PCF via email
17-June PCF
Confirming Go/No-Go
Issue management
Contingency discussion if necessary

## Slide 14: Retail Checkpoint Criteria / Reasons for Delay
Criteria​ | Description | Status | Commentary
Testing | All UAT test cases executed with no critical defects that cannot be remedied for 31 May go-live. | Delayed | 5MS has had delays completing its final UAT cases, largely impacted by data issues from current MSATS data. Initial fixes supplied were not successful. We now have a different approach for these issues, and will proceed with the remainder of the test cases when these are fixed. These fixes will be delivered into the Pre-Production environment week commencing Monday 24 May, after which 5MS will complete profiling runs there.
Solution Stability | End-to-end solution operating stably in Test with no process blockers or unexplainable pauses/interruptions to processing. |  | Stability has improved, and enabled testing execution to progress. Improvements (i.e. defensive programming) introduced have been successful. Some initial stability issues were experienced in Pre-Production however AEMO is confident this has been tuned and therefore rectified.
Remediation | Known remediation work (internal reports performance, business activity monitoring) completed and remediation for any new defects scheduled. | In Progress | Internal work on Business Activity Monitoring has progressed well. Challenges continue to be experienced with Operational Reporting delivery that may impact business efficiency, but not presently expected to block go-live.
Performance | “Day in the Life Testing” completed with no performance issues identified that cannot be remedied for 31 May go-live. |  | All Day In The Life testing now completed, with the volumes ingested / outputted matched live industry requirements.
Production Cutover | Data migration on track and no blockers to meeting criteria/schedule for pre-production deployment. | Delayed | Data Migration to Production was delayed by the MSATS data issues, and would not have met 31 May deployment timelines.
Industry Test | On track to commence Retail Industry Test on 19 April. | In Progress | From industry testing two defects have been found that would significantly impact multiple participants, and therefore risk market function at the Platform go live. Both of these need development then testing by industry personnel: CH35 limit on filename – change into Pre-Production week commencing Monday 24 May. Settlement run output RM Reports not containing from and to dates – change into Pre-Production week commencing Monday 31 May (successful testing permitting)
Overall | 5MS has been impacted by COVID, which has slowed down defect fix rate. However over the last week three key personnel have returned to work |  | The Retail workstream is now red as it is not in a position to meet the 31 May 2021 eMDM Platform go-live date. There are currently no unresolvable items, but more time is required to resolve the data issues and deliver the functional changes for the industry.

## Slide 15: Retail Testing Progress
Observations:
UAT progress has been made in both test case execution and pass levels, now no more UAT first-time execution and 2% re-runs remaining.
Test execution productivity slowed due to the MSATS data issues.
Target is for all test cases to be executed by end-April was not met, however all PAE test cases have now been executed. It will be re-running failed tests to confirm resolution of outstanding defects.
AEMO will run Settlement runs in the MDM Pre-Production environment on conclusion of the PAE UAT execution and data defect resolution.
 | As at 16-Apr |  |  | As at 14-May |  | 
 | % Executed | % Executed Passed | % Total Pass | % Executed | % Executed Passed | % Total Pass
System Test | 100 | 100 | 100 | 100 | 100 | 100
System Integration Test | 96 | 99 | 95 | 100 | 99 | 99
User Acceptance Test | 95 | 96 | 91 | 100 | 98 | 98
Retail test metrics for go-live are provided for additional level of transparency and will help participants understand AEMO’s Retail platform progress towards go-live (see next slide).

## Slide 16: Next Steps
Special Executive Forum 1 June
  Include update on Retail progress against checkpoint criteria
Revised timeline discussion with RWG to be scheduled (aiming for Friday 28-May)
5MS Project Team available for one-on-one meetings to discuss individual participant impacts or dependencies as required – please contact the 5MS mailbox.

## Slide 17: Readiness Implications
Greg Minney

## Slide 18: Readiness Implications – for discussion
Area | Activity | Implication / Impact
5MS Market Trial | Market Trial Commencement | Start date of market trial 19/7 (TBC). Alignment of full 5-minute bidding to Market trial timing
 | Market Trial Period | Market trial period maintained Reduced timeframe between completion of Market Trial and Market Start, but no 5MS industry-wide activities compromised by this
Metering Transition | 5 Minute Metering Data delivery (to AEMO) | Milestone date remains as 22/6 unchanged, minimal impact to participant transition period
 | Metering Installation and configuration | No dependency on Retail Platform delivery, no impact to transition
 | GS NMI classification and NONCONUML population and data delivery | Capability available 21/6, minimal impact to individual participants, majority of rollout plans indicate July, August population and activation
 | Tier 1 Basic Metering Data | No dependency on Retail Platform delivery, no impact to transition
Participant Transition | Bi Lateral Testing | No impact – retail pre-prod environment remains available
 | 5 Minute Metering Delivery (b2b) | No impact – subject to participant agreement, not dependent on Retail Platform delivery
5MS Rule Commencement |  | Increased risk profile for Retail deployment and change to market trial start dates. Transition impact to be confirmed with RWG/TFG

## Slide 19: Readiness Working Group Update
Greg Minney

## Slide 20: 5MS Rule Commencement – Round 7 as at 14/5 – updated for Retail platform
 | On track | On track for commencement date
 | Risk 1 – Risk to major milestones or deliveries | Remediation or contingency activation required to ensure on track delivery for Rule Commencement
 | Risk 2 – Risk to rule commencement | Cannot be addressed with available contingencies to be on track for commencement date
Activity | Status | Comments
AEMO Business Readiness for 5MS and GS (Part A) |  | Bidding Platform deployed to Production 1 April Retail Platform go-live rescheduled to 21 June AEMO Program rated Amber for Retail Go-Live Settlements platform scheduled 17 May – On-Track Rescheduling of platform deliveries is not expected to impact 5MS Rule commencement or 5MS market trials.
Essential Industry Capabilities for 5MS commencement (Part A) |  | On track for 1 Oct 21 commencement Metering Service Providers (MCs, MPs, MDPs) generally reporting on track, metering installation and configuration well progressed One MSP highlighting their program as Amber against MTP criteria Generators reporting on-track
Summary: 5MS Rule Commencement |  | Overall, Industry and AEMO components of essential capability is rated as on track for 5MS Rule commencement, noting the rescheduling of the AEMO Retail Platform, and Market trial commencement. The heightened risk profile is noted, with the risk that further slippage may impact critical path transitional activities, along with individual participant impacts.
Other industry capabilities for 5MS and GS (Part B) |  | Other Participant readiness activities proceeding in line with 5MS and GS rule commencements Individual participant readiness risks noted in regards Global Settlement activities, with no systemic risks
On track
On track
On track
Risk 1
Risk 2
Risk 1
On track

## Slide 21: Part A 5MS Essential Capability – round #7 as at 14/5
Responsible Participant | Essential Criteria | Status | Comments
Generator | Generators and MNSPs are able to submit 5-min offers |  | 17 Generators representing 95% of NEM volume reporting on-track 15/17 intend to participate in Market Trials Average program completion in range 50-74% One key participant is currently not providing a readiness report, impact on criteria to be established 16/17 intend to commence 5 minute bidding within transition period, initial deployments have occurred Progress reported for UFE allocation trails other retailer specific capability progress
MP, MC, MDP | All essential meters* are able to produce and store and deliver 5-min data |  | One MSP is reporting on track against compliance obligations but amber against AEMO MTP readiness criteria due to minimal schedule contingency. AEMO discussing contingency approach with the MSP Previous “late” status recovered by MP ​Rollout plans received for 99% of Tranche 1 meters, with all plans indicating completion prior to 1 October, 40% of meters currently 5 minute capable, updated plans received 1 May and will include tranche 1 metering delivery
AEMO | The 5-minute bidding and dispatch solution, including the web bidding interface is deployed |  | AEMO Platform deployed 1 April, to commence bidding transition period
 | The Metering Data Management (MDM) solution is deployed |  | Mitigation Action: Retail Platform Deployment rescheduled to 21 June, criteria rated Amber reflecting ongoing delivery risk and potential impact to dependent activities
 | The 5-minute settlements solution is deployed |  | AEMO Settlement Platform 30 minute deployment scheduled for 17th May Industry testing in progress Certification testing of platform successfully completed
Summary - Essential Criteria | - | - | Overall essential criteria for 5MS rule commencement rated as on track. AEMO’s Metering platform ratings reflect the shift in planned go-lives and noting the risk to critical path of transitional activity. Individual participant exceptions are noted in essential capability categories for Metering service provision
 | On track | On track for commencement date
 | Risk 1 – Risk to major milestones or deliveries | Remediation or contingency activation required to ensure on track delivery for Rule Commencement
 | Risk 2 – Risk to rule commencement | Cannot be addressed with available contingencies to be on track for commencement date
On track
Risk 1
Risk 2
On track
On track
On track
Risk 1
On track
On track

## Slide 22: Part B – Other Industry Capabilities – Round #7 as at 14/5
Responsible Participant | Criteria | Status | Comments
Retailer | Receive and process 5-minute metering data. Receive and process 5-minute settlement data. |  | All responding retailers (17, representing 85 % of retail load) reporting ‘On track’. Coverage lower this round with one major retailer not reporting 16/17 retailers plan to participate in Market trials. 5 intend to receive 5min data pre 1 Oct 10/17 intend to perform in Bi-Lateral Testing, 1 Q1, 7Q2 commencement 16/17 ‘On-track’ for 5 min settlement data, with 1 late 1 at risk for UFE Allocation
DNSP | Receive and process 5-minute metering data. |  | 10/10 DNSPs reporting ‘On track’ to receive 5-minute data and planning on participating in market trials.
 | Provide GS metering and standing data updates (incl. NCONUML). |  | 10/10 DNSPs reporting overall program ‘On track’ with average program completion of 50-74% Some DNSPs in Victorian Jurisdiction are reporting at risk or late for GS Data population, with impact assessments requested re timing and energy volumes Type 7 Metering Data “On Track” 1 Participant reporting ‘At-risk’ for the delivery of NCONUML,
TNSP | Receive and process 5-minute metering data |  | 6/6 TNSPs reporting ‘On track' to receive 5-minute data 2/6 have the intention to receive 5-minute data prior to the Rule commencement date
 | Provide GS metering and standing data updates |  | 6/6 reporting ‘On track’.
MDP | Provide 5-minute metering data T1-3 distribution connected meters, type 7 meters. |  | 16/17 MDPs reporting ‘On track’, representing 100% coverage of Tranche 1 NMIS 1 participant ‘At risk’, recovery plan is in place 17/17 MDPs report ‘On track’ for the delivery of interval metering data by 1 October, including 1 MDP flagging “A risk” for delivery of T1-3 customer meters
 | Provide type 4, 4A, Vic Ami metering data at 5-minute granularity by 1 December 2022 |  | Majority of Roll-out scheduled to commence 3rd quarter of 2021. Rollout plans requested from impacted participants by 1 March 2021 100% of MDPs reporting ‘On track’ for interval meter delivery by Rule commencement.
 |  |  | 3 MDPs reporting ‘Completed’, 6 MDPs reporting “On Track” 1 MDP reporting ‘Late’, with plan to commence delivery prior to 1 Oct and expected impact on small number of meters
 | Provide basic metering data for tier 1 NMIs to AEMO. |  | 3 MDPs reporting ‘Completed’, 6 MDPs reporting “On Track” 1 MDP reporting ‘Late’, with plan to commence delivery prior to 1 Oct and expected impact on small number of meters
MP, MC | All T1-3,4* meters are able to produce and store 5-minute data. |  | 18 /19 MPs representing tranche 1 meters reporting ‘On track’, 1 reporting ‘Late’ with a stated remediation plan 16 Rollout plans covering 93% of tranche 1 meters received, 25% of tranche 1 meters currently 5 minute capable.
Summary | - | - | Overall summary “on track” for 5MS rule commencement , no systemic issues identified, individual exceptions noted for some participants with impact on initial values of UFE reported for those profile areas
On track
On track
On track
On track
On track
On track

## Slide 23: RWG/TFG/ITWG Update
RWG:
  Bring forward next RWG to 26th May (TBC)
  Confirmation of milestone dates for remainder of program
  Metering Transition plan impact assessment
  Retail go-live plan updates for approach and timing
    Walk though of Retail go-live plan will be rescheduled
  Settlements go-live Debrief
ITWG:
  Market Trial Scenarios and planning
  Invitation industry testing for retail
TFG:
  Special TFG to confirm updated plan and timeline

## Slide 24: Industry Test Progress
Settlements Industry Testing
3 settlement runs provided for industry consumption from current MSATS platform:
  Runs can be compared to production run at same point in time
  Forms basis of settlement platform operation at platform go-live (17th May)
Further 3 Settlement runs to be provided for industry consumption from new Retail Platform from 24th May
  Runs will also provide opportunity to compare against equivalent production settlement runs
  Forms basis of settlement operation against retail platform from 21st June, and is included in assessment of retail platform readiness
All settlements industry testing performed @ 30 minute as this is basis of platform go-live
Retail Invitation Industry testing:
Industry test period to continue to support participant readiness in ​preparation for 21 June go-live
  Participant confirmation of key issues
  Continuation of participant testing

## Slide 25: Market Trial Planning
Market Trial Focus Group established to develop initial view of industry scenarios to agree scope of 5MS market trial
Initial MTFG Session (29th March) identified suggested priority scenarios
AEMO to provide scenario plan by execution week including consideration of extension trial runs
Scenarios identified to date include:
30-5 minute settlement week (5 days 30 / 2 days 5 minute)
Daily / weekly operation of 5 minute settlement operations
Bidding scenarios incorporating price sensitivities, rolling sum pricing, intervention data
Metering scenarios in general to support settlement testing scenarios
UFE reports run on the basis of available test data , so can be tested for functionality not data outcomes
Consideration to be given to incorporating scenarios where execution enables some level of customer switching support
Issues and exceptions arising will not be addressed by 5MS program
Enables some co-ordination of activity between participant groups
Once scenarios agreed, industry participation and pairing will be established.

## Slide 26: Contingency Planning - Summary of Feedback Received and Next Steps
Anne-Marie McCague

## Slide 27: Reminder of Contingency Options and Scenarios
At the last PCF three contingency options were discussed:
Option 1: Move the commencement date for all aspects of 5MS rule
Option 2: Move the start date for a subset of the 5MS rule (i.e. for AEMO settlement only)
Option 3: Resettle the market at 5-min
At the RWG on 04-May two timeline scenarios were discussed:
Scenario 1: Short Slippage – 4 weeks max
Scenario 2: Slippage longer than 4 weeks

## Slide 28: Summary of Feedback (1)
19 responses were received (some represented multiple participants)
10 responses indicated a preference for Option 1
  2 noted that the benefits included the simplistic approach
  4 noted that moving the date to 01-Nov and aligning B2B 3.5/3.6 would be more efficient
    1 noted WDR and CS should also be aligned
  3 noted, this approach is not favoured as it extends their transition period which increases costs
  1 noted that in the case of a delay, the date should be set to avoid the summer period which could potentially mean post Q1 2022
4 responses indicated a preference for Option 2
  1 noted that this option (and option 3) should not be used if commencement is in December as it would coincide with business shutdown period
  Partial deployment could be challenging given the interdependencies between 5MS and WDR/CS (3) and for 1 respondent the deployment is a linked go-live across their systems (noted for Option 3 also)
  1 noted that this may result in a compression of metering readiness activities
  2 noted the potential impact to the financial market (this was also noted for Option 3)
2 responses indicate a preference for Option 3
  1 responses considered that this option works best for financial products however 2 considered the impact higher
  Complexity of solution was not favoured by 4 responses
  5 responses raised concerns that this may add risk to prudentials, cashflow, reconciliation and settlements.
3 did not provide a clear preference.

## Slide 29: Summary of Feedback (2)
Impact to Global Settlement commencement dates:
  Wide range of dates from no reduction in the soft-start period (1), 1 month (1), 2 months (3), 3 months (1) to 20 weeks (1). 1 response noted that a 5MS date change does not necessarily need to lead to a GS date change and that the two could be combined.
Notice period:
  2 responses noted that a notice on whether the rule commencement date was changing or not should be provided by 14-June
  Wide range of notice periods for new date: 5 months (1), 4 months (2), 3 months (3), 10 weeks (1), 2 months (2), 4 weeks (1), 3 weeks (1)
  8 responses noted that certainty of go-live date was important while 4 responses noted that the reduction in the overall delay was of more importance.
Impacts to Regulatory Implementation Roadmap
Numbers in brackets denote the number of responses

## Slide 30: Conclusions and Next Steps
A wide variety of responses were received from participants on each of the topics, without consensus emerging
Conclusions/themes emerging from the feedback include the following:
  Option 1 was the most supported option. Option 3 flagged as having negative impacts by multiple participants.
  No clear distinction emerged for preferred options in the event of a short delay vs a longer delay.
  GS soft start transition period is currently 7 months. Support exists for a shorter transition period, in the range of 4 - 5 months – but not unanimous.
  Advanced notice period emerged as a theme, with support for notification in the June timeframe – although not unanimous.
  Certainty of go-live date emerged as important for a number of participants (planning and resource deployment) – consistent with feedback on the advanced notice period. But counter-balanced by some participants seeking to minimise delays (cost implications).
Next Steps: AEMO, AEMC and AER to consider feedback in detail and align on an approach for short delay and long delay scenarios Update to be provided at the special Executive Forum, direction from market bodies required by early-mid June timeframe

## Slide 31: Industry Risks and Issues – Impact of Retail Go-Live Date Change
Anne-Marie McCague

## Slide 32: Industry Risks and Issues - Trend
The purpose of this session is to review the impact of the delay to the Retail Go-Live on the key PCF risks
The risk review will take into account the three key areas of risk:
  Retail delay
  AEMO and industry readiness
  Volume of regulatory change

## Slide 33: Retail Risk
Risk ID | Description | Current Residual Rating | Comments
R33 | Further delays to AEMO Retail Systems impact 5MS rule commencement critical path There is a risk that further delays beyond those identified put the critical path through market trial to 5MS rule commencement (01-Oct-21) at risk | Significant | Trend is now worsened Re-scheduling of the Retail Platform go-live heightens the risk profile for the 5MS commencement date. Recommend the Residual Likelihood be increased from Unlikely to Possible. This increases the residual rating to Critical.
​ | Improving​ ​ No Change /Stable​ ​ Worsened ​
Issue ID | Description | Rating | Mitigations
I12 | No Remaining Contingency for Retail Deployment Issues identified during Dress Rehearsal 2 and Azure migration coupled with existing Retail timeline challenges mean that delays have occurred within the 5MS Retail workstream. There is no schedule contingency within this workstream to compensate for the time needed to remediate these issues therefore the scheduled go-live of 31-May-21 will not be met. | High | Remains High Trend is now worsened with further delay

## Slide 34: AEMO & Industry Readiness
Risk ID | Description | Current Residual Rating | Comments
R34 | Delay to AEMO 5MS Retail impacts participants readiness There is a risk that the delayed availability of the 5MS Retail solution impacts participants readiness programs resulting in delays in some participants programs. | Significant | Risks to participant readiness are expected to be heightened due to timeline compression. Trend is worsened. Readiness Round 8 will be issued 02 June. Participants will be requested to assess their readiness against the updated timeline. This will provide a view on the impact of the Retail delay on participant programs.
R11 | The AEMO business and operations are not ready for 5MS Rule Commencement on 1 Oct 21 The AEMO business may not be ready to deliver the full extent of the 5MS deliverables by 5MS and GS rule commencement including business processes and resource training, results in failure of Go Live for 5MS and GS Program | Significant | Pressures remain on business readiness due to delays in Testing and internal readiness, trend should be remain Worsened. This will be further assessed and reported through Readiness Round 8.
R19 | Risk of a critical mass of participants not being ready at identified critical path milestones Critical capability of participants fail to meet expected industry Readiness critical path milestones, resulting in failure to be ready for go-live and impacting the proper functioning of the market. | Medium | As R34.
​ | Improving​ ​ No Change /Stable​ ​ Worsened ​

## Slide 35: Volume of Regulatory Change
Risk ID | Description | Current Residual Rating | Comments
R37 | New 5MS Retail Solution Go-Live Dates impact other regulatory change programs There is a risk that the changes to the 5MS retail timeline may have impacts on other AEMO change programs (e.g. Customer Switching or WDR) which may result in a need for those programs to replan having knock-on effects to the industry. | Medium | No direct impact to the regulatory roadmap as a result of the deferral of the Retail go-live until 21-June. However, heightened risk profile exists for flow-on consequences from any further delays Risk was closed at last session but has been reopened as it is now live again
R06 | Interaction with other industry changes that have already been adopted through rule changes Significant regulatory changes across the energy sector will stretch resources allocated to market change programs, resulting in potential impacts to participants resourcing and program delivery. | Significant | New Retail go-live date does not impact this risk
R09 | Impact to 5MS from other rule changes that are being considered Future rule changes could affect the implementation of 5MS, resulting in impacts to industry program implementation timelines | Significant | Retail delay does not impact this risk.
R30 | Risk that new 5MS and GS Go-Live dates could impact other industry change programs The new commencement dates are closer to some other industry change programs. There is a risk that industry and AEMO resources and systems may be constrained during a period of multiple major go-lives which may lead to difficulties with timelines and system stability. | Significant | Rule commencement dates are not impacted by the Retail Go-live date change; therefore this risk is directly not impacted. However, heightened risk profile of flow-on consequences to other regulatory initiatives is noted. Recommend trend is changed to worsened.
​ | Improving​ ​ No Change /Stable​ ​ Worsened ​

## Slide 36
Are there any new risks or issues to be raised?

## Slide 37: Forward Meeting Plan
Anne-Marie McCague

## Slide 38: High-Level Plan for 2021
Month | Topics | Month | Topics
January | AEMO go-live decision making process Risk Review Readiness and go-live dashboard | 17 June | Market Trial prep status Debrief on Retail Go-Live* Retail Cutover Preparation Status
18 February | Retail Solution Status Exec Forum Agenda | 23 July | Market Trial progress Readiness Reporting #8 Debrief on Retail Go-Live*
18 March | Dispatch Cutover Preparation Status Readiness Reporting #6 Retail Checkpoint Criteria – assessment and outcomes Retail Pre-prod – status and go/no-go date Retail Production go-live – checkpoint date and criteria Settlements Certification Process Conclusions | 19 August | Market Trial progress Risk Review – focus on rule commencement Exec Forum Agenda
23 April | Debrief on Dispatch go-live Settlements Cutover Preparation Status Risk Review Retail Checkpoint Criteria – assessment and outcomes Retail Production go-live – confirmation of go/no-go date | 16 September | Results of Market Trial Preparing for 1 Oct – Ind Go-Live Plan review Readiness Reporting #9
19 May | Readiness Reporting #7 Exec Forum Agenda Approach to Global Settlements engagement – due to focused efforts in the Retail workstream, this discussion will be postponed until at least August. Retail Production: Confirming go/no-go Retail Cutover Preparation Status* - postponed | 22 October | Debrief and reconfirmation of approach for Global Settlements
This table provides a list of key topics. The normal updates will also be provided at each PCF. This table will evolve as the year progresses.
*Dates depend on Go/No-Go notice

## Slide 39: Upcoming Meetings AEMO | Program Calendar and Timelines
Current as at 11/05/2021

## Slide 40: General Questions
Peter Carruthers

## Slide 41: Meeting Close
Peter Carruthers