## Slide 1: 5MS & GS Program Consultative Forum – Special Session – 33a
Friday, 4 June 2021
This meeting is recorded for the purpose of minute taking.
Please disconnect from your workplace VPN for the WebEx call​

## Slide 2: AEMO Competition Law Meeting Protocol
Under no circumstances must Participants share Competitively Sensitive Information. Competitively Sensitive Information means confidential information relating to a Participant which if disclosed to a competitor could affect its current or future commercial strategies, such as pricing information, customer terms and conditions, supply terms and conditions, sales, marketing or procurement strategies, product development, margins, costs, capacity or production planning.
AEMO is committed to complying with all applicable laws, including the Competition and Consumer Act 2010 (CCA). In any dealings with AEMO regarding proposed reforms or other initiatives, all participants agree to adhere to the CCA at all times and to comply with this Protocol. Participants must arrange for their representatives to be briefed on competition law risks and obligations.
Participants in AEMO discussions must:
Ensure that discussions are limited to the matters contemplated by the agenda for the discussion
Make independent and unilateral decisions about their commercial positions and approach in relation to the matters under discussion with AEMO
Immediately and clearly raise an objection with AEMO or the Chair of the meeting if a matter is discussed that the participant is concerned may give rise to competition law risks or a breach of this Protocol
Participants in AEMO meetings must not discuss or agree on the following topics:
Which customers they will supply or market to
The price or other terms at which Participants will supply
Bids or tenders, including the nature of a bid that a Participant intends to make or whether the Participant will participate in the bid
Which suppliers Participants will acquire from (or the price or other terms on which they acquire goods or services)
Refusing to supply a person or company access to any products, services or inputs they require

## Slide 3: Agenda
# | Time | Topic | Presenter
1​ | 14:00 – 14:05 | Welcome, Introductions and Apologies | Peter Carruthers
2 | 14:05-14:20 | Retail Status Update | Graeme Windley
3 | 14:20 – 14:25 | Next Steps | Peter Carruthers
4​ | 14:25 – 14:30 | General Questions | Peter Carruthers
5 | 14:30 | Meeting Close | Peter Carruthers

## Slide 4: Welcome
Peter Carruthers

## Slide 5: Approach to Retail Status Updates
14-May
Retail No-Go Communicated to PCF via email
19-May PCF
Timeline replanning
Impacts of replan
Retail Checkpoint update
21-June
5MS Retail/ Metering Solution Go-Live
Key milestones
Communication timeline
07-May
PCF Update Session
01-June Exec Forum
Retail Checkpoint Update
Impacts of replan
11-June
Retail Go/No-Go Communicated to PCF via email
17-June PCF
Confirming Go/No-Go
Issue management
Contingency discussion if necessary
04-June PCF Update
Retail Checkpoint Update

## Slide 6: Retail Status Update
Graeme Windley

## Slide 7: Retail Checkpoint Criteria against 21 June Go-Live
Criteria​ | Description | Status | Commentary
Testing | All UAT test cases executed with no critical defects that cannot be remedied for 21 June go-live. | Delayed / In Progress | 5MS has had delays completing its final UAT cases, largely impacted by data issues from current MSATS data. Numerous fixes deployed have been successful in unblocking the changes in the lower environments enabling PAE to run successfully again. AEMO is in the process of applying these fixes to the Pre-Production environment, however this has held up the delivery of 3 x Settlements run in Pre-Production for Industry testing.
Solution Stability | End-to-end solution operating stably in Test with no process blockers or unexplainable pauses/interruptions to processing. |  | Stability has improved, and enabled testing execution to progress. Improvements (i.e. defensive programming) introduced have been successful. Some initial stability issues were experienced in Pre-Production however AEMO is confident this has been tuned and therefore rectified.
Remediation | Known remediation work (internal reports performance, business activity monitoring) completed and remediation for any new defects scheduled. | In Progress | Internal work on Business Activity Monitoring and Operational Reporting have progress to the point where the program has a solution capable of meeting Production requirements and will continue to deploy these internally over the next few weeks. In addition, the 5MS program has also been impacted by COVID, with multiple team members either in India or with family members in India impacted by the virus and needing time off work. This has slowed down issue resolution, however the situation is improving.
Performance | “Day in the Life Testing” completed with no performance issues identified that cannot be remedied for 21 June go-live. |  | All Day In The Life testing now completed, with the volumes ingested / outputted matched live industry requirements.
Production Cutover | Data migration on track and no blockers to meeting criteria/schedule for pre-production deployment. | In Progress | Data Migration to Production is progressing on schedule to 21 June, noting adjustments were required due to the MSATS data issues.
Industry Test | Performance of the solution within industry test meets expectations | Delayed | From industry testing two defects have been found that would significantly impact multiple participants, and therefore risk market function at the Platform go live. Both of these have been developed by AEMO: CH35 limit on filename – change in Pre-Production Settlement run output RM Reports not containing from and to dates – change now due into Pre-Production Wednesday 9 June (successful testing permitting) As above, delivery of 3 x Settlements runs have been delayed due to the MSATS data issue impacts.
Overall |  |  | 21 June is amber as a result of the issues listed above. Retail platform test status shown overleaf.

## Slide 8: Retail Test Status
Status Provided at the Exec Forum
Testing has resumed following remediation of the MSATS data issues
Indicated accordingly that we were more confident than not that go-live on 21 June would proceed
Status Since Exec Forum
Testing has continued in the 5MS lower environments
However, we are still bedding in the changes and promoting those changes through the environments
As such, we are yet to make available Settlements runs to industry in Pre-Prod
We anticipate providing these Settlements runs on Tuesday and Thursday of next week
Successful delivery of these runs is evidence of readiness of the end-to-end process for production go-live
We are optimistic but not certain that these Settlements runs will be made available
Conclusion
Progress since the Executive Forum is positive but slower than we would like
The time available to successfully demonstrate that our data issues have been satisfactorily resolved is less, and therefore we now regard the time remaining until go-live decision as tight

## Slide 9: NCONUML Functionality Update
AEMO’s priority is to maintain the 21 June Retail go-live release.
As discussed with the RWG, AEMO noted that AEMO UAT needed to be complete prior to the testing of NCONUML. As reported in the previous section, UAT is ongoing.
AEMO is confirming that the NCONUML functionality will be delivered in a release post the Retail go-live on 21 June.
The NCONUML release date will be confirmed with PCF on 17 June but will be beyond 5 July.
Impacted Metering Transition Plan activities will be revised in line with revised release date.
AEMO recognises that this compressed timeline for the NCONUML activities may cause potential compliance issues for some participants
AEMO is investigating ways to mitigate this impact

## Slide 10: Next Steps
Peter Carruthers

## Slide 11: Next Steps
AEMO will bring forward the Go/No-Go statement to 11 June
Go: cutover will commence as scheduled
No/Go: AEMO will discuss revised timeline and contingency plan with PCF on 17 June
Next Executive Forum 7 July
PCF pack will be circulated on 15 June as slides are dependent on Go/No-Go status

## Slide 12: General Questions
Peter Carruthers

## Slide 13: Upcoming Meetings AEMO | Program Calendar and Timelines
Current as at 03/06/2021

## Slide 14: Meeting Close
Peter Carruthers