## Slide 1: 5MS & GS Readiness Working Group #15 (incl. Systems Working Group)
Tuesday13th October 2020
WebEx only: **Please disconnect from your workplace VPN for the WebEx call**
PLEASE NOTE THIS MEETING WILL BE RECORDED FOR THE PURPOSE OF PREPARING MINUTES

## Slide 2: AEMO Competition Law Meeting Protocol
AEMO is committed to complying with all applicable laws, including the Competition and Consumer Act 2010 (CCA). In any dealings with AEMO regarding proposed reforms or other initiatives, all participants agree to adhere to the CCA at all times and to comply with this Protocol.
Participants must arrange for their representatives to be briefed on competition law risks and obligations.
Participants in AEMO discussions must:
Ensure that discussions are limited to the matters contemplated by the agenda for the discussion
Make independent and unilateral decisions about their commercial positions and approach in relation to the matters under discussion with AEMO
Immediately and clearly raise an objection with AEMO or the Chair of the meeting if a matter is discussed that the participant is concerned may give rise to competition law risks or a breach of this Protocol.
Participants in AEMO meetings must not discuss or agree on the following topics:
Which customers they will supply or market to
The price or other terms at which Participants will supply
Bids or tenders, including the nature of a bid that a Participant intends to make or whether the Participant will participate in the bid
Which suppliers Participants will acquire from (or the price or other terms on which they acquire goods or services)
Refusing to supply a person or company access to any products, services or inputs they require.
Under no circumstances must Participants share Competitively Sensitive Information. Competitively Sensitive Information means confidential information relating to a Participant which if disclosed to a competitor could affect its current or future commercial strategies, such as pricing information, customer terms and conditions, supply terms and conditions, sales, marketing or procurement strategies, product development, margins, costs, capacity or production planning.

## Slide 3: Agenda
Greg Minney

## Slide 4: Agenda (1/2) **Please disconnect from your workplace VPN for the WebEx call**
#` | Time | AGENDA ITEM | Responsible
1 | 10:00 – 10:05 | Welcome, introduction and apologies | Greg Minney
2 | 10:05 – 10:10 | Agenda | Greg Minney
3 | 10:10-10:20 | Minutes/Actions | Anne-Marie McCague
General Update |  |  | 
4 | 10:20 – 10:30 | 5MS Program Update | Greg Minney
5 | 10:30 – 10:35 | Procedure update | Simon Tu
6 | 10:35 – 10:45 | Testing Update | Tui Grant
Dispatch / Bidding Readiness |  |  | 
7 | 10:45 – 10:50 | Dispatch / Bidding Update | Ian Devaney
8 | 10:50 – 11:00 | Dispatch and Bidding Go-Live Plan | Greg Minney
Settlements Readiness |  |  | 
9 | 11:00 – 11:05 | Settlements Update | Mark Hillaby
Retail / Metering Readiness |  |  | 
10 | 11:05 – 11:10 | Retail / Metering Update | Jim Agelopoulos
11 | 11:10 – 11:15 | RM20 PPS Report Simplification | Paul Lyttle
12 | 11:15 – 11:25 | Transition Focus Group Update | Blaine Miner
13 | 11:25 – 11:30 | Retail Go-Live Plan | Greg Minney
Meeting Closing Items |  |  | 
14 | 11:30 – 11:35 | Forward Plan and Other Business | Greg Minney
15 | 11:35 – 11:40 | Upcoming meetings/ focus groups | Anne-Marie McCague
16 | 11:40 | Meeting Close | Greg Minney

## Slide 5: List of Appendices
A1: L2 Readiness Milestones

## Slide 6: Minutes & Actions
Anne-Marie McCague

## Slide 7: RWG Actions
No. | Status | Action | Comment
15.3.1 | Closed | RWG to identify existing wholesale representative for the Market Systems User Group (MSUG) and contact 5MS mailbox if there is no existing representative | Nominations have been received and the invitation has been circulated. Meeting will be 14 Oct.
15.3.2 | Open | RWG to provide feedback on the proposed settlements platform go-live date of 19 April 2021, including any impacts to participants’ programs, testing requirements, and any suggested mitigations | Feedback due 23 Oct. All feedback received to date is that there is no impact.
15.7.1 | Closed | RWG to inform AEMO if their organisation is able to assist AEMO with preparing the testing approach, or executing formal invitation testing of the retail platform | Nominations received – AEMO will contact the nominees.
15.7.2 | Closed | RWG to provide a list and description of any required testing that cannot be carried out in 5MS Staging, is unacceptably complicated by the requirement to repoint from one environment to another, and cannot wait until the functionality has been deployed into the pre-production environment | Feedback received to date does not identify issues. Will close this action but participants may get in contact at any point if issues arise as per the Issue mitigation measures.
15.7.3 | Closed | AEMO to update the Industry Risks and Issues Register with the mitigation measures agreed at the RWG | Complete
15.12.1 | Closed | RWG to provide feedback on proposed simplification to the RM20 PPS Report | Feedback received from 4 participants. Update provided in section 11 of this pack.
15.13.1 | Closed | RWG to nominate Cutover Focus Group members | Nominations received – invitations will be circulated for 16 Oct.

## Slide 8: Program Update
Greg Minney

## Slide 9: 5MS Program Timeline Level 1 and External Level 2 Milestones 1/2
Current as at 18-09-2020

## Slide 10: 5MS Program Timeline Level 1 and External Level 2 Milestones 2/2
Current as at 18-09-2020

## Slide 11: AEMO Systems Deployment Cutover Risk - Update
Risk Description | Risk Assessment |  | 
The current Cutover approach has the 3 AEMO systems deployments in close succession. Retail Metering the largest, most technically complex and riskiest cutover going first on 9 March, then followed by both the Dispatch and Settlements systems deployments together 3 weeks later, on 1 April. A go-live criteria for Settlements is a stable metering platform. The current timetable only allows one week for the Retail solution to be stabilised prior to commencing cutover activity for Settlements which is high-risk. | Inherent Likelihood | Inherent Consequence | Inherent Risk Rating
 | Possible | Major | Significant
 | Residual Likelihood | Residual Consequence | Residual Risk Rating
 | Unlikely | Moderate | Medium
AEMO has presented the proposal to change the deployment date for the Settlements solution to 19 April 2021 to the PCF and RWG.
To date there has been no feedback received.
AEMO has organised a Market Systems User Group (MSUG) for 14 October to review upcoming changes to the data model, including both 5MS and non-5MS changes (such as MT-PASA).
AEMO requests participant feedback on the proposed date change after the MSUG has taken place by 23 October 2020 to allow for discussion at the November PCF.
AEMO does not see a reason not to make this change, but will not confirm this until the MSUG session has concluded.

## Slide 12: Integrated WDR & Customer Switching Timeline
The integrated timeline for Wholesale Demand Response (WDR) and Customer Switching was presented at the PCF on 01-Oct
Key dates:
  5MS: 01-Oct-21 (rule commencement)
  CS: 01-Oct-21 (go-live)
  WDR: 24-Jun-21 (open for registration)
  WDR: 24-Oct-21 (go-live)
System impacts were also presented
PCF pack is available on PCF webpage
WDR and CS teams requested feedback from PCF by 09-Oct-20
WDR has established a Consultative Group. To join, or for any WDR related queries/feedback: WDR@aemo.com.au
For queries/feedback related to Customer Switching: ERCF@aemo.com.au

## Slide 13: Procedure update
Simon Tu

## Slide 14: 5MS/GS-related procedure change log
Procedure issue | Status | Final Determination Date
Proposed procedural change to MDFF quality flag (N flag)* | Consultation commenced 6 August, anticipated to be concluded early December. | December 2020
New NCONUML NMI Class codes available in list for SORD.​ | To become part of broader requirements for the changes to the SORDs (v3.5 of the procedures) currently scheduled for an effective date of 10 Nov 2021.​ | 22 July 2020
Proposal for RWD | Part of MSATS Standing Data Review. Final Determination has been published. | Published – 7 September 2020
Removal of end user details from inventory table | Consultation commenced 6 August, anticipated to be concluded early December. | December 2020
TNI 2 for cross-boundary meters* | Part of MSATS Standing Data Review. Final Determination has been published. | Published - 7 September 2020
Removal of register ID = suffix requirement | Consultation commenced 6 August, anticipated to be concluded early December. | 7 December 2020
5MS Procedures washup | Consolidation to open for comment 1 May 2021. | 1 July 2021
Proposed change to MSATS: MDM Procedures and Understanding Load Profiles Published from MSATS document to clarify existing requirements for the 5 minute load profile and RM reports. | Consultation commenced 12 October, anticipated to be concluded mid March 2021. Included in package of the Retail Procedures (Wholesale Demand Response) consultation. | March 2021
*raised by the 5MS Program

## Slide 15: 5MS/GS-related procedure change log
Procedure issue | AEMO Retail Systems Impact | Available in Staging | Readiness Considerations
MDFF file size and transaction limit in file* | 10MB file size supported for B2M MTRD for Mkt Settlements. 10MB file size supported for B2B MTRD for B2B Mkt Activities. | R30 - 31-Aug-20 - Staging environment supports B2B Transaction (SORD, CUST, MTRD etc) exchange between Participants. | Participant Mkt Systems must be capable of accepting 10MB B2B MTRD files unless a bilateral agreement is in place,
New NCONUML NMI Class codes available in list for SORD. | System impacts are yet to be identified. | TBD: Dependant on evaluation of system impacts and finalisations of v3.5 of the B2B Procedures: Service Order Process. | TBD
Proposed procedural change to MDFF quality flag (N flag)* | Rejection of B2M MTRD MDFF meter reads where quality flag is ‘N’. Results in B2M MTRD Transactions with the status of ‘Partial’ or ‘Rejected’. | R1 - 1-Dec-19 - Support for new B2M MTRD validations. | Participant Mkt Systems must not send ‘N’ for B2B or B2M MTRDs.
Proposal for RWD | No impact to 5MS Retail systems. | N/A | ReadTypeCode amended from ‘Optional’ to ‘Required’. Fourth character added to identify whether a meter is capable of reading at five-minute granularity.
Removal of end user details from inventory table | No impact to 5MS Retail systems. | N/A | N/A
TNI 2 for cross-boundary meters*# | CATS CR support for TNI2 field. MSATS Browser to support display TNI2 for NMI Discovery Transactions. aseXML schema support extension to support TNI2 inclusion (r39). | R18 and R19 - 31-Aug-20 - Support for TNI2 for CATS CRs. | TNI Code assigned, by AEMO, however Participants to undertake the generation of associated CR2xxx transactions, to register a cross boundary meter using TNI 2. Migration to r39 aseXML necessitated.
Removal of register ID = suffix requirement | No impact to 5MS Retail systems. | N/A | Material participant readiness activity impact if existing requirement retained.
* raised by the 5MS Program
# r39 schema impact

## Slide 16: Testing Update
Tui Grant

## Slide 17: 5MS Staging Environment Defects Identified
Issue ID​ | Description​ | Status​ | Action​
​NCR1 | Missing files from 28 Aug FOR tradingprice or averageprice30 ​ | Closed​ | Fixed and regeneration of missing files inprogress​
1992​ | Screen display issue only - An extra TNI2 field is getting displayed under Address Information section in NMI Master, Point in Time NMI Master Summary and NMI Discovery Type 1 and Type 2 search page.​ | InProgress​ | It is a display issue only no functionality affected​
2193​ | Market Portal does not contain MSATS screens​ | Closed | Now available from within the market portal
2185​ | Unable to login to MSATS with newly created and updated user id and password​ | In Progress​ | Once created/updated in MSATS users can reset password by logging onto the market portal​
2349​ | ​ Incorrect rejection of CATS requests via FTP because of file name validation. ​ | Closed​ | Now working as expected​
NCR2 | A performance issue affecting the generation and publication of reports for wholesale has been identified and is currently being remediated to allow dispatch and bidding reports to run faster | Closed | Current reviewing logs to identify possible issues.
2643 | Performance issue related to loading large volumes of CATS transactions | In progress | Submit lower numbers of CR’s until fixed

## Slide 18: Industry Test: Dispatch & Bidding 29 November 2020
Participants can receive support through AEMO Support Hub
5MS Team will be available for Q&A session at 09:30 AEST for the week commencing 30-Nov-20
If required, similar arrangements can be put in place for a period in January
Note: Registration for APIs can be done in advance of the Industry Test period. To register, contact AEMO Support Hub
Further discussion will take place at ITWG on 21-Oct-20.
The Industry Test period for the Dispatch and Bidding solution will commence on 29-Nov-20

## Slide 19: Dispatch / Bidding Update
Ian Devaney

## Slide 20: Bidding / Dispatch Staging, Pre-production & Production timelines
STAGING
PRE-PRODUCTION
PRODUCTION
01 Oct 2021
05 Jul 2021
29 Nov 2020
01 Apr 2021
01 Oct 2021
LEGACY | BIDDING TRANSITION | 5MS RULE
30-minute bidding only via: FTP (txt) Web Bidding (Legacy) | 30-minute bidding via: FTP (txt) Web Bidding (Legacy) 5-minute bidding* via: FTP (JSON) Web Bidding (5MS) API *Each 5-minute bid within each half hour must be identical, giving the same effect as the submission of a 30-minute bid. | 5-minute bidding* only via: FTP (JSON) Web Bidding API *30-minute bid emulation restriction lifted
LEGEND
For business continuity reasons, 30-mins offers and bids will be accepted until 01 Oct 21

## Slide 21: Systems Workstream – Dispatch & Operations
5 MINUTE SETTLEMENT SYSTEMS TRACKING | TIMING |  |  |  |  |  |  |  |  | 
 | Internal HLIA | Focus/Group | SWG Engagement | External HLIA | Draft Tech Spec | Final Tech Spec | User Guides | 5MS Staging | Preprod | Production
DISPATCH and OPERATIONS |  |  |  |  |  |  |  |  |  | 
PACKAGE 1 - Bidding FTP and API |  |  |  |  |  |  |  |  |  | 
Transition | Aug-18 | Oct-18 | Aug-18 | Nov-18 | Dec-18 | 2-Apr-19 | 31-Oct-19 | 29-Nov-19 | Nov-20 | Apr-21
Bidding Data Model | Aug-18 | - | Sep-18 | Mar-19 | Dec-18 | 2-Apr-19 | 31-Oct-19 | 29-Nov-19 | Nov-20 | Apr-21
Bidding Format | Aug-18 | - | Sep-18 | Nov-18 | Dec-18 | 2-Apr-19 | 31-Oct-19 | 29-Nov-19 | Nov-20 | Apr-21
PACKAGE 2 - Bidding Web UI |  |  |  |  |  |  |  |  |  | 
Bidding Web UI and APIs | Aug-18 | Nov-18 | Dec-18 | Jan-19 | Mar-19 | 31-Jul-19 | 16-Dec-19 | 29-Nov-19 | Nov-20 | Apr-21
PACKAGE 3 - Dispatch, Pre-dispatch and PASA |  |  |  |  |  |  |  |  |  | 
Dispatch | Aug-18 | - | Oct-18 | Nov-18 | Oct-18 | 2-Apr-19 | - | 29-Nov-19 | Nov-20 | Apr-21
Predispatch P30/7DAY | Aug-18 | - | Oct-18 | Nov-18 | Oct-18 | 2-Apr-19 | - | 29-Nov-19 | Nov-20 | Apr-21
Predispatch P5 | Nov-18 | Oct-18 | Nov-18 | TBC | TBC | TBC | - | TBC | Nov-20 | Apr-21
ST and PD PASA | Aug-18 | - | Oct-18 | Nov-18 | Oct-18 | 2-Apr-19 | 31-Oct-19 | 29-Nov-19 | Nov-20 | Apr-21
PACKAGE 4 - Pricing and Miscellaneous |  |  |  |  |  |  |  |  |  | 
Trading Price / Price Revision | Aug-18 | - | Feb-19 | Nov-18 | Mar-19 | 31-Jul-19 | - | 15-May-20 | Nov-20 | Apr-21
Administered Pricing and CPT | Aug-18 | - | Feb-19 | Dec-18 | Mar-19 | 31-Jul-19 | - | 15-May-20 | Nov-20 | Apr-21
Suspension Pricing | Sep-18 | - | Feb-19 | Dec-18 | Mar-19 | 31-Jul-19 | - | 15-May-20 | Nov-20 | Apr-21
Negative Residue Management | Sep-18 | - | Feb-19 | Dec-18 | Jun-19 | 31-Jul-19 | - | 15-May-20 | Nov-20 | Apr-21
RERT | Oct-18 | - | - | - | - | - | - | - | - | -
PACKAGE 5 - Full Data Model |  |  |  |  |  |  |  |  |  | 
Full Data Model | Sep-18 | Ongoing | Ongoing | Apr-19 | Ongoing | 31-Jan-20 | 16-Mar-20 | 29-Nov-19 | Nov-20 | Apr-21
Current as at 18-09-2020

## Slide 22: Bidding & Dispatch Go-Live Plan
Greg Minney

## Slide 23: Background
The AEMO Bidding platform is scheduled to go-live on 1 April 2021
AEMO will develop a Bidding platform go-live plan in consultation with the RWG
This session will outline the high-level structure of the plan.

## Slide 24: Proposed scope - draft
In scope
High cutover approach
Industry responsibilities and expectations,
AEMO Platform Go/no-go decision timeframes
Communication and notification plan
Contingency process and notification
  Introduction of new service
Participant Data Model release considerations
Out of scope
Participant deployment approaches for 5MS bidding capability
Participant roll-back plans

## Slide 25: Bidding platform go-live plan principles
The following principles are specific to the Bidding platform go-live plan:
Impact on participant operations will be minimised to the extent possible
AEMO to perform the cutover, making capability available prior to Industry participant deployments
AEMO will independently assess and inform the industry on the go-live decision for AEMO’s Bidding platform and communicate status during the cutover process
Participants will comply with the cutover plan to facilitate the cutover
Participants will develop their individual plans that have regard to the key activities and dates set out in the Bidding platform go-live plan and Bidding Transition plan
Must continue to fulfil all regulatory and compliance obligations during the system cutover

## Slide 26: Next Steps
Development of draft approach for RWG Consultation

## Slide 27: Settlements Update
Mark Hillaby

## Slide 28: Settlements Staging, Pre-production & Production timelines
Staging
Pre-production
Production
1 Oct 2021
1 Apr 2021
1 Oct 2021
Legacy | New Settlement Platform | 5MS Rule | GS Rule
30-minute Settlements | 30-minutes settlement to 1 October 2021 | Five-minute settlement and Global Settlement soft-start - UFE Reporting | All Retailers become liable for UFE
1 May 2022
Incl. UFE Reporting from 05/07/21
Supports 30MS, 5MS and GS modes
Legend
17 Feb 2021
1 Feb 2022
5 Jul 2021

## Slide 29: Systems Workstream - Settlements
5 MINUTE SETTLEMENT SYSTEMS TRACKING | TIMING |  |  |  |  |  |  |  |  | 
 | Internal HLIA | Focus/Group | SWG Engagement | External HLIA | Draft Tech Spec | Final Tech Spec | User Guides | 5MS Staging | Preprod | Production
SETTLEMENTS |  |  |  |  |  |  |  |  |  | 
PACKAGE 1 - Reallocations |  |  |  |  |  |  |  |  |  | 
Reallocations | Dec-18 | Nov-18 | Dec-18 | Mar-19 | 31-Jul-19 | 15-Oct-19 | 1-Nov-19 | 1-Nov-19 | 1-Mar-20 | 1-Apr-20
PACKAGE 2 - Settlements and Billing |  |  |  |  |  |  |  |  |  | 
Settlements | Oct-18 | Nov-18 | Dec-18 | Mar-19 | 30-Aug-19 | 15-Dec-19 | - | 16-Mar-20 | Feb-21 | Apr-21
Billing | Oct-18 | Nov-18 | Dec-18 | Mar-19 | 30-Aug-19 | 15-Dec-19 | - | 16-Mar-20 | Feb-21 | Apr-21
PACKAGE 3 - Prudentials and Estimation |  |  |  |  |  |  |  |  |  | 
Prudentials | Sep-18 | Nov-18 | Dec-18 | Mar-19 | 31-Oct-19 | 31-Jan-20 | 15-May-20 | 15-May-20 | Feb-21 | Apr-21
Estimation | Oct-18 | Nov-18 | Dec-18 | Mar-19 | 31-Oct-19 | 31-Jan-20 | - | 15–May-20 | Feb-21 | Apr-21
Full Data Model | Refer DISPATCH |  |  |  |  |  |  |  |  | 
Current as at 18-09-2020

## Slide 30: Settlements Workstream Update
SIT & UAT testing is underway with internal teams
Certification activities are continuing
Dress rehearsal for cutover activities are being exercised over the coming months

## Slide 31: Retail/Metering Update
Jim Agelopoulos

## Slide 32: Retail Metering Staging, Pre-production & Production timelines
Staging
Pre-production
Production
Legacy | 30MS with new platform | 5MS Rule | GS Rule
30-minute meter reads | 30-min settlement 5-min reads supported Standing data updates for GS | UFE calculation and 5-min settlement | LR updated to GLOPOOL
5 Jul 2021
1 Feb 2021
1 Feb 2022
31 Oct 2020
1 Oct 21
1 May 2022
9 Mar 2021
Legend
GS from 1st quarter 2021 - TBC
1 Oct 2021
Date to be confirmed.

## Slide 33: Systems Workstream - Metering
Current as at 05-10-2020

## Slide 34: RM20 PPS Report Simplification
Paul Lyttle

## Slide 35: RM20 PPS Report Simplification
The RM20 PPS report displays the profile values for each Profile Name, these include:
  Controlled Load Profiles, and
  Net System Load Profiles (NSLP)
  5 Minute Load Profile (5MLP) (new to 5MS)
Unlike NSLP and 5MLP, calculation of Controlled Load Profile is a single profile for each ProfileName
  To simplify the PPS report output AEMO will only be providing a single set of Controlled Load Profile values
  This simplification will flow onto the RM25 SettlementProfileShapeData report
Feedback from participants was requested at the previous RMG meeting.
  AEMO received 5 responses
    3 participants indicating there was no impact
    2 participants requested further information that has been provided
    With no outstanding question or objections AEMO will implement this change with the MDM release.
Notes: Market readiness strategy update
Propose to:
  distribute draft strategy to RWG members out-of-session
  Provide to PCF members for their information
Merging Industry Test and Market Trial Strategy
AEMO is considering feasibility of Merging Industry Test and Market Trial Strategy deliverables into a single deliverable:
  Supports overall view of all testing phases at strategy level
  Integration of approaches with transition and go-live Strategy
  Align deliverable dates – maintain or improve final release dates for testing strategy
Test plan development for each phase will confirm scope, approach and scenarios
  Performed in collaboration with Testing WG
Interim Readiness Reporting
  42 responses received as at 1 August 2019
  RWG briefing (Webex) arranged for 6 August 2019 to review interim results
Transition Approach
  Framework, Objectives and Strawperson approach presented
    Process to engage directly in development of overall approach
  Transition Focus group to be established to progress
  Planned focus group date 30 August (Melbourne)
Testing Principles
  Summary of approach provided
  Will provide PCF members overview this meeting

## Slide 36: Transition Focus Group Update
Blaine Miner / Paul Lyttle

## Slide 37: Agenda Items
Review and consider the consolidated metering rollout plans for Tranche 1 and Tranche 2 metering
Present and discuss initial Industry level CATS transaction volumes associated with the MTP
Share and discuss current AEMO thinking regarding Cross Boundary categories, conditions and requirements

## Slide 38: Consolidated metering rollout plans - Pre-5MS Commencement
Volumes driven by the requirement to have all Basic Meter datastreams activated by 1 July 2021
  Assumes a 'flat' activation approach
Chart: Pre 5MS Go Live - Meters To-Be Updated
| Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
1-3 | 980 | 973 | 361 | 6925 | 435 | 480 | 665 | 665 | 465 | 365 | 1065 | 913 | 150 | 0
COMMS4/4A/VicAmi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 1175 | 1275 | 2675
BASIC | 0 | 0 | 0 | 99984 | 199967 | 199967 | 199967 | 199967 | 199967 | 99984 | 0 | 0 | 0 | 0
UMCP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1635 | 1635 | 1635 | 0 | 0
Total | 980 | 973 | 361 | 106909 | 200402 | 200447 | 200632 | 200632 | 200432 | 101984 | 3800 | 3723 | 1425 | 2675

## Slide 39: Consolidated metering rollout plans - Post-5MS Commencement
Volumes driven by the requirement to have all applicable T4, T4a and VICAMI meters delivering 5min data by 1 Dec 2022
Peak months between Jul and Aug 2022 peaking at 290,000 meters updated per month
Chart: Pre 1 Dec 2022 - Meters To-Be Updated
| Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1-3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COMMS4/4A/VicAmi | 2675 | 12075 | 16075 | 119075 | 134036 | 147686 | 159108 | 212108 | 222108 | 289708 | 279708 | 210708 | 184408 | 158797 | 0
BASIC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UMCP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 2675 | 12075 | 16075 | 119075 | 134036 | 147686 | 159108 | 212108 | 222108 | 289708 | 279708 | 210708 | 184408 | 158797 | 0

## Slide 40: CATS Transaction Volume Estimates - Pre-5MS Commencement
Single CATS CR expected for most of the changes
Numbers of CR Transactions to peak at 200,000+ month
  Majority of changes related to Tier 1 Basic Meter Datastream activation
Numbers of CR Notifications (“REQ”, “PEND”, “COM”) estimated to peak at 600,000+ month
Chart: Pre 5MS Go Live - CATS CR Numbers
| Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
1-3 | 3087 | 3064.95 | 1137.15 | 21813.75 | 1370.25 | 1512 | 2094.75 | 2094.75 | 1464.75 | 1149.75 | 3354.75 | 2875.95 | 472.5 | 0
COMMS4/4A/VicAmi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3311 | 3536.75 | 3837.75 | 8051.75
BASIC (No Act DS) | 0 | 0 | 0 | 99984 | 199967 | 199967 | 199967 | 199967 | 199967 | 99984 | 0 | 0 | 0 | 0
UMCP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4905 | 4905 | 4905 | 0 | 0
Total | 3087 | 3064.95 | 1137.15 | 121797.75 | 201337.25 | 201479 | 202061.75 | 202061.75 | 201431.75 | 106038.75 | 11570.75 | 11317.7 | 4310.25 | 8051.75

## Slide 41: CATS Transaction Volume Estimates - Post 5MS Go Live to 1 Dec 2022
Three CATS CRs expected for most changes: Inactivate Net datastreams, activate Register level datastreams and update Meter Read Type code (RWDA)
Numbers of CR Transactions to peak at 870,000+ month
Numbers of CR Notifications (“REQ”, “PEND”, “COM”) estimated to peak at 2,610,000+ month
  Does not consider multiple Participants receiving Notifications
Chart: Post 5MS Go Live to 1 Dec 2022 - CATS CR Numbers
| Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1-3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COMMS4/4A/VicAmi | 8051.75 | 36345.75 | 48385.75 | 358415.75 | 403448.36 | 444534.86 | 478915.08 | 638445.08 | 668545.08 | 872021.08 | 841921.08 | 634231.08 | 555068.08 | 477978.97 | 0
BASIC (No Act DS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UMCP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 8051.75 | 36345.75 | 48385.75 | 358415.75 | 403448.36 | 444534.86 | 478915.08 | 638445.08 | 668545.08 | 872021.08 | 841921.08 | 634231.08 | 555068.08 | 477978.97 | 0

## Slide 42: Cross Boundary Categories
Cross Boundary Supply Categories
Metered at the Boundary
Not Metered at the Boundary
  Unmetered – emergency connection between supply and receiving distribution networks that is used infrequently
  Metered at End User connection point – generally a single connection point in the receiving distribution network connected to a service or a circuit from the supply distribution network

## Slide 43: Cross Boundary conditions and Requirements
Metered at the Boundary
DNSPs, in consultation with AEMO, will create Cross Boundary NMI
LNSP = Supply DB Participant ID
TNI = Supply DB TNI
NSP2 = Receiving DB Participant ID – populated by AEMO
TNI2 populated by AEMO
Not metered at the Boundary
Approval must be obtained from AEMO
AEMO, in consultation with DNSPs, will determine the metering or energy volume assessment arrangements for the Cross Boundary Supply

## Slide 44: Cross Boundary conditions and Requirements
Unmetered at the Boundary (Emergency)
LNSP, in consultation with AEMO and receiving DB, must provide methodology for assessing energy volume flowing at the Unmetered Cross Boundary Supply
LNSP must develop processes and procedures that include:
  Energy volume assessment methodology,
  Identification of time period the Unmetered Cross Boundary Supply was in use,
  NMI and datastream activation process, and
  Provision to AEMO of details of the form in which information related to each use of an Unmetered Cross Boundary Supply

## Slide 45: Cross Boundary conditions and Requirements
Unmetered at the Boundary (Emergency) - continued
DNSPs, in consultation with AEMO, will create Cross Boundary NMI
LNSP = Supply DB Participant ID
TNI = Supply DB TNI
NSP2 = Receiving DB Participant ID – populated by AEMO
TNI2 populated by AEMO
LNSP must ensure that NMI and datastreams are active only for the period when the Unmetered Cross Boundary Supply is in use, otherwise the NMI and datastreams must not be active

## Slide 46: Cross Boundary conditions and Requirements
Metered at End User connection point
DNSPs must provide AEMO with End User NMIs
End User connection point must have remotely read interval meter (can be 5, 15 or 30-minute)
DNSPs, in consultation with AEMO, will create/maintain “Cross Boundary NMI”
LNSP = Receiving DB Participant ID
TNI = Supply DB TNI
NSP2 = Supply DB Participant ID – populated by LNSP (new CR6xxx)
Targeting the end of October 2020 to provide the draft ‘Cross Boundary Supply Guideline’

## Slide 47: Retail platform go-live plan
Austin Tan & Greg Minney

## Slide 48: Consultation approach for Retail platform go-live plan
Early engagement
  AEMO seeks early feedback from RWG:
  31 Aug 20 RWG provides feedback on scope and approach to Retail go-live plan
First draft
  9 Oct 20 AEMO publishes first draft of plan for review
Cutover Focus Group
  16 October First Cutover Focus Group to discuss plan
Feedback deadline
  23 Oct 20 Deadline for industry to provide feedback on first draft plan
Second draft
  6 Nov 20 AEMO publishes second draft of plan
Feedback deadline
  20 Nov 20 Deadline for industry to provide feedback on second draft plan
Final plan
  4 Dec 20 AEMO publishes final paper after considering suggestions and Dress Rehearsal updates
Revisions
  TBC AEMO revises plan based on any updates

## Slide 49: Next steps
AEMO to publish first draft of plan on 9 October 2020
AEMO to establish cutover group in 16 October to discuss draft plan
  RWG members to nominate members for initial review group
  Cross section of impacted participant roles (MDP, DNSP, FRMP)
  Focus of discussion:
    Processing management for participants during cutover
    Communications approach
    Refinement of timings
Feedback to be provided:
  Participation in PVM
  Proposed approach to initial communication post go live

## Slide 50: Forward Plan and Other Business
Greg Minney

## Slide 51: Essential Metering Capability
Participants have raised questions regarding the consistency of terminology and definition for essential metering capability
Essential capability for market start – includes essential meters – defined as T1-3 and 4 transmission connected – those meters being necessary for the accurate calculation of the NSLP
Clarification required in relation to Contingency plan which in addition highlights Cross Boundary meters as essential meters
Clarification: Contingency plan will be updated to reflect the definition used in the case of essential meters for market start
Rationale:
  Cross boundaries are not essential for market start since it is possible to calculate the NSLP without them, although it may be inaccurate. They are therefore not essential. However, they are required.
  Where a cross boundary meter is yet to be implemented (as required for the calculation of UFE ) the accuracy of the UFE calculation will be impacted (an existing inaccuracy) Tracking of essential metering capability for rule commencement will continue based on current definition
Definition and tracking of essential metering capability does not obviate participants of compliance requirements with regard metering capability and availability.

## Slide 52: Next RWG Meeting
Confirmation on proposal to change Settlements go-live date
Bidding / Dispatch platform pre prod release preparation
Debrief from TFG
Staging update – Retail platform shift to 5-minute operation
Readiness Survey #4 – issued Tuesday 6 October

## Slide 53: Upcoming meetings/focus groups
Anne-Marie McCague

## Slide 54: Upcoming meetings
Current as 7 Oct 2020
https://aemo.com.au/initiatives/major-programs/nem-five-minute-settlement-program-and-global-settlement

## Slide 55: Questions

## Slide 57: Appendices

## Slide 58: Appendix Contents
A1: L2 Readiness Milestones

## Slide 59: A1: L2 Readiness Milestones

## Slide 60: Level 2 Milestones – Readiness
Key Milestones (Program) |  |  |  |  | 
ID | Milestone | Target Date | Expected Date | Owner | Status
L2-RE11 | Metering Service Provider Accreditation Plan Finalised | 13-Mar-2020 | 18-Feb-2020 | AEMO | Complete
L2-S12 | Reallocations Go-Live | 01-Apr-2020 | 01-Apr-2020 | AEMO | Complete
L2-RE32 | Industry Test for Reallocations Concludes | 31-Mar-2020 | 31-Mar-2020 | AEMO | Complete
L2-RE22 | Industry Transition Plan – Dispatch​ final complete | 28-Aug-2020 | 28-Aug-2020 | AEMO | Complete
L2-M11 | Industry Test preparation completed by participants for MDM and B2M Go-Live | 01-Feb-2021 | 01-Feb-2021 | Participants | 
L2-M12 | Industry Test preparation completed by AEMO for MDM and B2M Go-Live | 01-Feb-2021 | 01-Feb-2021 | AEMO | 
L2-RE29 | Retail MDM (incl. B2M) Industry Test Commences | 01-Feb-2021 | 01-Feb-2021 | AEMO | 
L2-RE30 | Retail MDM (incl. B2M) Industry Test Concludes | 03-Mar-2021 | 03-Mar-2021 | AEMO | 
L2-RE18 | Industry Go-Live Plan Retail MDM finalised | 20-Nov-2020 | 20-Nov-2020 | AEMO | 
L2-M24 | B2M Go-Live | 09-Mar-2021 | 09-Mar-2021 | AEMO | 
L2-M10 | 5 minute files in MDFF accepted by AEMO | 01-Apr-2021 | 01-Apr-2021 | AEMO | 
L2-D7 | Dispatch Industry Test preparation completed by participants | 29-Nov-2020 | 29-Nov-2020 | Participants | 
L2-D8 | Dispatch Industry Test preparation completed by AEMO | 29-Nov-2020 | 29-Nov-2020 | AEMO | 
Milestone complete
Milestone on track
Milestone not achieved
Milestone at risk
Domain | Initiative | 2019 |  |  |  |  |  |  |  |  |  |  |  | 2020 |  |  |  |  |  |  |  |  |  |  |  | 2021 |  |  |  |  |  |  |  |  |  |  | 
 |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  | 
Readiness |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec
L2-RE11
L2-RE32
L2-S12
L2-RE22
L2-M11
L2-M12
L2-RE18
L2-M24
L2-M10
L2-D7
L2-D8
L2-RE29
L2-RE30
Current as at 18-09-2020

## Slide 61: Level 2 Milestones – Readiness
Key Milestones (Program) |  |  |  |  | 
ID | Milestone | Target Date | Expected Date | Owner | Status
L2-S10 | Settlements Industry Test preparation completed by participants | 17-Feb-2021 | 17-Feb-2021 | Participants | 
L2-S11 | Settlements Industry Test preparation completed by AEMO | 17-Feb-2021 | 17-Feb-2021 | AEMO | 
L2-RE28 | Dispatch Industry Test concludes | 15-Mar-2021 | 15-Mar-2021 | AEMO | 
L2-RE32 | Settlements Industry Test concludes | 15-Mar-2021 | 15-Mar-2021 | AEMO | 
L2-RE19 | Industry Go-Live Plan Settlements, Dispatch & Bidding finalised | 19-Mar-2021 | 19-Mar-2021 | AEMO | 
L2-RE23 | 5MS Capability Market Trial preparation completed by participants | 05-Jul-2021 | 05-Jul-2021 | Participants | 
L2-RE24 | 5MS Capability Market Trial preparation completed by AEMO | 05-Jul-2021 | 05-Jul-2021 | AEMO | 
L2-RE31 | 5MS Capability Market Trial commences | 05-Jul-2021 | 05-Jul-2021 | AEMO | 
L2-RE20 | Industry Go-Live Plan – 5MS Capability final complete | 01-Aug-2021 | 01-Aug-2021 | AEMO | 
L2-D10 | 5MS Capability Market Trial concludes | 27-Aug-2021 | 27-Aug-2021 | AEMO | 
L2-D11 | 30-min Bidding no longer accepted by AEMO | 01-Oct-2021 | 01-Oct-2021 | AEMO | 
L2-RE25 | MDMT format no longer accepted by AEMO for interval meters | 01-Oct-2021 | 01-Oct-2021 | AEMO | 
L2-RE26 | GS Market Trial preparation completed by participants | 01-Feb-2022 | 01-Feb-2022 | Participants | 
L2-RE27 | GS Market Trial preparation completed by AEMO | 01-Feb-2022 | 01-Feb-2022 | AEMO | 
L2-RE21 | Industry Go-Live Plan – GS Capability final complete | 21-Dec-2021 | 21-Dec-2021 | AEMO | 
Domain | Initiative | 2019 |  |  |  |  |  |  |  |  |  |  |  | 2020 |  |  |  |  |  |  |  |  |  |  |  | 2021 |  |  |  |  |  |  |  |  |  |  | 
 |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  | 
Readiness |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec
L2-S10
L2-S11
L2-RE32
L2-RE23
L2-RE24
L2-RE20
L2-D10
L2-D11
L2-RE25
L2-RE21
L2-RE31
L2-RE328
Current as at 18-09-2020
Milestone complete
Milestone on track
Milestone not achieved
Milestone at risk
Milestone deferred
L2-RE19