## Slide 1: 5MS & GS Cutover Focus Group #1
Friday 16 October 2020
WebEx only: **Please disconnect from your workplace VPN for the WebEx call**
This slide pack was developed for the Transition Focus Group meeting. This version of the slides has been annotated with notes from the meeting. These additional notes are either in blue text of are on new slides indicated by a yellow background.

## Slide 2: AEMO Competition Law Meeting Protocol
AEMO is committed to complying with all applicable laws, including the Competition and Consumer Act 2010 (CCA). In any dealings with AEMO regarding proposed reforms or other initiatives, all participants agree to adhere to the CCA at all times and to comply with this Protocol.
Participants must arrange for their representatives to be briefed on competition law risks and obligations.
Participants in AEMO discussions must:
Ensure that discussions are limited to the matters contemplated by the agenda for the discussion
Make independent and unilateral decisions about their commercial positions and approach in relation to the matters under discussion with AEMO
Immediately and clearly raise an objection with AEMO or the Chair of the meeting if a matter is discussed that the participant is concerned may give rise to competition law risks or a breach of this Protocol.
Participants in AEMO meetings must not discuss or agree on the following topics:
Which customers they will supply or market to
The price or other terms at which Participants will supply
Bids or tenders, including the nature of a bid that a Participant intends to make or whether the Participant will participate in the bid
Which suppliers Participants will acquire from (or the price or other terms on which they acquire goods or services)
Refusing to supply a person or company access to any products, services or inputs they require.
Under no circumstances must Participants share Competitively Sensitive Information. Competitively Sensitive Information means confidential information relating to a Participant which if disclosed to a competitor could affect its current or future commercial strategies, such as pricing information, customer terms and conditions, supply terms and conditions, sales, marketing or procurement strategies, product development, margins, costs, capacity or production planning.

## Slide 3: Consolidated meeting actions
# | Action | Owner | Due Date
1.4.1 | AEMO to provide estimate on when backlog of meter data will be processed after the retail platform is back online. | AEMO | 20 Nov
1.5.1 | AEMO to consider if Milestone dates need to be updated on POAP | AEMO | 20 Nov
1.6.1 | CUFG to inform AEMO if able to take part in PVM | CUFG | 13 Nov
1.6.2 | CUFG to inform AEMO if they intend to transition to B2M API, or RM39 schema at the go-live. | CUFG | 13 Nov
1.7.1 | AEMO to confirm definition of ‘current’ schema once AEMO moves to RM39. | AEMO | 20 Nov

## Slide 4: Agenda **Please disconnect from your workplace VPN for the WebEx call**
High level cutover approach
Cutover schedule
  Industry activities and actions
  Indicative timings and impact on participant processing
  Approaches to progress updates during cutover
  Rollback decision
Participant Verification Monitoring
Next steps

## Slide 5: Attendees
Organisation | Attendee | Organisation | Attendee
AEMO (Chair) | Greg Minney | Energy Queensland | Nicole Bright
AEMO | Alex Alexander | Metering Dynamics/ Yurika | Cindy Matthews
AEMO | Anne-Marie McCague | Mondo | Nev Lewis
AEMO | Austin Tan | Origin Energy | Evelyn Loveband
AEMO | Blaine Miner | Origin Energy | Sourav Basu
AEMO | Carol Bosnjak | Plus ES | Linda Brackenbury
AEMO | Liz Bernhardt | SAPN | David Woods
AEMO | Paul Lyttle | SAPN | Jason Anthony
AEMO | Tui Grant | TasNetworks | Adrian Honey
AGL Energy | Andrew Peart | United Energy | Jack Friel
AusNet | Andrew Greenwood-Smith | United Energy | Wilmund Foong
CitiPower / Powercor | Greg Szot | United Energy | Mark Maidment
Endeavour Energy | Dino Ou | n/a | Rob Riddell
Energex | Steve Smith | SAPN | Siddhesh Tawate

## Slide 6: High level cutover approach
The cutover of the Retail platform will be performed in a manner to minimise impact to participant operations. To deploy AEMO’s new Retail platform, AEMO will stop processing B2M transactions and B2B transactions for periods during the cutover.
The cutover will also result in the activation of the R39 Schema and will require MDPs that currently send data to VPXP to send data to NEMMCO instead.
Industry Participants
AEMO
Key:
Communicate Proceed decision to Industry*
Participants to stop sending relevant B2M transactions
Process outstanding meter data files
Data migration
Stop processing B2B Transactions
1
2
3
4
Deploy 5MS upgrades into impacted AEMO applications
5
Participants restart B2M transactions and B2B transactions (NB timings may vary to minimise downtime)
Invitation Participant Verification Monitoring (PVM)
6
7
8
* Includes rollback contingencies

## Slide 7: Notes (1/7)
AEMO confirmed that:
  The R39 schema update applies to B2M only. The B2B schema is on R38 and will remain as R38.
  VICTUOS participants currently sending meter data to VPXP should send meter data to NEMMCO after the retail platform go-live.
Participants were advised to check their schema settings, and update based on schema preferences before the cutover. More details can be found on page 26 of the Guide to MSATS Web Portal, available at: https://www.aemo.com.au//media/files/electricity/nem/retail_and_metering/market_settlement_and_transfer_solutions/2020/guide-to-msats-web-portal.pdf?la=en&hash=D01A639B28A12893CEA92077570B8FF9.
Enhancement to the Participant B2M schema options now allows participants to apply different schema versions for each Transactions Group (CATS, NMID, MTRD)
  A participant noted that the CATS Transaction group needs to be updated to support the changes to NMI standing data within the r39 schema.

## Slide 8: Cutover Schedule (1)
# | AEMO actions | Industry Impacts and actions |  | Planned Start Time (Market Time, Approximate only) (TO BE CONFIRMED) | Communication Channel
 |  | Specific Role | All Roles |  | 
1 | AEMO performs preparatory migration activities in readiness for the retail platform cutover | n/a | n/a | Mon 8/02/21 00:00 | n/a
2 | AEMO notifies participants that B2M transactions will not be processed from 6 March 2021 6am market time. | n/a | n/a | Fri 5/03/21 17:00 | Market Notices (forwarded by 5MS mailbox)
3 | MDP Participants advised to update party participant from VPXP to NEMMCO | MDP ONLY - VICTUOS participants change destination from VPXP to NEMMCO | n/a | Sat 6/03/21 06:00 onwards | 5MS mailbox
4 | AEMO notifies participants that B2M transactions have stopped being processed | n/a | - MSATS Browser continues to be available – read only - B2B still operating - Stop sending B2M transactions - Acknowledge messages and clean out Inbox | Sat 6/03/21 06:00 | Market Notices (forwarded by 5MS mailbox)

## Slide 9: Notes (2/7)
AEMO confirmed that:
  B2M and B2B transactions will not be processed from the holding of transactions on 6 March 2021, until they are restarted at the end of the upgrade process scheduled for 7 March 2021.
  Inflight B2M transactions will not be cancelled, all change requests will be processed to the next transaction status providing a sync-point for process continuation after the upgrade.

## Slide 10: Cutover Schedule (2)
# | AEMO actions | Industry Impacts and actions |  | Planned Start Time (Market Time, Approximate only) (TO BE CONFIRMED) | Communication Channel
 |  | Specific Role | All Roles |  | 
5 | AEMO data migration commences | n/a | n/a | Sat 6/03/21 08:00 | n/a
6 | AEMO notifies participants that B2B have been stopped | All | - Stop sending automated B2B transactions - Participants to make arrangements for emergency B2B transactions during outage period - Acknowledge messages and clean out Inbox | Sat 6/03/21 17:00 | Market Notices (forwarded by 5MS mailbox)
7 | AEMO stops MSATS Browser read access (TBC) | n/a | No more read access to MSATS | Sat 6/03/21 17:00 | n/a
8 | AEMO commences deployment updates to market applications | n/ a | n/ a | Sat 6/03/21 17:00 | n/a

## Slide 11: Notes (3/7)
AEMO confirmed that:
  Timings in the cutover schedule is in market time, and are still subject to change. A final schedule will be release after AEMO completes dress rehearsals in December 2020.
  AEMO intends to commence cutover activities in line with the timings of the final cutover schedule, however time will be provided for participants to acknowledge files after step 6 of the cutover plan.
  When AEMO is not processing B2B transactions, Participants are expected to use contingency B2B approaches for urgent B2B transactions (e.g. similar to during B2B outages)
  If AEMO is requested to rollback, any B2M transactions processed from the point of cutover commencement and the roll back decision will be lost during the roll back process and will need to be resubmitted by Market Participants.
AEMO noted that the detailed approach on how B2M and B2B transactions will be stopped will be confirmed at a later stage. Currently AEMO intends to notify participants ahead of time before stopping batch handlers, participants are then able to use this period to acknowledge all current transactions prior to batch handlers being stopped.

## Slide 12: Cutover Schedule (3)
# | AEMO actions | Industry Impacts and actions |  | Planned Start Time (Market Time, Approximate only) (TO BE CONFIRMED) | Communication Channel
 |  | Specific Role | All Roles |  | 
9 | Advise selected participants PVM can start | n/a | Continue Hold on Market transaction - Perform PVM (selected participants (e.g. run sample of market transaction) | Sun 7/03/21 09:00 | Market Notices (forwarded by 5MS mailbox)
10 | AEMO performs PVM with select participants | n/a | - Select participants perform PVM with AEMO | Sun 7/03/21 10:00 | n/a
11a | AEMO informs participants of Full Market Go-live – including any restrictions on processing In the event of a rollback, please see section 3.4.2 | n/a | MSATS Available | Sun 7/03/21 15:30 | 5MS mailbox
12a | AEMO recommences processing and monitors B2M and B2B transactions | n/a | - Start processing back log of B2B, B2M and meter data, noting any possible restrictions | Sun 7/03/21 15:30 | 5MS mailbox

## Slide 13: Notes (4/7)
AEMO confirmed that:
  Participants are not required to transition to delivering MDMF files at the retail platform go-live date
  The MSATS browser will be available at step 11a of the cutover plan
  The B2B outage will impact all B2B transaction groups
  Any restrictions at go-live will be dependant on the outcome of cutover activities, AEMO does not expect any restrictions however this may be implemented based on system performance
  Performance testing of the retail solution is currently in progress, after testing is completed AEMO will provide an estimate of how long MDM will take to ‘catch-up’ on processing the backlog of meter data.
PVM is not regression testing or new functionality for market commencements, but involves the monitoring of select transactions prior to the retail platform go-live.
Action 1.4.1: AEMO to provide estimate on processing backlog of meter data after the retail platform upgrade is complete.

## Slide 14: Cutover Schedule – Rollback decision
# | AEMO actions | Industry Impacts and actions |  | Planned Start Time (Market Time, Approximate only) (TO BE CONFIRMED) | Communication Channel
 |  | Specific Role | All Roles |  | 
11b | AEMO informs Participants of the Revert decision |  | - Ensure that systems can be compatible with AEMO’s retail platform pre-cutover. Prepare to resend market transactions since cutover commencement | Sun 7/03/21 15:30 | Market Notices (forwarded by 5MS mailbox)
12b | AEMO performs Restoration and technical verification | n/a | n/a | Sun 7/03/21 15:30 | n/a
13b | AEMO notifies stakeholders of completion of rollback | n/a | - Resume market operations | Mon 8/03/21 09:00 | 5MS mailbox
14b | AEMO informs participants that have conducted business transactions outside of market systems to process and acknowledge transactions via B2M | n/a | Participants that have sent transactions during cutover period to resend any B2M transactions, and reprocess B2B transactions as required | Mon 8/03/21 09:00 | 5MS mailbox

## Slide 15: Notes (5/7)
AEMO confirmed that:
  9 March 2020 was the previously communicated go-live date of the retail platform, however current timings of the upgrade estimate the retail platform to be live on 7 March 2020.
  B2B transactions will to be processed from the point that B2B batch handers are shut down.
  B2M transactions will be processed from the point that B2M transactions are held on recommencement.
  There is no change for hostnames and IP address for eHub.
  Stopping of B2B batch handlers have been separated from the stopping of B2M batch handlers to reduce the impact on market B2B transactions where possible.
No issues were raised in relation to AEMO’s proposed communication approach during the cutover
Action 1.5.1: AEMO to consider if Milestone dates need to be updated on POAP

## Slide 16: Participant Verification Monitoring (PVM)
The purpose of Participant Verification Monitoring (PVM) is to have selected participants confirm the ability to process market transactions , or identify issues prior to recommencement of market systems
Will consist of a small sample of transactions conducted in a defined window across a range of participants including MDPs, FRMPs, DNSPs (if available)
Outcomes will form component of industry communications for go-live, including if there are restrictions on capability to be notified
PVM scenarios and participants will be developed dependent on availability and capability (including intention to immediately implement B2M via API, R39 Schema, etc ) and included in final go-live plans

## Slide 17: Notes (6/7)
AEMO confirmed that based on the current approach, a rollback decision would affect both B2B and B2M.
Action 1.6.1: CUFG to inform AEMO if able to take part in PVM
Action 1.6.2: CUFG to inform AEMO if they intend to transition to B2M API, or RM39 schema at the go-live.

## Slide 18: Development timeline
Early engagement
  AEMO seeks early feedback from RWG:
  31 Aug 20 RWG provides feedback on scope and approach to Retail go-live plan
First draft
  9 Oct 20 AEMO publishes first draft of plan for review
Cutover Focus Group
  16 October First Cutover Focus Group to discuss plan
Feedback deadline
  23 Oct 20 Deadline for industry to provide feedback on first draft plan
Second draft
  6 Nov 20 AEMO publishes second draft of plan
Feedback deadline
  20 Nov 20 Deadline for industry to provide feedback on second draft plan
Final plan
  4 Dec 20 AEMO publishes final paper after considering suggestions and Dress Rehearsal updates
Revisions
  TBC AEMO revises plan based on any updates

## Slide 19: Other business
Are there any other content the CUFG would like to see reflected in the plan?

## Slide 20: Notes (7/7)
AEMO noted that it is not mandatory to for participants to use B2M APIs after the retail go-live, and FTP will still be supported. Participants can also choose to remain on the R35 schema instead of upgrading to the RM39 schema unless participants plan to utilise the new reporting functionality.
VPXP is only used for the VICTOUS process, all other transactions are sent to NEMMCO. The new MDM will not process any data from VPXP after the retail platform go-live. Participants currently sending data to VPXP should send it to NEMMCO after go-live.
Action 1.7.1: AEMO to confirm definition of ‘current’ schema once AEMO moves to RM39.

## Slide 21: Next steps
Participants to provide feedback on Retail platform industry go-live plan by Friday 23 October
AEMO to circulate example list of PVM transactions for feedback
Participants to inform AEMO if able to take part in PVM

## Slide 22: Questions