## Process
National Energy Market ESB 2025 Reforms
NEM2025 Implementation Roadmap
| Standard implementation process and estimated timeframes |  | Key on Roadmap
1. Policy development and design
2. Rules development (begins at open Rule Change, ends at Final Determination)
3. Initiation (once Rules are defined), includes high-level pre-execution design
4. Detailed pre-execution design
5. Procedure/Guideline development
6. Technology delivery
7. Industry testing and trials
| 8. Effective date |  | l
Related processes - timeframes may vary across initiatives
Proof of concept trial
Internal scoping process (for pre-requisite initiatives; prior to initiation)
Internal process mapping and optimisation (for pre-requisite initiatives)
Production roll Out
| S | Non-complex reform/design with minor/minimal changes; or |  | Estimated timeframe | Assumptions
| Non-complex and minor changes within existing frameworks and minimal system changes anticipated |  |  | (months)
| 1. Policy development and design |  |  | 6
| 2. Rules development (begins at open Rule Change, ends at Final Determination) |  |  | 6
| 3. Initiation (once Rules are defined), includes high-level pre-execution design |  |  | 3
| 4. Detailed pre-execution design |  |  | N/A
| 5. Procedure/Guideline development |  |  | 6 | 1 round of consultation; some overlap with Detailed pre-execution design and Solution delivery
| 6. Solution delivery |  |  | 9 | After initiation phase completes
| 7. Industry testing and trials |  |  | 3 | After Solution Delivery completes; includes time for required adjustments to the system arising to address issues arising during testing
| M | Some complexities; minor complexities in design but anticipated to require several changes; or |  | Estimated timeframe | Assumptions
Some complexity with implementation due to several system changes anticipated; non-complex design
| 1. Policy development and design |  |  | 6 to 12
| 2. Rules development (begins at open Rule Change, ends at Final Determination) |  |  | 6 to 12
| 3. Initiation (once Rules are defined), includes high-level pre-execution design |  |  | 3
| 4. Detailed pre-execution design |  |  | N/A
| 5. Procedure/Guideline development |  |  | 9 | 2 rounds of consultation; some overlap with Detailed pre-execution design and Solution delivery
| 6. Solution delivery |  |  | 12 | After initiation phase completes
| 7. Industry testing and trials |  |  | 4 | After Solution Delivery completes; includes time for required adjustments to the system arising to address issues arising during testing
| L | Complex reform/design with significant system changes required. |  | Estimated timeframe | Assumptions
Complex reforms and changes; complex design, several anticipated system changes; or
Non-complex design but significant procedural changes, system touch-points are anticipated.
| 1. Policy development and design |  |  | 12
| 2. Rules development (begins at open Rule Change, ends at Final Determination) |  |  | 12 to 24
| 3. Initiation (once Rules are defined), includes high-level pre-execution design |  |  | 4
| 4. Detailed pre-execution design |  |  | 6 to 12
| 5. Procedure/Guideline development |  |  | 12 | 2 extended rounds of consultation; some overlap with Detailed pre-execution design and Solution delivery
| 6. Solution delivery |  |  | 18 | After initiation phase completes
| 7. Industry testing and trials |  |  | 6 | After Solution Delivery completes; includes time for required adjustments to the system arising to address issues arising during testing
| XL | Highly complex reform/design with a large number of significant changes required |  | Estimated timeframe
Highly complex reforms and changes; complex design, significant number of high-impact system changes
| 1. Policy development and design |  |  | 12
| 2. Rules development (begins at open Rule Change, ends at Final Determination) |  |  | 24
| 3. Initiation (once Rules are defined), includes high-level pre-execution design |  |  | 4
| 4. Detailed pre-execution design (applies to more complex initiatives) |  |  | 12
| 5. Procedure/Guideline development |  |  | 18 | 2 extended rounds of consultation, runs parallel to technology delivery
| 6. Technology delivery |  |  | 24 | After initiation phase completes
| 7. Industry testing and trials |  |  | 6

## Definitions
National Energy Market ESB 2025 Reforms
NEM2025 Implementation Roadmap
Definitions and Instructions for NEM2025 Implementation Roadmap
| Heading / Term | Definition and Instructions
| Impacted Industry Sector | Indicates the primary section of the industry that is impacted by the regulatory change. If two sections of industry are impacted, choose the primary section. If more that two sections are impacted, choose 'Industry-wide'. Wholesale = Generation, Wholesale Market and/or Contracting impacted by the rule change Networks = Transmission and Distribution networks impacted by the rule change Retail = Retailers, other contestable service providers and/or customers are primarily impacted by the rule change Industry-wide = More that two sections of the industry are impacted by the rule change
| Reform Status | Committed = Final determination made; and/or implementation in progress In progress = Rule development in process (i.e. open Rule with at least a Consultation on Draft Determination, or Consultation Paper with clear indication of design) Conceptual = Policy and market design in process (e..g Directions Paper on high-level design options, or Review of Framework, details of design remain uncertain) Note: A reference to rule change may also include a law change; or a reference to a review process where the outcome will be a law or rule change
| Effective Date Status | Committed = Final Rule has been published (i.e. certainty on requirements and Effective Date) Proposed = Effective date proposed in draft rule determination Estimated = AEMO estimated go-live date (where no proposed timeline currently exists or an effective date is uncertain or unknown)
| Implementation Status | Policy development and design = early stage of the reform process (i.e. prior to a rule change process commencing) Rules development = a rule change process is in progress (begins at open rule change through to final rule determination) Initiation = AEMO kicks-off an initiative once the rules are defined; includes high-level pre-execution design) Detailed pre-execution design = Applied to some larger initiatives with complex changes and large procedure or guideline development – where it is not feasible to wait until they are final to commence IT Build because it would extend the rule effective date. Procedure/Guideline development = Procedural changes are in progress or required to implement the rule change; runs parallel to technology delivery Technology delivery = IT systems and processes implementation and engineering implementation Industry testing and trials = Runs within the technology delivery phase to test solution with market participants before the effective date.
| Key IT regulatory projects | Significant implementation impact = Medium or major IT/system capex project required to implement the rule change by AEMO and/or industry Strategic reform initiatives = Initiatives identified by COAG Energy Council and/or Energy Security Board
| Include on Roadmap? | Yes - Material (i.e. High or Medium impact) IT, system or engineering implementation project Yes - Strategic Reform e.g. COAG EC priority No - Not Material or Strategic No - Complete
Definitions and Instructions for industry testing and trials
| Heading / Term | Definition and Instructions
| Industry Test | Participants can get into the pre-prod environment and conduct unstructured tests as they see fit
| Invitation industry Test | Where a subset of participants agree (on a volunteer basis) to participate in an Industry Test. AEMO does not develop formal scenarios, but participants conduct bilateral testing on an agreed basis
| Market Trial | Where AEMO develops structured scenarios which are designed for widespread participation from our industry colleagues and structured to demonstrate/test particular scenarios. High effort required from all, generally reserved for new markets or big market changes (like 5MS)

## NEM2025 Roadmap V1 Reg Led
National Energy Market ESB 2025 Reforms | National Energy Market ESB 2025 Reforms
| NEM2025 Implementation Roadmap | [9 empty] | Key:
| REGULATORY-LED PATHWAY | [10 empty] | Policy development and design | [13 empty] | Rules development (open Rule Change through to Final Determination) | [12 empty] | Initiation, including high-level pre-execution design | [11 empty] | Proof of concept trial
| Version 1 | [12 empty] | AEMO Procedure/Guideline development | [11 empty] | Detailed pre-execution design | [12 empty] | Committed solution delivery | [11 empty] | AEMO process mapping and optimisation
[12 empty] | Solution delivery | [13 empty] | Production roll Out | [15 empty] | Industry testing and trials | [6 empty] | AEMO scoping process
[11 empty] | l | Committed effective date | [12 empty] | p | Proposed effective date | [11 empty] | u | Estimated effective date | [10 empty] | Grouped release
[12 empty] | Resource Adequacy Mechanisms and Ageing Thermal Generation | [15 empty] | Essential System Services, Scheduling and Ahead Mechanisms | [12 empty] | Data Strategy
[12 empty] | Integration of DER and Flexible Demand | [15 empty] | Transmission and Access | [12 empty] | AEMO Strategic / Foundational Pre-requisite
KEY FOR THE TYPES OF DEPENDENCIES
[6 empty] | Hard |  |  |  |  | Committed* |  |  | Final Rule has been published (i.e. certainty on requirements and effective date) | [18 empty] | * Reform Status only applies to core NEM2025 initiatives
[6 empty] | Hard design |  |  |  |  | In progress* |  |  | Rule development in process (i.e. open Rule with at least a Consultation on Draft Determination, or Consultation Paper with clear indication of design)
[6 empty] | Soft |  |  |  |  | Conceptual* |  |  | Policy and market design in process (e.g. Directions Paper on high-level design options, or Review of Framework, details of design remain uncertain)
Soft design
HORIZON 1
HORIZON 2
HORIZON 3
[25 empty] | R1 |  |  |  |  | R2 |  | R3 |  |  | R4 |  | R5 |  | R6 | [8 empty] | R7
|  | Impacted Industry Sector | Reform Status | Code | Reform Initiative | Dependencies |  |  |  | 2022 | [6 empty] | 2023 | [9 empty] | 2024 | [7 empty] | 2025 | [5 empty] | 2026 | [5 empty] | 2027
Initiative Category | [9 empty] | Q1 | Q2 |  | Q3 |  | Q4 |  | Q1 |  |  | Q2 |  |  | Q3 |  | Q4 |  | Q1 |  | Q2 |  | Q3 |  | Q4 |  | Q1 | Q2 | Q3 |  | Q4 |  | Q1 |  | Q2 | Q3 | Q4 |  | Q1 |  | Q2 | Q3 |  | Q4
ESB INITIATIVES WITH IT SYSTEM IMPLEMENTATION IMPACTS
TNSP NEM2025 |  | Wholesale, networks | Committed |  | Efficient management of system strength on the power system | [10 empty] | l |  |  | l
Core NEM2025 |  | Wholesale | Committed | FFR | Frequency control - Fast Frequency Response | ODMT | DSTM | IES | [6 empty] | MASS | l | [8 empty] | l
Core NEM2025 |  | Wholesale | In progress | MTP | Increased MT PASA information | [19 empty] | u
Core NEM2025 |  | Wholesale | Committed | IES | Integrating Energy Storage | STP | DSTM | [11 empty] | l | [10 empty] | l
Core NEM2025 |  | Retail | Conceptual | FTA2 | Flexible trading arrangements model 2 | FRC | IDX | [22 empty] | u
Pre-requisite Strategic |  |  |  | PC | Portal Consolidation (establishment of f/w and architecture) | IDAM | [22 empty] | u |  | Deferred and would commence 2025-26 onwards
Pre-requisite Strategic |  |  |  | CMSTR2 | CoMaStR Phase 2 | STP | [22 empty] | u |  | Deferred and would commence 2025-26 onwards
Pre-requisite Base |  |  |  | IDAM | Identity and access management (infrastructure establishment) | [26 empty] | u |  | Deferred and would commence 2025-26 onwards
Pre-requisite Base |  |  |  | IDX | ESB Industry Data Exchange (infrastructure establishment) | IDAM | PC | [24 empty] | u |  | Deferred and would commence 2025-26 onwards
Core NEM2025 |  | Wholesale | In progress | PFR | Primary Frequency Response Incentive Arrangements | IES | [25 empty] | p
NEM2025 |  | Wholesale | In progress | STP | ST PASA - Replacement project and methodology update | CMSTR | FPU | ODS | DST | [27 empty] | l
Pre-requisite Base |  |  |  | ODMT | Operational Decision-Making Tools | BRE | ODS | STP | CMSTR |  |  |  | Indicative, incremental delivery range of 3 years, agile delivery model and continuous development
Pre-requisite Base |  |  |  | ODS | Operational Data Store | FPU | STP | SCDL | [16 empty] | Following delivery of Platform: indicative incremental range of 1.5-2 years
Pre-requisite Base |  |  |  | BRE | Business Rules Engine | ODMT | [11 empty] | Indicative range for incremental delivery
Pre-requisite Base |  |  |  | FPU | Forecasting Platform Uplift | CMSTR | IDAM | [31 empty] | u
Core NEM2025 |  | Wholesale | Conceptual | OSM | Operational Security Mechanism | ODMT | [22 empty] | u | [9 empty] | u
Pre-requisite Base |  |  |  | SCDL | SCADA Lite | [14 empty] | u | [11 empty] | u
Core NEM2025 |  | Wholesale | Conceptual | SL | Scheduled lite | SCDL | IES | FTA | [23 empty] | u | [6 empty] | u | First release reflects Visibility Model. Second release reflects Dispatchability Model.
Core NEM2025 |  | Wholesale | Conceptual | ROR | Ramping/operating reserves | FPU | ODMT | [40 empty] | u
Core NEM2025 |  | Wholesale | Conceptual | TU | Turn-up services | SCDL | DSTM | [28 empty] | Indicative Range subject to outcomes of ARENA trials
Core NEM2025 |  | Network | Conceptual | DOE | Dynamic operating envelopes | FTA2 | FRC | [19 empty] | Indicative: DNSP-led, capabilities developed at different times with a range of entry points across Participants
Core NEM2025 |  | Industry-wide | Conceptual | D-Hub | DER Data Hub and Registry Services | FTA2 | FRC | [21 empty] | Indicative Range: Iterative implementation; start simple and continually develop over time as required
Core NEM2025 |  | Industry-wide | Conceptual | DER OT | DER Operational Tools | FTA2 | FRC | [16 empty] | Indicative Range: Start simple and continually develop over time as required
Core NEM2025 |  | Network | Conceptual | DLNS | Distribution / local network services | SL | [20 empty] | Indicative Range: Start simple and continually develop over time as required
Pre-requisite Strategic |  |  |  | DSTM | Dispatch Target State | STP | [6 empty] | INDICATIVE DEVELOPMENT RANGE OF 2-4 YEARS SUBJECT TO FURTHER ANALYSIS ON SCOPE | [32 empty] | Deferred and would commence 2025-26 onwards
Pre-requisite Strategic |  |  |  | DSTM | Bids/Offers Target State | STP | [6 empty] | INDICATIVE DEVELOPMENT RANGE OF 2-4 YEARS SUBJECT TO FURTHER ANALYSIS ON SCOPE | [32 empty] | Deferred and would commence 2025-26 onwards
Pre-requisite Strategic |  |  |  | DSTM | Constraints Target State | STP | [6 empty] | INDICATIVE DEVELOPMENT RANGE OF 2-4 YEARS SUBJECT TO FURTHER ANALYSIS ON SCOPE | [32 empty] | Deferred and would commence 2025-26 onwards
Pre-requisite Strategic |  |  |  | FRC | FRC Target State | IDX | BRE | DER |  |  |  |  | INDICATIVE DEVELOPMENT TIMEFRAME SUBJECT TO FURTHER ANALYSIS; MULTI-STAGE IMPLEMENTATION LIKELY | [32 empty] | Deferred and would commence 2025-26 onwards
Data Strategy |  | Industry-wide | Conceptual |  | Data Services | [9 empty] | Includes various stages of stakeholder engagement and public consultation, issues paper, draft options paper, and options report and recommendations
Data Strategy |  | Industry-wide | Conceptual |  | Bill Transparency | [13 empty] | Includes various stages of stakeholder engagement and public consultation, issues paper, draft options paper, and options report and recommendations
Data Strategy |  | Industry-wide | Conceptual |  | Electric Vehicles | [13 empty] | Includes various stages of alignment with DER and DEIP work, current process report, draft options paper, and options report and recommendations
Data Strategy |  | Network | Conceptual |  | Network Visibility | [16 empty] | Includes various stages of public consultation, AER Data Register development, gap analysis and case studies report, draft gap assessment report, recommendations report.
Data Strategy |  | Industry-wide | Conceptual |  | Consumer Research / Metrics | [15 empty] | Includes various stages of alignment with Energy Equity Working Group work, review of existing research and metrics, draft metrics and approach report, public consultation, research approach pilot, and ongoing approach report

## NEM2025 Roadmap V1 Strategic
National Energy Market ESB 2025 Reforms | National Energy Market ESB 2025 Reforms
| NEM2025 Implementation Roadmap | [10 empty] | Key:
| STRATEGIC PATHWAY | [11 empty] | Policy development and design | [12 empty] | Rules development (open Rule Change through to Final Determination) | [14 empty] | Initiation, including high-level pre-execution design | [10 empty] | Proof of concept trial
| Version 1 | [13 empty] | AEMO Procedure/Guideline development | [10 empty] | Detailed pre-execution design | [14 empty] | Committed solution delivery | [10 empty] | AEMO process mapping and optimisation
[13 empty] | Solution delivery | [12 empty] | Production roll Out | [17 empty] | Industry testing and trials | [5 empty] | AEMO scoping process
[12 empty] | l | Committed effective date | [11 empty] | p | Proposed effective date | [13 empty] | u | Estimated effective date | [9 empty] | Grouped release
[13 empty] | Resource Adequacy Mechanisms and Ageing Thermal Generation | [14 empty] | Essential System Services, Scheduling and Ahead Mechanisms | [14 empty] | Data Strategy
[13 empty] | Integration of DER and Flexible Demand | [14 empty] | Transmission and Access | [14 empty] | AEMO Strategic / Foundational Pre-requisite
KEY FOR THE TYPES OF DEPENDENCIES
[7 empty] | Hard |  |  |  |  | Committed* |  |  | Final Rule has been published (i.e. certainty on requirements and effective date) | [17 empty] | * Reform Status only applies to core NEM2025 initiatives
[7 empty] | Hard design |  |  |  |  | In progress* |  |  | Rule development in process (i.e. open Rule with at least a Consultation on Draft Determination, or Consultation Paper with clear indication of design)
[7 empty] | Soft |  |  |  |  | Conceptual* |  |  | Policy and market design in process (e..g Directions Paper on high-level design options, or Review of Framework, details of design remain uncertain)
Soft design
HORIZON 1
HORIZON 2
HORIZON 3
[25 empty] | R1 |  |  |  |  | R2 |  |  |  | R3 |  |  | R4 |  | R5 |  | R6
|  | Impacted Industry Sector | Primary Objective | Reform Status | Code | Reform Initiative | Dependencies |  |  |  | 2022 | [6 empty] | 2023 | [8 empty] | 2024 | [8 empty] | 2025 | [6 empty] | 2026 |  |  |  |  | 2027
Initiative Category | [10 empty] | Q1 | Q2 |  | Q3 |  | Q4 |  | Q1 |  |  | Q2 |  | Q3 |  | Q4 |  | Q1 |  | Q2 |  | Q3 |  | Q4 |  |  | Q1 |  | Q2 | Q3 |  | Q4 |  | Q1 |  | Q2 | Q3 | Q4 | Q1 |  | Q2 | Q3 |  | Q4
ESB INITIATIVES WITH IT SYSTEM IMPLEMENTATION IMPACTS
TNSP NEM2025 |  | Wholesale, networks | Security | Committed |  | Efficient management of system strength on the power system | [10 empty] | l |  |  | l
Core NEM2025 |  | Wholesale | Security | Committed | FFR | Frequency control - Fast Frequency Response | ODMT | DSTM | IES | [6 empty] | MASS | l | [7 empty] | l
Core NEM2025 |  | Wholesale |  | In progress | MTP | Increased MT PASA information | [18 empty] | u
Core NEM2025 |  | Wholesale | Market | Committed | IES | Integrating Energy Storage | STP | DSTM | [11 empty] | l | [9 empty] | l
Core NEM2025 |  | Retail |  | Conceptual | FTA2 | Flexible trading arrangements model 2 | FRC | IDX | [21 empty] | u
* Portal Consolidation and CoMaStR do not have external impact at this release stage
Pre-requisite Strategic |  |  |  |  | PC | Portal Consolidation (establishment of f/w and architecture) | IDAM | [22 empty] | u | Indicative range for subsequent phases required for roll-out
Pre-requisite Strategic |  |  |  |  | CMSTR2 | CoMaStR Phase 2 | STP | [22 empty] | u | Indicative range for subsequent phases required for roll-out
Pre-requisite Base |  |  |  |  | IDAM | Identity and access management (infrastructure establishment) | CMSTR | [26 empty] | u | On-boarding and transition plan (including discontinuation of existing systems) to be determined
Pre-requisite Base |  |  |  |  | IDX | ESB Industry Data Exchange (infrastructure establishment) | IDAM | PC | [25 empty] | u
* IDAM and IDX do not have external impact from this release
Pre-requisite Base |  |  |  |  | SCDL | SCADA Lite | [14 empty] | u | [12 empty] | u
Core NEM2025 |  | Wholesale |  | Conceptual | SL | Scheduled lite - Assumes a single rule change for both models | SCDL | IES | FTA | [24 empty] | u | [6 empty] | u | First release reflects Visibility Model. Second release reflects Dispatchability Model.
Pre-requisite Base |  |  |  |  | ODMT | Operational Decision-Making Tools | BRE | ODS | STP | CMSTR |  |  |  | Indicative, incremental delivery range of 3 years, agile delivery model and cts development
Pre-requisite Base |  |  |  |  | ODS | Operational Data Store | FPU | STP | SCDL | [15 empty] | Following delivery of Platform: indicative incremental range of 1.5-2 years
Pre-requisite Base |  |  |  |  | BRE | Business Rules Engine | ODMT | [11 empty] | Indicative range for incremental delivery
Pre-requisite Base |  |  |  |  | FPU | Forecasting Platform Uplift | CMSTR | IDAM | [28 empty] | u
Core NEM2025 |  | Wholesale | Security | In progress | PFR | Primary Frequency Response Incentive Arrangements | IES | [24 empty] | p |  |  |  |  | u
NEM2025 |  | Wholesale | Reliability | In progress | STP | ST PASA - Replacement project and methodology update | CMSTR | FPU | ODS | DST | [28 empty] | l
Core NEM2025 |  | Wholesale | Security | Conceptual | OSM | Operational Security Mechanism | ODMT | [21 empty] | u | [11 empty] | u
Core NEM2025 |  | Wholesale | Reliability | Conceptual | ROR | Ramping/operating reserves | FPU | ODMT | [40 empty] | u
Core NEM2025 |  | Wholesale |  | Conceptual | TU | Turn-up services | SCDL | DSTM | [29 empty] | Indicative Range subject to outcomes of ARENA trials
Core NEM2025 |  | Network |  | Conceptual | DOE | Dynamic operating envelopes | FTA2 | FRC | [18 empty] | Indicative: DNSP-led, capabilities developed at different times with a range of entry points across Participants
Core NEM2025 |  | Industry-wide |  | Conceptual | D-Hub | DER Data Hub and Registry Services | FTA2 | FRC | [20 empty] | Indicative Range: Iterative implementation; start simple and continually develop over time as required
Core NEM2025 |  | Industry-wide |  | Conceptual | DER OT | DER Operational Tools | FTA2 | FRC | [15 empty] | Indicative Range: Start simple and continually develop over time as required
Core NEM2025 |  | Network |  | Conceptual | DLNS | Distribution / local network services | SL | [19 empty] | Indicative Range: Start simple and continually develop over time as required
Pre-requisite Strategic |  |  |  |  | DSTM | Dispatch Target State | STP | [6 empty] | INDICATIVE DEVELOPMENT RANGE OF 2-4 YEARS SUBJECT TO FURTHER ANALYSIS ON SCOPE
Pre-requisite Strategic |  |  |  |  | DSTM | Bids/Offers Target State | STP | [6 empty] | INDICATIVE DEVELOPMENT RANGE OF 2-4 YEARS SUBJECT TO FURTHER ANALYSIS ON SCOPE
Pre-requisite Strategic |  |  |  |  | DSTM | Constraints Target State | STP | [6 empty] | INDICATIVE DEVELOPMENT RANGE OF 2-4 YEARS SUBJECT TO FURTHER ANALYSIS ON SCOPE
Pre-requisite Strategic |  |  |  |  | FRC | FRC Target State | IDX | BRE | DER |  |  |  |  | INDICATIVE DEVELOPMENT TIMEFRAME SUBJECT TO FURTHER ANALYSIS; MULTI-STAGE IMPLEMENTATION LIKELY
Data Strategy |  | Industry-wide |  | Conceptual |  | Data Services | [9 empty] | Includes various stages of stakeholder engagement and public consultation, issues paper, draft options paper, and options report and recommendations
Data Strategy |  | Industry-wide |  | Conceptual |  | Bill Transparency | [13 empty] | Includes various stages of stakeholder engagement and public consultation, issues paper, draft options paper, and options report and recommendations
Data Strategy |  | Industry-wide |  | Conceptual |  | Electric Vehicles | [13 empty] | Includes various stages of alignment with DER and DEIP work, current process report, draft options paper, and options report and recommendations
Data Strategy |  | Network |  | Conceptual |  | Network Visibility | [15 empty] | Includes various stages of public consultation, AER Data Register development, gap analysis and case studies report, draft gap assessment report, recommendations report.

## Previous View (hidden)
National Energy Market and Gas Markets
Regulatory Implementation Roadmap | [10 empty] | Key:
[12 empty] | Policy development/market design | [12 empty] | Rules development | [9 empty] | Procedure/guideline development
[12 empty] | Implementation - IT systems, processes | [12 empty] | Indicative IT implementation | [9 empty] | Engineering Implementation
[11 empty] | l | Committed Go-Live Date | [6 empty] | p | Proposed Go-Live | [6 empty] | n | Indicative Go-Live | [5 empty] | u | Estimated Go-Live |  |  |  | + | Updated for version 6
Impacted Industry Sector | Primary Objective | Reform Status | Reform Initiative |  | 2020 |  |  |  |  | 2021 | [9 empty] | 2022 | [11 empty] | 2023 | [7 empty] | 2024 |  |  |  |  | 2025 |  |  |  | 2026
[5 empty] | Q1 | Q2 |  | Q3 | Q4 | Q1 |  | Q2 |  |  | Q3 |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  | Q2 |  | Q3 | Q4 |  |  | Q1 |  | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
INITIATIVES WITH IT SYSTEM IMPLEMENTATION IMPACTS
Industry-wide | Market | Committed | Five Minute Settlement (5MS) | [9 empty] | 5MS (IT platform) | l |  |  | l | AEMC final determination - go-live 1 Oct 2021
Retail | Consumer | Committed | Reducing Customer Switching Times | [13 empty] | l | Updated to align with 5MS go-live - 1 Oct 2021
Industry-wide | Consumer | Committed | Wholesale Demand Response Mechanism | [13 empty] | l | AEMC final determination - go live 24 Oct 2021
Retail | Consumer | Committed | Electricity B2B changes | [14 empty] | l | v3.5 and v3.6 - 10 Nov 2021
Gas |  | Committed | Gas B2B changes | [14 empty] | l | IN003/20 (business enhancements, schema uplift) - 29 Nov 2021
Industry-wide | Market | Committed | Global Settlements | [10 empty] | GS soft start |  |  | l |  |  |  | GS (extern) |  |  | l | AEMC final determination - go-live 1 May 2022
Retail | Consumer | Committed | Metering Coordinator Planned Interruptions (MCPI) | [20 empty] | l | AEMO notice to reschedule to 1 May 2022, bundled with MSDR
Retail | Operational | Committed | MSATS Standing Data Review (MSDR) | [19 empty] | v1 | l |  |  |  |  | v2 | l | v1 MCPI and schema for MSDR go-live 1 May 2022 and v2 majority of MSDR go-live 7 Nov 2022
Retail | Market | In progress | Regulatory Arrangements for Stand Alone Power Systems (SAPS - Priority 1) | + | [25 empty] | n | AEMC recommended implementation 12 months after law and rule changes made
Retail | Consumer | In progress | Energy Consumer Data Right | + | [24 empty] | T1 | l | [6 empty] | T2 | l | CDR rules go-live Nov 2022 and Nov 2023
Retail | Market | Proposed - Review | Review of Regulatory Framework for Metering Services | + | [33 empty] | u | IT implementation likely but not yet clear, dependent on review outcomes
Wholesale | Reliability | In progress | ST PASA - Replacement project and methodology update | + | [23 empty] | n | Estimated timing, subject to rule change process
Wholesale | Market | In progress | Integrating Energy Storage Systems (IESS) (C) | [30 empty] | p | Implementation planning co-ordinated through Reform Delivery Committee
Wholesale | Security | Committed | Fast Frequency Response Market Ancillary Services (B) | [33 empty] | l | Implementation planning co-ordinated through Reform Delivery Committee
Wholesale | Security | In progress | Primary Frequency Response Incentive Arrangements (B) | + | [36 empty] | p | Implementation planning co-ordinated through Reform Delivery Committee
Wholesale | Reliability | In progress | Operating Reserve Market (B) | [22 empty] | Indicative Execution Range: Procedures, IT | [16 empty] | Implementation planning co-ordinated through Reform Delivery Committee
Wholesale | Security | In progress | Introduction of ramping services (B) | [22 empty] | Indicative Execution Range: Procedures, IT | [16 empty] | Implementation planning co-ordinated through Reform Delivery Committee
Wholesale | Security | In progress | Synchronous Services Markets (B) | [22 empty] | Indicative Execution Range: Procedures, IT | [16 empty] | Implementation planning co-ordinated through Reform Delivery Committee
Wholesale | Security | In progress | Capacity commitment mechanism for system security and reliability services (B) | [22 empty] | Indicative Execution Range: Procedures, IT | [16 empty] | Implementation planning co-ordinated through Reform Delivery Committee
ESB INITIATIVES WITH IT SYSTEM IMPLEMENTATION IMPACTS
Industry-wide |  | In progress | Resource Adequacy Mechanisms and Ageing Thermal Generation (A) | + | [5 empty] | Market Design | [6 empty] | Indicative Execution Range: Legislation, Rules, Procedures, IT | [22 empty] | Extended Execution Range
Immediate:
Initial:
Industry-wide | Market | In progress | Essential System Services, Scheduling and Ahead Mechanisms (B) | + | [5 empty] | Market Design | [6 empty] | Indicative Execution Range: Legislation, Rules, Procedures, IT | [22 empty] | Extended Execution Range
Immediate:
Initial:
Industry-wide | Market | In progress | Demand Side Participation (C) | + | [5 empty] | Market Design | [6 empty] | Indicative Execution Range: Legislation, Rules, Procedures, IT | [22 empty] | Extended Execution Range
Immediate:
Initial:
Industry-wide | Market | In progress | Transmission and Access (D) | + | [5 empty] | Market Design | [6 empty] | Indicative Execution Range: Legislation, Rules, Procedures, IT | [22 empty] | Extended Execution Range
Immediate:
Initial:
INITIATIVES WITH LIMITED IT SYSTEM IMPLEMENTATION IMPACTS (including ESB initiatives)
Wholesale | Security | Committed | Mandatory Primary Frequency Response |  |  |  | l | [18 empty] | Implementation timing shown is indicative and depends on individual generator circumstances, managed through the self-assessment process
Network |  | In progress | Technical Standards for Distributed Energy Resources | [15 empty] | l
Wholesale | Security | Committed | Efficient management of system strength on the power system (B) | + | [26 empty] | l |  | l
Wholesale |  | Committed | Generator Registrations and Connections | + | [17 empty] | l
Network |  | Committed | Access, Pricing and Incentive Arrangements for Distributed Energy Resources | + | [11 empty] | l | [9 empty] | l
Network |  | Committed | Implementing a General Power System Risk Review | [16 empty] | l
Industry-wide |  | In progress | Enhancing Operational Resilience to Indistinct Events | + | [22 empty] | p
Industry-wide | Market | In progress | Renewable Energy Zones - Implementation (Stage 2) (D)
Networks | Market | In progress | Governance of DER Technical Standards | + | [18 empty] | Indicative timing, subject to rule change process
GAS INITIATIVES
Gas |  | Committed | DWGM simpler wholesale price | [27 empty] | l
Implemented as a single AEMO project
Gas |  | Committed | DWGM improvement to AMDQ regime | + | [26 empty] | l
Gas |  | In progress | Measures to Improve Transparency in the Gas Market | [21 empty] | n | Subject to passage of legislation
Gas |  | Proposed - Review | Extending the Regulatory Framework to Hydrogen and Renewable Gases | +
INITIATIVES WITH LIMITED CERTAINTY
Retail | Consumer | In progress | Updating the Regulatory Frameworks for Embedded Networks | + | [34 empty] | u | Assumes rules development is re-initiated

## Version control
National Energy Market ESB 2025 Reforms
NEM2025 Implementation Roadmap
| Version | Date | Description
| Pre v. 0.01 | 2022-02-23 | First working draft for discussion and review by Design Authority on 16/2/2022. This version only considers known regulatory timeframes or assumptions, and implementation process assumptions, for initiatives within the NEM2025 reform program. It is not an integrated version that considers other initiatives within AEMO (e.g. Digital) that may impact the solution and/or the timeframes for delivery of the NEM2025 initiatives, with the exception of the ST PASA replacement initiative.
| Pre v. 0.02 | 2022-03-02 | Second draft incorporating Design Authority feedback, SME review and feedback. Updates made to each pathway, the implementation process and timeframes. Updates to DER Marketplace initiatives.
| v. 0.1 | 2022-03-11 | First working draft for discussion and review by the Reform Delivery Committee on 21/3/2022.
| v.0.2 | 2022-03-29 | Second draft incorporating RDC feedback for discussion with RDC at next workshop scheduled on Thursday 31/03/2022
| v1 | 2022-04-06 | Final draft for industry consultation incorporating RDC feedback.
| v1.1 | 2022-05-05 | Update to Data Strategy initiatives

## Log of changes
National Energy Market ESB 2025 Reforms
NEM2025 Implementation Roadmap
| Version | Date | Reform/initiative | Change
| v0.2 | 2022-03-29 | Scheduled Lite | Update both pathways to reflect releases for the Visibility Model and the Dispatchability Model
| v0.2 | 2022-03-29 | OSM | Developed a 'phased approach' option (row 69, hidden)
| v0.2 | 2022-03-29 | Ramping reserves | Developed a timeline for RDC discussion reflecting the date by which the rule change FD must be complete (by Dec 2022) for OR to be effective in 2025 (row 73, hidden)
| v0.2 | 2022-03-29 | SCADA Lite | Updated to reflect in-flight elements (release 1). Release 2 will enable the Schedule Lite Visibility model.
| v1 | 2022-04-06 | OSM | Updated OSM to reflect the phased approach as the preferred approach for both pathways.
| v1 | 2022-04-06 | Ramping reserves | Deleted hidden row. Only the pathway with current policy/regulatory process assumptions reflected on both pathways.
| v1 | 2022-04-14 | ST PASA Replacement | Updated the ST PASA timeline to reflect updated information published in AEMO's letter to the AEMC on proposed timing to implement the Updating Short-Term PASA rule change.
| v1.1 | 2022-05-05 | Consumer Research / Metrics | Removed given lack of IT system or process impacts