## Slide 1: Pipeline Capacity Trading Update
October 2018

## Slide 2: Capacity Trading Project
Pipeline Capacity Trading reform package includes the development of:
  a capacity trading platform (CTP),
  a day-ahead auction (DAA) of contracted but un-nominated capacity,
  standards for key contract terms in transportation agreements,
  a reporting framework for secondary capacity trades, and
  common gas day
The reform package is to be implemented by 1 March 2019.
Key components of the implementation project include:
  Legal, regulatory and contractual architecture
    changes to the National Gas Law (NGL), the National Gas Rules (NGR), the Regulations and the Operational Transportation Services Code, which will be made by the South Australian Minister and give effect to the package of reforms. (GMRG)
    Market procedures and participant agreements. (AEMO)
    Standardised operational transportation agreements. (Facility Operators)
  Market systems (AEMO)
  Market readiness – including guides, training, facility operator testing and market trial (AEMO)

## Slide 3: Legal Framework
Part 22 (GSH) Legal framework and market conduct rules
National Gas Law Powers, functions and duties
Legal framework for subordinate instruments
Capacity Transfer and Auction Procedures
Made by AEMO
Denotes contractual arrangements
Regulations
Liability caps, civil penalty and conduct provisions
Part 18 (GBB) Secondary trade information and other transparency measures (e.g. allocation arrangements)
National Gas Rules
Auction Agreement
Made by AEMO
Part 24 (Facilitating capacity trades and capacity auction) Legal and governance framework for the Code, service provider obligations to facilitate trades and exemptions
Part 25 (Capacity Auction) Legal framework, auction design, market conduct, service provider obligations and payment mechanism
Part 26 (Standard Market Timetable) Legal framework for harmonised gas day start time and nomination cut-off times, and obligations associated with transition
Part 15A (Registered Participants) Provides for AEMO to recover its costs from participants
Part 15B (Procedures) Sets out the matters about which AEMO can make procedures
Operational Transportation Service Code
Initial Code made by SA Minister Subsequent amendments made by AER
Standard Operational Agreement Published by Service Providers
Exchange Agreement
Made by AEMO
Key
DWGM procedures
Made by AEMO
BB procedures
Made by AEMO

## Slide 4: Legal Framework – Consultation Dates
Date | Responsibility | Process
July – Nov 2018 | SA Minister | Amendments to the NGL progressed through SA Parliament and once NGL changes are proclaimed, the amendments to the Regulations and the NGR, and the initial Code will be made.
Aug – Sep 2018 | AEMO | Formal consultation on the Capacity Transfer and Auction Procedures, the Auction Agreement and changes to the Exchange Agreement
Sep – Oct 2018 | AEMO | Publication of registration kit for service providers
Sep – Oct 2018 | AEMO | Consultation on second draft of the specification of service points, zones and pipeline segments.
Oct 2018 | AEMO | Publication of registration kit for market participants.
Oct – Nov 2018 | AEMO | Formal consultation on other Procedures.
 | AEMO | Publication of training material for facility operators and for other market participants
 | AER | Formal consultation on record keeping guidelines.
On or before 1 Dec 2018 | AEMO | AEMO to make the Capacity Transfer and Auction Procedures and Auction Agreement and amend the Exchange Agreement and other Procedures.
 | AER | AER to make record keeping guidelines.
Procedure consultation page: http://aemo.com.au/Stakeholder-Consultation/Consultations/Capacity-Trading-Reform-Package?Convenor=AEMO%20Gas

## Slide 5: Market Readiness Program
Objectives of the market readiness program:
  Support the readiness of industry participants to commence operation of the capacity trading platform and day-ahead auction, and
  Support a smooth transition to live operation.
Key components of program:
  Market Readiness Reporting and Coordination
  Training and Market Guides
    First round of training scheduled for late Oct / Nov.
    Second round of training in January 2019.
  Facility Operator Testing
    Mid-November to mid-December.
  Market Trial
    Commencing January 2019.

## Slide 6: DWGM Accreditation Procedures
AEMO will be amending the Accreditation Procedures to meet the requirement to integrate the CTP and DAA with the DWGM.
To trade capacity at a DWGM interface point a participant must first have applied for and be accredited at that point.
DWGM Participants who trade capacity at a DWGM interface point will be taken to have a issued deemed application (a revised application) for accreditation at that interface point.
On receipt of a deemed application AEMO will:
  Increase or decrease the participant’s MHQ and ramp times (where applicable) to reflect the corresponding transportation capacity traded via the CTP or DAA
Adjustments to accreditation for deemed applications will be made automatically and occur after a CTP transfer has been confirmed or DAA auction results have been published.

## Slide 7: DWGM Accreditation Procedures
Expected DWGM interface points for DAA and CTP include:
  Tashub
  Vichub
  Culcairn (injections and withdrawals)
  SEAGas
  Mortlake
  Otway
  Iona
AEMO will be developing a new INT report to assist participants in understanding changes to their accreditation.
  The new report will provide participants with a view of their accreditation beyond the current 2-day window as specified in INT118.

## Slide 8: Gas Bulletin Board Procedures
The proposed BB Procedures changes include:
  Amendments to allow for registration of allocation agents and allocation points.
  Reporting requirements for allocation agents.
  Reporting requirements for nameplate rating for receipt and delivery points.
  Additional transparency measures required for the pipeline capacity trading reforms.
AEMO has commenced formal consultation on the first round of Gas Bulletin Board Procedure changes required for the pipeline capacity trading reform package.
  Consultation on the PPC closed on 28 September.
AEMO has prepared an Impact and Implementation Report (IIR)
  Consultation on the IIR due to close in late October.